 Programme Completion Review

Title: Reducing poverty through Local Economic Development (LED) in the Commonwealth
Final Programme Spend £ (full life): / £3.9 million	Review Date:	June 2021
Programme Code: 204042	Start Date: / August 2017	End Date: / March 2021

Summary of Programme Performance

Year	2018	2019	2020	2021
Programme Score	A	A	A	A
Residual Risk Exposure Rating	Minor	Minor	Minor	Minor

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-1-204042/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.fcdo.gov.uk/projects/GB-1-204042/documents

A. Summary and Overview

Description of the programme and what it has achieved

The Commonwealth Local Government Forum (CLGF) was established in 1995 and is officially recognised by the Commonwealth Heads of Government. CLGF works to promote and strengthen effective democratic local government across the Commonwealth through local investment opportunities, job creation and improving the environment in which to do business. CLGF facilitate the exchange of good practice in local government through its extensive membership (more than 200 members in 47 Commonwealth countries) at national and local government level.

Under a previous £4.5 million programme funded by FCDO (2012–2016), CLGF successfully piloted a Local Economic Development (LED) approach, raised awareness for LED and demonstrated the potential impact of LED. This £3.9 million programme aimed to further deepen and embed that approach by rolling out LED at scale with local government partners in six focal countries (Botswana, Ghana, Sri Lanka, South Africa, Eswatini (formerly Swaziland) and Zambia), work in three other countries; and with lessons learned shared widely with other Commonwealth countries. The programme was due to conclude in July 2020 but was granted a no-cost extension to March 2021 to enable CLGF and its partners to navigate the impact of COVID19 on final activities.

The project has met, and in a number of areas, exceeded its expected targets. The project has served to demonstrate, in a practical way, that LED is an important tool for Government and Local Government to strengthen community engagement and resilience, enhance livelihoods, create jobs, and reduce poverty.

The project focused on developing and and supporting LED strategies in selected partner countries. The results have reinforced the theory of change and the levels of local buy-in have been high throughout. The relevance of LED in poverty reduction has been further reinforced by the global pandemic which has highlighted the importance of local responses to threats and challenges in building resilient communities able to withstand external shocks.

CLGF has been able to leverage significant additional support to reinforce FCDO’s contribution, and it is positive to note that a number of project partner countries are building support for local economic development into their post-COVID recovery strategies, e.g. South Africa.

Key results include:
- The project supported the creation of 1,850 jobs (which is one of a series of objectives), with over 16,000 individuals having benefitted from the provision of training and skills development programmes run as part of the programme;
- 55 local councils developed LED strategies and implemented actions in support of their local communities economic empowerment;
- 5 national governments produced or revised guidance on LED to better support local government in the implementation of LED and the mobilisation of local communities towards pro-poor, gender sensitive, participatory and inclusive economic development;
- Over £3.4 million has been mobilised for ‘bankable’ projects developed by local councils and their partners, built on local knowledge of existing and under-development value chains and economic potential;
- Over 350 elected leaders and council staff have built their capacity in LED and supported the institutionalisation of LED into their local councils.
Major lessons learned, evidence generated and recommendations

The programme has highlighted the importance of working with and through the key statutory actors responsible for local economic development both at the national and local level. By working at the local level with individual local governments, with national associations of local government and with ministries responsible for local government, CLGF has been able to support work undertaken by councils aligned with local realities and potential, as well as with citizens’ priorities.

Capacity building activities for local leaders and technical staff has supported the development and adoption of pro-poor, gender sensitive, participatory and locally responsive LED plans and strategies, which formed the framework against which the councils are delivering LED services.

The LED strategies also formed the basis for enabling the development of – and securing investment for - bankable projects. The investment fairs offered a key opportunity for local governments to profile their LED projects, framed within their LED strategies, and present them to potential investors, bringing investment and jobs into local communities.

The project has identified a number of lessons and good practice examples which the CLGF is promoting among its membership and more widely internationally. The CLGF has contributed to the body of evidence-based research on LED, with papers and reports, including a report on LED as a Driver for Trade, and articles published in the Commonwealth Journal of Local Governance. Other countries in the Commonwealth are also now actively embracing and implementing the LED model as a result of this programme.

LED is likely to play a major part of the post COVID recovery in many Commonwealth countries. This project has developed approaches that can be adopted as part of that effort and CLGF should continue to capture and widely share lessons with Commonwealth members and more widely internationally.

How this report was conducted

This report was prepared by the FCDO programme team, drawing on information and data provided by the CLGF and its partners. This included information from surveys conducted by CLGF’s partners with local commuinities and business organisations.

Actions following approval of this report

The CLGF will provide its annual audited statement for the Financial Year 2020/21 by March 2022, to allow for full closure of the programme.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	3,900,000.00 GBP	3,900,000.00 GBP
Timeframe	August 2017 – August 2020	August 2017 – March 2021
Outcomes	Outcome: Economic development, investment, and increased job opportunities in local communties in target countries. / Indicator 1 (final target): Local Business forums/associations (representing formal and informal traders) / chambers of commerce etc in four council areas report improved environment for doing business as a result of LED.	Target met: Of the 55 councils supported, 14 councils directly engaged with local chambers of commerce, business fora & associations who reported improvements in the business environment as a result of the council’s LED work.
	Indicator 2 (final target): At least 1,500 jobs created, positively impacting over 5,000 lives.	Target met: 1,850 jobs were recorded as created, with over 16,000 individuals having benefitted from the provision of training and skills development run as part of the programme.

Overall assessment of programme outcomes, sustainability and VfM

The project achived its logframe outcomes within the budget allocation, though additional time was agreed for the final year of the project to mitigate against the impact of the covid-19 pandemic and provide partners more time to consolidate results generated from project work.

LED strategies and programmes were implemented in 55 councils across the nine partner countries under Outputs 1 - 3. Key stakeholders, including business associations and chambers of commerce, local cooperatives and NGOs, from across each council area were consulted on the visioning for the strategies, and subsequently engaged during their implementation. Surveys were undertaken in the initial and final phases of the project to provide an assessment of how the implementation of the LED strategies was supporting an improved local business environment. Anecdotal and empirical evidence gathered across the project has confirmed that staff, local leaders and local community representatives have a much greater awareness and understanding of LED and the role they can play in ensuring local economic development. Information derived from recipients of councils’ economic development services confirms that improvements have resulted.

Implementation of LED strategies in 55 councils supported the creation of jobs through improved business support systems, the strengthening of value chains and value addition, support to training and skills improvement, and the development and implementation of bankable and catalytic projects. By the end of the project, 1,850 jobs have been recorded as created as a direct impact of the project, with an additional 16,000 individuals having benefitted from training and skills development run as part of the programme.
[note] CLGF collected data on job creation at three levels: (a) directly from ‘bankable’ projects supported within the project; (b) directly as outcomes of the pilot council implementation of their LED strategies; and (c) indirectly through the implementation of national LED strategies and LED rollout. The final figure is drawn from data collected from areas (a) & (b), as national ministry partners were not at a point in their monitoring and evaluation of strategies to be able to provide national data, however proxy data collected on the implementation of national programmes at the local level was collected in some countries. This will be key work in the monitoring towards SDGs targets and could be a good area for futhern programming.

With regard to sustainability, working with and through the national and local institutions (National Minisitries of Local Government & Local Councils) has ensured that policy at both the national and local level is now in place to support LED. The project allowed for testing of new methodologies and participatory practices and LED has been institutionalised into the work of local government. LED strategies have enabled local governments to build consensus and to actively leverage investment into local communities. Local partners’ perceptions and understanding of LED has been enhanced. CLGF is confident that the LED strategies developed with the project’s support will continue to guide the local partner councils’ development and priorities in the future, and also provide a framework for supporting ongoing job creation and improved livelihoods in these council areas.
CLGF has prioritised value for money in its approach, working with and through its members with a small team of local staff able to be responsive and adaptive to changing circumstances. The project has demonstrated significant impact, high levels of political buy-in and demonstration of changes in behaviour. This investment has played a catalytic role in enabling CLGF and project partners to leverage significant extra resources (£3.5million), adding further value to FCDO’s investment.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

CLGF’s Theory of Change

The theory of change builds on the lessons learned from FCDO’s earlier programme of support. The project aimed to provide local government organisations with the skills, capabilities and support needed to design and deliver strategies that provide the environment needed for local economic development and create a series of bankable projects that will leverage additional investment. The project focused on fewer countries but in greater depth, looking to demonstrate replicability by investing at scale.

The theory of change remained valid through the project which achieved its expected outcomes. The results framework and logframe targets also remained consistent across the project lifetime. The CLGF undertook surveys with project partners and recipients of partner council’s economic development services to provide a comparison of performance and impact of project activities. Data obtained through the surveys was disaggregated in most cases by the CLGF’s partners to provide information by gender, age and income.

## C: Detailed Output Assessment

Output Number and Title		Output 1: National/provincial local economic development (LED) strategies designed and rolled out (Botswana, Zambia and Sri Lanka).
Output Score		A Output met expectation.
Impact weighting (%)		50%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Number of countries that have adopted the CLGF approach to LED and are rolling out national LED strategies which are designed to be (1) pro poor, (2) gender sensitive, (3) enable local participation, (4) locally responsive	National/provincial LED strategies designed and rolled out in at least 2 countries (Aug 2020).		National/provincial LED strategies designed and rolled out in at least 2 countries (March 2021).	Target met: CLGF has successfully supported the implementation of LED strategies which are (1) pro-poor; (2) gender sensitive; (3) enable local participation and (4) are locally responsive in the three target countries (Botswana, Sri Lanka and Zambia). / In Zambia LED Guidelines were developed and included in the national integrated development planning process, and rolled out to all councils who now develop LED plans as part of their development planning responsibilities. A National LED Rollout Plan was developed in partnership with the Ministry of Local Government, the Ministry of Commerce, Trade and Industry and the Local Government Associations to support the process. / In Botswana, guidelines on LED Strategies, Value Chain Maps and Bankable Business Plans were developed in partnership with the Ministry of Local Government and Rural Development and integrated into the national LED Guidelines. LED planning and implementation has been integrated into the programme of national skills development with the University of Botswana. This will be further rolled out by the Ministry of Local Government. / In Sri Lanka, CLGF worked with the Ministry of Provincial Councils and Local Government on revisions to the Local Government Act which strengthened the role of Local Government in LED. The terror attacks in April 2019, followed by political instability and the Covid-19 pandemic, however, impacted the project’s ability to rollout fully at a national level. However, CLGF worked in partnership with the national Local Government Association to showcase the LED approach with Guides and lessons disseminated to Local Governments.

1.2 Percentage of citizens surveyed in areas implementing LED report improvement with the council’s economic development services (disaggregated by gender).	75% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services, disaggregated by gender (Aug 2020).	75% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services, disaggregated by gender (March 2021).	Target Met: Surveys conducted in the final phase of the programme reported improvements in satisfaction levels in partner councils’ economic development services. / In Botswana 80% of respondents at council level reported an improvement in the councils’ LED services to the informal sector. / In Zambia 75% of respondents at council level reported improvements in the responsiveness and inclusiveness of councils leadership by the end of the project, and 62% of respondents reported that the councils’ economic development services had improved. / In Sri Lanka 92% of respondents at council level reported improvements in access and delivery of council business development services. In addition, 95% of respondents reported improvements in the economic development projects being implemented at council level.
1.3 Target councils demonstrate increased capacity to develop bankable projects and successfully leverage investment.	8 (2/3) of target councils develop bankable projects and successfully leverage funding of up to £1.5m for implementation of LED priorities (Aug 2020).	8 (2/3) of target councils from Output 1 and/or Output 2 develop bankable projects and successfully leverage funding of up to £1.5m for implementation of LED priorities (March 2021).	Target exceeded: 34 participating councils (under Outputs 1 and 2) developed bankable project proposals. As of March 2021, over £3.4 million of investment had been mobilised, supporting 28 projects. / In Zambia, Botswana and Eswatini investment fairs were held in the final phase of the project. These brought together different ministries and parastatals, development banks, development partners and agencies, and private sector investment bodies with the local councils who presented their detailed proposals. These fairs elicited significant interest and councils are following up on additional funding and partners to further advance their projects.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The CLGF worked with partner Governments and 34 councils to develop and implement LED strategies that are (1) pro poor, (2) gender sensitive, (3) enable local participation, and (4) are locally responsive. Local participation and responding to local needs is at the core of CLGF’s LED methodology and was integrated into national LED rollouts and LED strategy development and implementation at council level. These were locally driven processes, with local governments convening a broad cross section of the local population to input into the strategies. The CLGF supported councils with targeted interventions with the formal and informal sectors as well as providing training and capacity building for Small and Medium Enterprises, youth, women and disabled groups. The CLGF also supported councils with the implementation of revisions to council policy and practice to streamline business support services, and the development of ‘bankable’ projects.

Indicator 1.1: The development of LED strategies has enabled local governments and communities to share visions and agree on priority projects to develop their locality, providing a focal point for communities and a guiding framework for the mobilisation of resources and investment.

In Zambia the CLGF supported the Ministry of Local Government and the Local Government Association with the launch and roll out of Local Economic Development Guidelines for Local Authorities. The plan provided a strategic framework and action plan for LED, aligned to the 7th National Development Plan. LED guidelines have been reflected in the Government’s National Integrated Development Planning (IDP) process, which provided a platform for engagement with local stakeholders and to use mutual learning and indigenous knowledge.

A National LED Coordination Committee was established bringing together 19 relevant Government ministries, agencies, and departments. The Committee has led to enhanced coordination and collaboration among key actors as well as helped to promote a whole of government approach to development.

In Botswana, the LED rollout is aligned to the Government’s national agenda (11th National Development Plan and Visions 2036) and Agenda 2030 plan, with poverty eradication as the core overarching priority. The national LED Framework and Action Plan are intended to guide and accelerate sustainable and inclusive economic growth and diversification at the sub-national level. Guidelines were developed on (1) LED Strategy Development, (2) Value Chains Analysis, and (3) how to develop Business Plans, and these have been integrated with the national LED framework guidelines (developed under the previous project) to provide a comprehensive LED guide. Training and mentoring was provided to enhance LED knowledge and capacity among partners.

The CLGF also supported the Ministry of Local Government and Rural Development (MLGRD) and the University of Botswana with integrating LED topics into the University’s curriculum which will support access to high quality LED training for new council staff members.

In Sri Lanka, the CLGF supported the Ministry of Local Government and Provincial Councils in its review of local government responsibilities (Acts and Ordinance), supporting the inclusion of a set of key amendments including an insertion of a new section that empowers local government to promote and secure socio-economic development. The review has informed a proposed revision of the Local Government Act that is intended to empower local governments to invest on LED related development projects and service provision where local government has either direct or indirect responsibility for services supporting the local business environment.

In addition the CLGF helped partner councils in Sri Lanka to establish LED Committees and has reviewed the councils’ citizens’ charters demonstrating how local government can work actively to support local economic development within the framework of the Local Government Act. The Local Government Association (FSLGA) has been actively disseminating pilot outcomes to its wider membership to support national LED rollout.

Indicator 1.2: The KAP baseline surveys informed the development of LED strategies and priorities at council level. Follow up surveys were undertaken in the final phase of the programme to assess the impact of the LED implementation and support the councils in focusing their ongoing LED work.
[note] Knowledge, Attitude & Practices (KAP) survey consisting of predefined set of questions to provide access to quantitative and qualitative information.

In Botswana, the KAP surveys focused on the informal sector, with consultations taking place over the course of the project and culminating in a series of informal economy dialogues undertaken in late 2020 and early 2021. 620 participants (46% men, 54% women) working in the informal sector as vendors and/or ‘hawkers’ were consulted. 80% of respondents reported an improvement in the councils’ LED services to the informal sector. Due to the pandemic, a number of these council level surveys had to be conducted remotely (e.g. through a whatsapp forum) and so partner councils did not collect detailed information on respondents’ backgrounds.
In Sri Lanka, members of the local business community in the 6 partner councils were consulted: respondents were 71% men and 29% women, with an age profile of 19% 20-30; 26% 30-40; 36% 40-50; 19% >50. Most had participated in focal groups with the council in the early phase of the project where priority areas for council work were identified as improving the provision and access to business services as well as improving the councils’ offer in terms of economic development projects. 92% of respondents in the final survey reported improvements in access and delivery of council business development services, and 95% reported improvements in the economic development projects.. There was also a clear indication that where a council had prioritised work on a specific theme identified in its original survey this had significantly improved public satisfaction in that area. For example, in Karachchi PS, where the council had worked to more actively promote and follow the commitments in its Citizen’s Charter, 73% of respondents indicated positive knowledge and increased use of the Charter.

In Zambia, the four lead pilot councils worked closely with their ward development committees in developing their LED strategies, in order to increase public understanding and involvement in council decision making. Ward committees were either formed or revitalised, engaging 618 local people. Initial surveys were undertaken which returned negative results with regard to perception of council economic development support services and the councils’ leadership, inclusivity and accountability. The councils made these areas a priority for improvement as they moved forward with their LED strategies. In the final KAP surveys 75% of respondents from across the ward committees reported improvements in the responsiveness and inclusiveness of councils’ leadership by the end of the project, and 62% reported that the councils’ economic development services had improved. 68% of respondents were male and 32% female, with an age profile as follows: 60% 18-34, 30% 35-65 and 10% 65+. This process of engaging the ward committees throughout the development and implementation of the LED strategies supported clear prioritization and increased community engagement.

Indicator 1.3: As at the end of the project, 34 partner councils (under outputs 1 and 2) had developed bankable project proposals, which have secured funds of over £3.4 million.

The development of bankable projects was an important step forward for the partner councils in their work to operationalise and implement their LED strategies. Local officials who, at the beginning of the project, had a limited understanding of business planning and the different resources the council had available to it to encourage investment in targeted projects and value chains were actively supported by the CLGF in this endeavour.

National trade fairs took place in Botswana, Eswatini and Zambia in March 2021, having been delayed to the final phase of the project due to the impact of the COVID-19 pandemic in partner countries. All of the fairs had Ministerial engagement. For example, in Eswatini the acting Prime Minister, Themba Nhlanganiso Masuku, opened the fair and noted the support the project had provided over the 4 years of its implementation in the country.

The investment fairs brought together different ministries and parastatals, development banks, development partners and agencies, and investment bodies with the local councils who presented their detailed bankable projects. There has been significant subsequent interest and the various partners are following up on additional investments into their projects. In total, these investment fairs, along with ongoing work at the local level engaging local investors and partners in the final phase of the project resulted in investments totalling £2.3m, contributing towards an overall total of over £3.4 million mobilised for projects over the project period.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The relationships which CLGF developed with local and national local government actors enabled them to test activities on the ground, and influence local and national decision making, resulting in successful upscaling and roll out, with LED being integrated or mainstreamed into national development strategies.

The programme helped to build local partners’ capacity to better understand their local economies and the value chains that relate to them, supporting them to design and promote ‘bankable’ projects which have successfully attracted private sector or development funds.

CLGF’s LED approach integrates equity and inclusion and LED strategies developed through the project are (1) pro poor, (2) gender sensitive, (3) enable local participation, and (4) locally responsive. This approach ensured focus was given to supporting women and marginalised communities. For example, in Sri Lanka, two of the pilot council (Baddegama and Uddubbadawa) supported development of a traditional food outlet that created 60 part time jobs for local women, allowing them to meet their family responsibilities while also improving their livelihoods.

The costs of activities against this output remained within the budget parameters set at the outset of the programme.

Lessons learned through this output, and recommendations for future programming

CLGF’s support helped demonstrate the value of inclusive approaches both at the national and local level. Local Economic Assessments (LEA) provided a key input to both LED strategies and the development of bankable projects ensuring that work undertaken by councils aligned with local realities and potential, as well as with citizens’ priorities.

LED capacity building with local leaders and technical staff, was a key priority that underpinned the efforts for successful LED strategies at both the local and national levels.

Work on bankable projects requires a number of previous actions to be in place and for LED to be well understood and integrated into the council processes. Mainstreaming LED into the work of local councils has supported the resilience of partner councils to shocks, such as from the current pandemic, and be better able to respond to new stresses and community priorities. The investment fairs were an opportunity to focus attention on LED and to open doors to potential investment opportunities, both from private investors and public entities. They profiled local government as actors in economic development which in some countries was a shift in how the sector was perceived.

A key lesson from the project has been the value of working at both a national and local level. The results of local LED approaches have been used by Ministries to inform the development of national policies/guidelines on LED. CLGF advise that there is also emerging evidence of LED approaches making the case for decentralisation, e.g. Botswana.

From a local government perspective, LED approaches have highlighted a positive aspect of the work of councils and is helping to build a more consultative and developmental relationship between the council and the community in many of the target councils, demonstrating how such engagement can be used to help address the concerns of disadvantaged groups such as women and youth entrepreneurs.

Lessons from this project have been shared within FCDO, including the team that leads on cities engagement.

Output Number and Title Output 2: Increased capacity to roll out LED in selected countries (Ghana, / South Africa and Eswatini (formerly Swaziland). / Output Score A+ Output moderately exceeded expectation. / Impact weighting (%) 20% Impact weighting revised since last AR? No
Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
2.1 Number of countries embedding the CLGF approach to LED, where appropriate, in national policy, legal, regulatory and capacity development frameworks for LED.	Two countries have increased capacity and are rolling out their LED strategy (Aug 2020).	Two countries have increased capacity and are rolling out their LED strategy (March 2021).	Target met: CLGF has successfully supported the embedding of the CLGF approach to LED in the three target countries (Eswatini, South Africa and Ghana), supporting the development of national policies and frameworks that are (1) pro-poor; (2) gender sensitive; (3) enabling of the local participation and (4) locally responsive.
2.2 Capacity of technical staff and political leaders to deliver LED services increased (councils and ministries)	Increased capacity of 200 technical staff and political leaders to deliver LED services demonstrated (Aug 2021).	Increased capacity of 200 technical staff and political leaders to deliver LED services demonstrated (March 2021).	Target exceeded: Over 350 technical staff and political leaders supported through training and other capacity building activities has increased capacity in LED deliveryin the three target countries.
2.3 Improved economic opportunities for citizens in areas implementing LED	60% of surveyed citizens who have used council LED services report improved economic opportunities (Aug 2020).	60% of surveyed citizens who have used council LED services report improved economic opportunities (March 2021).	Target met: Surveys were undertaken in the initial and final phases of the programme. The final surveys confirmed that councils had made important progress in delivering services to their citizens. / 10 councils undertook the final citizen survey to better understand which areas had improved in accessing LED services and where additional focus was still needed. / In Ghana 63% of repondents reported that business services had improved and 54% reported that council communication and information had improved. / In Eswatini the final survey was focused on services provised to the informal sector. 82% of respondents indicated that consultation had improved with the local council. / In South Africa 63% of respendents reported that communication and awareness raising from the council had improved, and 70% reported a improvement in LED services.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Indicator 2.1: Over the project period, key achievements have been:

In South Africa, CLGF worked with the Ministry of Cooperative Governance and Traditional Affairs (COGTA) and South African Local Government Association (SALGA) to develop Regional Economic Development Guidelines, that focused on how to support better coordination and planning between municipalities, across districts and provinces and in cross-border and supranational environments. The Guidelines provide a practical resource to support creation of regional economic development plans. Testing was undertaken in Bojanala District prior to it being finalised and circulated to all regional authorities in early 2020. CLGF also worked with COGTA on the National LED Framework which provides the wider context for the targeted work CLGF has been supporting on regional economic cooperation. These guidelines have been adopted and will be rolled out by the Government, providing an additional layer of framing to the implementation of LED at the local and regional level.

In Ghana, CLGF worked with the Ministry of Local Government and Regional Development (MoLGRD) and National Association of Local Authorities of Ghana (NALAG) in the review of the National LED policy, supporting both the reassessment of the 2013 Policy, and the development of the revisions based on these recommendations. The revised policy was taken to a finalising workshop in August 2020, and the validated National LED Policy 2020 was launched by the Ministry in December 2020. The revised LED Policy is expressly “built around the principles of gender equality, equity and inclusiveness in local economies and encourages effective and inclusive participation of different stakeholders without distinction based on status, gender or class”.

In Eswatini, CLGF worked with its partners on the national rollout of LED, building capacity with councils and working with the Ministry of Housing and Urban Development (MoHUD) on developing the guidelines for LED funding options, specifically around private finance initiatives for urban local government. These guidelines were launched by the Acting Prime Minister, Themba Nhlanganiso Masuku, during the National Investment Fair in March 2021. The LED rollout is linked to the priorities of Eswatini’s National Development Strategy, which is expressly a pro-poor development strategy and has at its core improving the living standards in the country through poverty eradication, employment creation, gender equality, social integration and environmental protection.

Indicator 2.2: The project has supported over 350 council technical staff and some elected leaders through a series of trainings and capacity building activities including peer-learning and cross-country exchanges, to build LED capacity and SDG awareness. This has helped to institutionalise these focal areas into the local councils full scope of work.

In Eswatini, 128 council staff members took part over the project period in a capacity building process around LED strategy development and implementation. Officers were trained and mentored on conducting local economic assessments, developing LED strategies, value chain mapping and the marketing of projects.

In South Africa, 52 local government offficals in the Bojanala District took part in the project’s capacity building around regional LED in support of work to strengthen regional coordination and multi-level governmental support to regional development.

In Ghana, 176 Council Assembly Members and technical staff took part in LED training linked to localising the SDGs and then applied this training in the implementation and oversight of their LED pilot projects.

CLGF responded to the COVID-19 pandemic by moving training activities online, having worked with partners to align with their technological capacity and ensure the widest possible participation in virtual/online learning. This capacity building was also adapted and updated to allow a successful transfer of knowledge in an online format. This process was successful in allowing the project to respond to the new and emerging needs of beneficiaries and support discussions on the revisions to LED strategies and bankable project proposals in contexts where council staff and leadership could not meet in person. This process of ongoing exchange and adjustment over 2020 was instrumental in assuring the ongoing buy-in the project objectives and was a key component in the preparations of partner councils towards the National Investment Fairs which took place in March 2021. The move to deliver some activities online also allowed CLGF to increase the project’s reach especially among technical staff at council level.

CLGF tracked a sample of its key practitioners who play integral roles either with the pilot councils, Ministry or Local Government Association within each country, of whom 34% were women and 66% men, with a role profile of 7% elected, 24% director level, 39% manager level and 29% officer level. Their feedback on the support provided by CLGF has been positive. Participants highlighted increased confidence in leading LED processes as well as strengthened technical skills in strategy development, public outreach, project development and implementation. They also highlighted the full system approach to LED and cross-department collaboration, as well as the CLGF “learning through doing” approach as key in supporting their professional development.

Indicator 2.3: Surveys were undertaken with stakeholders in the three partner countries. The ongoing covid-19 pandemic over the final year of the project made the implementation of the final KAP surveys quite challenging. In some cases the methodology for undertaking the surveys had to be changed from face to face collection to telephone or ‘at distance’ collection, or piggybacking onto existing council activities. This was especially the case in Eswatinti and South Africa which had prolonged and challenging lockdowns.

In Eswatinti, the initial survey highlighted the need for improved consultation with local business and the informal sector. The final survey was focused on women in the informal sector as part of the councils’ focus on increasing support to vulnerable women. 100% of participants were from the informal sector and 82% reported that consultation with the local council had improved over the project period and that there was now regular consultation with the informal sector. 93% of respondents were women and 7% men, with an age profile of 32% 18-34 and 68% 35-65 years of age. The average monthly income of respondents ranged from 2,950ZAR to 723ZAR (£150-£36).

In Ghana, the initial survey highlighted a desire for improved communication and information on council services. The final survey was targeted specifically towards Small and Medium Enterprises operating in the council area. 63% of respondents reported that LED business services had improved in the council area and 54% reported that communication with the council had improved over the course of the project. Respondents were 51% men and 49% women and 60% 25-44, 35% 45-65 , with the final 5% made up of under 25 and over 65.

In South Africa, the initial surveys of businesses in Matlosana and Madibeng council areas outlined concerns linked primarily to delivery of essential services and economic infrastructure, such as electricity supply, sewage facilities, road infrastructure and refuse collection. Improving these services was an important part of the Small Town Regeneration (STR) Strategies developed by the two councils, which also included a focus on socio-economic infrastructure, good governance, skills development, town promotion, and communication and development partnerships. In the final survey, 70% of respondents (63% of whom were men, 37% women) indicated that LED services had improved and 63% reported improved communications from the council. The employment profile of respondents was 43% self-employed, 48% worked or owned SMEs, 4% were employed in the public sector and 5% were unemployed.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
This work has demonstrated value for money by drawing on CLGF’s wide technical expertise, much of which was accessed at low or no cost from within its network of members to support existing investment by governments in the LED rollout.

CLGF’s LED approach encouraged a focus on women and marginalised communities in project development. In Ghana, for example, pilot project work supported women engaged in value addition to traditional products such as Shea butter production, casava processing and palm oil production. In Siteki, Eswatini work with the council supported a group of 40 women to register a cooperative to create access to economic activity and mutual support for their existing businesses.

The costs of activities against this output remained within the budget parameters set at the outset of the programme.

Lessons learned through this output, and recommendations for future programming
The output demonstrated the value of participatory and inclusive approaches, building on many of the partnerships established under the earlier project. Providing space for inter-governmental dialogue has been important in supporting LED rollout in the three countries, allowing different actors to come together to raise challenges, barriers and concerns impeding the national rollout of viable LED policies and processes. The institutional relationships and trust between partners built over the project period continues to ensure that CLGF is included in key strategic discussion and activities (such the update of the Ghana LED policy).

CLGF has a wealth of knowledge and good practice both in LED policy and practice as well as in the potential peer support that its network can draw on both in terms of individuals and institutions. Drawing on this technical and practitioner expertise is a key interest for the project partners at all levels.

Output Number and Title Output 3: Increased awareness of LED potential in selected countries with some fragility (drawn from Bangladesh, Cameroon, Lesotho, India, Pakistan, Sierra / Leone, Zimbabwe). / Output Score A+ Output moderately exceeded expectation. / Impact weighting (%) 15% Impact weighting revised since last AR? No
Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
3.1 National actors (i.e. Ministry of Local Government, Local Government Associations, business fora) use lessons from demonstration projects and national/regional exchange to inform enabling policy and LED practice to empower local governments to deliver LED.	National actors in at least two countries use lessons from demonstration projects, national and regional exchange and learning, to inform policy development (March 2021).	National actors in at least two countries use lessons from demonstration projects, national and regional exchange and learning, to inform policy development (March 2021).	Target met: National actors in India, Sierra Leone, and Zimbabwe successfully used lessons from demonstration work to inform national/state policy and practice on LED. / Zimbabwe and Madhya Pradesh (India) have used lessons from demonstration projects to integrate LED approaches into national/state policies and programmes. / In Sierra Leone the Guidelines developed by the project in LED and Procurement have been taken up by the local government association and are being disseminated across its full membership (all 22 councils in the country).
3.2 LED demonstrated as an approach to integrated local development	4 councils have demonstrated the LED approach through the development and implementation of LED strategies (Aug 2020).	4 councils have demonstrated the LED approach through the development and implementation of LED strategies (March 2021).	Target Exceeded: 15 councils across the three target countries have developed and implemented LED strategies which are showing positive impacting in the local community with regard to supporting economic development and livelihoods.
3.3 Improved economic opportunities for citizens in areas implementing LED.	50% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services (disaggregated by gender) (March 2021).	50% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services (disaggregated by gender) (March 2021).	Target Met: Final citizen surveys were undertaken over October 2020 – March 2021 to gauge the impact of project work on the lives and livelihoods at the local level. / In Zimbabwe 76% of respondents reported improvements in council consultation processes and 60% reported improvment in the local business environment. / In Madhya Pradesh, India 93% of respondents reported improvements in support to start-ups and Small and Medium Enterprises. / In Sierra Leone, 76% of respondents reported improved communciaiton and customer service from their local council, and 64% reported improvements in the LED services available to Small and Medium Enterprises.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Indicator 3.1: Over the course of project national actors have drawn on CLGF work to improve policy and practice for LED. Key achievements include:

In Zimbabwe, the CLGF supported the Urban Councils Association of Zimbabwe (UCAZ) to conduct its annual conferences aimed at reaffirming the position of Urban Local Authorities in national governance and economic development and to highlight their role in service delivery and promotion of investments in their areas. CLGF report that the Government of Zimbabwe has signalled its adoption of the LED approach in to its planned national devolution policy that empowers 10 provinces and 92 councils to effectively promote their local economies.
[note] While Zimbabwe is not currently a Commonwealth member, the CLGF has maintained its close relationship with local government in the country and has continued to work on a number of initiatives supporting local government and local communities’ access to services. In Zimbabwe, FCDO project funds were only used to support activities of local government associations and/or local councils.

In India, the Madhya Pradesh State Rural Livelihoods Mission (MPSRLM) has, with CLGF support, developed a tailored training module on LED which is being used with all of its practitioners and professionals. The CLGF also helped the SMART Cities initiative that supports Small and Medium Enterprise incubation centres, broaden its focus from “tech only” to also include start-ups focused on social enterprise and outreach to vulnerable and poor communities. The initiative delivered a month-long online platform called “Start-up Pathshala” that provided targeted orientation and training to over 10,000 start-up entrepreneurs and linked them to State and National institutions, such as Jabalpur Incubation Centre(JIC), Incubation Masters and the Confederation of Indian Industries. As a follow up to this work, the CLGF produced a Compendium of Government Provisions for Entrepreneurs and Start-ups, launched by the Chief Minister of Madhya Pradesh, and being disseminated to all SMART City incubation centres across the State.

In Sierra Leone, guidelines for local councils using procurement processes to support LED were developed and validated through a consultation process with local councils in January 2020. The Sierra Leone Government and the national local government association took part in this process. A national dissemination event was held in March 2021 bringing together representatives of Government, local Government and the UNDP and EU Delegation to discuss the practical implementation of the guidelines.

Indicator 3.2: In Zimbabwe, nine councils developed and are now implementing LED strategies. This is the first time that local councils in Zimbabwe have been asked to take an active developmental perspective on their local economies. A programme of capacity building and support from CLGF helped them through the full process - from undertaking local economic assessments, to developing their internal staff capacity to develop, implement and oversee the LED plan, through to the implementation of specific projects within the plan. For example, Mbire council developed a LED strategy which highlighted the district’s tourism and agriculture potential and promoted investment opportunities which helped to secure private sector investment into its priority areas, such as ARDA Mushumbi which has set up a farm employing more than 3000 contract workers, which is specializing in in organic agriculture.

In Madhya Pradesh, India, the cities of Jabalpur and Ujjain have implemented initiatives supporting incubation centres and ‘start-ups’ which provide advisory support, mentoring, office space and facilities to entrepreneurs in their first year of business start-up. Forty start-ups have now graduated from the incubator centres and are operating independently. One of these, “Hope for Faith Youth” has created an e-marketing platform which links rural artisans & self-help groups to online markets, creating and/or reinforcing 50 jobs.

In Sierra Leone, the four pilot councils focused their LED strategies on helping Small and Medium Enterprises (SMEs) in their local area to be able to potentially benefit from council procurement opportunities. They have also increased awareness and capacity among their staff to consider opportunities for local providers through production of guidelines and training. 200 SMEs received training and support on business basic procurement and business management skills and and an additional 350 individuals received training on specific thematic focal areas (such as agriculture or waste management/recycling). 96 SMEs registered with their respective councils for procurement opportunities and 24 consortiums have been formed, allowing smaller businesses to come together and bid for larger contracts. To date, 10 SMEs have won contracts.

The councils also supported specific catalytic LED projects in their local area on waste recycling & urban agriculture, creating jobs for 520 individuals. In Bo and Koidu cities, projects focused specifically on job creation for young people. The waste recycling youth groups were set up and training and support was provided in developing cooperatives, for example in council accreditation, registration and the opening of bank accounts, to allow them to access finance from financial institutions to expand their businesses as needed moving forward.

Indicator 3.3: Consultation with stakeholders has been integral in developing the council LED plans and priority activities. In the final months of the project a final round of outreach was undertaken with communities participating in the LED piloting to get their feedback on the impacts of the project.

In Zimbabwe, citizen feedback in the initial survey indicated job creation as a top priority, and in response councils prioritised building good relations with existing businesses and supporting development of small and medium enterprises. In the final survey, 60% of respondents reported improvement in the local business environment. The councils also worked to prioritse communication and the delivery of LED service undertaking internal changes such as the creation of business departments, business unit focal persons, and LED forums. In the final survey 76% of respondents reported an improvement in council consultation processes. 35% of respondents were women and 65% men, with an employment profile of 62% self-employed, 17% owners or employees of SMEs whilst 21% did not provide information.

In Sierra Leone, the project focused significantly on providing services to SMEs. The initial survey identified a need for improved communication by councils on economic opportunities and on council services. In the final survey, 76% of respondents reported improved council communication and customer service. 64% reported improvements in the LED services available to SMEs. 54% of respondents were women and 46% men, 54% were self-employed and an additional 29% worked or ran SMEs.

In Madhya Pradesh, India, the initial survey highlighted the need for additional support to small business development. Working with the framework of the Smart City Incubation initative, the council worked to provide support to start-up SMEs. In the final survey, 93% of respondents reported an improvement in support to start-ups and SMEs. All participants in the survey represented SME startups. 93% were men and 7% women, with an age profile of 71% 20-29 and 29% 30-39.

To address the gender disparity in access to the Start-up incubators the project worked with the incubation centres to develop a specific focal area for support to women lead start-ups. This not only increased the number of women taking part in activities lined to the incubation centres in late 2020-2021 but it also encouraged one incubate to develop a platform which links crafts produced by rural local artisans (with a focus on tribal peoples and women), coordinated by local self-help groups into a widely accessible online shopping cart. This initiative is one of the social enterprise start-ups being supported through the incubation centres. The CLGF was able to draw in the MPRSLM to further support and expand the reach of this initiative across the women focused self-help groups linked to MPRSLM programmes.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The use of the CLGF network has delivered value for money by ensuring that action was linked to national and local policy and priorities. Leverage of additional funds has resulted in significant added value on FCDO’s investment. Successful leverage has seen the anticipated number of target councils implementing LED strategies exceeded and has enabled local government to implement LED with a wider direct impact on livelihoods and local communities.

CLGF’s LED approach ensured focus was given to supporting women and marginalised communities in project development and support. Work in India, in partnership with the MPRSLM, focused on women self-help groups, building their capacity in LED and strengthening sustainable income streams for 10,000 women.

The costs of activities against this output remained within the budget parameters set at the outset of the programme.

Lessons learned through this output, and recommendations for future programming

The main lesson from this output is the importance of tailoring LED processes to each country’s national context. While CLGF drew on experience from other country work to propose ideas and solutions to challenges, political will, support and champions play a critical role as does tailoring interventions to socio-economic and cultural appetites. Involving local, provincial and national stakeholders is a key driver of LED interventions and, while this process can slow down activities and interventions, it is essential for longer term sustainability and real system reform. An important lesson in building uptake for LED across government is framing local successes within the framework on national development policies so that all levels of government can see the benefits. The programme has seen considerable successes with this approach.

Output Number and Title Output 4: CLGF acknowledged as a Commonwealth centre of LED learning and / good practice. / Output Score A+ Output moderately exceeded expectation. / Impact weighting (%) 15% Impact weighting revised since last AR? No
Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
4.1 Regional and global policy events highlight the effectiveness of LED as a means of achieving sustainable development.	Three regional and/or global policy events highlight the effectiveness of LED as a means of achieving sustainable development (Aug 2020).	Three regional and/or global policy events highlight the effectiveness of LED as a means of achieving sustainable development (March 2021).	Target exceeded: CLGF has highlighted LED at a number of key forums including: / - The annual UN High Level Political Forums (HLPF) where local government was among groups making representations on SDG progress. (June 2018; Sept 2019; June 2020 (virtual)); / - The World Urban Forum (WUF) where CLGF worked with other organisations, such as Cities Alliance to highlight LED (Oct 2019; Feb 2020); / - The World LED Forum in 2017 where CLGF profiled its work on institutionalising LED across the Commonwealth; / - CHOGM 2018 where CLGF highlighted the importance of local government in LED and good governance. / CLGF promoted LED across its membership, including at the November 2017 Commonwealth Local Government Conference. CLGF also organised regional policy events, e.g. a Southern African regional meeting was held in Zambia in 2019 which brought together 130 participants from Ministries, Local Government Associations and partner councils from 10 countries in the SADC region. The pandemic meant CLGF conducted its planned regional meetings in West Africa and Asia on-line in March 2021. These brought together 49 (from 5 countries) and 53 (from 6 countries) participants respectively.

4.2 National actors capitalise on the Commonwealth's shared systems, structures, language and governance to successfully implement LED.	CLGF members in three countries not participating in output areas 1,2 and 3 use CLGF resources and good practice on LED to inform policy and practice (August 2021).	CLGF members in three countries not participating in output areas 1,2 and 3 use CLGF resources and good practice on LED to inform policy and practice (March 2021).	Target exceeded: CLGF has actively implemented its knowledge management strategy throughout the project. / CLGF has increased the number and variety of materials and resources held in its knowledge hub and additionally provided specific advisory support to some CLGF members wanting to implement LED within their own context, are drawing on lessons from the project. Currently CLGF is supporting organisations in Fiji, Uganda, Belize and Jamaica in implementing LED. / A survey of Members on LED was undertaken in early 2021 as part of CLGF’s wider review of its strategic plan. 70% of respondents rated LED as one of the most valuable aspects of CLGF's work to their organisation, and respondents gave both CLGF’s knowledge products and projects & capacity building 4/5 stars when asked to rate these areas.
4.3 CLGF’s knowledge hub has a sustained increase of quality LED-focused resources, reviewed on an annual basis with annual increases in the number of visitors to the knowledge hub on the CLGF website.	Peer review of LED-focused resources confirms good quality resources in the Knowledge Hub and number of visitors has increased by at least 10% per annum (Aug 2021).	Peer review of LED-focused resources confirms good quality resources in the Knowledge Hub and number of visitors has increased by at least 10% per annum (March 2021).	Target met: CLGF has seen a 51.5% increase in users to the knowledge hub over the course of the project. / A peer review of the LED focused resources in the Knowledge hub was undertaken in year three and it confirmed their quality and relevance. Since the review CLGF has worked to increase the range of country level material available on LED, though this continues to vary by region due to differing academic, national and development agency focus on LED at a country level across the Commonwealth.
4.4. Percentage of funding leveraged against FCDO contribution.	65% of the FCDO contribution leveraged (August 2021).	65% of the FCDO contribution leveraged (March 2021).	Target exceeded: CLGF has successfully leveraged £3.5million against the FCDO funding for project work in the three focal regions of the project (Southern Africa, West Africa and South Asia). This has come from a mix of regional, national and sub-national sources, including the EU, CLGF member Local Government Associations, Ministries and councils.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Indicator 4.1: CLGF has participated in and worked to promote local economic development in a number of global and regional policy events over the course of the programme to actively promote the outcomes of the project and to highlight the important role of local government in local economic development and achieving global development targets. Key priorities have included:
- UN HLPF annual events
- The World Urban Forum 2020 & Asia Pacific Urban Forum 2019
- The World Local Economic Development Forum 2017
- Commonwealth Heads of Government Meeting (CHOGM) 2018
- COP26 preparatory meetings & Mayors and Ministers dialogue on Local and Regional Contributions to achieving the Paris Climate Agreement.

CLGF has used its participation in these fora to disseminate learning and good practice emerging from the LED project, and strengthen the ability of local government to support LED within the framework of their existing mandates.

CLGF has also supported its members through the provision of policy advice. For example, as part of its role in the UN High Level Political Forum (HLPF) Global Taskforce (GTF), CLGF provided inputs to the local government statements on localising SDG 8 and 16 and mobilised members of its executive committee along with its Deputy Secretary General to speak during the 2nd Local and Regional Governments' Forum, in September 2019 within the framework of United National General Assembly high-level week. The Forum saw the adoption of the constituency’s Statement to the SDG Summit. At the 2021 HLPF, SDG8 will be one of the goals to be reported on and CLGF members have been contributing to a report on localisation in their respective countries.

Building on the increasing recognition of local government’s role in achieving the SDGs, CLGF is working closely with other global local government partners to secure a more meaningful partnership between local government and the UN. Discussions about how this will be achieved are currently underway with the UN Secretary-General’s office, with UN Habitat and across the wider UN system.

Prior to its postponement, the CLGF was engaged in preparations for events at the Kigali CHOGM focused on highlighting the role of local government in sustainable development, and drawing on lessons from this programme. CLGF was also working with a cross section of Commonwealth partners, including the Association of Commonwealth Universities, the Commonwealth Architects Association and the Commonwealth Association of Planners, as well as the Princes Foundation and the Government of Rwanda, to highlight the importance of a stronger focus on sustainable urbanisation in the Commonwealth.

Indicator 4.2: CLGF has actively sought to disseminate lessons and experience to the wider CLGF membership. Although the 2020 CLGF biennial conference (CLGC) was postponed due to the Covid-19 pandemic, CLGF decided to develop a series of workshops and convened a number of online meetings to ensure information and experience sharing could continue. Regional seminars on LED and Trade were delivered for Africa, Asia and the Caribbean regions in the 2nd half of 2020, and regional meetings on LED and Resilience were delivered online in West Africa and Asia, as well as dialogues in Southern Africa on Women’s local economic empowerment in 2021.

CLGF continues to be responsive to its members’ requests for support and is currently supporting its members in Fiji, Uganda, Belize and Jamaica on the implementation of national and local LED work. In Uganda, CLGF has worked with the Ugandan Local Government Association and drawn on work undertaken in South Africa to integrate a regional approach into its ongoing work on LED. A project funded through an EU grant was recently launched which will focus on using CLGF’s LED methodology to build “strong & sustainable partnerships leveraging external resources to the local development agenda in line with the SDGs”. In Belize, CLGF is supporting Belize City council on work improving evidence-based municipal planning and decision making to support community inclusiveness and policy development. As part of this work, the council is integrating the CLGF approach to LED into their slum upgrading and public space enhancement work.

CLGF undertook a member’s survey where participants were asked to rate how valuable different elements of the organisation’s LED work were to them. Training courses and participation in LED projects were rated highest in terms of value, followed by accessing tools and materials through the knowledge hub.

In addition, 70% of respondents rated LED as one of the most valuable aspects of CLGF's work to their organisation, and respondents gave both CLGF’s knowledge products and projects & capacity building 4/5 stars when asked to rate these areas (with 5 being the highest rating and zero stars the lowest).

Indicator 4.3 CLGF increased the number of high-quality resources on LED within its knowledge hub and its online resources, and reported significant year-on-year increases in users. CLGF tracked the use of materials on the knowledge hub with journal articles being sighted in other publications nearly 1300 times since 2015, an increase of 319 citations on the 2019 data. CLGF is promoting the knowledge hub through its communication with members and partners toward increasing recognition of it as a key source of information and good practice on local government and LED.

A dedicated knowledge management strategy on resources and good practice on LED was developed and continues to be implemented. CLGF undertook a review of the materials available on the knowledge hub to assess the breadth and quality of these materials and received favourable comment on available resources on equitable economic growth and the experience of Southern countries in the implementation of LED. CLGF continues to work with its research and university partners to increase the number of country specific resources available.

CLGF has produced a regular Journal on Commonwealth Local Governance, which has included articles on LED and has used materials from the knowledge hub to support its work, with e.g. the Cities Alliance, to promote equitable economic growth.

Indicator 4.4: CLGF has successfully leveraged over £3.5million, equivalent to 90% of the FCDO contribution, for work aligned with the programme plans at the global, regional, national and sub-national level. FCDO funding has helped CLGF and its partners to leverage partnerships with other organisations. For example, international donors and partners supporting CLGF cross-Commonwealth partnerships (Microsoft and the Commonwealth Secretariat); national donor programmes (e.g. a €1.9 million contract with the EU Delegation in Zambia for targeted work with local government including LED activities); and CLGF members and partners directly involved in the national and local projects (including the State Government in Madhya Pradesh (India) which is providing 90% of the cost of the LED orientation activities, or the local councils in Ghana which have all made commitments from council budgets to pilot projects designed under the CLGF). This member co-funding of activities supports partner buy-in to the work and provides an important indicator of long-term sustainability through institutionalisation of project work into wider Local Government Association (LGA), Ministry and council practices.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

FCDO’s investment has helped CLGF to secure a significant investment in a larger portfolio of projects in support of LED. CLGF’s advocacy has also ensured that CLGF has been able to champion LED as a strategy for poverty reduction and achieving SDGs across its Commonwealth membership and more widely in international debate and dialogue.

The costs of activities against this output remained within the budget parameters set at the outset of the programme.

Lessons learned through this output, and recommendations for future programming

CLGF’s effectiveness as a Commonwealth organisation and in its wider global advocacy is significantly linked to the evidence base it draws from its project work at country and council level. A strong focus on evidence-based policy making has the potential for real impact with Commonwealth members. CLGF is recognised as a leader on LED and is called on by organisations to ensure that advocacy messages related to LED properly reflect the reality of local governments, both in the challenges and potential result that LED can deliver (as of the case with the Global Task Force submission to the UN High Level Political Forum).

CLGF has deseminated the learning and good practice coming out of the project. Its biennial conference in 2017 had a strong focus on LED and provided an imoortant opportunity to share the outcomes of CLGF’s earlier DFID funded project. While it has not been possible for CLGF to hold an additional biennial conference during the lifetime of this project, it has used regional and national meetings as a means of sharing experience and good practice across its practitioner network and leafership. This has been reinforced by the production of publications, case studies and research drawing on project learning which have been been widely disseminated to its members and partners.

Information on this programme has been shared with the FCDO Commonwealth unit and Cities Team.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating for this programme was MINOR, which has remained stable throughout the project period.

The Business Case reflected that the main major risk to the success of this programme was political change in target countries, and the resulting potential for change of direction within national and/or local administrations. Other risks included: staff turnover and a lack of delivery capacity in LGAs and pilot councils.

Whilst there have been elections, changes in leadership and in some cases instances of political instability in some target countries, commitment to LED among the national, regional and local administrations has remained strong throughout the programme period, with targets achieved in line with anticipated milestones.

CLGF has worked consistently to build buy-in to the programme across the political spectrum in each country, as well as securing a wider more general cross-Commonwealth buy-in to LED as a methodology for delivering sustainable development. It has taken a flexible and adaptive approach to the development of workplans in close partnership with a range of stakeholders so as to ensure a wide base of support for objectives and activities. These have been effective and CLGF’s proactive engagement, local teams on the ground, and pragmatic approach to adaptive management mean the residual risk remained MINOR and the targets have been achieved.

The Covid-19 Pandemic introduced some additional risks; however the extension successfully sought to mitigate these with additional time to adjust and re-prioritise work with partners. Some activities, including the investment fairs had to be moved on-line. Although the income targets were met for the bankable projects in particular, it is impossible to know whether this would have been further exceeded had the fairs been organised as physical meetings. It should be noted that risks arising from the pandemic may impact on the way in which LED is sustained in the long term.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

CLGF has managed to ensure activities have remained on track throughout, and all targets have been met and in line with agreed budget, thanks to an adaptive approach to project management.

CLGF has remained committed to good practice in the management and delivery of its programmes and projects and has a set of internal policies in place to ensure equal opportunities and safeguarding (gender strategy, safeguarding policy, whistleblowing, risk management, etc.) in line with FCDO’s due diligence process. It established a team of staff based in the different regions of the Commonwealth involved in the programme to ensure that programme support was easily accessible to members and downstream partners, and to maximise opportunities for sustaining new approaches and offering opportunities for regional learning and exchange.

The teams in the regions and staff based in London have worked closely together to ensure that the CLGF has been able to provide detailed quarterly narrative and financial reporting (and annual audited statements) to the FCDO programme team, supplemented by regular meetings and communications to ensure FCDO was kept abreast of developments, day to day project management issues, and also to assess and mitigate key risks arising. FCDO has assisted CLGF in engaging DFID (latterly FCDO) country offices and ensuring participation in selected events.

With regard to value for money, the CLGF programme had very little direct procurement of goods and services, however, procurement processes were in place throughout the project and included competitive bidding when specialist services were required for any purchases. As a membership organisation with an extensive network of members and partners, CLGF identified and mobilised technical expertise and capacity at low or often no-cost to the project. In addition to ensuring that the programme could draw on experienced and skilled expertise with experience of working in the local government sector, this also helped to strengthen Commonwealth links and partnerships at the local level.

Date of last narrative financial report	March 2021	Date of last audited annual statement	For Financial Year 2019/20 (dated March 2021)