## Annual Review Template – from April 2020

Title: ReBUILD for Resilience (R4R) Research Programme Consortium (RPC)
Programme Value £ (full life): £7,682,203		Review date: / May 2021
Programme Code: 301133	AMP start date: 01/03/20 / Actual start date: / 01/05/20	AMP end date: / 28/02/26 / Planned end date: / 30/04/26

Summary of Programme Performance
Year	2021
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Not yet published
DevTracker Link to results framework:	N/A

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
Two billion of the world’s poorest people live in fragile and conflict-affected settings and that figure is rising, fuelled by growing inequality, violence, conflicts and other shocks. In these fragile and shock-prone (FASP) contexts progress towards Universal Health Coverage is slow. When health systems experience a shock, it can lead to collapse, a maladaptive response or resilience. Sometimes additional needs can be absorbed by the existing system, other times the system adapts temporarily, alternatively the system undergoes transformation where it permanently changes.
ReBUILD for Resilience (R4R) is an international consortium of organisations from Lebanon, Myanmar, Nepal, Sierra Leone and the UK which examines health systems in fragile settings experiencing violence, conflict, pandemics and other shocks and how these health systems respond. Its aim is to produce high-quality, practical, multidisciplinary and scalable health systems research which can be used to build health systems resilience and improve the health and lives of many millions of people. The primary research question is ‘How do we develop resilience capacities to ensure responsive effective, inclusive, gender-equitable and sustainable health systems in fragile and shock-prone settings?
Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The project has scored ‘A’, fulfilling all contractual requirements in its inception year. Despite significant challenges, including the impact of covid-19 on travel/meeting opportunities and the coup in Myanmar limiting planned activities and partnerships, R4R have laid solid foundations for a successful RPC. The consortium partnership, governance systems and ways of working have been established. The project has developed the research framework, questions and approach, and monitoring, research uptake and capacity strengthening systems are all in place. In addition to achieving their logframe indicators, R4R have conducted a number of research, research uptake and capacity strengthening activities (all outputs available here). To illustrate, four Covid-19 response studies are underway - a draft paper on understanding the politics of sexual and reproductive health adaptation in eastern DRC is already available, whilst drafts from other studies on all partner countries are underway. See also: UHC2030 policy brief on COVID-19 priorities in fragile settings; an interagency brief on health financing research priorities in the COVID-19 era; R4R have also been responsive to FCDO evidence needs, e.g. by updating an earlier literature review on Health Systems Strengthening and leading a health systems learning journey for FCDO advisers.

Major lessons and recommendations for the year ahead [1/2 page]

Key lessons are:
- The importance of flexibility and resilience in the face of changing circumstances - over the past year, R4R have successfully adapted their mode of working, programme activities and plans, and timelines in response to COVID-19, budget changes and a coup in Myanmar.
- The value of building and improving on previous experience – it is clear that this group has benefitted from the experience of managing a previous RPC (ReBUILD). They have built learning from previous experience into their new strategy documents e.g. the Monitoring & Evaluation approach which was developed towards the end of the ReBUILD programme will enable R4R to better monitor stakeholder engagement and uptake from the outset
- The importance of investing in good governance and detailed planning at the start of a programme - R4R have used the inception phase very well to set out governance procedures, detailed workplans, modus operandi, consortium values etc. They have put in place strong foundations on which to build a successful programme

Recommendations
R4R should:
Further revise the logframe and workplan in line with the most recent budget changes introduced by FCDO for 2021/22, by 31 July
- Maintain the ability to adapt (up or down) in the face of current and future uncertainties in context, including budget– to be reflected in all relevant programme documents, by 31 July
- Set out how the programme can be adapted to achieve its objectives in full in the particular context of ongoing uncertainties around working in Myanmar, by 31 July
- Maintain a focus on marginalisation in research studies (ensure sufficient analysis on who is marginalised, specifically in humanitarian/shock/conflict settings, the reasons why (which may be political) and interventions to ensure greater access for marginalised people) - ongoing
- Continue to be responsive to FCDO requests for evidence – build flexibility for this into the workplan and budget – by 31 July

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The ultimate aim of R4R is to build health systems resilience in fragile settings (experiencing violence, conflict, pandemics and other shocks) and so improve the health and lives of many millions of people, by producing high-quality, practical, multidisciplinary and scalable health systems research. The planned research activities are complemented by comprehensive capacity building and research uptake strategies that are designed to increase the ability of key stakeholders to generate and use research evidence at the local, national and international levels.

The programme’s Theory of Change (ToC), developed during the tender process and revised during inception is depicted below. The ToC is underpinned by a series of assumptions, some of which are currently presenting an increased challenge to the programme - budget reductions, COVID-19 related travel restrictions, and political instability and economic shocks across RPC countries. R4R are further revising the logframe (in line with the ToC) for the implementation period in light of these factors and this will be the basis of future monitoring.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The year under review was the inception period and this review assesses a logframe that was designed specifically for the inception period. The planned outcome was to ‘Develop a fully functioning RPC’, and the project has fulfilled all of the objectives of this first year.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The project has met all necessary outputs during the inception period; this provides a solid foundation for implementation going forward.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]
Output Title	Delivery of satisfactory inception report
Output number:		1	Output Score:	A
Impact weighting (%):		100%	Weighting revised since last AR?	No

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

R4R has delivered an excellent inception report with detailed annexes across all of the expected deliverables listed above. All milestones have been met and, in some cases, exceeded. In addition to establishing robust governance structures around due diligence, partner collaborations, financial and project management and monitoring systems, R4R have set up strong approaches to research uptake and capacity strengthening.

A detailed research framework has been developed and ten research hypotheses on resilience selected on this basis to be tested and refined. There are two broad approaches – (1) Learning sites: medium to long-term research platforms in specific districts or geographical areas, which facilitate collaboration between researchers, health managers and local stakeholders. These sites facilitate action research cycles and longitudinal research into barriers, adaptations, and responses to adaptations, and allow R4R to study the impact and management of shocks and stressors in real time. The first site will start in year 2; and
(2) Thematic research, which will be undertaken by partners and associates, building on activities, priorities and opportunities identified in the inception phase.

In addition to development of the framework and hypotheses, the consortium has developed four COVID-19 responsive fund studies, which have all received ethical approval and are collecting data. The studies include “Understanding health system resilience to respond to COVID-19 in federalised context…” (Nepal); and “The gendered experience of close to community providers in FSAP settings; implications for policy and practice during and post COVID-19 (Lebanon, Sierra Leone, Nepal, Myanmar). Outputs (peer and non-peer reviewed) will be produced by September 2021.

The Health Systems Strengthening literature review, produced in 2019 for FCDO, has been refreshed and shared.

The capacity building strategy is based on strong principles (multi directional, multi-level (individual, organisational and enabling environment), strong focus on southern lead research, a detailed baseline assessment and detailed activity plan across research, uptake and management, and an M & E plan to measure changes. The capacity building strategy links across to other workstreams.

The communications and research uptake strategy is well developed, with clear objectives and audience, key messages, outputs and tactics on the demand and supply side which are well defined at global, regional, and focus-country level, across all partners. Recognising that policy windows may also arise, technical ability may increase take up. Measures of success are laid out. There is a strong link with the capacity building strategy, the monitoring and evaluation strategy, and with the gender, equity and inclusion approaches.

The project has demonstrated compliance with open access publishing and data sets.

The project has developed a comprehensive monitoring framework and logframe indicators also developed (albeit that the logframe is subject to further revision).

The project has a comprehensive approach to gender and equity.

Robust approaches to governance and management arrangements have been put in place, including a management team, management committee and working groups, and the consortium advisory group which first met in October 2020. The VfM strategy has been outlined with good focus on financial metrics and equity. A safeguarding training session was held during the inception year and country risk assessments have been completed. The first annual consortium meeting was held virtually in November 2020, and the programme has developed strong partnership values, describing how partners will equitably work together as a consortium.
In the inception year, R4R have completed research, research uptake and capacity strengthening activities. Further outputs – available here - build on the previous phase of R4R (ReBUILD). These include a UHC2030 policy brief on COVID-19 priorities in fragile settings; an interagency brief on health financing research priorities in the COVID-19 era; participation in the Health Systems Global Thematic Working Group on Fragile and Conflict-Affected Settings (TWGFCAS); participation in the gender and COVID-19 working group; contribution to UNHCR panel on financing refugee health care; contributions to the Lancet Commissions on Syria and Migration and Health; leading a health systems learning journey for FCDO advisers; producing blogs for mental health day and UHC day; presenting at THET conference on health system strengthening and international partnerships; supporting drafting of NIHR brief on health system resilience in COVID era; contributing to HSG panels (for example, on learning health systems); monthly consortium training events on communication skills and hosting of an external webinar on disability-inclusive health systems in fragile and shock-prone settings.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

R4R’s VfM strategy is sound and outlines the RPC’s approach across all 4xEs (economy, efficiency, effectiveness and equity). The work of the consortium over the past year has represented very good VfM for FCDO. They have produced all of the outputs required of the inception period to a very high standard. Moreover, as outlined above, R4R have hit the ground running and delivered outputs across the 3 key components of research, research uptake and capacity building during the inception period. They have responded well to capturing lessons from the COVID-19 pandemic and to FCDO’s request that they update the health systems strengthening literature review. In summary, R4R have effectively delivered beyond the basic requirements of the inception year despite the challenges of developing a consortium during COVID-19; they have laid solid foundations which should stand them in very good stead for delivering VfM over the programme’s lifetime.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The output this year was specific to the inception period. Changes include adjustments to the inception year workplan at the beginning of year 1 to ensure that deliverables were achievable in the context of COVID-19 (e.g. no international travel, data collection activities for the four COVID-19 research studies were carried out by researchers in person only when appropriate and virtual means were used in the majority of studies). There was a pause in all Myanmar related activities following the coup in early February 2021 and a further revision to the workplan/logframe is in hand to take account of that and a budget reduction in 2021/22.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

No previous recommendations. Lessons & recommendations for the year ahead are outlined above.

D: RISK [½ to 1 page]

Overview of risk management
The project holds its own risk register that is monitored and discussed with FCDO at regular meetings. FCDO manages its own risk register and matrix.

Overall risk rating: The overall risk rating is currently Moderate. The risk assessment was updated in May 2021 following receipt of the inception report. This has been updated to align to the new FCDO risk management system. The risks are all within FCDO’s risk appetite.

Overview of project risk and mitigation
Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Moderate	Moderate	Minor	Moderate	Moderate	Minor	Moderate

Strategy and Context – Major – The project works in countries at risk of crises, including the current impact of COVID-19 on project activities. This is closely monitored and project activities are being adapted where possible. It has been recognised from the outset that instability in RPC countries, notably Lebanon and Myanmar, risk potentially negatively impacting on RPC activities, timelines and budgets. There is currently a heightened risk in Myanmar as a result of the recent coup. This is being managed effectively with only desk based activities ongoing and on the premise that there is no interaction with the local government; this situation will be kept under review. The programme has experience of working on research in fragile environments and identified opportunities to learn about health systems response during and after COVID-19.

Policy and Programme Delivery – Moderate – The project depends on strong partnerships with local consortium members; and with stakeholders in each country (particularly for successful uptake of findings, policymakers and practitioners). The risk is of a high turnover of partners or policymakers that results in delayed/non-delivery of research to time and budget; and that stakeholders are not engaged or unable to implement research findings. This is being mitigated by establishing strong relations from inception and the research questions are being developed in line with local needs. LSTM has strong institutional experience of managing an RPC working on health systems research in shock prone contexts.

Public Service Delivery and Operations – Moderate – This risk is that partners are challenged to understand FCDO’s systems and priorities. This has been mitigated by frequent meetings and clear guidance provided through the inception phase, providing a strong platform moving forward into implementation. Several R4R partners have experience of working on a DFID funded RPC and are familiar with guidelines / requirements /expectations.

People – Minor – The consortium has developed good systems and processes to ensure there is a strong culture of peer support, equity within the consortium and that capacity strengthening is embedded within the project.

Safeguarding – Moderate – This arises from the potential for harm caused by research activities in the focus countries, which may be heightened in context of COVID-19. LSTM have a strong safeguarding policy (developed jointly with a number of other international research programmes), in line with guidance from FCDO on our safeguarding policy. Consortium wide training was held during the inception year to discuss the key principles of safeguarding and identify a safeguarding lead within each partner organisation. Each partner will/has conduct/ed a risk assessment to highlight any capacity gaps around safeguarding, and will work with the LSTM safeguarding lead to strengthen these areas.

Financial and Fiduciary – Moderate – LSTM has comprehensive financial management procedures and has demonstrated that good governance and financial systems are being put in place to help protect from fraud or misuse of funds. Training and capacity development across financial management procedures are also to be considered as part of capacity strengthening strategy.

Reputational – Minor – The research topics are not controversial and it is not expected, at this stage, that findings will be contentious. LSTM is an experienced FCDO research partner with strong governance and ethics and a good understanding of DFID expectations around standards and appropriate use of funds.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

The R4R Research Programme Consortium (RPC) contract started on 1st May 2020 after a delayed procurement competition. Liverpool School of Tropical Medicine (LSTM) has overall management of the consortium working with various core delivery partners, in Myanmar, Nepal, Lebanon and Sierra Leone:

- Queen Margaret University, Edinburgh
- College of Medicine and Allied Health Sciences, Sierra Leone
- American University of Beirut, Lebanon
- Burnet Institute, Myanmar (It was initially planned that the Department of Medical Research in Myanmar would also be a partner)
- HERD International, Nepal
The team has successfully completed its inception phase. Throughout this period, FCDO Health Research Programme Team has collaborated, working closely with the LSTM Research Director and Chief Executive Officer and Research Director at Queen Margaret University, managing contractual terms and conditions, developing workplans and providing uptake links with other FCDO advisors and research programmes.

There were quarterly progress meetings between the consortium and FCDO to discuss progress on partner agreements, country research project development, ethical implications, project risk, finance and forecasting. There have been additional ad hoc meetings to discuss specific issues such as working in Myanmar and budget changes.

Due to the impact of COVID-19 and pressure on the global and UK financial economies, the R4R programme budget was reduced in year 1, with spending deferred into years 2 and 3. LSTM adapted workplans to the budget reduction well: given that global travel and meetings were a large part of the inception year budget, with staff moving to working at home full time and using digital technology, savings were identified. Procurement and Commercial Department colleagues were consulted throughout the contract amendment process to ensure compliance. A contract amendment was issued to reflect revised workplan activities, budget changes and revised commercial proformas. The ongoing impact of the pandemic continues to be closely monitored and appropriate risk mitigations put in place.

R4R are currently revisiting their workplan and budget to take account of an FCDO initiated budget reduction in 2021/22.

The first Consortium Advisory Group (CAG) meeting was held in October 2020. The CAG supports R4R through strategic oversight and guidance, and is represented by members with skills complementary to those in R4R, including expertise in health systems, FASP settings, gender & equity, policy and research uptake and capacity building. The 2nd CAG meeting has been scheduled for 3rd June 2021.

A strong, effective Financial Management Plan has been developed as part of the inception report, with LSTM developing and implementing a series of reporting and audit processes to mitigate financial risk in the delivery chain and aid the smooth running of the programme. The Financial Management Plan and reporting templates set out the high expectations of the consortium to include open book accounting, transactional reporting and audit spot checks.

Invoices are paid quarterly in arrears. Regular, efficient forecasts were received throughout the year from the LSTM Programme Manager. Technical progress and financial narrative reports are submitted quarterly in advance of invoice payments being released.

Moving into implementation, regular forecasting updates will be required as close monitoring of budgets is a high priority, ensuring effective delivery, accountability and transparency of the British Taxpayers GBP.

LSTM Annual Report and Financial Audited Statements have been submitted to FCDO for audit compliance.

Date of last narrative financial report	30/4/21	Date of last audited annual statement	31/12/20