## IDT PORTFOLIO LOGFRAME
PROJECT NAME | Strategic collaboration with UK statistics system
IMPACT | Impact Indicator 1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
Quality, timely, reliable and disaggregated data is available and used worldwide to support delivery of the Global Goals and ensure no one is left behind. | World Bank Statistics Capacity Building Score for primary partner countries: - Kenya (KNBS) - Ghana (GSS) - Rwanda (NISR) | Planned | Kenya 57.8 Ghana 68.9 Rwanda 77.8 | (No target documented) | Kenya 57 Ghana 73 Rwanda 80 | Kenya 58 Ghana 74 Rwanda 81 | Kenya 59 Ghana 75 Rwanda 82
|  | Achieved |  | Kenya 55.6 Ghana 71.1 Rwanda 78.9
Source
World Bank Statistics Capacity Building Score http://datatopics.worldbank.org/statisticalcapacity/
| Impact Indicator 2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of SDG indicators with at least one data point in the last five years (for primary partner countries): - Ethiopia (ACS, part of UNECA) - Kenya (KNBS) - Ghana (GSS) - Rwanda (NISR) | Planned | Rwanda 56
Achieved
Source
SDG team
OUTCOME1 | Outcome Indicator 1.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Increased availability and frequency of high quality disaggregated data | Cumulative number of case studies of changes in quality, frequency or coverage of national data sets in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology) | Planned | 0 | 1 | 5 | 10 | 12
|  | Achieved |  |  | 11
Source
ONS reporting
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTCOME2 | Outcome Indicator 2.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Increased availability and frequency of high quality disaggregated data | Cumulative number of case studies of capacity building in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology) | Planned | N/A | N/A | N/A | 10 | 12
|  | Achieved | N/A | N/A | N/A
Source
ONS reporting
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
TIER 1 PARTNERSHIPS
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumption
Kenya National Bureau of Statistics increases the availability and quality of SDG data, and capacity is built, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3
|  | Achieved |  | 1 | 3
Source
DFID and ONS joint assessment
| Output Indicator 1.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of national statistical strategies / sectoral modernisation plans or equivalent developed informed by ONS support and advice | Planned | 0 | 0 | 2: (communications strategy and strategic plan) | 4; (cumulative - + Code of Practice and NSDS) | 5 (cumulative + Code of Practice)
|  | Achieved |  |  | 2
Source
KNBS/ONS reporting; Indicator added in 18/19
| Output Indicator 1.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Case Studies of where ONS support and delivery of the workplan has helped deliver changes to how KNBS operates | Planned | 0 | 0 | 2 | 4 | 6
|  | Achieved |  |  | 2
Source
KNBS/ONS reporting; Indicator added in 18/19
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Number of people trained with ONS support and rating training as effective | Planned | 0 | 0 | 5 | 15 | 30
|  | Achieved |  |  | 0
|  | Source | [5 empty] | RISK RATING
|  | KNBS/ONS reporting; Indicator added in 18/19 | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
550000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Ghana Statistical Service increases the availability and quality of SDG data, and capacity is built, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 4
|  | Achieved |  | 1 | 3
Source
DFID and ONS joint assessment
| Output Indicator 2.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of cases of where ONS have provided advice on strategic policy documents: (e.g. Statistical Bill, communications strategy, other policy documents) and there is evidence that this advice has had an influence on the final product (cumulative) | Planned | 0 | 0 | 2 | 3 | 5
|  | Achieved |  |  | 4
Source
ONS reporting: Indicator added in 2018 AR
| Output Indicator 2.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of leaders mentored and/or trained by ONS support, and rating training as effective (cumulative number of individuals) | Planned | 0 | 0 | 20 | 50 | 50
|  | Achieved |  |  | 40 GSS leaders have received training x1 GSS Senior Leader has taken up ONS mentoring
Source
ONS reporting Indicator added in 2018 AR
| Output Indicator 2.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative). | Planned | 0 | 0 | 3 (2 from the following examples: SDGs NRP, data templates (inc metadata) and new data sources groundwork ) | 5 | 5
|  | Achieved |  |  | 2
Source
ONS reporting Indicator added in 2018 AR
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Examples of where ONS support has led to more rigorous statistical infrastructure and systems; that are sustainable and promote good practice (e.g. statistical standards and concepts, adoption of national or international standards, programmes to upskill staff etc) | Planned | 0 | 0 | 2 | 3 | 5
|  | Achieved |  |  | 3
|  | Source | [5 empty] | RISK RATING
|  | ONS reporting Indicator added in 2018 AR | [5 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
550000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Rwanda Statistics Office increases the availability and quality of SDG data, and capacity is built, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3 | GoR support for legal reforms. Supportive environment for innovation in NISR and broader GoR. Engagement from stakeholders also involved in data science in Rwanda (other government departments, universities etc) World Bank and GoR commitment to complete training centre
|  | Achieved |  | 3 | 3
Source
DFID and ONS joint assessment
| Output Indicator 3.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of national statistical strategies / sectoral modernisation plans / NISR strategies and policies or equivalent informed by ONS advice during the reporting period (not cumulative) | Planned | 0: NSDS 2 evaluation supported by ONS in 2017, concluded that NSDS 3 needs to integrate data revolution policy | 1: NSDS3 drafted by June 2018 with clear integration of data revolution strategy as informed by ONS advice in areas such as capability, IT and legal frameworks | 1: Final NSDS published with clear evidence of ONS inputs. Progress towards NSDS3 objectives being made | Total: 3 first drafts + 1 completed document First drafts: Security Strategy, Data Protection law, Data Management Policy Complete: QA protocol for SDG indicators published and being implemented (adapted, increased) | Total: 3 examples where ONS has advise on the draft of a new policy or refine an existing policy or draft policy.
|  | Achieved |  | 2: Two completed documents, plus ongoing advice on legal framework that is shaping NISR’s approach but has not yet resulted in a published document - NSDS3 finalised with clear evidence of ONS inputs. - Terms of Reference for ICT infrastructure tender published online in July 2019 | 1
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| Output Indicator 3.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Cumulative number of active or complete data science projects ONS has supported (eg scoping, mentorship) | Planned | None | One project underway | One published and one more underway | Target: 5 2 scoped (GIS visit) 2 with active mentorship 1 complete (BNR visualisation). | Target: 8 3 scoped 2 with active mentorship 3 complete
|  | Achieved |  | One project (SDG platform) underway and two more being scoped | 1
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| Output Indicator 3.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Case Studies of where ONS has helped NSOs to develop training materials / capacity development approaches | Planned | 0 | 1: milestones towards establishing NISR Training Centre and Data Hub on track | 1: milestones towards establishing NISR Training Centre and Data Hub on track | Target: 2 - Training facilitators for L&C training - Develop induction materials for new data science team | Target: 1 - Revised capability-building plan for data science
|  | Achieved |  | 1: in 2018 ONS data science campus undertook training needs assessment and developed a draft capability plan | 1
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Cumulative number of instances where people are trained with ONS support, and rating training as effective (cumulative) Note: if one person attends 2 different courses they will be counted twice (once for each course) | Planned | 0 | 180 | 270 | 100 | 150
|  | Achieved |  | 1 | 50 staff trained on Python
|  | Source | [5 empty] | RISK RATING
|  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring | [5 empty] | Low
| Output Indicator 3.6 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of SDG indicators where ONS has provided methodological advice to either fill a data gap or improve the quality of existing data for that indicator | Planned | N/A | N/A | N/A | 1 | 3
|  | Achieved | N/A | N/A | N/A
|  | Source | [5 empty] | RISK RATING
|  | NISR / ONS reporting | [5 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 576355 | [5 empty] | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
UNECA provide an enabling environment for African National Statistics Offices, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3
|  | Achieved |  | 2 | 2
Source
DFID and ONS joint assessment
| Output Indicator 4.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Examples where ONS and UNECA have supported improvements to national statistics through support on specific topics (e.g. census, economic statistics, or CRVS ) | Planned | 0 | 0 | 3 | 5 | 4
|  | Achieved |  |  | 2
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 4.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Africa Statistical Leaders mentored or trained through UNECA led, ONS supported training, and rated training as effective | Planned | 0 | 0 | 30 | 60 | 45
|  | Achieved |  |  | 0
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 4.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Case Studies of where ONS support and delivery of the workplan has helped deliver changes to how UNECA operates | Planned | 0 | 0 | 2 | 3 | 4
|  | Achieved |  |  | 2
Source
ONS reporting: Indicator added in 2018/19
IMPACT WEIGHTING (%) | Output Indicator 4.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Number of examples where ACS have supported UNECA customers and/or African countries in the use/application of data science techniques or jointly worked with African countries on data science projects. | Planned | 0 | 0 | 1 | 2 | 3
|  | Achieved |  |  | 0
|  | Source | [5 empty] | RISK RATING
|  | ONS reporting: Indicator added in 2018/19 | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
550000
INPUTS (HR) | DFID (FTEs)
GLOBAL PROGRAMMES
OUTPUT 5 | 5A) International Cooperation: influencing on statistical modernisation
| Output Indicator 5.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Weighted average (by spend) of scores for flexible facility activities related to ONS engagement in key data for development international events | Planned | Not measured | A | A | A | A
|  | Achieved |  | A++ | A+ | TBC | TBC
Source
Each relevant flexible facility project will set out clear targets and indicators in the terms of reference, which must be agreed by the DFID/ONS steering committee. These will be monitored after the event and reported back to the steering committee. A weighted average of the scores (on the scale A++, A+, A, B, C) using DFID output scoring methodology will be calculated as part of the annual review.
5B) SDGs: ; advice and TA on SDG monitoring, reporting, and data disaggregation
| Output Indicator 5.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of case studies of partner countries successfully cloning and using UK/US SDG platform as a direct result of ONS support (cumulative) | Planned | 0 | 1 | 3 | 5 | 6
|  | Achieved |  | 2 | 3 | TBC | TBC
Source
Case Studies to be documented by ONS and verified by national NSO. Case studies count if ONS provided direct inputs and they have gone on to use / publish / further develop the tool.
| Output Indicator 5.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Expert advice on data disaggregation to support the SDGs and the leave no one behind agenda provided to champions in the implementation of their IDC action plans. | Planned | N/A | N/A | N/A | 1 | 3
|  | Achieved | N/A | N/A | N/A
Source
Case Studies to be documented by ONS and verified by national NSO. Case studies count if ONS provided direct inputs and they have gone on to use / publish / further develop the tool.
C) Economic Stats (leadership and effective TA);
| Output Indicator 5.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Effective progress towards targets in workplan for project to improve the quality consistency and dissemination of statistics on employment and productivity | Planned | N/A | A | A | A | A
|  | Achieved |  | B | B
Source
Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
| Output Indicator 5.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Effective participation of ONS in ICP technical working groups | Planned | No participation | Workplan developed and participation initiated. Targets for future years set. | A | A | A
|  | Achieved |  | Targets for ONS participation have been set and participation has been initiated. | A
Source
Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
D) Data Science; awareness raising, projects and capability building
| Output Indicator 5.6 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Effective progress towards targets in workplan for establishment of data science campus hub in DFID East Kilbride | Planned | N/A | N/A | A | A | A
|  | Achieved |  | N/A | A+ | TBC | TBC
Source
Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
IMPACT WEIGHTING (%) | Output Indicator 5.7 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
30% | Effective progress towards developing a new tool for storing, and analysing results and finances data – Data Trailblazer [FF5] | Planned | N/A | N/A | A | A | A
|  | Achieved |  | N/A | A | TBC | TBC
|  | Source | [5 empty] | RISK RATING
|  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
£2.3 million?
INPUTS (HR) | DFID (FTEs)
TIER 2 PARTNERSHIPS
OUTPUT 6 | Output Indicator 6.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Deliver effective TA to Tier 2 partner countries in identified areas: | Namibia (Qualitative) | Planned | N/A | N/A | N/A | Positive feedback from secondee to ONS data science campus, that IDT supported her wider learning | Positive feedback from NSA management that ONS has followed up on commitments to support data science
Achieved
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 6.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| India (Qualitative) | Planned | N/A | N/A | N/A | Positive feedback from MOSPI senior leadership on high level exchange visit; Plans for follow up work made and targets for 2021 set | N/(A to be decided after the outcome of the study visit)
Achieved
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 6.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Nepal (Qualitative) | Planned | N/A | N/A | N/A | Report on initial visit produced; positive feedback on ONS advice; and decision on future collaboration | N/A to be decided depending on the scoping visit outcome
Achieved
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 6.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Zambia (Qualitative) | Planned | N/A | N/A | N/A | Positive feedback from CSO that support delivered from IAOS conference was helpful in building wider capacity. | N/A current involvement in IAOS will finish and the future involvement will be decided
Achieved
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 6.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Sierra Leone (Qualitative) | Planned | N/A | N/A | N/A | Scoping report produced and decision on future relationship taken. | N/A to be decided depending on the scoping visit outcome
Achieved
Source
ONS reporting: Indicator added in 2018/19
IMPACT WEIGHTING (%) | Output Indicator 6.6 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
10% | China - number of visits per year (either to China or UK) (Quantitative) | Planned | N/A | N/A | N/A | 1 | 1
|  | Achieved | N/A | N/A | N/A
|  | Source | [5 empty] | RISK RATING
ONS reporting: Indicator added in 2018/19
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Ref Outcome 1.1 Method
1.1 Cumulative number of case studies of changes in quality, frequency or coverage of national data sets in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology)
| Contribution of ONS | Major |  | Count these for narrative reporting but not scored towards the target | Score case studies in this area
Moderate
Some Minor
Insignificant
|  |  | Insignificant | Minor | Moderate | Major
Impact on national data sets

## Ref DS Campus Method
| B | A | A+ | A++
C
Administration | No planning documents in place | Some of the key planning documents developed | Theory of change, risk register, issue register and stakeholder map all developed in a consultative way and being periodically used and updated | Theory of change, risk register, issue register and stakeholder map all developed in a consultative way and being regularly used and updated | All documents in place, and evidence that these are really driving prioritisation and enabling the hub to be most effective
Capability | No report | Report on MDataGov materials and adaptations to use in international development context; | Report, plus some progress towards adapting materials and methodologies for delivering data science training to NGO / international agency staff, both producers and consumers of data science | Report, plus full suite of adapted materials and methodologies | Report, full suite of materials, and training being rolled out.
Decision support tool scoping | A few or no fully formed project proposals, or a lack of real prioritisation | A good list of ideas, but no real sense of prioritisation or links to the theory of change | A long list of project proposals, prioritised, with a short list of scoped and researched projects. Projects underway. | As A, and at least one demonstrator project that illustrates the unique offers of the Data Science Hub and can be used in decision making for those in the International Development community. | As A, plus more than one demonstrator project, or at least one which demonstrated real impact through its use in the international development community.
Mentoring | No mentoring | Mentoring scheme developed, with some of the data science staff engaging externally | Each of the Data Scientists recruited has regular face to face contact with members of their potential user community | Each of the data scientists recruited also has a strategic mentoring relationship through which they are helping to automate the use of data in a partner organisation | A demonstrated impact on automating the use of data in a partner organisation, due to these mentoring relationships can be seen

## Ref Partnership indicators
Progress towards establishing an effective project workplan
| 4 | 3 | 2 | 1 | 0
| As per 3 with measurable progress towards outputs taking place | As per 2, with some quick wins starting to take place | Clear work plan agreed between ONS and partner, with tangible activities and measures of success identified | Potential areas for collaboration identified but no workplan developed | No workplan in place
Partner | 2017 (baseline) | 2018 (target) | 2018 (actual) | 2019 (target) | 2019 (actual) | 2020 (target) | 2020 (actual)
Rwanda | 0 | 2 |  | 4 |  | 4
Kenya | 0 | 2 |  | 4 |  | 4
Ghana | 0 | 2 |  | 4 |  | 4
UNECA | 0 | 2 |  | 4 |  | 4
Measure of partner commitment towards establishing effective partnership with ONS
| 4 | 3 | 2 | 1 | 0
| Agenda being fully driven by partner: setting the priorities, pushing ONS to deliver in a timely way | Partner engages positively and proactively ensures that ONS support is being channelled to their most pressing needs | Partner engaged with ONS, respond positively and quickly to suggestions for support, provides their views openly and in a timely way e.g on the priorities and timings for the activities | Agreement that a partnership would be beneficial, but limited evidence of commitment from partner so far, content of partnership and timings for visits largely being driven by ONS. | Only very preliminary indication of commitment from partner for a partnership with ONS
Partner | 2017 (baseline) | 2018 (target) | 2018 (actual) | 2019 (target) | 2019 (actual) | 2020 (target) | 2020 (actual)
Rwanda | 1 | 2 |  | 3 |  | 3
Kenya | 0 | 2 |  | 3 |  | 3
Ghana | 0 | 2 |  | 3 |  | 3
UNECA | 0 | 2 |  | 3 |  | 3

## AR 2019
Strategic collaboration with UK statistics system
Results Chain |  |  |  | Indicators | Planned | Achieved | Score |  | Source
2019
IMPACT | Quality, timely, reliable and disaggregated data is available and used worldwide to support delivery of the Global Goals and ensure no one is left behind. |  | World Bank Statistics Capacity Building Score for primary partner countries: - Kenya - Ghana - Rwanda |  | 0% | 0% |  | #N/A | 0
|  |  | Number of SDG indicators with at least one data point in the last five years (for primary partner countries): - Kenya - Ghana - Rwanda |  | 0 | 0 |  |  | 0
OUTCOME | Increased availability and frequency of high quality disaggregated data |  | Cumulative number of case studies of changes in quality, frequency or coverage of national data sets in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology) |  | 5 | 0 |  | #N/A | ONS reporting
|  |  | 0 | [5 empty] | 0
OUTPUTS | Kenya National Bureau of Statistics increases the availability and quality of SDG data, with ONS support | 15% | 1.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 4 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 1.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | DFID and ONS joint assessment
|  |  | 1.3 | Number of national statistical strategies / sectoral modernisation plans or equivalent developed informed by ONS support and advice | 2: (communications strategy and stratgic plan) | 0 |  |  | KNBS/ONS reporting; Indicator added in 18/19
|  |  | 1.4 | Number of stories of change of where ONS support and delivery of the workplan has helped deliver changes to how KNBS operates | 3 | 0 |  |  | KNBS/ONS reporting; Indicator added in 18/19
|  |  | 1.5 | Number of people trained with ONS support and rating training as effective | 5 | 0 |  |  | KNBS/ONS reporting; Indicator added in 18/19
| Ghana Statistical Service increases the availability and quality of SDG data, with ONS support | 15% | 2.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 4 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 2.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | DFID and ONS joint assessment
|  |  | 2.3 | Number of cases of where ONS have provided advice on strategic policy documents: (e.g. Statistical Bill, communications strategy, other policy documents) and there is evidence that this advice has had an influence on the final product (cumulative) | 0 | 0 |  |  | ONS reporting: Indicator added in 2018 AR
|  |  | 2.4 | Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative). | 20 | 0 |  |  | ONS reporting Indicator added in 2018 AR
|  |  | 2.5 | Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative). | 3 | 0 |  |  | ONS reporting Indicator added in 2018 AR
|  |  | 2.6 | Examples of where ONS support has led to more rigorous statistical infrastructure and systems; that are sustainable and promote good practice (e.g. statistical standards and concepts, adoption of national or international standards, programmes to upskill staff etc) | 0 | 0 |  |  | ONS reporting Indicator added in 2018 AR
| Rwanda Statistics Office increases the availability and quality of SDG data, with ONS support | 15% | 3.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 4 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 3.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.3 | Number of national statistical strategies / sectoral modernisation plans or equivalent informed by ONS advice | 1: Final NSDS pubished with clear evidence of ONS inputs. Progress towards NSDS3 objectives being made | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.4 | Number of joint data science projects, with published results | One published and one more underway | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.5 | Number of Stories of change of where ONS has helped NSOs to develop training materials / capacity development approaches | 1: milestones towards establishing NISR Training Centre and Data Hub on track | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.6 | Number of people trained with ONS support, and rating training as effective (cumulative) | 270 | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| UNECA provide an enabling environment for African National Statistics Offices, with ONS support | 15% | 4.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 3 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 4.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | DFID and ONS joint assessment
|  |  | 4.3 | Number of examples of where ONS and UNECA have supported improvements to national statistics through support to the census office on specific topics (e.g. economic statistics, CRVS or gender data) | 3 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.4 | Number of Africa Statistical Leaders mentored or trained through UNECA led, ONS supported training, and rated training as effective | 30 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.5 | Number of stories of change of where ONS support and delivery of the workplan has helped deliver changes to how UNECA operates | 2 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.6 | Number of examples where ECA have supported African countries in the use/application of data science techniques or jointly worked with African countries on data science projects. | 1 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.7 | Number of examples of where ONS and UNECA have supported improvements to national statistics through support to the census office on specific topics (e.g. economic statistics, CRVS or gender data) | 3 | 0 |  |  | ONS reporting: Indicator added in 2018/19
| Flexible short term technical assistance delivers effective results | 40% | 5.1 | Weighted average (by spend) of scores for flexible facility activities related to ONS engagement in key data for development international events | A | 0 |  | #N/A | Each relevant flexible facility project will set out clear targets and indicators in the terms of reference, which must be agreed by the DFID/ONS steering committee. These will be monitored after the event and reported back to the steering committee. A weighted average of the scores (on the scale A++, A+, A, B, C) using DFID output scoring methodology will be calculated as part of the annual review.
|  |  | 5.2 | Number of case studies of partner countries successfully cloning and using UK/US SDG platform as a direct result of ONS support (cumulative) | 3 | 0 |  |  | Stories of change to be documented by ONS and verified by national NSO. Case studies count if ONS provided direct inputs and they have gone on to use / publish / further develop the tool.
|  |  | 5.3 | Effective participation of ONS in ICP technical working groups | A | 0 |  |  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
|  |  | 5.4 | Effective progress towards targets in workplan for project to improve the quality consistency and dissemination of statistics on employment and productivity | A | 0 |  |  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
|  |  | 5.5 | Effective progress towards targets in workplan for establishment of data science campus hub in DFID East Kilbride | A | 0 |  |  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
#REF!
#REF!

## Ref Scoring
The below explains the meaning of the letter-based scoring approach. If, for example, an output is exceeded by 50% of the stated target, so achieves 150% or 1.5 times its intended value, it would lead to an A++ score at Annual Review.
A++ | 150%
A+ | 125%
A | 100%
B | 75%
C | 50%