Annual Review - Summary Sheet
Title: AAWAZ Voice And Accountability Programme, Pakistan
Programme Value: £34.3 million		Review Date: May 2015
Programme Code:	Start Date: May 2012	End Date: May 2017

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	B	A	A
Risk Rating	Medium	Low	Medium

Summary of progress and lessons learnt since last review
The Annual Review (AR) in 2014 was very critical of some areas of AAWAZ's work so, alongside the usual reports, the AR Team created a timetabled Action Plan covering five priority areas to ensure timely remedial action was taken. The Management Organisation (MO) and four consortium partners responsible for implementation of the project responded well to the challenge. The Action Plan was translated into a seven section Annual Review Action Plan.[1] Despite the size of the task, the project has made good progress in implementing both the Plan other key recommendations from the AR team.
[1] This covered: M&E and learning; VFM and more flexible budgets; strengthening of the MO; capacity building; reorientation of Output 2; revitalising AAWAZ forums and Aagahi Centres; and a seventh catch all section covering improving advocacy, engaging with youth as agents of change; updating core documents including the theory of change, supporting women to contest elections, etc.

The project now has a solid baseline for measuring performance and a revised and much improved M&E system. Documents providing a conceptual framework for the programme including a theory of change, revised logframe, gender strategy and VFM framework have been finalised. Output 2 has been reoriented away from conflict resolution to pre-emption.

Considerable progress has been made in raising community awareness on gender relations, inclusion and rights. Its behaviour change workshop has met with enthusiasm from members of village forums where it has been rolled out. Individuals from excluded groups are now participating in AAWAZ forums at all levels although the quality of their participation should be improved. Relocation of the Aagahi centres to safer, more accessible sites plus the fact that 430 of 450 Centres are run by female resource persons, is attracting more women visitors. At District level, successful advocacy along with AAWAZ campaigns have raised the project's visibility and credibility with local officials and politicians resulting in positive two-way dialogue processes. In many Districts, forum members now sit on the official peace committees.

The MO has been strengthened significantly and is able to provide first class technical support to the programme. Its Senior Management Team and Strategic Learning Unit are both working well and quarterly reporting has improved steadily, to focus on results rather than activities. Financial systems across the programme have been strengthened and the 2014 costed workplan was a distinct improvement on 2013's. The fact there is no straightforward way to record payments to CBO implementing partners, caused problems during the year. This issue needs to be resolved. Increased support from DAI Europe has been an important element in this progress.

Overall, AAWAZ staff say that the 2014 AR had a positive impact. Despite the increased workloads associated with implementing the Action Plan, the results have been rewarding. Senior staff in the MO and the partners appreciate the significant level of support and guidance provided by DFID during first six months after the AR. DFID’s role was critical in helping AAWAZ take ownership of, and implement, the Action Plan. In addition, significant increases in the support provided by DAI Europe have ensured an improvement in the MO's performance and kept progress on track.

AAWAZ met or exceeded the targets for almost all key indicator milestones. Members of the 2014 AR team involved in this 2015 AR, were struck by a new, positive energy amongst AAWAZ staff at all levels. Many staff made the point that for the first time they feel that they are now working as one team with one vision for the AAWAZ project. Notwithstanding the progress made last year, the AR team has identified e a number of areas that should be improved. These are discussed in Sections B and C below.

Summary of key recommendations for the next year
The overall recommendation for the coming year is to increase the pace of implementation while simultaneously deepening the quality of the work. The focus should be on outcomes and making these sustainable. To ensure this happens and the recommendations of this review are implemented, AAWAZ should create its own action plan for the coming year.

Make capacity building a central pillar of AAWAZ's work. More extensive, more professional and strategically targeted capacity building is essential for deepening quality. Key areas include gender equality, women's political leadership, advocacy, tools for strengthening inclusion and for pre-empting violence, citizens' rights re the state, strategic planning and how to maintain and sustain village forums. Special attention should be paid to those at the grassroots, including CBO/CPOs/activist implementers.

In order to facilitate the combination of increased speed and quality above, AAWAZ should embrace the use of high quality specialist STTA, both local and international. Other DFID programmes of a similar size and complexity do this, as indeed does DFID itself.

Revitalise the AAWAZ steering group (ASC) and ensure it receives from the MO the synthesised programme and financial management information it needs to play a more strategic oversight role.

Improve levels of critical, analytical and strategic thinking. The MO's Head of Programmes/DTL should accompany working groups as they develop strategic plans. Additional capacity building among staff should come from STTA.

Develop new strategic plans for communications, knowledge management, youth involvement and, once advocacy capacity building has taken place, for advocacy and campaigns. These plans need to be outcome oriented and include a clear rationale for all activities, as well as measurable objectives, timelines, resources needed and specific roles and responsibilities of staff.

Review forum membership and outreach to ensure forums involve as many members of the community as possible.

Deepen the reorientation of Output 2 so that all staff and forum partners have a strong conceptual framework and appropriate tools for implementation.

Continue to improve the costed workplan to allow increased flexibility and encourage innovation in implementation; analyse why programme expenditure is sluggish to reduce variances between budgets and expenditure.

Institute regular internal programme reviews to enable the ASC and management to identify strategic issues which should be addressed enhance the outreach and impact of the programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-114433/documents
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-114433/documents

Outline of the programme
The UK is providing up to £34.3 million in programme resources and technical assistance over 5 years (May 2012 to May 2017). The project is managed by a local office of DAI Europe, with direction from its London office, and is implemented by four well established and experienced local NGOs: Aurat Foundation, SAP-Pk, SPO and Sungi. The project has a large footprint across two provinces, Punjab and Khyber Pakhtunkhwa, covering 45 Districts and engaging directly with 4500 grassroots communities.

The stated outcome for the programme is that democratic processes in Pakistan are more open, inclusive and accountable to citizens. Four different areas are addressed to arrive at this outcome:
Helping women and excluded groups to participate safely in politics and in public spaces at federal, provincial and local levels
Building the skills of citizens and communities resolve disputes peacefully, work together for common solutions and be more tolerant towards minority groups and women
Facilitating women and other excluded groups to engage with government to improve responsiveness and accountability and demand improved delivery of services
Generating and synthesising improved evidence and communicating/championing this to political leaders and the elite
In addition, advocacy and influencing initiatives at District, Provincial and national levels will strengthen the legislative and policy environments for participation by women and excluded groups and change attitudes towards women and excluded groups.

DFID Pakistan is closely involved in the development of the AAWAZ project and has provided valuable intellectual and practical support through the responsible SSDA and SDA, Deputy Programme Manager Head of the Governance Group with additional oversight provided by the Head of DFID Pakistan. This is the third Annual Review of the project. Two Beneficiary Assessments have also been carried out in 2013 and 2014.

Donor experience over the last decade has demonstrated that top-down governance reform programmes, by themselves, do not produce concrete benefits for citizens. As a demand-side project, AAWAZ complements DFID's supply side work with government agencies by creating effective demand from groups of active citizens made up of women and men able to advocate for their rights and entitlements.

The context in which AAWAZ is being implemented is difficult at best, hostile at worst. Characterised by poverty, extreme gender inequality, insecurity, deteriorating human rights and a state that ignores the spread of an increasingly strict version of Islam intolerant both of non-Sunni sects and other religions, the outlook can seem discouraging. Pakistan lies 3rd in the countries most affected by terrorism, only Iraq and Afghanistan have higher scores.[2] Between 2014 and 2015 its ranking in the Global Peace Index improved by two places but at 154 out of 162 it is still among the 10 least peaceful countries in the world.
[2] Institute for Economics and Peace, index 2015 see: http://www.visionofhumanity.org/#page/indexes/terrorism-index/2013/PAK,AFG,IRQ/OVER

Pakistan ranks second from bottom (141 out of 142) in the latest, 2014, World Economic Forum's Gender Gap Index. And 146 out of 187 on the HDI Gender Development Index. 7.1 million girls are out of school and half of all women are illiterate, rising to 70% in rural areas. Violence against women in Pakistan is commonplace. Many women live in an atmosphere of fear, their safety guaranteed only by strict obedience to social norms and traditions and the wishes of the men around them. Domestic physical, mental and sexual abuse is routine. Honour killings, gang rapes, and acid attacks are far too frequent. The government does not compile national figures for honour killings but AAWAZ consortium partner, the Aurat Foundation, tracked news reports that showed that at least 1,000 Pakistani women are the victims of honour killings each year. As many are never reported, the true figure will be many times higher.

Pakistan faces other significant economic and social challenges. The economic cost of militarisation, lack of security and involvement in domestic and international conflicts is believed to be some US$ 40 billion a year.[3] Corruption has undermined public confidence in the state and the rule of law. Poor governance and the dominance of military, bureaucratic and political elites has distorted resource distribution. Poverty is increasing and the gap between rich and the poor is widening. Provision of basic services falls far short of international norms and many groups, including women, are excluded from access to services. As a result, over a third of Pakistanis remain poor, and under-educated.
[3] ibid

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
AAWAZ’s desired outcome is that democratic processes are more open, inclusive and accountable to its citizens. Although daunting given the hostile external context, since the last review, AAWAZ has managed to strengthen democratic and inclusive processes in the Districts where it works. The participation of women and minority groups in AAWAZ forums has increased. And in the districts the state has become more responsive as forums hold civil servants and elected representatives to account regarding the delivery of their rights. In addition, women now hold leadership positions in the various AAWAZ forums and, although final numbers will not be known until local government elections are held, there is a growing trend for women in AAWAZ forums to stand as candidates. Since prior to AAWAZ's involvement many of these women were confined to their houses, this is an impressive change. AAWAZ's outreach has been augmented by the work of Provincial Forums in promoting better laws and policies. And by provincial and national level campaigns that have prompted national debates on violence against women and girls, hate speech and the importance of local government.

Of course, more needs to be done to widen and deepen changes in attitudes and behaviours and to institutionalise the improvements in the citizen-state interface. While it may not be possible to achieve this fully in the remaining two years of the AAWAZ project, it is certain that a strong foundation for future advances will be in place.

Overall output score and description

Annual Output Score	A
Annual Output Performance	Outputs met expectation
Output Risk Rating	Medium

Output Description	Impact Weight (%)	Output Performance	Risk
Output 1:	30%	Outputs met expectations (A)	Medium
Output 2:	20%	Outputs met expectations (A)	Medium
Output 3:	30%	Outputs met expectations (A)	Low
Output 4:	20%	Outputs met expectations (A)	Low

Key lessons and key actions
- After consolidation in 2014, the coming year should be one that focuses on deepening quality while simultaneously increasing the pace of delivery and make changes sustainable. Achieving this will require some deliberate action.
  - We strongly recommend that the MO works with the consortium partners to create an action plan that will deliver more speed and better quality and ensure the implementation of AR 2015's recommendations. STTA should be employed wherever this will facilitate delivery of these goals.
- Deepening quality will require extensive, more professional and strategically targeted capacity building.
  - Creating a new strategic plan for capacity building across all outputs and themes should be a priority action. Areas that would benefit from additional skills development include women's political leadership, advocacy, strengthening inclusion and pre-empting violence, citizens' rights re the state, gender equality, strategic planning and management of village forums. Special attention should be paid to forum members, CBOs/CPOs/activists responsible for implementing the programme at the grassroots and district staff.
  - As developing high quality training materials consumes large amounts of time and money, AAWAZ should always review the local and international manuals that already exist and could be adapted for the programme. One example might be the Shirkat Gah manual on empowering women and building their leadership capacities.
AAWAZ does not have a separate, independent Board, so it falls to the MO's and consortium partners' Executive Directors in the AAWAZ Steering Committee (ASC) to take responsibility for strategic oversight of the programme. The AR 2014 made a series of recommendations for improving ASC functioning but as these appeared in an Appendix they have been largely ignored.
  - The ASC recommendations from AR 2014's 4th Appendix should be implemented. In addition, the AR recommends that the ASC monthly one day meetings should be replaced by quarterly two day meetings to allow Executive Directors sufficient time for reflection, analysis and strategic thinking. Each year at least one quarterly meeting should be held in the field.
- Over the last year, AAWAZ staff learned the value of joint planning and joint work in delivering consistent high standards across the programme. Cross programme working groups played a key role in this regard.
  - The activities of current working groups should continue and be strengthened by having critical	accompaniment from the MO's Head of Programmes/DTL. All working groups should have	ToRs. Attendance at working group meetings should be strictly limited with non members only	attending by invitation. To encourage responsibility and prevent hierarchy limiting free choice in	working group decision making, this rule should also apply to Executive Directors.
- A virtuous circle has emerged between successful advocacy for services and broadening support for AAWAZ village forums and the social transformations they promote. Initially considered irrelevant or subjected to disapproval from their community, forums and their social change agendas have gained legitimacy as everyone benefits from the new services forums have accessed.
  - There is a lesson here for future initiatives that aim to change social norms. For AAWAZ it also reinforces the need for integrated thinking that crosses all four outputs so that synergies are maximised for greater impact
- The 2014 AR Action Plan deliberately included detail of what should be in strategies and plan in order to guide staff towards more strategic and analytical thinking. This detail was omitted from the version created by the project. Plans and "strategies" produced during the past year reflect the fact that staff skills in critical thinking and strategic planning need to be improved.
  - All future plans should be strategic plans. Alongside accompaniment from the MO Head of	Programmes/DTL it would be useful to engage STAA to build capacity of MO and consortium	partner staff and facilitate the preparation of the revised strategic plans.
- Good advocacy is critical to the success of voice and accountability programmes. Although AAWAZ forums have had success in using ad hoc advocacy tools, with increased skills and a more thoughtful long term approach, much more could be achieved.
  - As recommended in the 2014 AR, high quality advocacy capacity building should be provided to forums at all levels as well as to key staff. This should be integrated into the overall capacity building strategy. External expert STTA should be used to support the development of training workshops that are targeted at different groups within the project.
- The re-focusing of output 2 away from dispute resolution towards the pre-emption of violence has been successful but Districts are requesting conceptual clarifications as well as help with practical tools for implementation.
  - Workshops to roll out the new conceptual framework and provide District staff and forum members with the methods and tools to implement the output should be an key element in the 2015 capacity building strategy
- Currently, membership of village forums is limited to 40 persons. While such exclusivity is not helpful for a voice and accountability programme practically it is not wise to involve everyone in everything.
  - AAWAZ should review forum membership with a view expanding it to include the whole community without damaging the effectiveness of their work. Tiers of membership could be an answer. Doing this would also mitigate against divide and rule tactics from hostile actors while widening programme impact
- District Coordinators and National Programme Managers note that a system of regular internal programme reviews is missing. This severely limits learning across districts and the consortium partners and the identification of issues which if addressed would increase programme impact.
- A schedule of internal reviews should be established for the next 18 - 21 months to promote learning and sharing. Each review should have clear objectives developed its participants. The occasional involvement of external critical friends should be considered. Innovative forms of reporting, like video diaries, presentations, etc. should be used to ensure the maximum outreach to project wide audiences. Since, to date, too little attention has been paid to the activities, strengths and weaknesses of the 174 CBOs/CPOs/activists that are responsible for delivering the project to local communities, these should the subject of the initial reviews.
- A costed workplan that is solely activity driven and acts like a straight jacket undermines the effectiveness of the programme. If activities are only sanctioned within the narrow confines of approved budget lines, this limits the scope for innovation and inhibits strategic reflection as the room for discretionary action is severely curtailed.
  - The MO provided a little more flexibility to implementing partners following AR 2014	recommendations and more is promised for 2015 but further relaxation of restrictions should be the target when the next revisions to the costed workplan are made.

Has the logframe been updated since the last review?
Yes. The log-frame was revised and approved by DFID Pakistan in February 2015.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Yes / (up from 25%

Indicator(s)	Milestones	Progress
Number of women and girls participating in awareness raising sessions and change agent training on participation in public spaces and political processes and women's right to freedom from violence and receiving change-agent training (data disaggregated by location/exclusion)	AAWAZ training manual and toolkit on gender equality and women's empowerment for participation in decision making developed. / 55 women master trainers trained / 15,000 women and girls (20% of the total women forum members) made aware on women's rights	AAWAZ training manual and key messaging on women's empowerment for participation in decision making developed / 60 women master trainers trained across four partners. / 9,424 women and girls (as of April 2015) made aware on women's rights
Number of men and boys participating in awareness raising sessions & change agent training on the role of male socialisation as a root cause of gender inequality, women's rights to freedom from violence, participation in public spaces & political processes	AAWAZ training manual & toolkit on gender equality & women's empowerment for participation in decision making developed. / 55 men master trainers trained / 15,000 men and boys (20% of male forum members) made aware of women's rights and masculinity	AAWAZ training manual and key messaging developed / 50 men master trainers trained across four partners. / 9,296 men and boys made aware on women's rights and masculinity
Number of women actively participating in AAWAZ forums and public events and in leadership positions	50,000 women actively participating in forum meetings / 10,000 actively participating in women assemblies/khuli katcheries / 7,500 women in leadership positions	59,547 women actively participated in forum meetings / Around 24,000 women actively participated in women assemblies/khuli katcheries and youth conventions / 10,028 women in leadership positions
Number of women receiving CNICs, registered as voters and supported to file nomination papers in the local government elections supported by AAWAZ	78% women receive CNIC / 68% women voters registered / xx women emerged as candidates for local government elections	80% women (99,403 women) have CNIC registration / 69% women (67,381 women) voters registered / Emerging trend of more & more women as candidates for local government elections

Key Points
Most LFA targets have been either met or exceeded. The programme has already delivered some significant changes for women at community level in terms of their participation in public and political life.

At village level there has been a significant increase in CNIC[4] and voter registration for women, both of which establish women as citizens and are an important first step towards women's full participation in political sphere. In addition CNIC also enables women to access state benefits like BISP and NRSP.[5]
[4] Computerised National Identity Card
[5] Benazir Income Support Programme and National Rural Support Programme

Some 7,300 women have been elected to official posts within AAWAZ forums, 20% of whom are young women. Their leadership skills have improved over the last year, a change reflected in their increased, effective participation in public spaces like Khuli Katcheries, assemblies and rallies. AAWAZ's Utha campaign on local government played a key role in encouraging women and men to contest the forthcoming local elections. In KP more than 500 women from AAWAZ districts, including excluded women, are standing for election, almost all of them for the first time. The date for local government elections in Punjab is not yet set but there to large numbers of women are planning to stand.
## Training on gender and exclusion has started and will be rolled out across all villages to build further awareness and consolidate the changes already seen amongst women forum members. Women at District level and below have already acquired reasonable skills in advocacy and are able to get services delivered. This has boosted women's confidence and increased acceptance of their changed roles in society.
## Although the standard number is set at 40, in practice the number of village forum members varies from between 20 - 45. The AR Team consider inclusiveness, quality of participation and effectiveness more important than numbers but for voice and accountability programme limiting membership seems inappropriate. Forums should be aiming to be fully engaged with the whole community, and membership is one way to do this.

Following the recommendations in the last AR which echoed those made by AAWAZ District Coordinators, improvements in the Aagahi Centres are also visible. Relocation to safer sites, having more information available and recruiting women to be resource persons[6] has resulted in increasing numbers of visitors, both women and men. Further development of Aagahi Centres and their resource persons is still needed to further increase their impact. Ideally they should play two roles: providing a safe space for women to meet regularly to share, learn and strategise; and acting as a citizen-government interface through which government can pass information to citizens and citizens find out about their rights and entitlements and how to access government.
[6] 430 out of the 450 Aagahi Centres now have women resource persons

Summary of responses to issues raised in previous annual reviews (where relevant)
Most of the recommendations given in last year AR have been addressed, including ensuring excluded group representative join the forums, the relocation of Aagahi Centres and having women Resource Persons and better information resources. Work with men and boys and with youth is in progress but need to be further developed.

A draft capacity building plan was developed but this only dealt with training on a single theme. This plan needs to be revised to become a strategic plan that deals with capacity building across the whole programme. Key documents revised after last year's AR, including the gender strategy, LFA, theory of change and Aagahi Centres Guidelines are socialised well with District staff and District forum members.
## Qualitative indicators are still missing. These need to be in place as soon as possible whether or not they appear in the LFA. Without them it is impossible to measure the depth of changes achieved.
## Recommendations
- The transformative aspect of women's leadership should be a focus over the next two years to ensure that women move from conditioning to positioning. To help build AAWAZ women leaders as influential agents of change avenues for joint learning within and beyond AAWAZ should be explored. Ideally, learning should include advocacy capacity building alongside contact with existing women MPAs re accessing decision makers.
- Aagahi Centre guidelines should be reviewed and a clear roadmap developed. This should include upgrading Aagahi Centre resources, wherever possible using the best materials already produced by other NGOs like Shirkat Gah and materials from government. And training for resource persons on both rights and services and enhancing women to women engagement.
Forum membership needs to be reviewed AAWAZ also should draw up plans for creating tiers of membership, e.g. executive councils, general councils, general members, etc. that would allow everyone to be part of the forum but would not damage overall forum efficiency and effectiveness.
- To prevent tokenism and ensure the equal participation and treatment of minority group and low caste forum members, awareness raising and capacity building should be rolled out across the AAWAZ in the coming year.
- The performance of provincial forums would improve with greater levels of secretariat support from AAWAZ, advocacy capacity building and a more structured and targeted process for influencing bills. Constructive dialogue with officials, legislators, implementing agencies and other CSOs should be encouraged.
- As part of developing a campaigns strategy to alongside an advocacy strategy, AAWAZ should consider one focused on women's rights through the lens of behavioural change that would aim to engage men and boys in order to create an enabling environment.
- Strategies for engaging men on masculinity and women rights and for engaging with youth need to
be developed. These must have clear aims and objectives and a rationale for the activities to be undertaken. Close monitoring of the impact of previous awareness raising exercises should guide future interventions
The new communications strategy needs a strong focus on effective upward and downward communication on laws and policies affecting women as well as other priority gender issues. Development of IEC materials that are suitable for non literates and provoke reflection, discussion and positive action at District level and below should be a key element.
New qualitative indicators of change, and of the processes that brought it about should be developed without delay.

Output Title	Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Yes / (up from low in 2014)	Impact weighting % revised since last AR?	Yes / (down from 25% in 2014)

Indicator(s)		Milestones		Progress
2.1 Number of women and men informed about support mechanisms and provided with awareness on non-violent communication and valuing diversity	At least 5 key messages developed and disseminated on non-violence and tolerance / 30,000 citizens including 50% of women, made aware of non violent communication and valuing diversity		Key messaging developed and disseminated on non-violence and tolerance / 30,000 citizens made aware through awareness raising sessions by May 2015 / 4,754 students and teachers sensitized on output theme On social media, 23,558 people viewed message followed by 587 shares that reached 117,400 people
2.2 Number of women, men and socially excluded citizens positively impacted by AAWAZ forum interventions/members' actions to protect them from discrimination, harmful cultural practices & violence (sectarian, gender, religious, etc.	1 million people in 45 districts		1.66 million people potentially benefitted. Details are as follows: / 0.78 million people potentially benefitted in 27 districts owing to prevention of sectarian/ interfaith conflicts / 0.88 million people potentially benefitted from pre-emption of 985 conflicts at village level including 375 family disputes and 31 sectarian conflicts
2.3 Number of women and excluded group members participating in AAWAZ Forums' local level peace building initiatives (data disaggregated by gender and religion)	10,000 women and excluded groups participating in events		20,068 (16,580 women, 1,357 men minority members, 160 persons with disability and 1,971 non-AAWAZ forum members) participated in events

Key Points
The work of Output 2 takes place against a national context characterised by increasing intolerance and a weak response to human rights violations from the state, as well as laws biased against women and minority groups and poor quality policing. This context makes the output central to AAWAZ's efforts to build a stable, inclusive and tolerant democracy. But also means that designing the right interventions is not simple.

Despite pushes in the other direction, it is encouraging that AAWAZ forum members demonstrate a willingness and enthusiasm for engaging in a wide range of activities to build tolerance and pre-empt violence. Peace melas, joint celebrations of the festivals of different religions and solidarity marches are just some of the initiatives they have taken up. In many Districts AAWAZ forum members are now members of the official District Peace Committee, or equivalent. And in some, as part of the these Committees, AAWAZ has played a key role in pre-empting serious sectarian violence, for example during Muharram in Multan, and in the process saved hundreds of thousands of lives from being blighted.

A new, highly experienced Technical Specialist joined the MO in February 2014. After consulting with consortium partners, she is developing a conceptual framework to deepen and give a tighter focus AAWAZ's work on the Output. This is founded on the fact that conflict is a normal and often healthy part of human life. As such, instead of trying to pre-empt conflicts the focus should be on continuing to promote the tolerance of differences as well as advocating non violent responses to conflicts.

Implementing the new concept will require a change in attitudes as well as behaviours. In Pakistan, violence is a common response to a dispute, often with a woman paying the price for an misdeed carried out by a man. The aim is that in the future, violence will come to be seen as an unacceptable means of wielding power, including the power of men over women, high castes over low castes, and majority Islamic sects over other sects and religions.

The AR notes that, while providing a good indicative guide, the numbers recorded by AAWAZ in relation to the pre-emption of major incidents like sectarian violence in cities, can be only an estimate based on previous violent incidents. Similarly, the extent to which activities can be attributed to AAWAZ when other actors are present will always be difficult to establish. In the future, designing instruments better at capturing quantitative and qualitative data related to pre-emption activities would be helpful.

Summary of responses to issues raised in previous annual reviews (where relevant)
The AR in 2014 identified this output as the weakest of the three programme outputs that focus on community and District level changes. Many local level staff were out of their depth when it came to dispute settlement and peace building.

The AR's recommendation for the output's focus should change from dispute resolution to prevention of violence has been implemented and a re-orientation of the programme has taken place. However, not all programme participants are 100% clear about what is expected in all circumstances. District staff request more capacity building to clarify thinking and provide forum members with the tools and methods.

Some of the recommended capacity building to develop the skills and understanding of district staff and forum members has taken place but high quality, more intensive training is necessary.

Recommendations
- A simple and brief guide to the new, refined concept for Output 2 should be rolled out across the programme. A brief strategy to achieve this should be put in place.
- This should be followed by capacity building to deepen the understanding of key District staff, CBOs/CPOs/activists and forum members and provide them with practical tools, consistent with the new concept. This should be a priority element in the recommended capacity building strategic plan.
- In particular, village level forums and Aagahi centres need more guidance on how to address domestic violence
- A focus on non violence intensifies the links with areas like gender based violence and violence over resources usually thought of as belonging to Output 1 and Output 3. A deliberate effort to create a one programme approach across the three outputs in relation to non violence will be essential.
- Specific indicators must be tailored to the refinements of the new approach and reporting guidelines issued to ensure reporting becomes more uniform. Regardless of the LFA, these indicators should include qualitative as well as quantitative measures. Footnotes on how numbers benefitting from pre-emptive actions were arrived at, and AAWAZ's contributions were assessed, should be provided on the logframe.

Output Title	Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes / (up 5% from 2014)

Indicator(s)	Milestones	Progress
3.1 Number of women and socially excluded citizens informed of rights, procedures and hotlines for accessing and demanding improved delivery of services from public officials and political representatives	An action plan on 5 key issues developed to equip and train resource persons of AAWAZ Aagahi Centres / 10,000 females accessing AAWAZ Aagahi Centres / 300,000 citizens informed through electronic media	Action plan developed / Awareness raising sessions held with 30,000 community members on rights, procedures and hotlines for accessing and demanding improved delivery of services from public officials / Over 13,000 women and girls accessed AAC – threefold increase over the last quarter / 295,556 people informed through PTV, radio and social media / Over 1.5 million people reached through SMS to inform on rights and hotlines
3.2 Number & types of demands raised with public officials & political representatives in education, health and other priority areas benefitting women, girls and other excluded groups (disaggregated by location/gender/nature of issue)	4,100 demands raised / 4,500 engagements with district and provincial government duty-bearers on policy or implementation issues impacting improved service delivery	5,868 demands raised / Over 5,000 engagements were made in khuli katcheries/one-on-one meetings between citizens including women members with district and provincial government officials on policy or implementation issues
3.3 Number of households impacted by improved service delivery (disaggregated by location/gender/nature of issue)	90,000 households benefitted	1,371 demands met including 612 education; 400 health; and 358 other issues / 338,582 households benefitted equivalent to 2.37 million people / Over 200,000 students prevented from dropping out (82,869 girls, 120,496 boys) / 136,171 households benefitted from health-related demands being addressed

Key Points
The enthusiasm, energy and pride of forum members is visibly evident regarding this area of the programme is visibly evident.

The understanding of village forum members regarding their rights to public services continues to grow. Significant demands have been raised by them as well as by their sister forums at union council and district level. Cooperation between village and Union Council forums enables additional pressure on state agencies to be exerted. Aagahi centres are playing a stronger role in this work although further improvements are necessary it they are to become a central interface for citizen-state relations.

Village forums have the freedom to identify their specific service needs and prioritise these for advocacy. This results in a wide range of different issues being raised from obtaining CNIC registration to having a doctor appointed to the local clinic. Although the variety of issues taken up may result in a small decrease in programme-wide efficiency, giving control to village forums is critical to their empowerment and to their long term sustainability.

A variety of advocacy methods for demanding services from local officials and political representatives is being used. One of them, the use of Khuli Katcheries, is employed across AAWAZ. These have provided a space for women and excluded groups to raise their voices in public and successfully influence decision-makers. Women have proved very successful in terms of persuading government to meet demands by presenting them in person at local line agency offices - either in the form of a protest, or through lobbying.

Obviously, not all demands can be met immediately. But success rates are high enough to empower village forums and boost their credibility with the wider community as successful advocates whose bring new services to the community and whose ideas about gender equality, inclusion and non violence merit further thought.

Some forums at district level have shown higher degrees of success than others. It appears that success correlates well with an approach that uses open and constructive dialogue with government line agencies, other public bodies and political representatives. This sometimes extends to inviting them to be forum members, or to attend forum meetings. Good relationships with officials have resulted in District forums being able to insert demands into official Annual Development Plans.

At present, it is not clear if forums are making the link between good governance and service delivery. Nor considering the relative value of different types of advocacy in building constructive relationships with government that might encourage greater transparency and the institutionalisation of dialogue processes. Also, at district level, many forums are still dealing with demands from individual communities, rather than aiming to improve service delivery across the whole district.

These weaknesses are linked to a narrow understanding of advocacy concepts and tools which is not surprising since they have not received quality advocacy training. . First-rate advocacy that stresses both people centred/rooted advocacy and approaches that promote good governance is a critical element in the success of voice and accountability programmes. Although AAWAZ forums have had success in using ad hoc advocacy tools, with increased skills and a more thoughtful long term approach, much more could be achieved.

Despite many valuable achievements, the AR team is concerned that figures currently reported may over-estimate of numbers of people benefitting.

Summary of responses to issues raised in previous annual reviews (where relevant)
Most recommendations of the AR 2014 have been implemented including increasing resources for Aagahi Centres Coordinators, and ensuring forum members do their own advocacy, rather than CBOs/CPOs/activists or other bigwigs doing it for them - although this element needs to be stressed continuously. The AR team did not the full extent to which the issue of poverty preventing participation in forum and forum events had been resolved. However, the increased flexibility in AAWAZ budgets should have given District Coordinators the space to deal with this at their discretion.

Reporting and monitoring of this output has improved and should improve further with the new MIS system in place.

Regrettably, AAWAZ was unable to provide the high quality advocacy capacity building that was recommended. This is a recommendation for 2015.

Recommendations (see also Output 1 recommendations)
Further development of Aagahi Centres and their resource persons is needed to increase their effectiveness. Alongside providing a safe space for women to meet, Aagahi Centres should aim to become a central interface for citizen-state relations through which government can pass information to citizens and citizens find out about their rights and entitlements and how to access government.
- Aagahi centre resource persons should be trained on referral systems to different government agencies and Aagahi centres should house standard material and information on government services and welfare entitlements. A search for existing materials produced by other organisations should take place before AAWAZ prepares its own.
- First class advocacy skills need to be built across AAWAZ, as recommended in the 2014 AR. This should reach forums at all levels as well as for CBOs and key District staff. External expert STTA should be used to support the development of training workshops that are targeted at different groups within the project. Advocacy capacity building should be a priority area in the overall capacity building strategy.
- It is very important that monitoring captures the changes in democratic participation, government responsiveness and related improvements in governance that already can be seen in the programme as these are significant for the long term sustainability of the work.
- A review of the way figures are assessed to report on logframe milestones should take place. In future the difference between total and incremental benefits should be clear, and realistic assessments of how many people actually, rather than theoretically, benefit from the delivery of a new service.

Output Title	Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa and Punjab
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		Yes / (down from medium	Impact weighting % revised since last AR?	Yes / (down from 25%)

Indicator(s)	Milestones	Progress
4.1 Effective evidence-based (qualitative and quantitative) M& E systems established	Log frame revised and approved by DFID. M&E plan developed and submitted to DFID. / MIS system developed and orientation provided to select staff of all partner organizations. / Knowledge management strategy and plan developed to leverage knowledge products through seminars, lobbying meetings and media interventions for advocacy	Log frame revised and approved by DFID. M&E plan developed and submitted to DFID / MIS system developed and orientation provided / Knowledge management strategy and plan developed as part of Communications Strategy - needs revision
4.2 Number of quality evidence-based research commissioned on select thematic issues and disseminate for policy and practice	7 studies completed. ( baseline study, migration of minorities, transgender issues, minority women’s political participation, tracking legislation, best practices in implementation, voice and accountability Index) / Two position papers (on hate speech/radicalization and local government) done / 2 case studies on Swat Amman Jirga and Shia-Sunni conflict completed / Research Advisory Group established / 6 projects valuing over 627,000 GBP launched under Response Fund	All 7 studies completed / Both position papers completed / Both case studies completed / Research Advisory Group established - needs reform / 6 projects launched
4.3 Cumulative number and types of quality advocacy campaigns initiated by AAWAZ, consolidated, synthesized and analysed by PARR	Policy Advocacy Action Plan prepared and monitored / 3 Campaigns (EVAW/G, anti-hate speech and local government) launched / 2,651,782 people reached on women rights through PTV, radio and social media	Policy Advocacy Action Plan prepared and monitored / 3 Campaigns (EVAW/G, anti-hate speech and local government) launched / 2,651,782 people reached on women rights through PTV, radio and social media

Key Points
SLU has produced 7 research papers and 2 case studies an issued grants to 6 innovative projects under the Response Fund. This represents considerable progress against last year performance. Given its impressive performance this output has scored A. These reflect the interests of programme implementers and are of a good standard. Some are of a style and quality that makes them suitable for publishing in academic journals.

Although SLU is aware of the need for target audiences to be identified at the initial stages of research and for a strong dissemination plan to be in place at the time research begins, these elements have not yet been developed.

One problem for dissemination has been uncertainty about who should launch and disseminate research studies. There is a call from consortium partners for them to take the lead in launching and disseminating studies and engaging in any resulting advocacy.

Confusion still exists about who is responsible for organising Knowledge Management (KM) even though it is part of the job description for a post in SLU. At present it appears in the draft communications strategy.

The current membership of SLU's Research Advisory Group (RAG) is limited to two academics that are on consultancy contracts, who rarely speak to each other. Their work has been limited to commenting on research drafts. One RAG members noted that it would be better to be involved at a very early stage in the research process and be able to contribute to refining concepts and methodology, as well as shaping the product for a particular audience.

AAWAZ has developed a policy advocacy action plan but this only covers gender-specific legislation rather than all the advocacy that is taking place across the programme. This may be due to a misconception that advocacy is limited to policy advocacy.

Three public campaigns have been launched during the past year: local government, anti hate speech; and Violence Against Women (VAW). They have all made an impression in the provinces where AAWAZ works. And the VAW campaign generated for the first time ever, nationwide public debate on the issue. However, at present, campaigns lack guiding strategies that lay out their objectives, schedules activities, says how long they will last and how success will be evaluated. This can lead to lack of clarity about their direction and focus. For example, the anti hate speech campaign became more like a peace campaign after the Peshawar bombings with the albeit very effective school painting initiative.

The draft communications strategy needs a thorough rethink. At present it is far too long and covers areas like advocacy and knowledge management. These should have their own separate strategies. The most important thing is that the revised strategy is that is should address the current needs of the project rather than creating a new agenda.

Summary of responses to issues raised in previous annual reviews (where relevant)
AR 2014 identified Output 4 as the most troubled part of the programme and scored it B. It recommended ending the relationship with SDPI and bringing both the research and M&E functions into the MO. All this has happened. Both the new Strategic Learning Unit as well as M&E unit are thriving. And M&E is benefitting from increased ownership by the consortium partners. A good baseline is in place and the LFA has been revised.

Recommendations
- Approval protocols for different types of research products should be put in place as soon as possible. No research should be published before approval from the head of the MO and the Executive Directors from the consortium partners. Named deputies should be chosen who will take over this responsibility if an organisational head is not available to undertake the task. This will ensure ownership of research across all the consortium partners.
- All research publications should clearly indicate they are from AAWAZ. Dissemination plans should be drawn up by SLU in consultation with consortium partners and clearly identify who will be responsible for what.
- The target audience(s) for research should be clearly identified before research begins alongside a specific dissemination plan. For any research to be useful it needs to be packaged in formats that are suitable for each different audience and contain audience-specific messages. All dissemination plans should indicate how the key findings of studies will be transmitted to forum members at all levels in suitable formats and languages.
- All research must include an executive summary of its contents and have recommendations for policy makers at the front of the document.
- The Research Advisory Group should be expanded to take in a mix of academics, policy experts, the head of SLU, the MO communications adviser and research specialists from the consortium partners.
- SLU should work with whoever is responsible for developing the AAWAZ advocacy strategy to ensure that it includes a section on how policy related research will be taken forward b consortium partners so that its recommendations result in changes in policy and practice.
- There should be a representative from SLU on the communications working group and the advocacy group.
- In the future, all public campaigns must have a clear long term roadmaps or strategies, be outcome-oriented and identify measurable results and timelines. Where campaigns involve individuals exposing vulnerabilities there must be follow up activities to ensure their long term wellbeing.
- Knowledge management should be housed in the SLU and a KM strategy should be produced, using assistance from external KM experts if required.
- Proposals for grants under the response fund should be required to identify their VFM metrics as part of their eligibility criteria.
- The communication strategy should be revised. The new strategy should be clear and concise in terms of objectives, methods, audiences and monitoring and evaluation criteria. The strategy include how AAWAZ will respond to some key challenges facing the programme including communicating messages from the village forums to the wider community, providing information to its target group on aspects which will help enhance women’s political participation and protection against domestic violence, increase their access to public services and social protection programmes, etc. in ways suitable for non-literate and semi literate audiences.
- It is noted that there is no separate outcome indicator for activities conducted under output 4. Dissemination and effectiveness of research and the success and impact of campaigns is not adequately captured in the latest logframe. Nor are there any indicators for measuring the effects of products produced under the Response Fund. SLU and M&E should reflect on how the results of research, campaigns, communication and advocacy should be assessed an introduce both qualitative and quantitative indicators for internal use.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The AAWAZ budget is divided into fee, operations and programme budget categories for the MO and each consortium partner. The fee component includes the core staff costs including overheads, operations includes travel, rent, accommodation, utilities, etc, while the programme budget includes all expenses which are incurred directly on activities associated at the field level.

The actual expenses for the current year up to April 20, 2015 were £ 5.24 million from this year’s annual budget of £7.699. Of the funds spent in the current year, 63% was on fee, 15% on operations and 22% on the programme. The major cost driver is staff salaries as the programme has 463 staff at various levels. This is normal for a complex programme of this type that involves direct social mobilisation in 4500 communities as well as research, advocacy and influencing at higher levels.

AAWAZ has begun to track its expenses at different geographical tiers. Prior to end of year figures being available, the biggest underspend variance of expenditure against budget was at village level. Consortium partners say that this will change in the end of year figures as it is due to slow accounting at that level. Nevertheless, an exploration of why spending is slow and/or low at this level should be undertaken. The Aagahi Centres consumed a major (37%) share of the programme expenditures this year due to the increased investment in staffing and resources.

VfM performance compared to the original VfM proposition in the business case:
The Programme has developed a VFM framework which helps to identify some of the key metrics on which information will need to be collected to yield a benefit cost analysis of the programme. While the MO and the consortium partners have begun to include some anecdotal evidence on value of money aspects in the report, a proper action plan needs to be developed to collect the information more systematically and verify the underlying assumptions in the theory of change. The staff of the monitoring and evaluation units needs to be provided some training on converting data into value for money statements. The record keeping at the forums and at the Aagahi centres needs to be undertaken in a manner which provides information on outcomes rather than activities.

The business case had included a partial analysis of the benefits that were expected to accrue from the programme. At appraisal, an expected benefit stream had been generated based on the quantifiable returns expected from the three outputs and a rate of return of 22% had been estimated based on a 10% discount rate over 15 years. The programme is not at this stage in a position to calculate the rate of return of the programme due to lack of information on the range of quantifiable benefits that are expected to accrue. However, the programme has attempted an initial IRR assessment based on available information but mostly assumption based on secondary sources. This analysis illustrates that the programme has the potential to generate a much higher rate of return than envisaged at appraisal. It is estimated that this programme has the potential of generating a rate of return of around 80% - unexpectedly high for the nature of investment. It is further estimated that the programme has the potential of generating at least 69% rate of return even if the programme ceases to produce any benefits.

Going forward, it will be critical to replace as many assumptions used in these estimations with actual evidence collected from the field. This is planned to be done using various instruments including robust and focused data collection, series of perception surveys, increased capacity of the M&E teams to collect evidence in a systematic manner, and independent impact assessment.

Assessment of whether the programme continues to represent value for money:
The programme continues to represent significant value for money. This is evident from the findings field visits, meetings with forum members and the wealth of anecdotal information which is emerging from case studies and updated cost benefit estimates. However, the programme has the potential to derive much greater value than it is currently deriving particularly from its work at the forums and Aagahi Centres. A series of recommendations have been made on how to improve its performance in this regard under relevant outputs.

Although updated rate of return at 80% for the programme suggests that potential benefits are much higher compared to original proposal, but it will be difficult to claim it with certainty unless critical assumptions/secondary source data is replaced with actual evidence from the field. Having said that, an illustration provided below suggest that the direction of travel is positive and the assumptions used in estimating the benefits are conservative and may only affect the actual rate of return positively once replaced with evidence.

Output 1 focuses on empowering women by supporting them to be an active part of the political process, reducing violence against women and supporting legislative reforms to create enabling environment. Within output 1, AAWAZ interventions have been able to help 99,403 women in getting CNIC while 67,381 women are now registered voters. Both of which establish women as citizens and are an important first step towards women's full participation in political sphere. In addition CNIC also enables women to access state benefits like BISP and NRSP.[7] It is estimated that these women are reached at unit cost of £24.2. On the benefits side, anecdotal evidence suggests that inclusion of women through CNIC and voter registration will lead to benefits through gradual access to BISP[8], access to assets[9] and access to businesses through financial inclusion[10]. Conservative estimates puts the benefits figure per women per annum at £204. This gives us an overall benefit cost ratio of 8.4. The estimation of benefits does not include the intangible benefits empowering women will have collectively. Other than gender equality being a basic human right, empowering women will lead to health and productivity of not just too whole family and communities but they also contribute improving prospects for the next generations[11].
[7] Benazir Income Support Programme and National Rural Support Programme
[8] This information is aggregated from partner organization reports or used as a proportion from a sample of partner organization reports or assumption is made that in each district 5% of the 17699 women who are currently eligible for BISP (2,000,000/113) but not registered have been assisted by AAWAZ to get a CNIC and enrol in BISP in a gradual manner. The current value per beneficiary is Rs. 18,000 (or £112.5) per annum.
[9] Actual data collected by AAWAZ sources suggest that 15% of the women who have been support will get access to asset while average amount of asset stood at Rs. 20,000 (£125)
[10] Assuming that 1% of the women facilitated in obtaining their CNIC by AAWAZ will be able to initiate a business as a result. Average benefit of Rs. 60,000 (£375) per women per annum.
[11] http://www.unfpa.org/gender-equality

The programme should commission a Third Party Survey in the middle of 2016 to collect information on some of the key metrics required to complete its VFM analysis. This analysis will help to provide analysis for the completion report in early 2017.

Quality of financial management
The overall system of financial management of the MO is well managed. However, the method of preparing the costed workplan has improved but is still very rigid and need to be made more flexible. The MO has devised a system of compliance and spot checks of the consortium partners which is able to identify any deviations from contractual agreements, identify irregularities and suggest measures to reduce financial risk. In addition, all partners are subject to external audit by an established chartered accountant firm including the MO which receives a detailed audit report and a Management Letter which highlights specific issues with its own system.

Date of last narrative financial report	April 2015
Date of last audited annual statement	May 2014

E: RISK (½ page)

Overall risk rating: Low/Medium/High

The overall risk rating of the environment under which the programme is operating has been changed from Low to Medium.

Risk to programme being disrupted/delayed
Risk by Output
Output 1 - Medium
Output 2 - Medium
Output 3 - Low
Output 4 - Low

The main reason for the heightened risk is the continuing security threat in the country, the growing fundamentalism that continues to restrict women’s space and the fear that has gripped minority communities due to religious intolerance. In this atmosphere, the legislative representatives are also afraid to take any bold initiatives to amend existing laws or bring new ones which are favourable for women or the minority communities. This overall environment limits women’s participation in political and public space and works against the overall objectives of the programme. The only way to mitigate this risk is to continue to lobby with the key legislative representatives and help them see that without some fundamental changes in the country, its path to development and growth will be stalled.

The Government is also increasingly suspicious of NGOs and has put many more limitations on their movement in many parts of the country. In KP NGOs cannot operate without an MOU and in many parts of Punjab they need a No Objection Certificate which delays their work. The mitigating actions that will be required to address this risk would be to treat the Government as a partner and share with them the overall approach and activities under AAWAZ in a transparent and open manner. DFID need to introduce AAWAZ as a key demand-side initiative in the context of their Strategic partnership framework and lobby for support.

NGOs and those seen to be working for the promotion of liberal values and face considerable threat themselves. The attacks of terrorist have become much more widespread and have become much more indiscriminate. Educational institutions, private and government organisations, NGOs and places of public gathering remain soft targets for terror attacks. Fear of such attacks has had a particularly significant impact on the programme’s ability to hold public events in KP. AAWAZ is in discussions with the KP government, pursuant to the MoU and steering committee referred to above on how to best counter such attacks.

Risk of funds not being used as intended
The project has robust financial systems, stringent procurement mechanisms, accounting controls, compliance mechanisms and internal and external audit procedures. The review team believes that fiduciary risk is minimal.

There have been some problems with compliance but more training is already being rolled out. One issue that needs a solution is where to account for grant and/or expenses payments to CBOs/CPOs/activists when no category exists for this at the moment.

Risk to Project Personnel
The MO has an experienced security officer who has established a single security link with all the consortium partners through which information is shared. Weekly updates on security from the UN, USAID and DFID are analysed and checked out against other sources including the Intelligence Bureau and senior police officers.

Despite the Punjab provincial government's hostile attitude of the towards NGOs, no direct threats have been made. The situation is tenser in KP where some staff were threatened by community members and where two offices were asked to close. These offices were re-opened after conversations with local authorities. A new MOU with the provincial government in KP should assist staff to obtain more easily No Objection Certificates (NOCs) for travel to the more sensitive areas where forums have been established.

Climate and Environment Risk
The project work involves only an insignificant impact on carbon emissions.
There is a risk of flooding, earthquake and other natural disasters. If these occurred in project districts they could interrupt or temporarily divert attention away from the main aims of the project.

Outstanding actions from risk assessment
The various partners are already working to counter these risks on an on-going basis as best they can through a multi-pronged strategy.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme has spent 52% of its overall budget in 58% of its time period and it is on track with respect to delivering its revised milestone targets.

In the current year, the programme has spent 84% of its staffing and fee budget, 75% of its operations budget and only 49% of its programme budget with an overall spend of 72% up to April, 2015. The final programme spend is expected to rise to around 70% by the FY end. Based on its financial performance in its initial years, AAWAZ will be expected to spend an average of 146% of its current year expenditures in the remaining two years of the programme.

The reason that the AAWAZ milestone targets are on track despite its underspend is because the milestone indicators are not very cost intensive and many of the targets depend upon the work that is undertaken by the forums themselves or public agencies such as NADRA for the issuance of CNIC, the Election Commission for the registration of voters, the National or provincial assemblies with regard to passage of laws and public line agencies with respect to addressing of demands raised by the communities, etc. Furthermore, the quality dimension of the outputs is not often fully captured in the milestone indicators such as the extent to which the members are participating actively in the forums.

Performance of partnership (s)
The functioning of the consortium partners as one well-functioning unit has been a challenge in AAWAZ given that it has a management organization, four main implementing partners with 473 staff spread over 45 districts and more than 174 CBOs/CPOs involved in various aspects of implementation in the field. However, there appears to be much greater cohesion among the partners this year compared with the previous years. The formation of working groups for different subjects such as M&E, communication, etc. has assisted in fomenting cooperation at the operational level. The induction of some technical specialists in the MO is likely to aid their interaction with partners and demonstrate their value added. The delay in signing the formal contracts between the MO and the consortium members created some uncertainty and should be avoided. The role of the CBO/sCPOs in implementing the programme needs to be recognised and budgeted for properly.

In the current year, DFID also appears to be playing its role of oversight and guidance much more effectively by doing so from a distance and not overly micro-managing the programme which it was doing last year because of its concerns about overall management capacity. The delay in the approval of many key documents last year such as the costed work plan, theory of change, log-frame and communication strategy was partly due to DFID’s concerns about the quality of these documents.

Asset monitoring and control
The MO conducts annual compliance review and spot verification at the regional and district offices of all the partner organizations and selected CPOs. The scope of the review includes inventory management and procurement. The MO also maintains an asset register and maintains logs for the use of vehicles.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not relevant to the project as it does not constitute financial aid.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The AR 2014 recommendation that M&E should be housed in the MO has been implemented. AAWAZ decided that rather than housing M&E in SLU is should be a standalone unit. This decision is endorsed by AR 2015.

The baseline report was finalised in December 2014 and provides a good basis for assessing the programme achievements. The direct feedback from the members of the forums at various levels met by the Annual Review team is extremely positive and there is long litany of stories and anecdotes which demonstrate the benefits that are emerging from the field.

The programme has also begun to collect evidence from the ground through case studies. Specific attribution will continue to be a problem as many organizations and individuals are working for the same overall objectives. Nevertheless, there is strong evidence that the programme is having an impact on the ground.

AAWAZ recently finalised its theory of change to examine some of its initial assumptions. While the theory of change has not changed in essence it has been refined to more accurately reflect the partners' combined understanding of what leads to the type of changes expected from its activities. Based on its theory of change, the programme also undertook the development of templates for a VFM analysis. This helped to more accurately identify the type of data required to undertake this analysis and also test some of the assumptions. However, some of the information presented by the programme has to be more carefully evaluated such as the level of participation, outreach, the incremental benefits and the outcomes of the forums at various levels including the progress reported by the Aagahi centres..

Monitoring progress throughout the review period
The programme has been able to develop a good system backed up by proper evidence for reporting on its log-frame. However, the system needs to be strengthened to ensure that the information collected accurately reflects incremental benefits. AAWAZ has recently designed an MIS system which will enable it to collect information more systematically from the field. This system is in the final stages of refinement and is expected to be rolled out soon. The programme has developed a set of dash board indicators which report on key performance on physical indicators and needs to include financial indicators. A standardized reporting format which also reports on outcomes needs to be designed and maintained by all forums and at the Aagahi Centres.

The system of data collection under each output should be refined to present a more realistic assessment of outreach. Review all the data collection tools at the forum levels as well as in the Aagahi Centres and the district and provincial level and provide them with a standardized tool for recording the data on their activities and outcomes. A clear plan of action should be developed with respect to third party surveys which will enable an assessment of the overall impact of the programme in the remaining programme period.

Logframe
The logframe was revised in February 2015 and DFID and AAWAZ expect no further revisions.

The AR Team has made a series of recommendations regarding additional qualitative and quantitative indicators that are needed for AAWAZ to track the volume and depth of changes achieved. These should be developed whether or not they are included in the LFA.