## Template
PROJECT TITLE | Start Fund Phase II- Start Network
IMPACT | Impact Indicator 1.1 |  | Baseline (July 2018) | Milestone (16 July 2018- 31 Mar 2019) | Milestone (1 Apr 2019- 31 Mar 2020) | Target (1 Apr 2020- 15 July 2021) | Business Case Extension (August 2021 - July 2022) | Assumptions
People's lives are saved, suffering aleviated and dignity protected during humanitarian crises | Cumulative # of disaster-affected people directly reached through Start Fund interventions (disaggregated by age, gender, geography and disability) | Planned | 9,755,842 Source: PCR Phase I | 2.4 million (cumulative: 12,155,842) with DFID contribution If we meet the target of total 15 million gbp from all donors, the reach milestone will be 4.8 million (cumulative 14,555,842). Note: based on a ratio of 10 million gbp reaching an estimated 3.2 million people) | 3.2 million (cumulative: 15,355,842) with DFID contribution If we meet the target of total 18 million gbp from all donors, the reach milestone will be 5.7 million (cumulative 20,255,842) Note: based on a ratio of 10 million gbp reaching an estimated 3.2 million people) | 4 million (cumulative: 19,355,842) with DFID contribution If meet the target of total 20 million gbp from all donors, the reach milestone will be 6.4 million (cumulative 26,655,842) Note: based on a ratio of 10 million gbp reaching an estimated 3.2 million people) | 5 million 3.4 million (cumulative: 24,355,842 22,710749) with DFID contribution If meet the target of total 22.9 million gbp from all donors in the disbursement pot, the reach milestone will be 7.4 6.4 million (cumulative 34,055,842 25,758,122) Note: based on an updated ratio of 10 million gbp reaching an estimated 3.2 2.8 million people) | • There will be humanitarian crises in the 2018-2022 period which will trigger the Fund's activation. •Start Fund is able to meet its fund raising targets from other donors.
|  | Achieved |  | 3,015,465 (cumulative: 12,584,902) 52% female, 48% male. 47.3% under 18, 47.4% 18-50 and 5.3% over 50 64,102 people with disabilities 88% South of Sahara, 5%South or Central Asia, 3.6% East Asia, 2% Middle East, 1.6% North and Central America, 0.2% South America | 3,579,082 (cumulative 16,191,867) 53% female, 47% male 46% under 18, 42% 18-50 years old, 12% over 50 5% West Africa 22% Central Africa 31% East Africa 4% MENA 24% Central America, including Mexico, and Caribbean 2% South America 8% South Asia 4% Southeast Asia |  | The above figure is based on Start Fund data comparing the average amount disbursed with the number of people reached by funded projects. This number fluctuates over time and is subject to change. The figure provided is based on the best current data.
Source
Project report forms
| Impact Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Cumulative # of disaster-affected people directly reached through Start Fund interventions disaggregated by Start Fund niche categories (as defined in the Start Fund Evaluation 2017)* | Planned | Group A Category 1) 67% of alerts complemented other funding mechanisms and funding streams in mainstream responses through gap filling in time or geography. Source: Under the Radar 2017 report. Category 2) 33% of alerts delivered funding to crises that are beyond the attention or reach of an ongoing emergency response (‘under the radar’), whether or not that response is internationally or locally-led. Source: Under the Radar 2017 report. Category 3) 10% of alerts (24/245) and 8.8% of activations (14/160) were prior to impending crises based on forecasting (anticipation). Source: Alerts 1-245; Salesforce Group B Category 4) 82% of alerts (201/245) and 85% of activations (136/160) were for onset of small to medium scale (rapid) crises. Source: Alerts 1-245; Salesforce Category 5) 18% of alerts (44/245) and 15% of activations (24/160) were for specific spikes in chronic (slow onset, including larger scale) crises. Source: Alerts 1-245; Salesforce | No proposed targets for categories 1, 2, 4 and 5. Indicator will be monitored for reporting purpose. However: -To strengthen compliance with the SF niche catergories, all activated alerts need to qualify against atleast one of the group A and atleast one of the group B niche categories. -For category 3, in accordance with the anticipation target for outcome 2.4: 12% alerts, 10% activations. | No proposed targets for categories 1, 2, 4 and 5. Indicator will be monitored for reporting purpose. However: -To strengthen compliance with the SF niche catergories, all activated alerts need to qualify against atleast one of the group A and atleast one of the group B niche categories. -For category 3, in accordance with the anticipation target for outcome 2.4: 18% alerts, 15% activations. | No proposed targets for categories 1, 2, 4 and 5. Indicator will be monitored for reporting purpose. However: -To strengthen compliance with the SF niche catergories, all activated alerts need to qualify against atleast one of the group A and atleast one of the group B niche categories. -For category 3, in accordance with the anticipation target for outcome 2.4: 30% alerts, 27% activations. | No proposed targets for categories 1, 2, 4 and 5. Indicator will be monitored for reporting purpose. However: -To strengthen compliance with the SF niche catergories, all activated alerts need to qualify against atleast one of the group A and atleast one of the group B niche categories. -For category 3, in accordance with the anticipation target for outcome 2.4: 30% alerts, 27% activations.
|  | Achieved |  | Category 1: Available in Year 2 Category 2: Available in Year 2 Category 3: 674,341 (22.4%) reached by anticipation activations Category 4: 2,973,298 (98.6%) reached by small to medium scale (rapid) crises Category 5: 42,166 (1.4%) reached by specific spikes in chronic (slow onset, including larger scale) crises. | Category 1: 2,147,400 (60%) reached through complimentary SF interventions Category 2: 1,431,682 (40%) reached through SF interventions into under the radar crises Category 3: 645,203 (18%) reached by anticipation activations Category 4: 2,836,856 (79%) reached by small to medium scale (rapid) crises Category 5: 79,709 (2%) reached byslow onset crises.
Source
Alert note (filtered by the activations), Allocation rationale (from the allocation minutes), SF Project report forms
| Impact Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Start Fund evidence and learning indicates that the mechanism is influencing the humanitarian system to meet Grand Bargain commitments | Planned | No Baseline. Reason: New Indicator. | 10% of stakeholders indicate that SF is very Significantly influencing the humanitarian system; 20% of stakeholders indicate that SF is Significantly influencing the humanitarian system; 30% of stakeholders indicate that SF is moderately influencing the humanitarian system | 15% of stakeholders indicate that SF is very Significantly influencing the humanitarian system; 30% of stakeholders indicate that SF is Significantly influencing the humanitarian system;30% of stakeholders indicate that SF is moderately influencing the humanitarian system | 20% of stakeholders indicate that SF is very Significantly influencing the humanitarian system; 40% of stakeholders indicate that SF is Significantly influencing the humanitarian system; 30% of stakeholders indicate that SF is moderately influencing the humanitarian system | 25% of stakeholders indicate that SF is very Significantly influencing the humanitarian system; 45% of stakeholders indicate that SF is Significantly influencing the humanitarian system; 35% of stakeholders indicate that SF is moderately influencing the humanitarian system
|  | Achieved |  | 69 % of members surveyed agreed that the Start Network is helping to bring about systemic changes to the humanitarian sector, and 31 % stated that they strongly agreed that this was the case. Many members said it has positively influenced increased collaboration, partnership and coordination; uptake and use of early preparedness and anticipation; faster response times; encouraging localisation practices; and more adherence to transparency and accountability. 49% of members reported that the Network was changing their organisational practices to a moderate or greater extent, and 41% stated it is changing their programmatic or project practices. | 92.5% agreed that the Start Network was having an impact on the humanitarian sector (42.5% to ‘a moderate extent’ and 15% to ‘a great extent’) and 88% of members felt that the Start Network was having an influence on other actors in the humanitarian sector (40% to ‘a moderate extent’ and 5% to ‘a great extent’). 85% of members reported that their interaction with the Start Network had changed their organisational practices and approaches (50% to ‘a moderate extent’ and 7.5% to ‘a great extent’) and 72.5% of respondents also said that their membership of the Start Network had influenced their programmatic practices and approaches (42.5% to ‘ a moderate extent’ and 5% to ‘a great extent’.)
Source
Network member survey
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The SF is well-equipped to respond to under the radar crises with a resilient humanitarian financing architecture | % of Start Fund alerts that are considered 'under the radar' crises according to the Start Fund 's internal definition** | Planned | 15 out of 45 activations (33%) that were analysed in 2017 classify as ‘under the radar’. These 15 activations resulted in £2,531,211 being awarded, accounting for 26.5% of Global Start Fund disbursement (£9,544,440) for those same 45 activations. Source: Analysis of 2017 alerts within the report "Start Fund Involvement in 'Under the Radar' Crises: An External Analysis". | A year-on-year increase in the no of 'under the radar' crises supported by the SF | A year-on-year increase in the no of 'under the radar' crises supported by the SF | A year-on-year increase in the no of 'under the radar' crises supported by the SF | A year-on-year increase in the no of 'under the radar' crises supported by the SF | • Availability of wider humanitarian financing to the crises that Start Fund responds. • External crisis indices (e.g. ECHO FCA ) continue to be available within the year of reporting.
|  | Achieved |  | Progress to be reported in the next reporting period. | 32% of projects reporting state the crisis was under the radar; 42% of alert notes identified as "under the radar"
Source
Alert note
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of ‘under the radar’ crises that appear on externally recognised indices (e.g. ECHO FCA) that lead to Start Fund alerts | Planned | 13% Source: PCR phase I- 13% of all ECHO FCA Index crises published in 2014-2017 resulted in Start Fund alerts | 17 (4% increment) | 22 (5% yearly increment) | 28 (6% increment) | 35 (7% increment)
|  | Achieved |  | Under the radar' internal definition will be tracked in Year 2 onward 16.9% of Start Fund alerts appear on ECHO’s latest Forgotten Crisis Assessment (FCA) index 26.7% of crises on ECHO’s latest FCA index had at least one Start Fund alert, with several leading to multiple alerts | 9% of Start Fund alerts appear on ECHO’s latest Forgotten Crisis Assessment (FCA) index 40% of crises on ECHO’s latest FCA index had at least one Start Fund alert, with several leading to multiple alerts
Source
Alert note and ECHO FCA Index
| Outcome Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects (of those that sought further funding) that managed to leverage additional funding as a result of a Start Fund activation | Planned | 80.5% Source: PCR phase I- 77 of 124 projects sought funding, and of those 62 secured funding with help from the Start Fund. 62/77= 80.5%. Alert range: 151-245. | Maintain 80.5% | Maintain 80.5% | Maintain 80.5% | Maintain 80.5%
|  | Achieved |  | 37 of the 60 projects (61.7%) that secured further funding are reported to be the result of a Start Fund activation. | 54 of the 72 projects (75%) that secured further funding are reported to be the result of a Start Fund activation.
Source
Start Fund project report forms
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.1 | Output Indicator 1.11 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
The Start Fund continues to grow funding to address short term funding gaps and leverage further funding | Total fundraising target and # of donors, disaggregated by their individual contribution | Planned | 5 donors to the fund (1 for blockchain); £12 million in the pot per year | 15 million, # of donors to be included in the annual report | 18 million, # of donors to be included in the annual report | 20 million, # of donors to be included in the annual report | 22.9 million in the disbursement pot, # of donors to be included in the annual report
|  | Achieved |  | £11,945,000 for 8.5 months (£14,971,000 for 12 months) 8 donors during the 8.5 months: DFID: £8,719,000 (£10,642,000 including 3 months of prior award) ECHO: £56,000 (£134,000) German Federal Foreign Office: £475,000 (£475,000) Belgium: £156,000 (£373,000) Ireland: £747,000 (£1,055,000) Ikea Foundation: £353,000 (£353,000) Jersey Overseas Aid: £225,000 (£225,000) Netherlands: £1,214,000 (£1,714,000) | £15.620,382 April 2019-March 2020 6 donors: DFID £10,603,915 IrishAid £1,024,433 Netherlands: £793,690 (from Oct 2019-March 2020) GFFO £ 797,395; IKEA Foundation:£1,770,948 Jersey Overseas Aid :£630,000
IMPACT WEIGHTING (15%) |  | Source
Donor cooperation agreement(s)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.2 | Output Indicator 1.21 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
Appropriate project quality and compliance checks are conducted | # and % of projects that, having been assessed through Start Fund 'spot checks', are found to pass minimum spot check standards *** | Planned | 15 out of 15 (100%) Source: Reports for all 15 'spot checked' projects (within 6 in-country visits) during Start Fund phase I. | 85% | 90% | 95% | 95% | Field security conditions allow for a sufficient number of spot check visits to be conducted
|  | Achieved |  | #: 10 %: 100% | #=8 %=100%
IMPACT WEIGHTING (5%) |  | Source
Spot check toolkit and subsequent trip reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
Early and rapid alerting to crises and decision making enables timely humanitarian action in each crisis context | % of Start Fund projects whereby crisis affected populations started receiving assistance within 7 days of their official start dates | Planned | 80% Source: Alerts 151-245; SF PCR Phase I | 85% | 90% | 90% | 90% | • There will be humanitarian crises in the 2018-2022 period which will trigger the Fund's activation. • Accessibility and security contexts allow for rapid intervention. • There will always be some no cost extensions due to extenuating circumstances demonstrating Start Fund's flexible approach. • Awareness of Start Fund's crisis anticipation facility continues to grow.
|  | Achieved |  | 55% | 81%
Source
Start Fund project report forms
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| # of days between crisis onset and alert raised for rapid onset crises (excludes slow onset alerts, which typically follow 'spikes' rather than crisis onset) | Planned | 19 days for alerts (18 days for activated alerts) Source: Alerts 1-245; Salesforce | 19 days | 18 days | 16.5 days | 16.5 days
|  | Achieved |  | 11 days | 13 days
Source
Alert notes. Data disaggregated for natural versus human-made rapid onset crises
| Outcome Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % Start Fund projects completed in 45 days | Planned | 96% Source: Alerts 1-245; PCR Phase I | 96% | 96% | 96% | 96%
|  | Achieved |  | 90.5% | 79%
Source
Start Fund project report forms
| Outcome Indicator 2.4 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of Start Fund alerts and activations that are anticipatory | Planned | Alerts 10% (24/245) Activations 8.75% (14/160) Source: Alerts 1-245; Salesforce | Alerts: 12% Activations: 10% | Alerts: 18% Activations: 15% | Alerts: 30% Activations: 27% | Alerts: 30% Activations: 27%
|  | Achieved |  | Alerts: 13.8% Activations: 17% | Alerts: 14% Activations: 14%
Source
Alert notes
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.1 | Output Indicator 2.11 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The Start Fund conducts timely interventions through crisis anticipation and early action | 2.11a % of Start Fund anticipatory alerts and 2.11b % of activations lerts that include Start team brokered forecasting information (e.g. climatic forecasting, scenario planning, collaborative risk analysis, vulnerability mapping) and other tailored support to support the pre-alert phase (such as provision of guidance notes and external forecast information, consultation and facilitation in advance of the alert, and inclusion on the monthly risk brief through horizon scanning prior to alert). | Planned | 100% Source: Alerts 203-245 (Jan-Jun 2018); PCR Phase I | 100% | 40% | 50% | 55% | • There will be humanitarian crises in the 2018-2022 period that can be forecasted and are suitable to lead to alert note submission. • Awareness of Start Fund's crisis anticipation facility continues to grow. • Crisis Anticipation Team continues to function at full capacity. • Members understand when to raise an anticipatory alerts and have the capacity to do so.
|  | Achieved |  | 2.11a: 33.3% (3/9 alerts in reporting period based on more rigorous interpretation of definition 2.11b: 37.5% (3/8 activations in reporting period based on more rigorous interpretation of definition | 2.11a: 27% 2.11b: 25%
Source
a. Alert notes; b. FOREWARN survey results/Allocation meeting minutes
| Output Indicator 2.12 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| # of decentralised forecasting and risk analysis groups established, trained, and engaged | Planned | No Baseline. Reason: New indicator. | 1 | 2 (3 cumulative) | 2 (5 cumulative) | 3 (5 cumulative)
|  | Achieved |  | 0 | 3 (3 cumulative)
Source
Anticipation tracker
| Output Indicator 2.13 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| # of applications for 'Analysis for Action' (AA) grants from the membership | Planned | 10 Source: Box folder with 'Analysis for Action' (AA) applications | 12 | 22 | 26 | 26
|  | Achieved |  | 12 cumulative (2 applications in this reporting period) | 16 cumulative (4 from this reporting period)
Source
Analysis for Action Grant folder on box (award letter)
IMPACT WEIGHTING (20%) | Output Indicator 2.14 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| 2.14a % of anticipation alerts activated which are rated 3 or below for likelihood (1-5 scale reflects the probability of a crises occurring according to the ACAPs briefing notes for anticipatory alerts) 2.14b Rota members who report supporting the activation of an anticipation alert when they felt a medium or high level of uncertainty about the situation unfolding as predicted in the alert note | Planned | 2.14a 33% Source: Alerts 1-245, ACAPS briefing notes 2.14b No Baseline. Reason: New indicator. | 2.14a 35% 2.14b Not applicable, first rota debrief to take place in May 2019. | 2.14a 37% 2.14b Year-on-year incremental support demonstrated by the rota members to support activations of anticipation alerts under uncertaintly | 2.14a 40% 2.14b Year-on-year incremental support demonstrated by the rota members to support activations of anticipation alerts under uncertaintly | 2.14a 42% 2.14b Year-on-year incremental support demonstrated by the rota members to support activations of anticipation alerts under uncertaintly
|  | Achieved |  | 2.14 a) 62.5% (5/8 during reporting period) 2.14b) Progress to be reported in the next reporting period. | 2.14 a) 22% (2/9 during reporting period) 2.14b) The activation rate for anticipation alerts has risen from 42% in 2017 to 79% in 2018 to 83% in 2019, suggesting the rota are comfortable activating alerts with a degree of uncertainty
Source
ACAPS notes; Rota debrief meeting minutes
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.2 | Output Indicator 2.21 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  | Assumptions
The Start Fund ensures fast decision making delivers rapid funding for humanitarian crises | % of Start Fund activations in which funding initiated within 72 hours | Planned | 77% Source: Alerts 1-245 (excluding anticipation); PCR | 79% | 81% | 84% | 84% | • There will be humanitarian crises in the 2018-2022 period which will trigger the Fund's activation.
|  | Achieved |  | 77% | 74%
IMPACT WEIGHTING (20%) |  | Source
Salesforce
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
Humanitarian relief is more appropriate through more locally driven decision-making, project implementation, and feedback (contribution towards the Grand Bargain Commitments ****) | % of project funds dispersed directly and indirectly to local/national NGOs (as per IASC definitions) | Planned | 74% dispersed directly to members, all of which in this alert range are international NGOs. 21% dispersed indirectly to local/national NGOs (in the form of implementing partners) 5% dispersed both directly to members and indirectly to local/national NGOs (in the form of implementing partners) that can't be disaggregated. Source: Start Fund Annual Report Apr 2017- Mar 2018, based on the alert range 151 to 202. Note: 3 of the Start Network's 42 member agencies are national NGOs (Caritas Bangladesh, Caritas Sri Lanka, and PARC), however none of these received funding within this reporting period. | 30% of project funds dispersed directly and indirectly to local/national NGOs (as per IASC definitions) | 16% proposed as the milestone based on the mid-term review. | 26% but can this be confirmed by June 2020 as we will have some trend analysis in place for the new localisation window | 30% | •The Tiered due diligence system is rolled out successfully. • Agencies continue to submit proposals with local and/or national partners. • Cash programming is considered appropriate to the context; cash programming is shown to enable improved decision making for local populations (https://reliefweb.int/sites/reliefweb.int/files/resources/research-briefctp-childoutcomesfinal.pdf)
|  | Achieved |  | 11% of project funds dispersed indirectly to local/national NGOs (as per IASC definitions). No amount dispersed directly to the local/national NGOs (as per IASC definitions) | 22% of project funds disbursed indirectly (subgranted) to local/national NGOs (as per IASC definition) No amount dispersed directly to the local/national NGOs (as per IASC definitions) | 26% but can this be confirmed by June 2020 as we will have some trend analysis in place for the new localisation window
Source
Start Fund project report forms
| Outcome Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Evaluations and verifications reflect coordination between member agencies | Planned | a) No baseline. Reason: New indicator. b) Spot checks capture information on coordination between members and partners rather than between members. c) No baseline. Reason: New indicator. | (a): None of the assessed projects score red against the score card (b and c): 95% of the assessed projects scoring green | (a): None of the assessed projects score red against the score card (b and c): 100% of the assessed projects scoring green | (a): None of the assessed projects score red against the score card (b and c): 100% of the assessed projects scoring green | Not proposing any target. Indicator will be monitored for reporting purpose
|  | Achieved |  | a) unavailable due to contextual challenges in collecting meaningful data b) 100% c) Data available in Year 2 | a) Communities consulted during field assessments were generally positive about SF project b) 100% c) When applicable, member agencies coordinate their CFMs for more comprehensive approach
Source
Field verifications: 10-15% of projects to be covered annually.
| Outcome Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects (of those that identified a need to adapt) that did adapt | Planned | 100% (but based on a small sample, since alert 223-245) | Maintain 100% | Maintain 100% | Maintain 100% | Maintain 100%
|  | Achieved |  | 100% | 100%
Source
Start Fund project report forms
| Outcome Indicator 3.4 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects that acted upon complaints or feedback from the target beneficiaries, of the projects that received them. | Planned | 20/30 (67%) received complaints or feedback that required changes. Of those 20 projects, all (20, 100%) acted upon them. Source: Report form data for alert range 223-245. | Every project that received complaints from the target beneficiaries shows evidence of actions to address the complain. (100% compliance). | Every project that received complaints from the target beneficiaries shows evidence of actions to deal with the complain. (100% compliance) | Every project that received complaints from the target beneficiaries shows evidence of actions to deal with the complain. (100% compliance) | Every project that received complaints from the target beneficiaries shows evidence of actions to deal with the complain. (100% compliance)
|  | Achieved |  | 100% | 100%
Source
Start Fund project report forms
| Outcome Indicator 3.5 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects reporting that crisis affected populations informed the project (disaggregated across different project stages- e.g. needs assessment, project design, project adaptation, project implementation, and project review/evaluation) [Grand Bargain commitment: Needs Assessment and Participation revolution] | Planned | 90% of projects reported crisis affected populations informed the project ● Needs assessment (NA): 96/124 (77.4%) of projects ● Project design (PD): 50/124 (40.3%) ● Project adaptation (PA): 48/124 (38.7%) ● Project implementation(PI): 103/124 (83.1%) ● Project review/evaluation (PR/E): 60/124 (48.4%) | 90% of projects reported crisis affected populations informed the project ● NA: increasing towards 82% ● PD: increasing towards 42%, ● PA: increasing towards 40%, ● PI: Increasing toward 86%, ● PR/E: increasing towards 55% | 92% of projects reported crisis affected populations informed the project ● NA: increasing towards 87% ● PD: increasing towards 45%, ● PA: increasing towards 42%, ● PI: Increasing toward 88% ● PR/E: increasing towards 60% | 95% of projects reported crisis affected populations informed the project. ● NA: increasing towards 95% ● PD: increasing towards 50%, ● PA: increasing towards 45%, ● PI: Increasing toward 90%, ● PR/E: increasing towards 70% | 97% of projects reported crisis affected populations informed the project. ● NA: Maintain 95% ● PD: increasing towards 55%, ● PA: increasing towards 50%, ● PI: Increasing toward 95%, ● PR/E: increasing towards 75%
|  | Achieved |  | 100% of projects reported crisis affected populations informed the project ● NA: increasing towards 84% ● PD: increasing towards 51%, ● PA: increasing towards 54%, ● PI: Increasing toward 90%, ● PR/E: increasing towards 55% | 100% of projects reported crisis affected populations informed the project ● NA: 91% ● PD: 80% ● PA: 89% ● PI: 73% ● PR/E: 86%
Source
Start Fund project report forms
| Outcome Indicator 3.6 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Current and future Start members are assessed and periodically re-evaluated against stringent tiered due diligence processes | Planned | All members underwent the Start Network's due diligence process and either passed or have time-bound improvement plans | Milestone 1 (July 2019): All 42 current Start members have undergone the refreshed due diligence assessment, and a tiered framework is piloted at national level with 10 potential new members. | Milestone 2 (July 2020): Tiered membership due diligence process is designed, tested and adopted; 10 new members undergo tiered due diligence. | Target (October 2021): Tiered membership due diligence process is deployed for 10 new members and 42 (pre-spin-off) members are re-validated. | Target (October 2021): Tiered due diligence process is scaled up and will enable the Start Network 'hubs' to onboard their own new members in addition to re-validating 39 (pre-spin-off) members and new global members.
|  | Achieved |  | Due to be completed by July 2019 as planned. 41 of the 42 members have undergone the due diligence refresh. A first draft of the Tiered Due Diligence Framework has been completed.Piloting the assessment of ten aspiring members commences by mid-July 2019. (see the narrative report for details). | As of March 2020, with regard to the due-diligence refresher, of the 22 members that were working on improvement recommendations - 19 have achieved a Full Pass, 2 have a Contingent Pass and are working on improvement submissions to achieve a Full Pass, and 1 has a Pause on funding, also working towards a Full Pass. Out of the current 41 members, one member still has not undergone the due diligence refresh process and has no access to funds.By the first week of April 2020 all 12 of the new members (all local/national orgs from DRC, India and Pakistan) in the tiered due diligence pilot had passed.
Source
Report from the Network Development Team
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.1 | Output Indicator 3.11 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The Start Fund supports flexibility and adaptability to meet changing contextual and disaster-affected community needs [Grand Bargain commitment: Participation Revolution] | % of projects (of those that request to adapt) where decisions are made by the Start Fund team within 24 hours | Planned | At award stage, project leads were instructed to contact the Start Team for informing of/asking for project changes. No response time arrangement was in place, however the Start Team responded as quickly as possible, typically within 24 hours. | Decisions regarding adaptability and flexibility requests responded to within 24 hours by the Start Fund team. 90% of project leads report familiarity with the Start Fund Handbook’s guidance on adaptability and flexibility. | 100% of requests regarding adaptability and flexibility receives a response within 24 hours by the Start Fund team. | 100% of requests regarding adaptability and flexibility receives a response within 24 hours by the Start Fund team. | 90% of requests regarding adaptability and flexibility receives a response within 24 hours by the Start Fund team. | • Members and implementing partners are aware of the flexbility and adaptability approach of the Fund.
IMPACT WEIGHTING (10%) |  | Achieved |  | The decision response time can vary from 24 to 36 hours, depending upon the nature of the request and the completeness of the information provided by the requesting agency. During the reporting period, for the majority of cases, this response time on average was around <48 hours For the second part of the indicator- since it is a new indicator, progress to be reported in the next reporting period. | 90% of requests received a response in 24 hours; 94% received a response in 48 hours 100% of projects report familiarity with Start’s adaptation and flexibility outlined in the handbook
Source
Implementation tracker, Start Fund project report forms
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.2 | Output Indicator 3.21 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The Start Fund works closely with local and national NGOs on the front line [Grand Bargain Commitment: National and Local Responders (Localisation) and Cash-based Programming] | % of projects that collaborated with a partner (local or national NGO as per IASC definition), based on joint decision making, joint implementation, capacity building (member to partner), capacity building (partner to member) | Planned | 75% worked with one or more partner organisations (non-Start Network members). Breakdown of the level of engagement projects had with partners: ● Information transfer: (71%) ● Consultation: (63%) ● Implementation: (61%) ● Decision making ownership: (51%) ● Capacity building (member to partner): (34%) ● Capacity building (partner to member): (17%) Source: PCR Phase I | 80% | 47% (5% increase from past year achievement). | 57% (10% increase from past year achievement). | 62% (5% increase from past year ). | • The Tiered due diligence system is rolled out successfully • Agencies continue to submit proposals with local and/or national partners.
|  | Achieved |  | 42% 77% Information Transfer 67% Consultation 48% Implementation 53% Decision Making Ownership 30% Capacity Building (member to partner) 18% Capacity Building (partner to member) | 48% 90% Implementation 70% Decision making ownership 53% Capacity building (member to partner) 13% Capacity building (partner to member) | Proposed-57% (10% increase)
Source
Start Fund project report forms
| Output Indicator 3.22 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects with a cash-based component, disaggregated by modality and method | Planned | 30% of projects delivered cash-based assistance. Breakdown by modality (of the 30% of projects that delivered cash-based assistance) ● Unconditional: 47% ● Cash for work: 10% ● Vouchers/tokens: 17% ● Other (mostly cheques): 26% Breakdown by method (of the 30% of projects that delivered cash-based assistance) ● Cash-in-hand: 50% ● Cash card: 4% ● Sim card/mobile transfer: 13% ● Bank transfer: 8% ● Other (mostly cheques and vouchers): 25% Source: Start Fund Annual Report Apr 2017- Mar 2018. No cash figures available in PCR Phase I. | 30% | 35% | 40% | 45%
|  | Achieved |  | 44%. Results disaggregated by cash-based modalities: Unconditional cash: 77% Conditional cash: 13% Unrestricted cash: 10% Restricted cash: 10% Other modality: 10% Results disaggregated by cash-based methods: Cash-in-hand distributions: 51% Bank transfers: 15% Mobile transfers/SIM cards: 18% Cash cards: 10% Other method: 13% | 50%. Results disaggregated by cash-based modalities: Unconditional cash: 75% Conditional cash: 14% Unrestricted cash: 16% Restricted cash: 25% Other modality: 27% Results disaggregated by cash-based methods: Cash-in-hand distributions: 57% Bank transfers: 5% Mobile transfers/SIM cards: 27% Cash cards: 5% Other method: 27%
Source
Start Fund project report forms
IMPACT WEIGHTING (15%) | Output Indicator 3.23 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of project expenditure spent on cash-based activities | Planned | 9.4% of project expenditure spent on cash-based activities Note: This is a minimum figure and likely to be higher, given that it only reflects cash-specific expenditure and not cash expenditure reported through FSL, Shelter and other sectoral budget lines. Source: Start Fund Annual Report Apr 2017- Mar 2018 | 12% | 15% | 20% | 25%
|  | Achieved |  | At least 19% | 26%
Source
Start Fund project report forms
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.3 | Output Indicator 3.31 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  | Assumptions
Start Fund proposals that have appropriate complaint & feedback mechanisms that are anonymous. [Grand Bargain Commitment: Participation Revolution] | # project proposals that demonstrate anonymous complaint & feedback mechanisms | Planned | No baseline. Reason: New indicator. | Every project proposal outlines an appropriate complaint and feedback mechanism | Every project proposal outlines an appropriate complaint and feedback mechanism | Every project proposal outlines an appropriate complaint and feedback mechanism | All (100%) of project proposals outlines an appropriate complaint and feedback mechanism | • Members continue to put in effort to strengthen collective complaint and feedback mechanisms. • Field security conditions allow for a sufficient number of spot check visits to be conducted
|  | Achieved |  | Progress to be reported in the next reporting period. | 98%
Source
Start Fund project proposals
| Output Indicator 3.32 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects reporting that one or more of the following beneficiary feedback mechanisms were used: help desk, phone, SMS, group meeting, exit survey, suggestion box, talking directly to staff, any other | Planned | 98% of projects reported that one or more feedback mechanisms were used, with the following percentages by mechanism type. ● Help Desk: 24% ● Phone: 48% ● SMS / Text / IVR Services: 21% ● Group meetings: 55% ● Exit survey: 24% ● Suggestion box: 15% ● Talking directly to staff: 72% Source: PCR Phase I | Not proposing any target. Indicator will be monitored for reporting purpose | Not proposing any target. Indicator will be monitored for reporting purpose | Not proposing any target. Indicator will be monitored for reporting purpose | Not proposing any target. Indicator will be monitored for reporting purpose
|  | Achieved |  | 100% Help desk: 27 (30.3%) Phone number: 61 (68.5%) SMS/Text/IVR services: 19 (21.3%) Group meetings: 48 (53.9%) Exit surveys: 21 (23.6%) Suggestion/Complaint box: 28 (31.5%) Talking directly to staff: 49 (55.1%) Other: 22 (24.7%) including via e-mail, radio, community leaders, and complaint committees. | 100% Help desk: 26% Phone number 59% SMS/Text/IVR services: 26% Group meetings: 59% Exit Survey: 20% Suggestion box: 34% Talking w Staff: 59% Other (mainly email): 3%
Source
Start Fund project report forms
IMPACT WEIGHTING (5%) | Output Indicator 3.33 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Data from beneficiaries (derived from PDMs, project assessments and independent monitoring) show an awareness of the existence of feedback mechanisms and how to use them | Planned | No baseline. Reason: New indicator. | 100% | 100% | 100% | 100% of a representative sample of projects (dependent on the annual total) show a positive trend towards arwareness of the feedback mechanisms and how to use them
|  | Achieved |  | % unavailable due to contextual challenges in collecting meaningful data. Approach to be revised in Year 2. | 100%
Source
Spot checks
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 4 | Outcome Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The Start Fund's performance and improvement is shaped by collective knowledge sharing and learning | Member feedback indicates an improvement in collective knowledge to strengthen the Start Fund mechanism and membership | Planned | No baseline: Reason: New indicator. Rota de-briefs (starting mid-May 2019) will be used as a baseline | A year on year improved trend from the baseline | A year on year improved trend from the baseline | A year on year improved trend from the baseline | No specific quantitative target but a year on year positive trend towards collective knowledge sharing and learning | • Continued engagement of current membership. • Significant engagement of new members.
|  | Achieved |  | Progress to be reported in the next reporting period. | Progress to be reported in the next reporting period.
Source
Rota de-briefs (starting mid-May 2019)
| Outcome Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of members participating in alert survey per alert | Planned | 21/42 members (50%) participating on average in alert survey per alert Source: Alert range 151-245 (in keeping with range of PCR Phase I) | 60% | 65% | 70% | 60%
|  | Achieved |  | 46% | 41% |  | With the addition of more local / national organisations with specific geographical focuses, the % of members responding is likely to decrease, hence target reduction.
Source
Alert Surveys
| Outcome Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of members involved in decision making meetings at least once (disagreggated by allocation and project selection meetings) | Planned | 41/42 (97.6%) of members involved in allocation meetings at least once 32/42 (76.1%) of members involved in project selection meetings at least once Source: Based on alert range 151-245 | % of members involved in allocation meetings at least once- maintain 98% % of members involved in project selection meetings at least once- 76% | % of members involved in allocation meetings at least once- maintain 98% % of members involved in project selection meetings at least once- 80% | % of members involved in allocation meetings at least once- maintain 98% % of members involved in project selection meetings at least once- 80% | % of members involved in allocation meetings at least once- maintain 80% % of members involved in project selection meetings at least once- 70%
|  | Achieved |  | Allocation meetings: 90% Project selection meetings: 83% | Allocation meetings: 98% Project selection meetings: 80%
Source
Allocation meeting and Project selection meeting minutes
| Outcome Indicator 4.4 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Evaluations, learning exchanges, learning grants and other modalities reflect collective knowledge sharing and learning within the membership and the humanitarian sector | Planned | No baseline: Reason: New indicator. Consolidated data from various sources for the Start Fund annual review for the first year of phase II will be used as a baseline | No specific quantitative target but a year on year positive trend towards collective knowledge sharing and learning | No specific quantitative target but a year on year positive trend towards collective knowledge sharing and learning | No specific quantitative target but a year on year positive trend towards collective knowledge sharing and learning | No specific quantitative target but a year on year positive trend towards collective knowledge sharing and learning
|  | Achieved |  | Improved trend evidenced (see the narrative report for details) | Improved trend evidenced (see the narrative report for details)
Source
Learning exchanges, evaluations, membership and stakeholder survey
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4.1 | Output Indicator 4.11 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The Start Fund drives learning and evidence-based improvements | # of external evaluations conducted per year with management response designed and published based on evaluation recommendations | Planned | 1 external evaluation conducted per year, given that 4 were conducted over the previous 4 years of the Start Fund, with 2 being broad in scope (e.g. External Evaluation of the Start Fund: Progress, Performance & Future Plans, published Nov 2017), and 2 being more thematic in scope (e.g. The Start Fund, Start Network and Localisation: Current Situation and Future Directions, published Apr 2017) | 1 each year with management response | 1 each year with management response | 0 each year with management response | 1 each year with management response | • MEAL team continues to function at full capacity • The design of the external evaluations is adaptive to the development of the Fund, including small or larger scale evaluations and greater and lesser frequencies • The Start team is mandated to call independent learning reviews on topics deemed to be of key importance to analysis and learning
|  | Achieved |  | 2 ongoing, 1 for the Start Fund and 1 for the anticipation | 1 evaluation on scale up done in 2019, with 1 management response developed 1 evaluation on anticipation funded by the GFFO grant
Source
Evaluations
| Output Indicator 4.12 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of recommendations that apply specifically to the Start Fund (from internal reports and external evaluations) that are agreed, actioned and completed | Planned | Out of 100 recommendations given: 95 (95%) were agreed 95 (95%) were actioned 50 (50%) were completed (so far, with all remaining still underway) Source: Council Meeting pre-read Nov 2017 | Of the agreed recommendations, 100% are actioned and are completed within the agreed timelines | Of the agreed recommendations, 100% are actioned and are completed within the agreed timelines | Of the agreed recommendations, 100% are actioned and are completed within the agreed timelines | Of the agreed recommendations, 100% are actioned and are completed within the agreed timelines
|  | Achieved |  | Nothing to report. We will report once the current evaluation on Start Fund scaling up is finalised. | 100% of the recommendations that needed to be actioned during the reporting period have been actioned and completed during the timelines.
Source
Management Response action tracking tool
IMPACT WEIGHTING (5%) | Output Indicator 4.13 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of projects involved in post-project learning exchanges | Planned | 91% of projects participated in post-project learning learning exchanges. Source: Start Fund Annual Report Apr 2017- Mar 2018 | 95% | 95% | 95% | 95%
|  | Achieved |  | 93% | 90%
Source
Learning exchange minutes
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4.2 | Output Indicator 4.21 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Assumptions
The Start Fund enhances collective information sharing | % of alerts that demonstrate enhanced collective information sharing, such as joint needs assessments, communities of practices, joint reviews etc | Planned | No baseline. Reason: New indicator | TBC | TBC | TBC | TBC | • Following incubation by the Start Fund, forecasting and risk analysis groups will be self-sustaining. • Continued engagement of current membership to share knowledge and learning from the Start Fund projects. • Significant engagement of new members to share knowledge and learning from the Start Fund projects. •Relevant and quality applications submitted by members to qualify for the learning grants.
|  | Achieved |  | Progress to be reported in the next reporting period. | 57%
Source
Does not yet exist. To be developed.
IMPACT WEIGHTING (5%) | Output Indicator 4.22 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| % of total disbursement pot allocated to learning grant initiatives | Planned | £84,853/£8,938,394 = 0.95% Source: Start Fund Annual Report Apr 2017- Mar 2018 | 1% of the total disbursement | 1% of the total disbursement | 1% of the total disbursement | 1% of the total disbursement
|  | Achieved |  | 0.79% | 0.68%
Source
Learning grant minutes
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
*'Niche' categories are as follows: (Group A) 1. Complementing other funding mechanisms and funding streams in mainstream responses through gap filling in time or geography; 2. Delivering funding to crises that are beyond the attention or reach of an ongoing emergency response (‘under the radar’), whether or not that response is internationally or locally-led. 3. Intervening prior to impending crises based on forecasting (anticipation); These three criteria are further disaggregated against the following two: (Group B) 4. Responding to the onset of small to medium scale crises; 5. Responding to specific spikes in chronic (including larger scale) crises. | **Note: Below is the basic definition and a more detailed & operational definition is in the learning report on “Under the Radar” crises. "Crises which are not the subject of, or linked geographically or thematically to, an active emergency response, whether or not emergency response capacity is coordinated by the respective, responsible government or the international system.” https://startnetwork.org/resource/start-fund-involvement-under-radar-crises-external-analysis | *** The Start Fund conducts verification of 10-15% of the projects through spot checks. |  | ****Start Fund contributes towards the following specific Grand Bargain commitments: 1. Greater transparency 2. National and local responders (localisation) 3. Participation revolution 4. Needs assessment 5. Cash-based programming 6. Harmonise and simplify reporting requirements

## Change frame - pre-summer '20 (hidden)
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE | Comments and Status from Start Fund
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Output Indicator 1.21 # and % of projects that, having been assessed through Start Fund 'spot checks', are found to pass minimum spot check standards *** | # and % of projects that, having been assessed through Start Fund 'field visit assessments’, are found to score low risk against the four parameters of project management, financial management, logistics and accountability to affected people Should we change this to just '% of projects...' given that no numbers are included in the milestone? |  |  | Done
2 | Output Indicator 2.11 2.11a % of Start Fund anticipatory alerts and 2.11b % of activations that include Start team brokered forecasting information (e,g climatic forecasting, scenario planning, collaborative risk analysis, vulnerability mapping) | 2.11a: % of Start Fund anticipatory alerts and 2.11b: % of activations 'that include Start team brokered forecasting information which is tailored to that alert (for example, an Analysis for Action grant report, or a hazard and location specific forecast analysis)’. Proposed milestone changes: Milestone 2: 40%; Milestone3: 50% We are happy to accept this amendment for years 2 and 3 |  |  | Thanks. No further comments
3 | Output Indicator 3.11 | Could we simplify the wording and milestones for this indicator? E.g. Indicator: % of projects (of those that request to adapt) where decisions are made by the Start Fund team within 24 hours Milestone: can this then be expressed as a %? |  |  | Done. Yes. Proposed revised milestone: 100% of requests regarding adaptability and flexibility receives a response within 24 hours by the Start Fund team.
4 | Output Indicator 3.21 | Given the application of the IASC definition, is there a need to amend the milestones? Similarly for Outcome Indicator 3.1 |  |  | Indeed. Completed a mid-year review for this milestone and subsequently following amendments are being proposed: Output indicator 3.21: 1 Apr 2019- 31 Mar 2020 Proposed-47% (5% increase from past year achievement); 1 Apr 2020- 15 July 2021: Proposed-57% (10% increase from past year achievement) Outcome Indicator 3.1: 1 Apr 2019- 31 Mar 2020: Proposed milestone is 16% 1 Apr 2020- 15 July 2021: proposed milestone 26% factoring in the new funding provision for the local organisations
5 | Output Indicator 1.12 | Just to clarify, I assume there is no need to amend the milestones for this as year 2 and 3 will take account for the full 12 months? With year 1 there was a discrepancy between the milestone (being based on 12 months) vs the 8.5 month reporting period |  |  | Yes.
6 | Output 1.11 | call for support is dependent on the automation project and is not going to get off the ground in this year. So, as discussed, we request that this is taken off from the logframe and is included in the narrative reporting as a commitment we had made in the business plan
7
8
9
10

## Change frame - post-summer '20 (hidden)
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | Subsequen Target Change | AUTHOR | DATE | Comments and Status from Start Fund | DFID Comments
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) |  | Joe Bloggs | 2018-01-01
1 | Output Indicator 4.21 | Current: % of alerts that demonstrate enhanced collective information sharing, such as joint needs assessments, communities of practices, joint reviews etc Suggested change: % of projects that demonstrate enhanced collective information sharing, such as joint needs assessments, communities of practices, joint reviews etc | N/A | David Burt | 2020-08-12 | This suggested change more accurately represents how data is collected and assessed. | • Output Indicator 4.21 We disagree with the suggested change to remove ‘alerts’. To us this is important that the consultation around alerts is kept in and measurable. This also seems to have remained ‘TBC’. Can Start suggest a figure/measure that can be tracked? For example, could the evidence be gleaned from the alert documents raised? | We suggested this change as methods of collective information sharing are only tracked at the project level i.e. we cannot discern this from alert level data in a systematic way. However, we could retroactively apply the data we collect from project reports to the relevant alerts, but this will only be for activated alerts.
2 | Outcome Indicator 4.1 | Current: Members in their feedback following rota de-briefs indicate an improvement in collective knowledge to strengthen the Start Fund mechanism and membership Suggested Change: Member feedback indicates an imrpvement in collective knowledge to strengthen the Start Func mechanism and membership | N/A | David Burt | 2020-08-12 | While the process of rota debriefs is revised, I suggest we make this more of a general indicator and use a wide array of data sources e.g. member surveys / post-rota KIIs and interviews | • Outcome Indicator 4.1 We agree with the suggested change by Start to the text. | OK
3 | Outcome 4.2 | Current: % of members participating in alert survey per alert Suggested Change: Maintain indicator but change target | Current: Target = 70% Suggested Change: 60 % | David Burt | 2020-08-12 | Likely to decrease based on current trends and increase of nationally-focused members,by decreasing the target we account for the inclusion of national organisations. | • Outcome Indicator 4.2 We agree with the suggested change by Start to 60%. | OK
4 | Outcome 4.4: | Current: Evaluations, learning exchanges, learning grants and other modalities reflect an improved trend towards collective knowledge sharing and learning within the membership and the humanitarian sector Suggested Change: Evaluations, learning exchanges, learning grants and other modalities reflect collective knowledge sharing and learning within the membership and the humanitarian sector | N/A | David Burt | 2020-08-12 | Have limited the scope as it is almost poissible to show 'an improved trend' but we can share examples of collective knowledge sharing. | • Outcome Indicator 4.4 We agree with the suggested change by Start to the text. | OK
5 | Output indicator 2.11a | Current: % of Start Fund anticipatory alerts (that include Start team brokered forecasting information (e,g climatic forecasting, scenario planning, collaborative risk analysis, vulnerability mapping) Suggested Change: % of Start Fund anticipatory alerts that include Start team brokered forecasting information (e.g. climatic forecasting, scenario planning, collaborative risk analysis, vulnerability mapping) and other tailored support to support the pre-alert phase (such as provision of guidance notes and external forecast information, consultation and facilitation in advance of the alert, and inclusion on the monthly risk brief through horizon scanning prior to alert). | Current: Target = 50% Suggested Change: 55% | Ed Parkinson | 2020-08-12 | Have expanded this indicator and included metrics will actually help us indicate the reach of guidance notes, but also the range of guidance notes available, and our own identification of appropriate crises on the risk brief. | • Output Indicator 3.21. We agree with the 57% proposed.
6 | Output indicator 2.11b | Current: % of activations that include Start team brokered forecasting information (e,g climatic forecasting, scenario planning, collaborative risk analysis, vulnerability mapping) Suggested Change: % of Start Fund anticipatory alerts that include Start team brokered forecasting information (e.g. climatic forecasting, scenario planning, collaborative risk analysis, vulnerability mapping) and other tailored support to support the pre-alert phase (such as provision of guidance notes and external forecast information, consultation and facilitation in advance of the alert, and inclusion on the monthly risk brief through horizon scanning prior to alert). |  | Ed Parkinson | 2020-08-12 | Have expanded this indicator and included metrics will actually help us indicate the reach of guidance notes, but also the range of guidance notes available, and our own identification of appropriate crises on the risk brief.
7 | Output indicator 3.33 | Current: % of beneficiaries per project (who were consulted) reported that they were aware of the existence of feedback mechanisms and how to use them, and comfortable providing feedback Suggested Change: Data from beneficiaries (derived from PDMs, project assessments and independent monitoring) show an awareness of the existence of feedback mechanisms and how to use them | N/A | David Burt | 2020-08-12 | This indicator is almost meaningless *the % who were consulted" = we could consult 1 person and it would be 100%, suggest overhauling and making this indicator related to a variety of sources - particularly as we will only be able to do things remotely until further notice. | • Output Indicator 3.33 doesn’t include the new text in the Change Frame tab. We agree with the comment in the Change Tab ie 1 could equal 100%. Can Start suggest a number? | The text appears for me?
8 | Outcome 3.2 | Current: Evaluations and verifications reflect a) positive feedback from beneficiaries regarding the appropriateness of the assistance, b) coordination between member agencies and, c) consistent effort towards collective feedback mechanisms Suggested change: Evaluations and verifications reflect coordination between member agencies | N/A | David Burt | 2020-08-12 | Hard to report against as it's so broad, I have removed the section about beneficiaries as I believe this is covered by 3.33. Also over the years it has become apparent that collective feedback mechanisms are not commonly used by members, and in some cases are detrimental to projects, so I have removed this. | • Output 3.2 Could Start elaborate abit more on the rationale for the change? We weren’t quite sure from the explanation in the Change Frame tab. For example, what how the collective feedback mechanism can be detrimental. | Members at the coutnry level have stated that collective feedback mechanisms don't practically work as well as a single agency setting up their own mechanism, the main arguments being: in terms of processes to handle feedback and whether those are the same or reconcilable across organisations / issues around data protection / identifying in advance which agency/ies needs to respond to the feedback. Start has received feedback from members that for specific issues such as feedback on fraud or bribery-related concerns, it can be easier as most organisations agree to certain mechanisms for sharing such information, but for regular programmatic feedback, it adds additional complexities in how to manage and respond. Organisations are also very sensitive about sharing complaints data with each other - in which members of staff can be identified as someone who has broken the law and/or internal policies - there's reputational risk but also extremely sensitive information being shared.So if you were going to do it, you'd need all sorts of data protection agreements, probably a third party to manage the hotline, really clear disaggregation of complaints (e.g. if the beneficiary couldn't identify the organisation, how would the complaint be forwarded to be managed etc.)
9 | Output 3.1 | Current: # project proposals that demonstrate appropriate complaint & feedback mechanisms that are confidential Suggested Change: # project proposals that demonstrate anonymous complaint & feedback mechanisms | N/A | David Burt | 2020-08-12 | Minor change, but confidentiality is much harder to report against as it depends on internal systems. I have removed appropriate as well as the inference is that the community had a say in which mechanisms were used, which we don't currently have a way to track. | Output Indicator 3.31. This needs to be quantifiable. We suggest potentially linking this to Indicator 1.21 on the spot checks. To make it measurable and avoid ambiguity of the ‘#’ can Start suggest a number/measure?
10

## Guidance Notes (hidden)
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.