## Annual Review Template

Title: Neglected Tropical Diseases Implementation Research Programme (NIRP) – COUNTDOWN
Programme Value £ (full life): £11,321,225 (Contract amendment pending to reduce to approx. £10.25m)		Review date: / June 2021
Programme Code: 203089	AMP start date: / 29 July 2013 / Actual start date: / 1 November 2014	AMP end date: / 31 October 2021 / Planned end date: / 31 October 2021

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020	2021
Overall Output Score	A	A	A	A+	A+	A+	A+	A+
Risk Rating	Minor	Major	Major	Major	Major	Major	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme
The Neglected Tropical Diseases (NTDs) Implementation Research Programme, COUNTDOWN, is a 7 year programme, led by Liverpool School of Tropical Medicine (LSTM) with partners in the 4 operating countries (Ghana, Liberia, Nigeria and Cameroon) where NTDs are prevalent. The programme is focused on delivering high quality evidence on cost effective, scalable and sustainable solutions necessary to control and eliminate 7 NTDs (trachoma, schistosomiasis, river blindness, elephantiasis, and three soil transmitted helminths) that together have been responsible for 90% of the total global burden of NTDs. The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) to simultaneously treat and control disease.

COUNTDOWN brings together researchers from a range of backgrounds and disciplines, health care providers, policy makers, laboratory scientists, research uptake specialists, Ministries of Health and Non-Government Development Organisations (NGDOs) and presents an opportunity to bridge the knowledge to implementation gap for shared health impact. Across contexts, COUNTDOWN has been working proactively and collaboratively with health policy makers and NTD programme implementers at country level to disseminate research findings on an ongoing basis and help ensure that evidence generated has been of maximum benefit to NTD programmes. It also consolidates the narrative of research to policy change in an accessible manner, supporting evidence informed policy at district (state), national and international levels. The programme’s efforts to increase the reach and scale up of NTD treatments is important in helping to accelerate progress towards meeting World Health Organisation targets on NTDs.

Summary supporting narrative for the overall score in this review
Output moderately exceeded expectations. COUNTDOWN has performed well this year and has continued to make good progress in all aspects of its work despite facing significant challenges as a result of COVID-19 restrictions (no international travel, inability to undertake fieldwork for most of the year), political instability in Nigeria, and a budget reduction as a result of FCDO business planning decisions. The programme revised their plans to best effect, focusing on research, capacity strengthening and stakeholder engagement activities that could be undertaken remotely, and prioritising the delivery of products to aid research dissemination and uptake. Nevertheless, some research projects have inevitably been delayed and face to face capacity strengthening and regional/international stakeholder engagement and dissemination activities, have been revised/cancelled.

Of particular note this year, has been:
- COUNTDOWN’s use of social research to co-produce adaptations to NTD programmes and overcome barriers to access, which has strengthened MDA and supported those living with NTDs in Nigeria and Liberia. COUNTDOWN’s multidisciplinary implementation research approach is regarded globally as a best practice model of NTD research.
- COUNTDOWN being asked by stakeholders, in recognition of their health systems focus and expertise, to support the restart of NTD activities after they were halted for a year by the COVID-19 pandemic.
- Research resulting in an improved understanding of systematic non-compliance of MDA enabled researchers to highlight the contextual challenges that exist and that overcoming these barriers is a complex interaction of political, societal, environmental and community factors.
- Evidence around how images can be powerful and are recognised beyond literacy levels, culture and language, and can help amplify the voices of those affected by NTDs to support social change.
Key lessons are:
- The continued importance of regular communication, experience-sharing and support across programme partners to support virtual working.
- That some capacity strengthening and stakeholder engagement activities can be undertaken successfully and cost-effectively through virtual means.
Key Recommendations are for COUNTDOWN:
- COUNTDOWN and FCDO to formally adjust the programme logframe to reflect changes in deliverables in the period to 31 October – by 9 July
- to prioritise the completion/delivery of those products with the greatest potential to impact policy and practice - by 31 October
- to consolidate and disseminate cross-country and cross-cutting research learning – by 31 October
- to focus on linking with priority stakeholders to maximise dissemination and research uptake opportunities - by 31 October
- COUNTDOWN and FCDO to agree on the disposal of programme assets - by 30 September
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

COUNTDOWN’s Theory of Change (depicted below) remains as revised in 2019, and continues to guide programme activities. In order to achieve its impact of “Reduced morbidity, mortality and poverty associated with NTDs from application of new evidence for cost-effective scale up of sustained control and targeted elimination in line with the WHO 2020 NTD Roadmap and the 2030 SDGs”, COUNTDOWN research has focused on: improving the availability and accessibility of NTD interventions to individuals and communities; and on influencing improved consideration of gender, equity and the most vulnerable in NTD programming, so that more people can access appropriate interventions and treatments and the effectiveness of NTD programmes is increased.

The programme logframe aligns with the Theory of Change and is the basis of monitoring progress. Milestones and deliverables have been reviewed in light of delays due to COVID- 19 and budget constraints.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Despite the challenges this year of COVID-19, political instability in Nigeria, and budget constraints, COUNTDOWN continues to perform well and to make good progress towards programme outcomes.

COUNTDOWN has identified key gaps in availability and accessibility to NTD services and has worked with stakeholders to address these and ensure that services can reach those most in need. COUNTDOWN has used participatory approaches to explore social norms and their gendered impacts on NTDS (research papers here and here), and has used data collected, analysed and presented by communities to make changes (e.g. to places where treatment is best delivered to ensure it is accessible to both men and women).

In the period to 31 October, COUNTDOWN’s focus will be on consolidation, demonstration of research findings, and linking with stakeholders for impact and sustainability.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
COUNTDOWN and FCDO had been planning to extend the programme to 31 March 2022 to allow for the completion of all activities that had been delayed as a result of COVID-19 restrictions. However, an extension is no longer viable in the context of revised business planning and current fiscal constraints, and the programme will reach its natural end date on 31 October.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers
Output number:		1	Output Score:	A+
Impact weighting (%):		60%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of approved research projects	i) Design: 0 / ii) Implementation: 0 / iii) Analysis/ Dissemination: 0 / iv) Completed: 20 / Total: 20	Moderately did not meet expectations. / i) Design: 0 / ii) Implementation: 0 / iii) Analysis/ Dissemination: 6 / iv) Completed: 15 / Total: 21
1.2. Open access research publications: / Total no. of peer reviewed journal articles / Additional indicators: / i) lead or co-author with home institution in LMIC / ii) female lead/co-author / iii) female lead/co-author with home institution in LMIC	34 peer reviewed articles in total. / Additional indicators: / i) Lead or co-author with home institution in LMIC: 15 / ii) Female lead/co-author: 23 / iii) Female lead/co-author- home institution in LMIC: 5	Moderately exceeded expectations. / 45 peer reviewed articles in total / Additional indicators: / i) Lead or co-author with home institution in LMIC: 26 / Ii) Female lead/co-author: 35 / iii) Female lead/co-author- home institution in LMIC: 9
1.3. Number of cross-country outputs and/or learnings	6 cross-country products that highlight how research exchanges have enabled change in research approaches, knowledge/skills and/or NTD programme design or delivery	Moderately exceeded expectations. / Achieved: 13
1.4. Open access knowledge products (presentations, blogs, briefs) produced and disseminated	250 knowledge products, including 18 policy briefs, developed and geographic dissemination mapped, including through website download and page views	Moderately exceeded expectations. / Achieved: 322 knowledge products; 19 policy briefs

Briefly describe the output’s activities and provide supporting narrative for the score.
Output moderately exceeded expectations. COVID-19 restrictions inevitably delayed progress on some research studies, with fieldwork necessarily being halted for a good part of the year. However, the team made best use of homeworking to focus on analysis, publications, knowledge products etc. and exceeded expectations in these areas.

There are 6 projects at analysis/dissemination stage:
- in Liberia, on: integrating the detection and management of Female Genital Schistosomiasis (FGS) into health systems in highly endemic areas;
- in Nigeria, on: developing an integrated community based detection and referral system for skin-affecting NTDs; establishing a community based support system for people affected by stigmatising skin diseases; evaluating a Participatory Action Research Cycle on an enhanced community engagement package for preventative chemotherapy of NTDs; and, strengthening health systems to manage FGS in highly endemic areas; and
- in Liberia and Nigeria, on decentralised, planning and implementation of MDA restart strategies in the context of COVID-19.
Work is on track to complete all 21 research projects by 31 October (programme end date).

A further 7 peer reviewed publications were produced this year: 5 have been published in open access journals; 2 submitted for publication.

A further 7 cross-country outputs/products were produced this year. Examples include:
- COUNTDOWN’s support for the development of TDR’s (the Special Programme for Research and Training in Tropical Diseases at WHO) new toolkit “Incorporating Intersectional Gender Analysis into Research on Infectious Diseases of Poverty” here
- A learning booklet on integrated management strategies for NTDs that affect the skin in Sub-Saharan Africa here
- A policy brief, highlighting key recommendations for action to strengthen COVID-19 responses, drawing on experience of health systems in UK and Liberia here
COUNTDOWN’s peer reviewed publications, policy briefs, case studies, and blogs can be found at https://countdown.lstmed.ac.uk/publications-resources

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Delivery of this output continues to represent VfM. In the face of COVID-19 restrictions, COUNTDOWN refocused towards activities that could be undertaken remotely and would add most value at this stage e.g. developing products to aid research uptake.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Changes included workplan adjustments in response: to COVID-19 restrictions and political insecurity in Nigeria.

 Key Lessons
- Photo booklets (created from a participatory research method that empowers participants to tell their own story) have been effective advocacy tools to highlight issues faced by people with NTDs e.g. stigma, social exclusion
- Involving persons affected by NTDs and care givers as co-researchers throughout the research and design intervention process can improve gender equality, equity and/or the situation of the most vulnerable.

Recommendations
As the programme draws to a close, COUNTDOWN should:
- Consolidate cross-country and cross-cutting research learning so that the sum of research findings is greater than individual studies;
- prioritise the completion/delivery of those products with the greatest potential to impact policy and practice.
## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control
Output number:		2	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Involvement of key stakeholders at national, state and district level in developing linkages, partnerships, across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming	4 examples of how networks established during COUNTDOWN will be sustained beyond the life of COUNTDOWN to influence change to NTD policy and practice	Moderately exceeded expectations. / Achieved: 9
2.2. COUNTDOWN undertakes research uptake and dissemination activities effectively	7 examples of change to NTD policy and practice resulting from COUNTDOWN evidence and research uptake	Moderately exceeded expectations / Achieved:10

Briefly describe the output’s activities and provide supporting narrative for the score. Moderately exceeded expectations. COUNTDOWN has continued to actively and successfully identify and engage with numerous key stakeholders to support evidence-based policy and practice for NTD control albeit that plans for face to face events have been adapted to take place virtually.

To illustrate, COUNTDOWN:
- is a founding member of the Genital Schistosomiasis (GS) Network comprising researchers, implementers, WHO, policy makers and communication experts who share information, findings, and progress on male and female GS, to improve diagnosis/treatment/prevention;
- is helping to strengthen mental health networks in Liberia, engaging with: the Ministry of Health and the Carter Centre, Liberia to strengthen stakeholder connections in country; United for Global Mental Health to strengthen collaborations/support future evidence uptake; and the NGDO NTD Network Disease Management and Disability Inclusion working group, focusing on stigma reduction and mental health;
- works at a strategic level internationally, including participating in several Health Systems Global Thematic working groups: Emerging Voices, Fragile & Conflict Affected Settings, Social Science Approaches, and Community Health Workers;
- is supporting MDA restart strategies in the context of COVID-19. Recent research, on Community Drug Distributor adherence/understanding of revised MDA guidelines and community perspectives on the safety of the MDA in the COVID-19 context, has identified challenges with adherence to new guidance and barriers to implementation. COUNTDOWN is well placed to influence evidence take-up, including with NTD programmes considering restarting MDA, implementing partners, WHO and donors.
- is supporting early case detection of skin NTDs and the prevention of negative health impacts from delayed diagnosis in Nigeria. Drawing on stakeholder meetings to map current and potential health seeking pathways for persons affected by skin NTDs, COUNTDOWN designed training packages/tools for community/primary health workers to recognise symptoms, provide basic treatment and refer cases on.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Delivery of this output continues to represent VfM. Whilst maintaining contact with stakeholders was challenging as a result of COVID-19, the strength of existing relationships helped COUNTDOWN re-engage with partners with renewed energy as country restrictions lifted.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Changes included workplan adjustments in response: to COVID-19 restrictions and political insecurity in Nigeria.
.
Key Lessons
- Improved health worker capacity to manage skin NTDs will improve access/quality of care for people affected (who are vulnerable to stigma and often present late).
- Including persons affected by skin NTDs and community health workers as key stakeholders ensured training materials were understood at community level.
Recommendations
Over the next few months COUNTDOWN should focus on linking with priority stakeholders to maximise dissemination and research uptake opportunities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country-based research communities
Output number:		3	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. Organisations engaged in COUNTDOWN implementation research have improved capacity	4 examples of sustainable change resulting from capacity strengthening at an institutional environment	Moderately exceeded expectations. / Achieved: 6
3.2. Individual stakeholders engaged in COUNTDOWN / implementation research have improved capacity	4 examples of sustainable change resulting from capacity strengthening of individual stakeholders	Moderately exceeded expectations. / Achieved: 6

Briefly describe the output’s activities and provide supporting narrative for the score.
Output moderately exceeded expectations. COUNTDOWN continued to work with programme partners to successfully enhance sustainable, multi-directional, capacity at both an institutional and individual level, and in response to identified needs. Whilst some cross-country training activities were cancelled due to COVID-19, those that could be undertaken virtually took place.

Examples this year, include:
- Support to ULPIRE (Liberian partner) to create a clear safeguarding policy, with supporting risk assessment processes and reporting structures, and the inclusion of identified safeguarding leads. Capacity strengthening was supported by a webinar and presentations, informed by learnings and scenarios captured through research experience, and tailored to the Liberian context. The scenarios are applicable across many LMIC settings and can be used by global health actors to develop safeguarding policies, and to build personnel capacities to uphold safeguarding ethics and principles during research.
- Support to all partner institutions as they shifted to homeworking during the pandemic, to assess the needs of research staff to continue working during lockdown whilst also planning for their return to the office and field working. This included: amending risk assessments and developing mitigating strategies for safeguarding staff and research participants; and retraining teams on multiple platforms for communications and virtual conference attendance.
- Mentoring junior researchers to support innovative research on NTDs and COVID-19, to inform the current outbreak response and future preparedness. Junior researchers undertook projects across the 4 COUNTDOWN countries and gained experience of multi-directional learning, research applications, ethical approvals and research planning and reporting.
- Hosting numerous capacity strengthening webinars - particularly useful to enhance individual researcher’s methodology skills e.g. on qualitative analysis, literature searches etc.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Delivery of this output continues to represent VfM. By ensuring that sustainability is central to COUNTDOWN’s capacity building strategy, the programme helps to ensure that investments made now support long lasting change and generate significant return in the long term.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Changes included workplan adjustments in response to COVID-19 restrictions - lots of capacity building activities have been conducted virtually.

Lessons learned this year
That it can be cost-effective to undertake capacity strengthening activities remotely rather than face to face. On-line training allows more people to learn at once and at the same cost, and can be just as effective as face to face training for some courses.

Recommendations for the year ahead
COUNTDOWN should wind down their capacity building activities over the next few months and give greater focus to finalising research and, importantly, research uptake.

D: RISK [½ to 1 page]

Overview of risk management
The project holds its own risk register that is monitored and discussed with FCDO regularly. FCDO manages its own risk register and matrix. FCDO risk ratings are shown in the table below.

Overall risk rating: The overall risk rating is currently Moderate. The risk assessment was updated as part of this review and is aligned to the new FCDO risk management system. The risks are all within FCDO’s risk appetite.

Overview of project risk and mitigaton
Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Major	Minor	Minor	Moderate	Moderate	Minor	Moderate

Strategy and Context – Major – COUNTDOWN research activities can be at risk from political instability and civil unrest in partner countries. This is closely monitored and project activities adapted where possible, for example by avoiding certain geographical areas. There is currently a heightened risk that research activities will be further delayed/not be able to be completed within the programme period, as a result of COVID-19 related pressure on health systems in Liberia and Nigeria e.g the rollout of MDA in Liberia hasn’t yet taken place and so research focussed on this has consequently been delayed. COUNTDOWN continue to closely monitor the situation and to adapt their plans accordingly in consultation with FCDO.

Policy and Programme Delivery – Major – As the programme draws to a close, it is important to maximise opportunities to disseminate research findings and to engage with/influence key stakeholders to advance research uptake. Planned, in person, cross-country events are not possible due to COVID-19 restrictions and, where possible, events are being moved online. This limits interaction and carries the risk that stakeholder engagement and influence will be less effective than planned. COUNTDOWN continues to mitigate this risk by disseminating findings widely through a range of communication channels and by carefully planning on-line events to help meet programme objectives.

Public Service Delivery and Operations – Minor - COUNTDOWN are familiar with FCDO requirements and expectations and the programme has a good track record of effective, proportionate contact/relations with FCDO. FCDO will continue to engage routinely with COUNTDOWN, closely monitoring performance.

People – Minor – COUNTDOWN has developed strong partnerships and a culture of peer support. The programme is highly focussed on inclusion and gender equity and has delivered very well on its programme of capacity strengthening.

Safeguarding – Moderate – At this stage, the risk mainly relates to ensuring that COUNTDOWN staff adhere to country guidance in UK, Liberia and Nigeria in relation to COVID-19. Teams are in regular contact and updates are shared on an ongoing basis. All partners have signed up to COUNTDOWN’s safeguarding policies and principles, designed to reduce the potential for harm arising from research in focus countries. Capacity strengthening activities in this area have been ongoing and have been tailored to research projects.

Financial and Fiduciary – Moderate – LSTM has comprehensive financial management procedures and has demonstrated good governance (close monitoring of budgets and reporting) which helps protect FCDO funds from fraud or misuse. There is an ongoing exchange rate risk that is being effectively managed through setting rates in advance and adjusting financial plans, and close monitoring.

Reputational – Minor– The research topics are not controversial and findings are not contentious. LSTM is an experienced research partner with strong governance and ethics and a good understanding of FCDO expectations around standards and appropriate use of funds.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

FCDO and LSTM have collaborated well throughout the year and have been in regular contact, by e-mail, telephone and online meetings to discuss a range of issues, including: technical progress, the impact of COVID-19 on the programme, the possibility of a contract extension, budget reduction, and invoicing and forecasting.

LSTM have been efficient in managing the programme budget and reporting on financial performance throughout the year. Spend of £976,571 in 2020/21 was approximately 2.7% over the programme forecast of £950,600, as a result of spend being ramped up when COVID-19 restrictions were lifted sooner than anticipated in both Liberia and Nigeria.

Due to the impact of COVID-19 and pressure on the global and UK financial economies, a planned extension to the COUNTDOWN programme will no longer go ahead, all underspend from earlier years has been removed and the budget allocation for the period to 31 October has been reduced to £750,000. Whilst disappointed, COUNTDOWN have been understanding and have worked with partners to revisit their workplan and budget.

Personnel is the most significant cost for the programme to date at 57%, with programme costs at 23%, travel at 9%, equipment at 2% and overheads at 9%.

COUNTDOWN has maintained a strong focus on economy and cost containment over the year and capitalised on opportunities to cost share among other projects when possible. Their conversion of research activities to a high number of concrete outputs (publications, tools, job aids etc) that have been widely shared and taken up, is testimony to COUNTDOWN’s efficiency. The successful leveraging of funds from various sources (including COR-NTD and effect:hope) in support of COUNTDOWN objectives totalled in excess of £143,000 over the last year, and enhanced the overall efficiency of the programme.

LSTM record all equipment/programme assets centrally and update the register quarterly. Assets are audited during programme management team visits to partner institutions.

LSTM Annual Report and Financial Audited Statements have been submitted to FCDO for audit compliance.

Date of last narrative financial report	30/4/2021	Date of last audited annual statement	25/11/20 here