 Annual Review Report

Title: North East Nigeria Transition to Development (NENTAD) Programme
Programme Value £ (full life): £400 million		Review date: June 2021
Programme Code: 300432	AMP start date: 27th April 2017	AMP end date: 31 March 2022

Summary of Programme Performance
Year	2017/18	2018/19	2019/20	2020/21
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Severe	Severe

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300432/
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300432/documents

List of Acronyms

AAP	Accountability to Affected Populations
AAH	Action Against Hunger
ANC	Antenatal Care
BAY	Borno, Adamawa and Yobe
BSFP	Blanket supplementary feeding programme
CBT	Cash-based transfer
DRC	Danish Refugee Council
GBV	Gender Based Violence
GoN	Government of Nigeria
ICRC	International Committee of the Red Cross
IDP	Internally Displaced Person
INGO	International Non-Governmental Organisation
IP	Implementing Partner
IPC	Integrated Phase Classification
IRC	International Rescue Committee
IRF	Internal Risk Facility
LGA	Local Government Area
MAM	Moderate Acute Malnutrition
MUAC	Mid-Upper Arm Circumference
NENTAD	North East Nigeria Transition to Development
NFI	Non-food item
NRC	Norwegian Refugee Council
NSAG	Non-State Armed Group
OPT	Outpatient Treatment
PLW	Pregnant and Lactating Women
PPE	Personal Protective Equipment
ProSPINE +	Promoting Rights and Supporting Protection Needs in NE Nigeria
PSS	Psychosocial Support
PWD	Persons with disabilities
RUTF	Ready to Use Therapeutic Food
SAM	Severe Acute Malnutrition
SC	Stabilisation Centre
SUNY	Scaling Up Nutrition in Yobe
TWB	Translators without Borders
UASC	Unaccompanied and Separated Children
UNHAS	United Nations Humanitarian Air Service
UNICEF	United Nations Children’s Fund
VAWG	Violence Against Women and Girls
WASH	Water Sanitation and Hygiene
WFP	World Food Programme
A. SUMMARY AND OVERVIEW

Description of programme
The North East Nigeria Transition to Development Programme (NENTAD) was designed to deliver humanitarian assistance and support the transition towards development programming in Borno, Adamawa and Yobe (BAY) states from 2017-2022. This is the fourth Annual Review of the five-year programme. NENTAD’s design was premised on the assumption that Nigerian security forces would provide an increasingly stable environment throughout the life of the programme, enabling the transition from humanitarian assistance to recovery and development. The trajectory at NENTAD’s inception in 2017 was promising. However, since August 2019 there has been significant and consistent deterioration in both security and humanitarian access with humanitarian needs are now reaching levels last seen in 2017. A business case addendum in 2018 increased the programme budget from £300 million to £400 million in recognition of the sustained scale and severity of humanitarian needs. A further business case addendum was submitted in May 2021 to raise the budget ceiling by £25m to enable delivery of the humanitarian component of the approved FCDO Nigeria Business Plan.

Over the five years, the programme was designed to provide:
- Up to 1.5 million people with food assistance
- Support for the treatment of Severe Acute Malnutrition (SAM) for up to 120,000 children under 5 years
- Emergency education for 200,000 conflict-affected children
- Basic health care in conflict-affected areas
- Support to safe humanitarian access and strengthened coordination in operational areas
- Delivery of protection services to the most vulnerable.
Context
The Lake Chad Basin crisis, affecting North East (NE) Nigeria, Niger, Chad and the Far North of Cameroon is now in its twelfth year. NE Nigeria is the epicentre of the crisis, with the largest number of internally displaced persons (IDPs) and people in need of humanitarian assistance in the region. In 2021 there are 8.7 million people in need of humanitarian assistance across Borno, Adamawa and Yobe states, compared to 7.9 million in January 2020; of which 1.9 million people are internally displaced. An estimated 1 million people live in areas inaccessible to humanitarian agencies, with little or no access to basic services. Up to 4.36 million people are projected to face critical levels of acute food insecurity (Integrated Phase Classification (IPC) 3 and 4) during the 2021 lean season (June-August) with high rates of malnutrition surpassing emergency thresholds in Yobe. The magnitude and severity of food insecurity is approaching levels seen in 2016/17 when the international community acted decisively to avert famine, with famine-like conditions already possible in inaccessible and hard to reach areas.

Insecurity in NE Nigeria continues to worsen, particularly in Borno and eastern Yobe, with regular attacks against civilians and humanitarian workers. In 2020 approximately 4,000 people were displaced each week on average due to the conflict. Around 85% of Borno State’s territory has been inaccessible to humanitarian agencies since September 2019. Non-state armed groups (NSAGs) control major transport and supply routes and regularly attack garrison towns. In Borno State, aid workers are now only able to access select towns outside the capital Maiduguri by helicopter. Humanitarian access has deteriorated due to worsening insecurity, compounded by bureaucratic impediments and logistical difficulties in reaching areas that are physically accessible.

The 2020 Humanitarian Response Plan (HRP) was costed at $1.08 billion, targeting 7.8m people (of 10.6m in need), after the Covid-19 pandemic caused targets to be revised upwards, and was funded at 57.8%. The 2021 HRP is costed at $1.01 billion, targeting 6.4 million people; committed funding is currently only 18%. Under-funding is driving critical gaps in the provision of food, shelter, water, health and nutrition services, as well as provision of common services, such as the Humanitarian Hubs and UNHAS.

During the review period, NE Nigeria was impacted directly and indirectly by Covid-19; however, the numbers of recorded cases remain relatively low and widespread community transmission in IDP camps has not occurred. The pandemic had a major impact on the delivery of aid operations as organisations rapidly adapted in order to keep staff and communities safe while still delivering critical services.

Implementing partners
The implementing partners (IPs) for the NENTAD programme during the review period are:
- Action Against Hunger (AAH)
- International Committee of the Red Cross (ICRC)
- IMPACT Initiatives
- International NGO Safety Organisation (INSO)
- International Organisation for Migration (IOM)
- International Rescue Committee (IRC)
- UN Children’s Fund (UNICEF)
- UN Department for Safety and Security (UNDSS)
- World Food Programme (WFP)
Insecurity continues to be a significant challenge for implementing partners with staff safety a serious and increasing concern, as NSAGs directly target aid workers and infrastructure. Bureaucratic impediments and limited availability of armed escorts compound operational challenges. Access to garrison towns was restricted during August and September 2020 following the shooting of an UNHAS helicopter. Due to heightened risks FCDO funded additional support to aid worker safety through to UNDSS and IOM.

Covid-19 increased humanitarian access challenges for several months in 2020 as staff movements were reduced to protect both vulnerable communities and staff themselves. There was also a significant drawdown of agency staff. IPs continued delivery of critical services by relying increasingly on national/local staff, and a greater use of community networks. Delivery plans were adjusted, as were beneficiary verification, data collection and distribution processes to follow Covid-safe protocols with an increased degree of remote management and virtual meetings.

Programme Management
The FCDO Nigeria Humanitarian and North East Team managed a reduction in capacity with the completion of one Humanitarian and Stabilisation Operations Team advisory deployment towards the end of the review period. Advisory input was provided remotely for significant periods as a result of Covid-19. One programme manager was replaced during the review period. Drawdown of staff during Covid-19 resulted in prolonged periods of remote working, requiring staff handovers to be managed remotely. Technical support to FCDO’s work on the cash-social protection nexus was provided remotely during the review period through the central Better Assistance in Crises (BASIC) programme.

The Covid-19 pandemic required adjustments to both partner plans and FCDO management. All IPs reviewed their operational presence and adopted Covid-sensitive practices to support the safety of staff and communities. Partner meetings and programme reviews were conducted virtually rather than in person. Field-monitoring by FCDO was not possible between March and September 2020 due to travel restrictions and Covid-19 protocols; however, regular meetings, quarterly reviews and third-party monitoring continued.

Summary supporting narrative for the overall score in this review
The NENTAD programme has met the majority of its outcome and output targets, resulting in an overall score of A. During FY 2020/2021 NENTAD:
- Responded to critical food needs of more than 750,000 people in need through in-kind or cash-based humanitarian assistance
- Treated over 43,000 children for Severe Acute Malnutrition (SAM) and provided ready-to-use therapeutic food supplies for over 94,000 children
- Prevented malnutrition for nearly 61,000 children aged under two years and 24,600 pregnant and lactating women
- Provided clean water to over 203,000 people, improved sanitation infrastructure for 110,000 people, and hygiene promotion materials for over 856,000 people
- Provided humanitarian protection services to over 380,000 people.
- Supported operation of nine humanitarian hubs in deep field locations
- Supported over 1000 staff of 133 humanitarian organisations with security information, analysis, training and crisis management support
- Supported air services for 9,175 humanitarian passengers and transport of 31,283 kg of humanitarian cargo.
Major lessons and recommendations for the year ahead
Acute and potentially catastrophic food insecurity persists in NE Nigeria. FCDO should continue to advocate for government and international action at the highest levels.

An important lesson from NENTAD is that the transition to development has not been possible given the continued intensity of conflict and the prolonged scale and severity of humanitarian needs. FCDO Nigeria should draw on this experience, and learning from similar contexts, to consider a focus on humanitarian, resilience and recovery objectives, rather than a transition to development reliant on external factors, in the design of the next humanitarian programme.

NENTAD’s spend will be significantly lower in the year ahead than for this reporting period. This will impact the scale of NENTAD’s intervention and will likely see some activities discontinue. A review of the NENTAD logframe and risk register is required to identify the impact this will have on milestones and the achievement of outcomes and impact.

There are significant opportunities for both NENTAD partners and the humanitarian operation overall to better communicate with affected communities and be guided by their input at all stages of the project cycle. This includes demonstrable improvement in acting on feedback from communities. It is recommended that FCDO and NENTAD IPs explore development of an improved model informed by those used in other contexts (such as Iraq and Afghanistan).

Staff safety concerns have led to a reducing footprint of non-local staff in several key areas, with an increased remote management. By October 2021, FCDO should review implications of this with partners, including suitability of workplans, targets, budgeting, and operational presence in coordination with other actors.

Access constraints experienced by international NGOs and UN agencies have demonstrated the importance of working with/through local actors and community-based mechanisms to ‘stay and deliver’ humanitarian assistance. Progressing on the localisation agenda is intrinsically linked to NENTAD’s risk management. FCDO should review where partners can strengthen programme delivery and manage operational risks in partnership with local actors.

Cash modalities are increasingly used by NENTAD and other humanitarian actors. FCDO should work on increasing coherence of approaches across NENTAD IPs, and partners of FCDO’s social protection and economic development teams to promote accountability, efficiency and effectiveness, including through better supporting local markets and laying the ground work for connection to the government’s social protection system, where feasible.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
NENTAD’s Theory of Change (ToC) was designed on the premise that conflict-driven humanitarian needs would decline during the life of the programme, allowing for an increase in ‘recovery’ activities and a progressive transition to development programming. The ToC reflects contemporary thinking around integrating humanitarian and development programming and is consistent with Grand Bargain commitments. The ToC captures spending through this business case, which is coordinated with recovery and development programming by FCDO Nigeria in NE Nigeria, in sectors including livelihoods, nutrition, infrastructure, education and governance.

Assumptions that insecurity would continue, and that successful programme delivery relies on both context and capacity of IPs to respond are still relevant. Major risks have been realised however, in terms of: i) deteriorating security environment, ii) constraints on humanitarian access, and iii) increased humanitarian need. Thus, while the premise of the ToC remains valid, key assumptions that would allow a gradual transition towards development have not held; particularly those relating to improvements in security, humanitarian needs, safe access to target locations and the enabling environment. Given the increased insecurity and humanitarian needs NENTAD is no longer anticipated to reduce humanitarian expenditure and deliver increased development spend by the end of the programme. FCDO Nigeria should draw on this experience, and learning from similar contexts, to consider a focus on humanitarian, resilience and recovery objectives, rather than a transition to development reliant on external factors, in future programme design.

The risk register was updated to include a new assumption that IPs can successfully flex their programmes to address the direct and indirect impacts of Covid-19 while sustaining an effective humanitarian response, in line with recommendations of the previous Annual Review.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
NENTAD performance is on track in terms of partner performance and output delivery. However, the deteriorating security and humanitarian context means that the contribution of outputs to sustainable attainment of outcomes will be less than anticipated during design. As outlined above, the assumptions underpinning the theory of change have not held in terms of reduced insecurity enabling a shift towards recovery. Instead, exacerbated by secondary effects of Covid-19, the conflict continues to drive acute food insecurity and its consequences on health outcomes such as malnutrition, displacement and high levels of protection threats, particularly for women and girls.

In the next year, food insecurity is expected to worsen, and malnutrition rates remain high or increase further. Food consumption patterns point to that of a near-catastrophic and potential famine situation for some people in fully or partially inaccessible areas, and food insecurity is projected to worsen during the 2021 lean season (June-August). NENTAD will continue to contribute to prevention of mortality and morbidity and to alleviate the suffering caused by conflict induced hunger and the protection risks to civilians. In the policy space, food security and famine prevention, humanitarian access, protection of civilians and aid worker security continue to be priorities alongside promoting greater accountability to affected populations and advancing the localisation agenda.

Progress against outcome indicators for the review period is summarised below:
Outcome: Food insecurity and the impact of conflict on affected populations reduces
Indicators	Milestone	Progress
1. Increased number of individuals benefiting from improved/enhanced protection	356,760	380,063
2. Proportion of infants 0-5 months of age who are fed exclusively with breast milk in targeted Local Government Areas (LGAs)	Borno: 53%	64.3%
3. Net enrolment rate in Yobe and Borno	N/A	N/A
4. % of households with borderline to acceptable food consumption score	70%	88.6%
5. % of households with reduced/stabilized coping strategy index	75%	79.80%
6. Proportion of children 6-23 months of age who receive a minimum acceptable diet (apart from breast milk) in targeted LGAs	Borno: 15% / Yobe: 10.30%	Borno: 0.9% / Yobe: 0.9%
[note] Figure is for unique beneficiaries.
[note] UNICEF April 2020- March 2020 Annual Report.
[note] North East Nutrition and Food Security Survey Round 9.

Outcome Indicator 1: Delivered by the ProSPINE Consortium, this outcome delivers holistic humanitarian protection assistance across five NGOs which collectively moderately overachieved, reflecting adaptive capacity by partners the face of operational challenges relating to increasing insecurity and the pandemic.

Outcome Indicator 2: Intended to measure improved nutritional status of children under 5 months, UNICEF monitoring found the exclusive breastfeeding rate was surveyed at 64.3%, higher than the target of 53% and a result of informing and supporting mothers and caregivers through Infant and Young Child Feeding (IYCF) activities.

Outcome indicator 3: Funding for this outcome transitioned to the Partnership for Learning for All in Nigerian Education (PLANE) programme in April 2020. Achievement of this outcome will be monitored through the PLANE Annual Review.

Outcome indicator 4 and 5: Household food consumption scores monitor intake of food staples, vegetables, oil, pulses, plus meat, fish or dairy. Overall, averaged across male and female respondents, 44.8% of households surveyed had an acceptable food consumption score while 43.8% were borderline across the BAY states. While indicator has been exceeded, the data indicates a significant negative shift from acceptable to borderline consumption scores. ‘Acceptable’ food consumption scores reduced from 60.5% in 2019 to 44.8% in 2020, while ‘borderline’ scores increased from 26.6% to 43.8%. Over 50% of respondents reported poor or borderline household food consumption, compared to little over 40% in 2019. While food consumption patterns improved or remained consistent for 72.9% of households year on year, it got worse or remained poor for 28.6%. Survey data indicates a significant difference between female and male perceptions of food consumption patterns, with women reporting poorer consumption overall. Women are often more informed about household food consumption needs and patterns than men, are often the first to reduce portions or skip meals when food is limited and are more aware of, and vulnerable to, protection risks when food security deteriorates.
[note] WFP, NE Nigeria Essential Needs Analysis February 2021.
[note] A decrease in reporting of poor food consumption scores from 13% in 2019 to 11.4% in 2020 also contributed to the increase in reporting of borderline food consumption. However, while men reported improvements, women reported a deterioration.
[note] 40.3% of women surveyed said household food consumption is acceptable, 40.8% reported borderline adequacy, and 18.9% reported poor consumption, compared to 46.5%, 40.8% and 8.7% of men surveyed, respectively.
[note] WFP, NE Nigeria Essential Needs Analysis February 2021; OCHA Nigeria, Humanitarian Needs Overview 2020; CARE International, Invisible Women and Girls Hunger Report, 2020.

More conflict affected households in NE Nigeria are employing severe consumption-based coping strategies. 34% of households surveyed had resorted to crisis or emergency coping strategies – and 80% of these did so to meet food needs. This does not include the 1.2m households that were inaccessible to humanitarian actors during the period who are likely to be amongst the most vulnerable. Thus, while the outcome indicator has been met, the data underlying this assessment indicates food security has deteriorated since 2019. This is consistent with Cadre Harmonise and FEWSNET analysis which indicates a large-scale deterioration in food insecurity, and a risk of famine in some locations.
[note] Cadre Harmonisé, March 2021, Final Fiche Report; FEWSNET, February 2021, Poor macroeconomic conditions and high conflict drive Crisis (IPC Phase 3) or worse outcomes in 2021.

Outcome indicator 6: The proportion of children aged between 6–23 months who receive a minimum acceptable diet was found to be 0.9% for both Borno and Yobe states, relative to targets of 15% and 10.30% respectively. This significant under-achievement is the result of the deteriorating humanitarian situation during the life of the programme, compounded by chronic development challenges.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
NENTAD is delivering large scale and life-saving humanitarian assistance, in a context of increasing humanitarian needs. Averting the risk of famine is an urgent priority, both through delivery of the NENTAD programme and the influence it enables. Discontinuing NENTAD would leave a major gap in the humanitarian response in Nigeria and result in an increase in suffering and preventable deaths. The humanitarian response delivered through NENTAD is a key pillar of the comprehensive HMG strategy to address the crisis in the Lake Chad Basin.

## C. DETAILED OUTPUT SCORING

Output Title	Increased availability of and access to protection information and services in conflict -affected Adamawa, Borno and Yobe states.
Output number:		1	Output Score:	A+
Risk Rating		Moderate	Impact weighting (%):	20%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone	Progress
1.1: # of beneficiaries who can identify and act upon protection concerns.	286,180	282,619
1.2: # of vulnerable individuals accessing protection services	54,275	168,350
1.3: # of UASCs identified, registered, and provided with case management services.	500	724
1.4: # of women and girls provided with dignity kits	700	1,103
1.5: # of women and girls engaged in psychosocial activities	3,600	3,449
1.6: # of people in detention benefiting from multi-sectoral protection activities	WASH: 2,064 / Food:1,170	WASH: 2,726 / Food: 2,797
[note] This milestone does not reflect unique beneficiaries as DRC’s explosive ordinance risk awareness activities were conducted in IDP camps where other DRC protection outreach also takes place. Unique beneficiaries were 187,496 while up 95,123 may have received the two sets of DRC activities (combined total of 282,619).

Briefly describe the output and provide supporting narrative for the score.
This output is designed to promote increased access to protection services in the BAY states. Expectations were met or exceeded for most indicators, in the challenging Covid-19 context, resulting in a score of A+.

Activities under this output were delivered primarily through the Promoting Rights and Supporting Protection Needs in NE East Nigeria (ProSPINE+) programme. ProSPINE+ is a consortium led by the International Rescue Committee (IRC) in partnership with Norwegian Refugee Council (NRC), Danish Refugee Council (DRC), Plan International and Translators Without Borders (TWB). The £8.3m budget for FY 2020/21 supported delivery of a holistic package of humanitarian protection services focussing on child protection, women at risk of sexual violence and abuse, psychosocial support services, access to civil documentation, mine action, rapid response to emergency needs, rights awareness, and case referrals to specialised services. Protection advocacy and Accountability to Affected Populations (AAP) objectives were also integrated across the programme. The International Committee of the Red Cross (ICRC) also contribute to this output through their work with detainees. In 2020 FCDO UK provided £15.1m to ICRC Nigeria, representing 23.3% of amount received against ICRC’s 2020 appeal.

Indicator 1.1 supported 187,496 unique beneficiaries including 342 persons with disabilities comprising 94,402 women, 65,802 men, 15,846 girls, and 11,446 boys. This is a composite of six indicators from the NENTAD logframe, two of which supported 95,123 individuals with both daily protection activities and explosive ordinance risk education (EORE). The target was moderately not met due to limitations on staff ability to access camps to reduce coronavirus transmission risk, reduced access to garrison towns during a period of UNHAS flight suspension during August and September, and the need for group sessions to have lower number of participants to manage social distancing requirements.

Indicator 1.2 measures access to services including information desks in IDP camps, assistance accessing birth certification and national identity documents, unconditional cash grants, and provision of assistance for people with disability including mobility aids, plus services relating to housing, land and property rights. Partners assisted 175,471 individuals 75,942 women, 47,429 men, 27,112 girls, 25,168 boys and including 1,885 (7%) persons with disabilities. Demand for some services increased as a result of the pandemic. Information centres received a surge in requests for food, information on available services, enquiries on Covid-19 and to report human rights violations or broader health, shelter or gender-based violence concerns which were heightened during the period. Outreach from community-based volunteer networks also increased as partners adapted their activities and delivery methods to mitigate the impact of localised movement restrictions and reduce risk of NGO staff transmitting the coronavirus into vulnerable communities.

Indicator 1.3 measures support provided to 274 conflict-affected children (157 girls and 117 boys) who are unaccompanied or separated from their parents/caregiver, including social reintegration for children formerly associated with armed groups. The target was slightly exceeded due to the increased capability of PLAN’s partner to identify and refer cases to them as a result of capacity building provided. Upon review Indicator 1.4’s milestone was increased from 500 to 700 dignity kits yet was still overachieved as cost planning proved to be high. 72% of the recipients of dignity kits were adolescent girls. IRC and PLAN were able to reduce kit costs by sourcing components from two different suppliers and packaging themselves. This enabled more kits to be procured, for which there is high need. Indicator 1.5 was 96% achieved, supporting 2,433 women and 1,016 girls with psychosocial support services; a significant achievement given the operational challenge of the period and the adaptations required. These included remote training and mentorship to community volunteers, reducing size of group sessions while increasing frequency, and adapting content of sessions to accommodate messaging and practice related to Covid-19.

Indicator 1.6 saw ICRC providing food and WASH assistance to detainees. Overall ICRC visited 21,277 detainees (4,958 FCDO attributable) which included 207 women and 88 minors (men account for remainder). 149 women and 256 minors were amongst the recipients of food assistance, and 207 women and 88 minors received WASH interventions. ICRC also worked with detaining authorities on Covid-19 awareness and prevention guidelines and met an increased demand for food and water provision resulting from economic impacts of the pandemic where gaps would otherwise have existed which contributed to the overachievement against the milestone.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The budget provided was sufficient for the targets agreed, although flexibility was required this year to enable budget realignments in response to the changing context, particularly the impact of the Covid-19 pandemic.

Economy: Partners have utilised master service agreements, master purchase agreements and tendering processes to drive down costs and promote savings without compromising quality. This has been important given the high level of procurement by the programme and the importance of establishing competitive pricing in advance of rapid response.

A significant reduction in non-project costs was noted this period as a result of office closures and virtual rather than in-person meetings, as a result of the pandemic. The economic impacts of the pandemic resulted in increased prices for some items and programme costs increased as a result, exceeding some budget lines slightly. Future programming should identify relevant lessons in cost management

Efficiency: ProSPINE+ consortium partners have been able to draw from established operational and community networks to navigate access challenges and to adapt programme delivery. This is contributing towards costs efficiencies and can be developed further to increase support to these groups.

Effectiveness: Use of community volunteer networks are designed to reach further into affected communities and strengthen outreach. Partnership with government entities and local leaders has increased access to communities, for example, access to civil documentation in hard-to-reach communities was increased following agreements between the National Identity Management Commission (NIMC) and National Population Commission NPC to provide outreach services. Similarly, ongoing partnership and mentorship with civil authorities has improved the effectiveness of identifying cases and delivering reintegration support for children associated with armed forces and armed groups. Strong cross-referral processes have been established between ProSPINE partners to support protection monitoring, case identification and outreach to a broader population than one partner can address alone, thus promoting a more effective protection response.

Equity: Both ProSPINE and ICRC have functioning feedback and complaints mechanisms enhanced by use of local language and audio communications. All partners integrate age, gender and disability into the design, delivery and monitoring of programmes. ICRC promote equity by seeking to respond in locations where no other actor is responding.

Describe any changes to this output, and any planned changes as a result of this review.
The ProSPINE+ logframe was revised to adapt to the impact of Covid-19. Some targets were revised downwards. Savings against management costs were reallocated to activities. A cost extension for the ProSPINE+ programme is planned to deliver a streamlined programme of activities building towards sustainability of services delivered by local actors.

Recommendations from previous Annual Review: See Annex 1. All recommendations have been implemented

Recommendations for the year ahead and lessons learned this year
- FCDO and ProSPINE+ partners to review milestones to seek improved accuracy between targeting and results, including deconflicting areas of potential overlap between differing activities.
- Cost extension for ProSPINE+ recommended to build towards sustainability of service delivery. ProSPINE+ partners should build on work with local actors to support delivery of the localisation agenda, supported by increased engagement by the consortium’s Senior Management Board.
- Lessons on improving AAP work should be identified and used to strengthen AAP for the overall response.
Output Title	Increase in equitable access to quality education provided by the Government of Nigeria and humanitarian partners to conflict-affected children in Borno and Yobe States.
Output number:		2	Output Score:	N/A
Risk Rating		Major	Impact weighting (%):	0%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	Yes ↓ Reduction from 5% to 0%

Indicator(s)	Milestone	Progress
2.1: # of children reached through formal and informal education.	N/A	N/A
2.2: # of children in Non-Formal Learning Centres (NFLCs) receiving scholarships to attend school	N/A	N/A
2.3: # of IDP/host girls and boys that have transitioned into formal school	N/A	N/A
2.4: % of IDP/host girls and boys who stay in school as demonstrated by regular attendance to formal school during the project	N/A	N/A
2.5: % IDP/host girls and boys aged between 6-14 improve their literacy and numeracy scores	N/A	N/A

Briefly describe the output and provide supporting narrative for the score.
Funding for Output 2 transitioned from NENTAD to the PLANE programme as of April 2020. It is now being measured under the PLANE logframe and monitored under that Business Case. With no activity under this Output this FY the impact weighting has reduced to zero.

Output Title	Increase in equitable access to food, cash and agricultural production assistance provided by humanitarian partners to targeted members of the conflict population in Adamawa, Borno and Yobe States.
Output number:		3	Output Score:	A
Risk Rating		Major	Impact weighting (%):	30%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestone	Progress
3.1: # of people who receive food assistance	472,799	584,480
3.2: # of people who receive cash assistance	323,206	389, 662
3.3: # of people who receive support to resume agricultural production.	76,162	90,810

Briefly describe the output and provide supporting narrative for the score.
This output is delivered by WFP and ICRC, and scored an A. Both WFP and ICRC moderately overachieved their targets and, whilst ICRC underachieved against Indicator 3.3, there were broader ICRC income-generating activities which are not captured here – such as cash-grants for breadwinners to raise livestock or produce handicrafts – that contributed to household incomes and should be factored into NENTAD’s logframe (see recommendations).

FCDO funding of £34m to WFP (contributing to Indicators 3.1 and 3.2) contributed to delivery of in-kind assistance to 533,727 individuals and cash assistance to 379,765 individuals (totalling 913,492 beneficiaries); an overachievement against targets of 123% and 120% respectively. 60% of beneficiaries were women, or 545,355 beneficiaries compared to 404,137 men. WFP’s monitoring indicated that cash assistance was more effective at preventing poorer food consumption outcomes than compared to those receiving in-kind assistance. As a result of this and other evidence WFP continues to shift from an in-kind modality to Cash-based Transfers (CBT) where appropriate.

There was widespread disruption of food supply during the review period, at both local level (lockdowns affecting market and farm resources) and internationally (scarcity of food commodities, cargo movement and import clearance challenges), compounded by insecurity of supply routes and operational locations in Borno and Yobe. Transport on main supply routes was severely hampered by the conflict with attacks on humanitarian and commercial convoys, with avoidance measures causing delays. WFP also faced challenges with registering new beneficiaries for CBT activities as new national policies forced a pause in the registration of new phone SIM cards. Alongside Covid-19 public health regulations this delayed onboarding of new beneficiaries to WFP's beneficiary and transfer management platform (SCOPE).

ICRC reached 50,753 individuals with in-kind food assistance and 2,804 individuals with cash assistance attributable to FCDO support, exceeding their target for food but underperforming in delivery of cash. Insecurity prevented the delivery of cash programming in specific communities in southern and north eastern Borno. ICRC’s pivot to support vulnerable households tackle secondary impacts of Covid-19 increased in-kind food assistance relative to cash, due to the limited viability of cash delivery platforms in those areas. ICRC’s livelihoods and resilience activities contributed to the delivery of Indicator 3.3 through provision of productive inputs (seeds, tools) and cash assistance to farmers of which assistance to 90,810 individuals is attributable to FCDO. Overall, ICRC moderately underachieved in the scale of their food production targets, largely due to underfunding against their appeal affecting this set of activities.
[note] ICRC received CHF82m against their appeal of CHF 105m, FCDO’s £15.2m contribution was therefore 23.3% rather than the 17.2% which informed setting the milestones, hence apparent over-achievement. In total, ICRC reached 389,742 rather than the 442,800 individuals targeted by the appeal.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Given food security represents the largest proportion of NENTAD’s spend and coverage, FCDO’s partnership with the WFP and ICRC has sought to ensure consistent quality VfM delivery. Progress against past recommendations has been continuous during the year.

Economy
WFP has maintained strong delivery across key economy indicators including:
- Completion of a Global Commodity Management Facility hub in Kano to store commodities procured when prices are favourable.
- Negotiation with the Financial Service Provider (FSP) to maintain the administrative costs for cash transfers at a constant rate which has resulted in a 49% reduction in the cost of the service given the depreciating rate of the Naira versus the US Dollar.
- Increased local food procurement, 86% of metric tonnage and 75% by value was sourced locally in 2020, up from 79% and 62% respectively since 2019. by value. Local procurement generally results in lower costs, allowing resources to go further, better meets taste preferences, supports market development and boosts the local economy.

Efficiency
Timely arrival of good quality food at WFP distribution sites reduced from 96% in 2019 to 93% in 2020. A marginal decrease in efficiency due to external factors, specifically the limited availability of military escorts and poor road infrastructure.
WFP expansion of the SCOPE platform improves risk management of duplicate beneficiaries. 57% of all beneficiaries were captured on SCOPE in 2020, up from 55% in 2019. Noting challenges this year, continued SCOPE expansion should be a focus in the next period.

Equity
- WFP provide safe and prioritised access to assistance for vulnerable groups, including people with disabilities, the elderly, care providers, Pregnant and Lactating Women (PLW) and female headed households during distributions and cash-out services.
- WFP have reviewed Project Management Committees and Food Management Committees in local communities to ensure broad representation of diverse age, gender and ethnicity in the local community. Feedback from these mechanisms and community consultations were used to inform programme adjustments.
- WFP developed a three-year country strategy on protection and AAP and now has a dedicated three-person protection and AAP team. Existing complaint and feedback mechanism include on-site help and feedback desks managed by partners and community outreach to submit feedback and complaints safely and confidentially.

Describe any changes this output, and any planned changes as a result of this review.
There were no changes made to this output during the reporting period Indicators and milestones for next year will be revisited to reflect the contributions planned to partners.

Recommendations from previous Annual Review
All recommendations from the 2019/20 Annual review have been implemented – see Annex 1 for details.
Recommendations for the year ahead and lessons learned this year
- FCDO and WFP to conduct a review of UK-funded cash programming by October 2021, including of implementation of recommendations from last review.
- WFP should work with the CWG and the Food Security Sector to ensure a harmonised cash transfer value calculation and ensure consistency on the frequency and duration of assistance in different settings.
- WFP and FCDO should establish a target for beneficiary coverage by the SCOPE platform by October 2021.
- WFP should continue to improve awareness of, and access to, accountability mechanisms at WFP activities. Regular monitoring activity should assess effectiveness of AAP mechanisms.
- NENTAD’s logframe to be reviewed by October 2021 to factor in all ICRC’s income generation activities that support progress toward NENTAD’s outcomes.

Output Title	Increase equitable access to health, nutrition and livelihoods services provided by the Government and humanitarian partners to targeted members of the conflict affected population in Adamawa, Borno and Yobe Sates.
Output number:		4	Output Score:	A+
Risk Rating		Major	Impact weighting (%):	20%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestone	Progress
4.1: # of children aged 6-23 months who receive preventative nutrition assistance (BSFP).	116,184	394,757
4.2: # of pregnant and lactating women who receive preventative nutrition assistance (BSFP)	72,246	83,531
4.3: # of new admissions at sites (OTP/SC) in targeted LGAs	Borno: 38,477 / Yobe: 5,100	39,033 / 4,162
4.4: # of PLW/caregivers of children who receive cash-based transfers with the objectives of improving nutrition	Borno: N/A / Yobe: 5,494	5,403
4.5: # of PLW/caregivers of children below 2 years engaged in income generating activities in pilot LGAs with the objective of improving nutrition	Borno: N/A / Yobe: 1,762	1,179
4.6: # of ICRC Supported Health Centres.	4	5
4.7: Proportion of Children under 5 successfully treated and discharged for SAM at OPT/SC in targeted LGAs	Borno: >75% / Yobe: >75%	96% / 88%
4.8: Proportion of confirmed crises that were responded to in a timely manner (2 weeks for nutrition; 1 week for cholera/measles)	80%	32%
[note] The NENTAD logframe lists a milestone of 952 individuals against this indicator for Yobe, which reflects a target after completion of a 33-week support programme. This is an error as the indicator actually measures those who receive assistance during the programme itself, and thus a milestone of 5,494 is used here as a more accurate target for partner performance. The Borno component of Indicator 4.4 and 4.5 was previously being implemented in Shani LGA by WFP but was phased out in June 2020.

Briefly describe the output and provide supporting narrative for the score.
WFP substantially overachieved against milestones, while AAH and UNICEF met milestones except for Indicator 4.8, which was substantially underachieved by UNICEF. This was because UNICEF significantly expanded their surveillance capability without increasing capacity to conduct in-depth investigations proportionately. Given the high-risk environment and severe challenges overcome by partners to maintain life-saving interventions and tackle acute malnutrition this Output receives an A+ scoring.

Outputs under WFP’s preventative nutrition programme (Indicator 4.1 and 4.2) involved the distribution of blanket supplementary feeding for 394,757 children under 5 years of age (191,062 boys and 203,695 girls) and 83,531 PLW, totalling 478,288 beneficiaries attributable to FCDO support. WFP nutritional assistance improved nutrient intake, strengthened dietary diversity, and emphasized optimal nutrition practices, especially among young children, women of reproductive age, adolescent girls, and other nutritionally at-risk groups. In the deteriorating security context, with conditions not conducive for transition to increased resilience and early recovery programming, WFP reduced targets for livelihoods work and increased food security and preventative nutrition targets. The NENTAD logframe did not update these milestones to reflect this shift, hence the apparently substantive overachievement against milestone. FCDO should ensure appropriate updates to the logframe are made in the coming review period, in such circumstances.

UNICEF and AAH supported existing government health facilities and systems providing health and nutrition services to conflict affected PLW and malnourished children in Borno and Yobe states. With Covid-19 affecting delivery of services, UNICEF provided remote technical support to community nutrition mobilisers and health workers for management of acute malnutrition and adapted plans to enable service continuity, for example, doubling the volume of Ready-to-Use Therapeutic Food (RUTF) rations distributed per person to reduce frequency of distributions and promoting social distancing at nutrition sites.

UNICEF admitted 39,033 new cases of children with severe acute malnutrition (SAM) in Borno through UK-supported project sites, and AAH admitted 4,162 in Yobe (Indicator 4.3). Partners demonstrated innovation by training and equipping mothers to conduct mid-upper arm circumference screening of their children for detection and referral of malnourished children, as the usual house-to-house screening was not possible due to Covid-19 safety measures. This approach resulted in more children being identified and referred for treatment, an approach which is now being replicated to tackle access constraints. UNICEF slightly exceeded the target for admissions in Borno, while AAH moderately missed their target of 5,494 admissions by 8% due to a significant deterioration in the security environment, particularly in Gujba and Tarmuwa, Yobe state. The Tarmuwa Stabilisation Centre was forced to close indefinitely with cases now requiring referral to neighbouring LGAs. Community fears of contracting Covid-19 also contributed to reduced SAM admissions. Successful treatment and discharge rates (Indicator 4.7) exceeded the SPHERE community management of acute malnutrition standard for both partners. FCDO provided UNICEF with £5 million for RUTF which enabled treatment of 94,304 children, supporting 28% of the total RUTF needed to treat children with SAM in NE Nigeria in 2020.
[note] The nutrition sector required 306,743 cartons of RUTF which included a 20% contingency. These were procured by UNICEF and distributed to nutrition actors (Action against Hunger, Save the Children, IRC, CARE and Catholic Relief Services), plus the Borno and Yobe State Primary Health Care Development Agencies. This supported 283 sites for the treatment of SAM among children aged 6-59 months.

AAH provided pregnant and lactating women with cash transfers to improve nutrition (Indicator 4.4) through monthly distributions of NGN 5,000 covering their child’s first 1,000 days from conception to two years. PLW/caregivers graduate the programme once the 33 months cycle is completed, thus registered beneficiaries fluctuate over time as women enter/exit the cycle of assistance. The 5,403 figure represents the peak number of beneficiaries between April-July 2020. The milestone for PLWs/caregivers engaged in income generating activities with the objective of improving nutrition (Indicator 4.5) was not reached as implementation was delayed when community members requested different types of activities that would not have contributed to the community level outcomes integral to the project design. A review of plans, agreed with FCDO, resulted in activities beginning later than planned.

ICRC (Indicator 4.6) pivoted their approach in the Covid-19 context to support a larger number of health facilities than originally planned, targeting areas receiving influxes of IDPs and refugees. Vaccinations, ante/post-natal care, pediatric care, treatment for malnutrition, and referrals for higher-level care were available at 23 primary-health-care facilities supported by ICRC with five attributable to FCDO funding. Infrastructure upgrades were also provided, including: 600 hospital beds; installation of water, electrical and other essential facilities for the isolation centre at Maiduguri General Hospital; and triage tents for Covid-19 screening. ICRC provided personal protective equipment and conducted trainings to control and prevent the spread of coronavirus. ICRC also built a new physical rehabilitation centre in Maiduguri in partnership with the authorities and the University of Maiduguri Teaching Hospital to increase the availability of rehabilitative services in NE Nigeria. Health centres in six detention facilities were supported to establish Covid-19 protocols and set up screening and isolation areas, treat malnutrition and support mentally ill detainees.
[note] ICRC supported 23 health facilities rather than 16, with the rounded figures in the results table reflecting FCDO attribution

Delivery of Indicator 4.8 requires a correlation between surveillance of malnutrition and/or disease concerns and responsive action. The responsive action requires further information to be gathered as part of a rapid investigation to substantiate a decision to launch a material response. This investigation relies on secondary sources which was not always available in the two-week timeframe required. During the year UNICEF expanded surveillance capability significantly, which saw many more alerts raised but for some months the secondary information was not available within a two-week period to launch a response, although responses were still conducted outside of that timeframe in the majority of cases.

Assess the VFM of this output compared to the proposition in the Business Case, based on performance over the past year.

Economy
AAH generated savings of £11,739 by using venues for training provided pro bono by civil authorities. Coordination between different FCDO-funded programmes on trainings included collaboration with the Health Reform Foundation of Nigeria (HeRoN) programme, with a training of trainers approach reaching 150 CHIPS agents at ward level, at lower cost to and reducing costs relative to inviting individuals to attend at State or LGA level.

Efficiency
AAH coordinated with State authorities and the World Bank to secure incentives for existing AAH beneficiaries who completed their course of antenatal care. Provision of mama kits and snacks provided to those attending for the fourth time encouraged attendance, and led to improved effectiveness of activities, enabling AHH to exceed their target by 141%.

A child treated for SAM should normally be subsequently transferred to a Targeted Supplementary Feeding Programmes (TSFP) for Moderate Acute Malnutrition (MAM) treatment. This is not implemented in Nigeria so AAH have amended their discharge criteria to also treat MAM following SAM treatment.

Equity
Both UNICEF and AAH projects focus in areas with higher rates of malnutrition (GAM and SAM rates) to provide lifesaving nutritional intervention for children under 59 months where they are needed most. Services are available free of charge for all children irrespective of gender, age, ethnicity, religion or socio-economic status, with strong awareness within communities of the equitable availability of the services for all children based on need.

Describe any changes to this output, and any planned changes as a result of this review.
Revisions were made to both UNICEF and AAH logframe to reflect the impact of Covid-19 and security challenges which rendered some implementing LGAs inaccessible. Not all outputs were revised downwards, with some targets raised to increase coverage and the number of beneficiaries reached. Planned changes to the log frame for FY 2021/22 are expected in light of ODA prioritisation and budget reviews across all programmes.

Recommendations from Previous Annual Review
All Recommendations from the 2019/20 Annual review have implemented- see Annex 1 below for status of progress.

Recommendations for the year ahead and lessons learned this year
- UNICEF to demonstrate to FCDO how they have strengthened monitoring of storage and distribution of RUTF supplies after transfer to partners by December 2021.
- FCDO to gather learning from UNICEF FIT and AAH SUNY projects, incorporate recommendations from the MQSUN and HNET reviews, and develop post-NENTAD nutrition programming approach by December 2021.
- FCDO to review all milestones in NENTAD logframe and ensure accuracy in line with WFP Country Strategic Plan by October 2021.

Output Title	Increase equitable access to water, sanitation and hygiene information, products and services provided by the Government and humanitarian partners to members of the conflict-affected population in Adamawa, Borno and Yobe States.
Output number:		5	Output Score:	A
Risk Rating		Major	Impact weighting (%):	10%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestone	Progress
5.1: # of people reached with improved access to clean water supply	166,760	147,511
5.2: # of people reached with improved access to sanitation infrastructure.	104,000	110,151
5.3: # of people reached with hygiene promotion.	864,000	854,379
5.5: # of beneficiaries whose living conditions improved through water and habitat activities.	206,469	178,803
5.6: # of water supply systems construction/rehabilitation including solar powered and hand pump	93	93
5.7: Tonnes of Greenhouse Gas Emissions Reduced or Avoided (tCO2e)	213	213
[note] Indicator 5.4 was removed in November 2019 as captured in the NENTAD logframe’s Change Log.

Briefly describe the output and provide supporting narrative for the score.
Partners were largely able to meet expectations in the face of severe operational challenges presented by the pandemic this output achieved an overall score of A.

UNICEF and AAH implement multi-sectoral projects with WASH elements contributing to nutrition and health outcomes in Borno and Yobe states, aiming to improve hygiene behaviours, access to sanitation services, and provide adequate water in communities and health facilities.

In delivering on Indicators 5.1 and 5.3 NENTAD partners provided improved clean water supply to 147,511 individuals, comprising 30,139 men, 37,637 women, 37,021 boys and 42,714 girls. Hygiene promotion activities assisted 854,379 individuals comprising 172,715 men, 213,631 women, 217,325 boys and 250,708 girls. AAH overachieved against their targets in Yobe, supporting 10,011 people with clean water and 15,826 people with hygiene promotion (against milestones of 7,000 and 14,000 respectively). UNICEF provided 137,500 people with clean water and 838,553 with hygiene promotion in Borno, moderately underachieving against their milestones of 159,760 and 850,000. This was due to Covid-19 movement restrictions temporarily limiting the ability of UNICEF’s contractors to travel and deliver activities which slowed down works requiring monitoring and presence of senior personnel. Despite its negative impacts, the pandemic provided an opportunity to strengthen good hygiene practices for personnel delivering public services and to affected populations in camps and host communities. Partners incorporated Covid-19 prevention into hygiene promotion activities, including training staff, health workers and community mobilisers and providing personal protective equipment where appropriate. Group sessions were held separately for men, women, boys and girls to reflect cultural norms and promote safe locations that are conducive to discussion of potentially sensitive topics.
UNICEF achieved Indicator 5.2 by supporting 110,151 IDPs and host community members with improved sanitation facilities, rehabilitation and improvement of latrines, de-sludging and disinfecting latrines and/or decommissioning unusable latrines under a community-led sanitation approach. In delivering against Indicator 5.5, ICRC assisted 767,396 people through its water and habitat activities, of which 178,803 are attributable to FCDO (39,392 women, 102,060 children, and 37,351 men). ICRC upgraded water storage/distribution systems at water-treatment plants in Adamawa and Borno, repaired or built water points (some solar-powered), installed latrines and set up waste-disposal sites. ICRC also built temporary shelters for IDPs and helped returnees rebuild homes with stabilized-soil bricks or provided them the materials to do so (benefiting around 40,000 people). Water systems at certain ICRC-supported primary-healthcare centres were repaired or upgraded, while handwashing stations and soap were distributed to several other health centres to support prevention of coronavirus transmission. The achievement reflects an 86% performance against the target, an underachievement due in part to a loss of access to some communities in southern Borno due to attacks by NSAGs, making these activities unviable. The Covid-19 pandemic hampered ICRC from conducting new assessments and engaging with communities. ICRC decided to pivot towards responding to the pandemic with resources allocated toward more emergency response and health activities resulting in an overachievement in those programme areas relative to plans pre-Covid.
[note] Milestones for ICRC activity were calculated as a planned attribution of 17.2% against the ICRC 2020 appeal. As ICRC appeal was not fully funded, FCDO attribution therefore rose to 23.3% against actual results.

UNICEF constructed/rehabilitated 93 water points in Borno supporting at least 99,180 people with 15 litres per day, meeting Indicator 5.6. 22 of these are newly installed solar units while the rest are rehabilitated or expanded. This use of solar powered water systems enabled UNICEF to meet the milestone for Indicator 5.7 and to contribute to International Climate Fund results.
[note] UNICEF also operated and maintained a further in addition to maintaining operation of 169 boreholes which provided sustained safe water access to over 235,000 persons.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
Both UNICEF and AAH’s comparative advantage has continued to help both the FIT Response and SUNNY projects achieve good VFM across the 4Es.

Economy
AAH rehabilitated 11 water points providing over 10,000 people with sustainable clean water at a cost of £20,779, the equivalent costs for water trucking for the year would be £225,270. UNICEF also achieved good VFM results in Borno state in WASH services. The cost of drilling a hand pump borehole cost $2,900 under the FIT project compared to the average cost of $3,902 from other sector partners in the state. This represents savings of $1,000 from every borehole constructed with project funds enabling the project to achieve more with same resources. In addition, the cost of constructing a solar motorized borehole with an average depth 200-300 metres cost $17,800 compared to the WASH sector average of $18,900 due to the economy of scale UNICEFs large scale procurement provides.

Efficiency
Access to safe water was provided through the rehabilitation of 13 water facilities (motorized boreholes, hand pump and open wells). For efficiency purposes, boreholes with a history of high yield were selected for the rehabilitation, thereby discharging a capacity of 7 litres per second with the water points located less than 500m from the households. Furthermore, UNICEF was able to achieve efficiency savings achieving an average cost of $22 per beneficiary gaining access to basic sanitation compared to the $27 WASH sector average.

Effectiveness
93 water systems were constructed during the reporting period ensuring communities and IDPs have sustained access to water. The FIT funded WASH intervention remained highly effective in preventing WASH related disease outbreak in project targeted IDPs camps and host communities. For instance, no cholera cases were reported in the reporting period in the locations targeted by the project even though most of these places were designated as cholera hot spots by Borno State 2019 Disease Surveillance and notification report.

Equity
25% (95) of sanitation facilities and latrines constructed under the FIT Response project are disability-friendly using the global standardized design. Additionally, female representation of 49% (compared to the WASH sector standard of 45%) in WASH committees, with 20% in WASH committee leadership positions, promotes representation of women’s and men’s needs.

Describe any changes to this output, and any planned changes as a result of this review.
The logframe will be reviewed during the next review period to ensure the full breadth of UK-funded activities delivered by UNICEF are captured. Indicators 5.1, 5.2 and 5.6 measure newly assisted individuals and installed units. In addition, UNICEF operate and maintain a further 169 boreholes in Borno with FCDO funding which provide water to 235,862 people (107,858 males and 128,004 females). The project also provides urban water treatment chemicals which benefited 777,428 persons and regular de-sludging of 7,214 latrines in 66 IDP camps in Borno used by an estimated 144,280 people.

Changes were made to output indicator 5.1 for AAH to reflect current realities and to indicator 5.7 based on revised calculation method agreed between FCDO and UNICEF. Planned changes to the log frame for the financial year 2021/22 have already been implemented by UNICEF in light of a reduced budget resulting from ODA prioritisation. There may be some relatively small adjustments to AAH’s logframe on review during the year.

Recommendation for Previous Annual Review
All recommendations from the 2019/20 AR have been implemented – see Annex 1 for details.

Recommendations for the year ahead and lessons learned this year
- By October 2021 FCDO and UNICEF to review all indicators and milestones to accommodate the budget forecast for FY 21/22, and to ensure reduced resources mitigate risk of harm.
- A light touch review of the cash for WASH component would be useful to document lessons including on inception, design and implementation.
- FCDO and UNICEF to review indicators to ensure activity and results attributable to NENTAD is accurately reflected in the NENTAD logframe, by October 2021.
Output Title	Humanitarian actors have enhanced capacity to respond and deliver assistance to conflict-affected population in the North-East of Nigeria where access is difficult and significant security challenges remain.
Output number:		6	Output Score:	A
Risk Rating		Moderate	Impact weighting (%):	15%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestone	Progress
6.1: > greater than 75% of NGOs surveyed strongly agree with the statement “INSO Nigeria services are relevant and useful and improve my NGOs understanding of security environment”	80%	91.67%
6.2: INSO sends flash SMS and emails on security incidents to NGO partners (Y/N)	Yes	Yes
6.3: INSO sends quarterly security analysis reports to NGO partners (Y/N)	Yes	Yes
6.4: # of passengers transported by UNHAS	9,094	9,175
6.5: # of kg of commodities transported by UNHAS	30,603	31,283
6.6: INSO delivers basic and advanced security management courses (Y/N)	Yes	Yes
6.7: # of Humanitarian Hubs in operation delivered by IOM	9	9
6.8: UNDSS deliver an operational Saving Lives Together Framework to support collective security management, information and analytical capacity	1	1

Briefly describe the output and provide supporting narrative for the score.
This output covers NENTAD’s support to enabling interventions to promote safe humanitarian access and assist operational delivery of humanitarian assistance. Two new partners, IOM and UNDSS, were supported in the last six months of the reporting period, complementing existing support for INSO and UNHAS. All milestones were met with some moderate overachievement, in a challenging operational context, resulting in an Output score of A.

INSO provide security information, analysis and advice to INGOs to support management of staff safety and security in this high-risk environment. INSO provide trainings and bespoke site assessments to aid development of security management policies and practices, in addition to crisis assistance. As of 31st March 2021, there were 133 organisations registered as INSO members within the Lake Chad Basin region and 1,017 staff registered on their distribution lists. INSO has continued to provide a highly relevant and quality service, with members continuing to show a high level of satisfaction in the services they receive (Indicator 6.1). The user survey conducted in June 2020 found 91.67% of respondents agreed or strongly agreed that INSO services help them plan, operate and deliver aid more safely. INSO met Indicators 6.2 and 6.3, issuing a total of 623 alerts and 848 updates on ongoing security incidents to 100% of its NGO partners, and four timely quarterly security analysis reports. 95.7% of respondents to the user survey found these alerts and reports useful.
[note] 63 INGOs in Nigeria, 17 INGOs in Cameroon, 22 INGOs in Niger, seven INGOs in Chad, nine international organisations including the ICRC, eight UN agencies, and seven donors.

INSO adapted their trainings to be delivered as online modules to adhere to Covid-19 guidelines and delivered nine basic security management courses and seven advanced courses during the year, attended by 220 NGO workers. There were however other courses reliant on practical simulations and/or group exercises which could not be delivered online and which were suspended during the reporting period.

UNHAS, is the main provider of transportation services to humanitarian actors in NE Nigeria with the use of fixed and rotary-wing aircrafts (helicopters). Illegal checkpoints and frequent attacks on key roads – including several incidents of aid workers being targeted and abducted – mean that most humanitarian actors do not permit on-duty staff to travel by road in Borno state. UNHAS services therefore continue to be in high demand to enable access to field locations outside of Maiduguri. FCDO contributed £4m, approximately 19% of UNHAS required annual operating budget ($27.4m). UNHAS met targets under Indicators 6.4 and 6.5 transporting 48,395 passengers and 165,000kg of humanitarian cargo for 110 organisations, an average of 2,016 passengers and 6,903kg of cargo per month. FCDO attributable results were 9,175 passengers and 31,283 tonnes of cargo.

Under Indicator 6.7 IOM continued to manage nine Humanitarian Hubs across eight locations (two in Banki) providing safe accommodation, office space, internet connectivity, meeting and training facilities to humanitarian workers. The hubs are increasingly playing a critical security role as demonstrated during several attacks infiltrating garrison towns where public buildings, NGO offices, and the hubs themselves have been targeted - Ngala and Dikwa hubs were both attacked during the reporting period. FCDO support enabled IOM to install security-fortification in the Gwoza, Dikwa and Damasak hubs (in line with recommendations of a UNDSS security audit) and covered a critical gap in the operating costs of the nine Hubs. Security upgrades for all hubs are completed. Dikwa installations were completed days before the town and hub were attacked by ISWA (more detail under VfM below).

FCDO support to UNDSS was designed to strengthen procedures for security collaboration and communication between the UN and NGOs. The recognised tool for this in humanitarian operations is the Saving Lives Together Framework (SLTF). FCDO funding supported dedicated personnel to strengthen implementation of this framework, particularly with regard to use of common services, such as UNHAS flights and humanitarian hubs. The Saving Lives Together Framework is now recognised as a functional initiative in the response, achieving Indicator 6.8, although further improvements continue to be a priority, including development by UNDSS and other key stakeholders of a context-specific set of Standard Operating Procedures for the SLTF in Nigeria.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.

Economy
‘No-show’ passengers for UNHAS flights waste seats which could otherwise be filled and limit the effectiveness of the UNHAS service. The UNHAS Steering Committee introduced a penalty system ($90) which led to significant reduction in ‘no-show’ passengers and supported UNHAS to maintain efficient planning and flight management.

UNHAS’ cost per passenger kilometre in 2020 was $1.95, down from $2.02 in 2019, while the cost per available seat kilometres was $0.82 in 2020, reducing from $1.16 in 2019. These gains are from cost-recovery for no-show passengers and the use of consistent vendors who offer highly competitive pricing.

Efficiency
IOM signed 6-months' supply agreements for daily operational commodities used by the hubs (i.e.’ food supplies, housekeeping supplies, diesel) which protected the hubs from price increases. IOM also ‘right-sized’ its staff profile across the hubs during 2020, reducing the number of staff working hours without affecting quality of service delivery.

Effectiveness
Security fortification of the Humanitarian Hubs are critical in making the field hubs safer. During an attack by ISWA on the Dikwa Hub in March 2021, FCDO-funded security features slowed access allowing staff and service users to shelter the hub’s bunker.

INSO’s quality, real time information about incidents as they occur, including hard-to-reach areas, via an adapted network of contacts and field monitors. Supporting precise information needs of NGOs facilitates decisions on movements and safe access to beneficiaries promoting continuity and safety of operations.

Describe any changes this output, and any planned changes as a result of this review.
The weighting for this output was increased from 10% to 15% reflecting the additional funding provided to IOM and UNDSS. Two new indicators (6.7 and 6.8) were added with the inclusion of IOM and UNDSS for projects ending by December 2021, at which point they will discontinue. No further changes were made to indicators. All milestones were reviewed to reflect changes in the operating context. Weighting across outputs will be reviewed again in the next review period.
[note] The weighting for Output 2 was reduced from 5% to 0%, as this output is no longer implemented by NENTAD.

Recommendations from previous Annual Review
All Recommendations from the 2019/20 Annual review have been implemented – see Annex 1 below for details.

Recommendations for the year ahead and lessons learned this year
- FCDO to engage UNDSS and other key stakeholders towards development of a context specific SLT Nigeria SOP and guidance document, by October 2021.
- FCDO to monitor and influence where necessary any constraint being placed on UNHAS’ ability to operate on an ongoing basis.

Output Title	Emergency response is timely, effective, accountable, value for money and conflict-sensitive and adaptive to address underlying vulnerabilities in the longer term, to build towards systems-strengthening development interventions
Output number:		7	Output Score:	A
Risk Rating		Minor	Impact weighting (%):	5%
Risk Revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestone	Progress
7.1: % of NENTAD projects directly monitored and supported by evidence based independent analysis and information	75%	78%
7.2: NENTAD procedures for emergency response funding (reallocation and Internal Risk Facility) developed, agreed, operational and effective	4 reallocations or IRF allocations enable timely and effective emergency response by relevant partners	11
7.3: Affected populations have the opportunity to provide feedback and register complaints and receive a response. (Y//N)	Yes	Yes
7.4: Northeast Nigeria Donor Partner Group meetings on the humanitarian-peace-development nexus are held and documented to support a coherent international approach when engaging with the Government of Nigeria (Y/N)	Yes	Yes, regular meetings held and documented during the reporting period

Briefly describe the output and provide supporting narrative for the score.
This Output combines activities mainstreamed across different NENTAD components (indicators 7.3 and 7.4) and stand-alone initiatives (indictors 7.1 and 7.2) designed to improve the quality of the humanitarian response. Milestones were met or moderately exceeded, earning a score of A.

Indicator 7.1: Led by IMPACT Initiatives, NENTAD’s Third Party Monitoring Consortium (TPM) provides external verification of aid delivery for six programmes within the NENTAD portfolio. A mixed method approach combines regular light touch monitoring (LTM) reports, system reviews, sectoral/thematic deep dive assessments and ad-hoc flash reporting. TPM delivered against all planned outputs for the year, successfully sharing 70 LTM reports which include maintaining monthly dashboards and Quarterly Factsheets measuring IP delivery against output and outcome indicators. TPM produced three deep dive assessments covering protection, food security and nutrition, three partner systems reviews on AAP, conflict sensitivity, and gender equality and social inclusion and a thematic Vulnerability and Essential Needs Assessment which was uploaded to the REACH Resource Centre and ReliefWeb websites and received 798 downloads. Both FCDO and IPs have used these products to improve internal monitoring, identify gaps and areas for strengthening, consider areas for project development and/or inform decision making. FCDO has used TPM products to triangulate information and results received from partners, and to investigate programmatic issues on programme delivery in the field.
[note] UNHAS, UNDSS, IOM and INSO are not monitored by TPM as funded activities do not directly engage affected populations. ICRC is also not monitored by TPM due to its mandate and role.

The Internal Risk Facility, measured under Indicator 7.2 was used to good effect during the reporting period, enabling flexibility of response. Two successful HNET bids to the FCDO Central Crisis Reserve resulted in an allocation of £8m in September and £7m in November 2020 which were allocated to WFP and ICRC to respond to the deteriorating food security trend. Three further internal allocations to support NENTAD utilised funds from elsewhere in the department totalling £14.2m. These amounts enabled increased contributions to WFP, ICRC and UNICEF. It also enabled the funding support to IOM and UNDSS programmes detailed in Output 6 above to address critical gaps.

Six dispersals were made under the ProSPINE+ programme after FCDO and IRC developed a robust process to handle rapid response to emergency needs. These supported adaptation to Covid-19, including the prevention campaign, and maintained capability to support emergency protection needs where no other actors were able to respond.
- DRC responded to IDP arrivals in Bama, Ngala, and Maiduguri supporting 4,156 households and over 24,000 people through provision of emergency shelter kits, non-food items (NFIs) and construction of communal shelters, in coordination with the with the State Emergency Management Agency.
- PLAN adapted to evolving child protection needs resulting from Covid-19 providing increased psychological first aid services to children, hygiene items, increased recruitment of community volunteers, public messaging materials for infection prevention control, and personal protective equipment (PPE) for staff and volunteers.
- IRC provided PPE for staff and volunteers to conduct case management support for women and children and conduct community outreach to support the Covid-19 sensitisation and prevention campaign.
- Translators Without Borders also contributed to this campaign, receiving an allocation to produce audio material in multiple languages for dissemination through radio programming, translating information materials to support Covid-19 messaging and information, plus scaled-up trainings for Protection actors.
- NRC provided emergency food assistance, shelter and NFIs to over 2,800 displaced persons arriving in Maiduguri having fled violence in Ngarannam (Borno). NRC also procured PPE to enable partners NIMC and NPC to reopen offices and resume services (which contributed to the overachievement against Output indicator 1.2).
- Plan and IRC conducted joint assessments and delivered an integrated emergency response after inter-communal conflict displaced thousands in/around Lamurde in Adamawa. NFIs and protection services (psychosocial first aid and hygiene kits to over 2000 children, case referral to specialised services, civil documentation, child protection messaging) were provided to over 5,700 people while 7,442 individuals across five communities participated in 267 sessions focussing on Covid-19 prevention, hygiene promotion, child protection and rights awareness.
Indicator 7.3: Monitored by the HNET team and TPM, feedback and complaints mechanisms are being implemented by all IPs to ensure affected persons have a convenient means of communicating their feedback opinions on interventions. A range of tools are being deployed such as community information centres, community dialogue sessions, surveys, focus group discussions, telephone hotlines, online dashboards and suggestion boxes. Reporting includes how communications are handled, resolution rate, and analysis to identify trends within the feedback. TPM conducted a partner system review of AAP mechanisms focusing on five key accountability principles: relevance, quality, resilience, communication with communities and staff behaviour. The report identified some areas for improvement which some IPs have acted upon; all recommendations on AAP will be addressed during the next review period.

On Indicator 7.4, the UK continued to chair the NE Donor Partners Group and the Humanitarian Donor Coordination Group, convening regular coordination meetings and to support strategic engagement through the UK-chaired NE Ambassadors forum. These structures play a key role in facilitating dialogue within the international community and establishing shared positions and approaches, and with key government stakeholders.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Efficiency: TPM monitors two VfM indicators to ensure efficiency in conversion of inputs to outputs: the ratio of programme costs to the number of research cycles accomplished that period and the number of outputs achieved. TPM reported a decrease in the ratio between programme costs and research cycle activities at £12,888 as compared to £20,231 at the end of last year. This was due to continued efficiencies within the team around research design, data collection, analysis, and dissemination. In addition, costs associated with data collection were still relatively low due to the use of remote data collection during period. TPM continues to track achieved outputs, providing assurance of delivery within agreed timelines. The target for this indicator has exceeded 100%.

Describe any changes this output, and any planned changes as a result of this review.
There was no major change to the output. The wording for Indicator 7.4 was revised to reflect what the indicator is measuring more clearly. There is no planned change to output and indicators. However, due to reduction in budget for FY 2021/22, the milestone for Indicator 7.1 and 7.2 would be revised.

Recommendations from previous Annual Review
All Recommendations from the 2019/20 Annual review have been implemented – see Annex 1 below for summary.
Recommendations for the year ahead and lessons learned this year
- By October 2021 FCDO to review AAP plans with IPs guided by TPM recommendations and discussions with other key actors.
- The NE Nigeria donor coordination groups should continue to work closely with the NE Ambassadors Group to support coordination and joint action on priority issues.
D: RISK

Overview of risk management
The overall risk appetite for the NENTAD programme remains SEVERE. NENTAD operates in an active conflict zone and, whilst rigorous controls are in place, the volatile security context presents a range of significant risks.

A serious risk for the programme this year was the increased threat on humanitarian actors posed by NSAGs, including abduction and executions, and attacks on humanitarian cargo and assets, further shrinking humanitarian space and reducing humanitarian access for NENTAD partners. Insecurity in the NE is anticipated to continue to worsen, and with it the constraints on humanitarian space, unless the Nigerian military authorities are in a position to enable improved humanitarian access to affected people in need; including the alleviation of policies which constrain movement and content of humanitarian cargo. Bureaucratic impediments emanating from policies of government agencies have also continued to constrain movement of cargo and staff. Humanitarian space has therefore shrunk further during the reporting period, severely constraining access, and presenting risks to the successful delivery of activities.

NENTAD IPs have experience working in complex emergencies and are assessed as well equipped to manage these on-going risks, although constant vigilance is required. The FCDO team is also alert to the risks and actively seek to ensure these are assessed, monitored, and analysed through regular engagement with IPs and broader research and discussion with key stakeholders.

In response to the increasing threat against aid workers and attacks on garrison towns FCDO funded IOM to reinforce the security features of the Humanitarian Hubs, and funded UNDSS to strengthen security coordination between the UN and NGOs. This supports the risks management capability for NENTAD IPs and users of these services, and the humanitarian community as a whole.

FCDO also continues to engage with UN leadership, the Humanitarian Country Team, and convene meetings of donors to support the humanitarian operations at the strategic level and support risk mitigation through humanitarian diplomacy and Federal and State advocate for the protection of civilians and the safety of aid workers.

The Covid-19 pandemic raised a severe delivery risk. Many IPs withdrew international staff from Nigeria in line with duty of care obligations, while humanitarian actors minimised their physical presence in camps to reduce the risk of transmitting the virus into vulnerable populations. This coupled with Covid-19 restrictions imposed by the authorities (eg. lockdowns) challenged delivery of critical humanitarian assistance. Covid-19 contributed to increased economic hardship and higher rates of criminality in some areas. These were mitigated through remote monitoring and delivery as well as the use of community structures in pre-positioning and distribution of essential food commodities. This help to ensure that critical lifesaving activities continue to be delivered without significant gaps.

Other key risks within the reporting period are fraud, aid diversion and safeguarding issues such as prevention of sexual exploitation and abuse. These risks are mitigated through due diligence assessments, independent audits commissioned by FCDO and regular follow up with IPs on recommendations to ensure weaknesses identified in their internal control systems are addressed. Enhanced DDA specifically addressing safeguarding risks, have been carried out on all IPs, with completion of all recommendations. Working collaboratively with IPs to strengthen areas of weakness and utilising the Third-Party Monitoring project have proved to be constructive methods to manage risk. For example, TPM share flash reports on alleged
fraud incidents which were duly followed up on and addressed.

All NENTAD programmes have a risk register and Delivery Chain Risk Map (DCRM) which identify delivery and fiduciary risks and mitigation measures, plus chart the flow of funds from IPs to end-beneficiaries. HNET maintains an overarching NENTAD DRCM with clear risk and mitigation measures which feeds into the NENTAD portfolio risk register. The portfolio risk register and Risk Appetite statement for NENTAD was updated in February and again in April 2021.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of NENTAD Partners
Partnerships between FCDO and IPs are well-established. Interaction has been largely virtual for much of the review period, which increased frequency of communication. Quarterly reporting and review meetings were conducted promptly with most of the IPs. IPs adjusted well to the Covid-19 context and managed risks effectively. IPs have been receptive and supportive of UK initiatives, including a field visit by UK Special Envoy for Famine Prevention and Humanitarian Affairs and the UK’s famine prevention initiative.

FCDO continued to build strong relationships and influence the agenda of the wider international community through leadership of the NE Ambassadors Group and chair of the NE Nigeria donor coordination structures. FCDO sit on the Humanitarian Country Team in Abuja and attend the Operational Humanitarian Country Team meetings in Maiduguri. This coordination contributes to improving the Value for Money of UK Aid, monitors strategic and operational level decision making, and supports action on priority issues relating to the humanitarian operation.

Table 1: NENTAD Live Agreements and Delivery Modalities
Name of Partner	Project	Committed Amount (£)	Start Date	End Date	Delivery Modality
INSO	NGO Security	1,089,000	1 April 2019	31 March 2022	Multi-Year AGA
IRC (Consortium lead)	ProSPINE +	16,549,708	1 April 2019	31 December 2021	Multi-Year AGA
AAH	Nutrition + WASH	7,623,518	1 April 2019	31 March 2022	Multi-Year AGA
IMPACT Initiative led Consortium	Third Party Monitoring	3,000,043	16 July 2018	31 March 2022	Multi-Year AGA
UNHAS	Flights & Logistics	10,000,000	1 June 2019	31 March 2022	Multi-Year MoU
UNICEF	Nutrition+ WASH	32,072,329	1 April 2019	31 March 2022	Multi-Year MoU
UNICEF	RUTF-SAM Treatment	5,000,000	1 December 2020	31 December 2021	Annual MoU
WFP	Food Security	88,077,832	17 October 2018	30 September 2021	Multi-Year MoU
IOM	Humanitarian Hubs	2,500,000	1 November 2020	30 April 2020	Annual MoU
UNDSS	Security Coordination	300,000	1 November 2020	31 October 2021	Annual MoU
ICRC	Multisectoral	4,000,000	1 January 2021	31 December 2021	Annual MoU
[note] Consortium members are IRC, DRC, NRC, Plan International and Translators Without Borders.
[note] Consortium members are IMPACT Initiatives, ACTED and Ground Truth Solutions.

Programme, Commercial and Financial Management
NENTAD financial management continues to be robust, achieving both ODA and year end targets. Given the scale of humanitarian need since inception, NENTAD has utilised £390.91m of the approved £400 million budget allocated representing 98% of the total approved budget. A Business case addendum for an additional £25m cost extension is required to enable delivery of the humanitarian component of the FCDO Nigeria Business Plan for FY 2021/22. Forecast for the period was £88.84m against actual spend of £88.33m representing 1% variance, and within the HMT threshold of 2%.

Variance was within the standard threshold throughout the year, other than for a brief period in June 2020. Close monitoring of IPs’ financial management has led to observed improvements in internal controls and quality of reporting. The quality and timeliness of financial reporting has been above average, particularly for INGO partners. Multilaterals such as ICRC and WFP have different financial years to FCDO, which creates a time lag of 3-6 months before FCDO receive certified financial reports. This sometimes limits visibility on the utilization and management of FCDO funds. This is reflected in global framework agreements with these multilaterals, though local arrangements offset resulting challenges to some extent.

All NENTAD INGO IPs undergo independent annual FCDO-commissioned audits. This year's audit covered the period April 2019 to September 2020. To improve the quality of the audit, HNET collaborated with the FCDO finance team to deliver a lesson learning session for all IPs on audit good practices and with the Audit firm on improving the quality of the audit report. A notable improvement in report quality and internal controls with IPs was observed. Corrective measures have been agreed to address issues identified in the audit. The audit report was unqualified.

All recommendations from previous DDAs have been fully implemented across the 10 partners. Implementation is ongoing on recommendations raised in the new DDAs conducted during the year.

The team continue to sensitise all IPs on fraud and safeguarding issues and the importance of reporting all alleged cases to FCDO immediately. Acting on a recommendation from the IAD 2019 audit, FCDO Nigeria developed and piloted a new Fraud Risk assessment checklist as part of the independent audit of the NENTAD programme. Findings indicated that overall, IPs have adequate fraud and safeguarding measures in place. Areas for improvement included the need for IPs to internalise these policies through measures such as regular staff trainings and ensuring compliance of downstream partners. FCDO Nigeria will support IPs to address these findings in the next review period.

All assets procured by IPs under the NENTAD programme are managed with quarterly updates submitted to FCDO annexed to the quarterly reports. Asset spot-checks are carried out each year as part of the independent audits. The most recent spot-check was carried out in May 2021 as part of the independent audit to validate the existence and location of all assets per the IPs assets register. There were some discrepancies due to delays in IPs updating their registers indicating more frequent spot-checks are needed to ensure accuracy of these registers. Increased FCDO staff presence in Maiduguri will support spot-checks every six months.

Date of last narrative financial report	Date: 29th April 2021- INSO / Date: 10th May 2021 TPM / Date: 13th March 2021- IOM / Date: 17th May 2021- UNICEF FIT Response / Date: 4th May 2021- IRC ProSPINE / Date: 21st May 2021- AAH SUNNY / Date: 22nd March 2021- UNDSS
Date of last audited annual statement	FCDO’s independent audit conducted May 2021 (covering period April 2019- September 2020) for INGO partners; IRC (ProSPINE), INSO, AAH and Impact Initiatives

Annex 1: Status of progress of 2019/20 Annual Review Recommendations.

Output 1.
Key Recommendations	Status of progress
In 2020/21, FCDO should work with the ProSPINE+ consortium and other stakeholders to develop a plan of action to increase access to national identification.	NRC continued to build on their partnerships with NIMC and NPC, making gains in the delivery of civil documentation. This includes plans to develop their capability for outreach and mobile services in hard-to-reach communities. NRC is engaging with the Nigerian government on plans to roll out a nationwide policy.
Consortium reporting in FY 2020/2021 should include disaggregated data on persons with disability and a review of actions to increase disability-inclusion of services.	Data for persons with disabilities (PWD) is now consistently reported quarterly. The consortium’s approach to PWD is an extension of the inclusion agenda that individual organisations adhere to in all areas of their operation.
Given overachievement against most targets, FCDO will work with the ProSPINE+ consortium to review indicators and milestones for the next review period.	Logframe reviewed with some indicators revised upward, while others less relevant were removed or rephrased. New activities specific to Covid-19 were introduced. This should be reviewed again for the next review period.
FCDO should work with ProSPINE+ to review the extent to which protection outputs will deliver protection outcomes and use this analysis to inform a protection sector strategy (particularly on gender-based violence and/or child abuse).	Gender Based Violence (GBV) and supporting children at risk are integral elements of the programme design for 2021.ProSPINE advocated on GBV issues during the year through awareness raising reports and working with civil society to advance access to justice. FCDO and IRC have pivoted the design of ProSPINE towards a greater focus on achieving outcomes for FY 21/22. FCDO have liaised with the Social Development Cadre and ‘VAWG champions’ to track ProSPINE+ on VAWG. Partners are now tracking disaggregated PWD and GBV data and reporting quarterly.

Output 3
Key Recommendations	Status of progress
WFP improved alignment and collaboration with cash actors (geography and modality). In 2020, this should include investigation on options for partners to piggyback on WFP’s mobile cash platform.	The follow steps are ongoing to realize greater CBT coordination and harmonization: 1) WFP Nigeria is playing a lead role on the External Cash Working Group to deliver a common approach on the use of cash based transfers (aligned with the Grand Bargain); 2) WFP developed a request for proposals from FSPs where humanitarian actors are invited and encouraged to participating using consolidated specifications; and 3) WFP continues to conduct contextual assessments and set up legal CBT framework with a joint approach. These actions taken in 2020 continue into 2021.
There is the need to improve and evidence Accountability to Affected Population (AAP)…similar to recommendation in the 2018/2019 AR… In 2020, WFP should provide quarterly updates on numbers of callers, number of concerns resolved, and numbers of callers referred to ensure hotline functionality as an effective feedback mechanism ensuring AAP.	WFP has made some progress on AAP, which should continue to be prioritised. WFP's AAP structure is made up of three components: provision of information; consultations of affected populations; and a functioning Complaints and Feedback Mechanism (CFM). / 1. Information provision: WFP Protection and AAP unit developed IEC materials which have raised awareness in local languages on topic of Covid-19, fraud and misconduct. Further materials are planned. / 2. Consultations: WFP and partners conducted consultations with affected populations to inform programming and identify barriers to access assistance in 8 locations and two protection risk assessments across Yobe, Borno and Adamawa (Aug-Dec 2020). / 3. CFM: Since September 2020 WFP has a nominated CFM manager responsible for updating the CFM SoP and expanding coverage of the CFM. WFP is also exploring expansion of the hotline and has supported partners in strengthening their help and feedback desks. A training for WFP CFM focal points and partner protection and AAP officers took place in March 2021.
FCDO should work with WFP and other donors in 2020 to continue to build GoN ownership, commitment, and capacity [to improving coverage and quality of food delivery in areas under GoN control].	WFP is intensifying work to develop national social protection mechanisms to increase the government’s capacity to protect vulnerable Nigerians against shocks and stresses. WFP coordinates with National and State Emergency Management Agencies and has provided technical capacity building support. During 2020 WFP has been a leading voice of advocacy with the GoN on the deteriorating food insecurity in the NE.
WFP to work with partners to implement multi-purpose cash at scale in accessible urban settings with functional markets, such as Maiduguri and Jere.	WFP's process of scaling the use of CBT is ongoing, and it has set up a national Cash Taskforce to expand its cash platform. WFP continues to shift from in-kind and voucher assistance to unrestricted cash transfers. WFP has used CERF-funding to complement FCDO funding to enable greater use of integrated multi-purpose cash transfers.
FCDO should work with all stakeholders, including the state and federal government to identify how access can be improved.	FCDO a) established an Access Adviser position within the INGO Forum to co-lead the access working group to drive this agenda; b) supported inclusion of NE Nigeria in UNSCR 2417 White Paper c) engaged CHASE team in London to raise profile of access constraints in NE Nigeria; d) led in-country visit by UK Special Envoy on Famine Prevention and Humanitarian Affairs visit which included dedicated briefing and advocacy with GoN on access constraints; e) maintains engagement with key stakeholders on access; and f) commissioned analysis on food insecurity from Tufts University to inform advocacy.
Review indicators and milestones to reflect the potential impact of Covid-19.	Indicators and milestones updated to reflect the impact of Covid-19
All reports by WFP and ICRC should include disaggregated data on disability and all assessments use the Washington Group Questions.	WFP has included the Washington Group Questions in all surveys, assessments and household M&E surveys. Disaggregation is done upon request, but sample sizes sometimes limit statistical utility of data. Disability is always a key targeting criterion for WFP programme activities, and data on disability is included in WFP general external reporting, although not yet in reporting to FCDO. / ICRC do not provide FCDO with disaggregated data. This is under discussion centrally.

Output 4
Key Recommendations	Status of progress
FCDO to review nutrition programming and share recommendations with nutrition partners and key actions, and timelines, identified.	Nutrition review completed June 2020. Recommendations shared and discussed with each partner.
FCDO and other donors should enable and encourage UNICEF to flex funding to respond to nutrition needs in the most inaccessible LGAs, and in spikes in need, particularly in light of anticipated food insecurity during 2020.	Covid-19 and increased insecurity have reduced rather than increased access. UNICEF and the Nutrition Sector working group are pursuing rapid response contingency planning to respond to new IDP arrivals and opportunities to access hard to reach locations. Donor flexibility will be required to support this.
UNICEF should streamline RUTF processes with partners, including agreeing shared SOPs in line with international good practice on: tracking average use of RUTF per child per site; delivery mechanisms; and supply-chain training.	UNICEF initiated agreement with 12 INGO partners implementing nutrition interventions in Borno state. Monthly partner meetings are held to review utilisation versus number of children admitted for treatment in each site. Supply-chain management training provided to partners and GoN counterparts.
FCDO to work with WFP to realign BSFP targets and consider screening all BSFP recipients to ensure that those who are acutely malnourished are identified and referred for appropriate treatment and care.	WFP’s approach is practical and appropriate in emergency situation for a short term, though needs to adapt to the protracted nature of the crisis. Further dialogue needed to influence government policy and practice in treating malnutrition.
Indicators and milestones will need to be re-visited with partners during quarter one.	Milestones reviewed resulting in some amendments. No change in indicators required. Frequency of the sentinel surveillance data collection was revised from monthly to quarterly.
Improve ownership of nutrition programming by government counterparts…to gain commitment at State and LGA government levels to identify barriers to government delivery of nutrition services [to promote] funding and managing of nutrition services.	UNICEF a) supported domestication of the Nigeria National Food Policy which saw formation of Borno State Committee on Food and Nutrition (SCFN); b) successfully advocated for state spending on nutrition activity incl. RUTF, therapeutic milks and associated child health; c) continue to lobby for additional commitments to be realised at state level. Further work is needed to address constraints linked to government budget allocation/release. Government budgets were significantly affected by oil price and economic impact of the pandemic. There remain significant gaps especially in hard-to-reach LGAs.

Output 5
Key Recommendations	Status of progress
FCDO and other donors support UNICEF as WASH sector lead… to integrate Open Defecation Free priorities in the process of IDP camp decongestion.	Draft workplans developed in Dikwa and Pulka with WASH partners, a review of latrine designs has been conducted with implementation underway with UNICEF partners with involvement of beneficiaries, camp management and Sector partners. Camp decongestion is a broader issue tied up with ongoing discussions with state authorities and longer planning process; UNICEF WASH sector lead feeding in on technical parameters.
Indicators and milestones will need to be re-visited in the coming year to reflect Covid-19 implications.	Indicators and Milestones updated to reflect the impact of Covid-19
Indicators, 5.6 and 5.7, added last year to meet International Climate Finance requirements, need revision to align FCDO and UNICEF calculations	Methodology for calculating the Results for Indicator 5.7 has been agreed with UNICEF.
UNICEF as lead for WASH and nutrition sectors in the NE should use its role to influence Borno state and LGAs to ensure strategic plans for these sectors are in place at LGA level.	At Federal level UNICEF and GoN collaborated on analysis leading to a 2021 - 2022 WASH Programme Strategic Note, shared with Borno State Rural Water Supply and Sanitation Agency to inform a review of the Borno State Water Policy. The WASH Sector Strategy has also been drafted and presented at sector level for final review.. / UNICEF and WASH sector worked with the Borno State Environmental Protection Agency to review faecal sludge management practices and protocols, resulting in policy and technical recommendations. UNICEF is also supporting a review of state approaches to hygiene promotion and water resources management.

Output 6
Key Recommendations	Status of progress
Targets for UNHAS and INSO to be reviewed in FY 2020/2021 in light of the changed operating context.	Milestone for 2020/21 for all UNHAS and INSO indicators has been revised to reflect the changing operating context
INSO faces challenges with registered members complying with critical security protocols, such as timely updates of staff field movements. FCDO should explore options to support INSO in increasing compliance.	FCDO reviewed the challenges with INSO and key stakeholders, and reached out to partners and other donors to encourage compliance with protocols. This action relates to the recommendation on the Saving Loves Together Framework (below) and new partnership with UNDSS. INSO and UNHAS now report significant improvement for INGO protocols. Security of local actors requires further review .

Output 7
Key Recommendations	Status of progress
The Saving Lives Together framework… is not yet operationalised effectively in Nigeria….FCDO should work closely with key stakeholders to ensure this framework is operationalised as a priority.	FCDO raised this as a priority issue in the Humanitarian Country Team and key stakeholders. FCDO funded UNDSS to deliver the SLTF jointly with partners INSO and UNHAS and are encouraging other donors to contribute. See updated recommendation under Output 6.
FCDO to ensure follow up on issues raised in TPM reporting is recorded and tracked systematically.	Lessons-learned session for the FCDO TPM Network conducted July 2020.
Indicator 7.4 should be adjusted to reflect declining security, Covid-19, and increasing humanitarian needs to reflect revised assumptions about the transition to development and develop the ambition for AAP.	Output 7.4 has been adjusted to now reflect the UK’s convening role in bringing together international donors across the humanitarian-peace-development nexus to support shifts in key areas of concern.
FCDO should draw from experience in similar contexts and the thematic ‘deep-dive’ on AAP to support development of an AAP strategy in the coming year.	TPM conducted a thematic deep dive. FCDO has influenced re-launch of Working Group. OCHA request for Standby Partnership deployment to support implementation received.
Additional resources will be required in 2020/21 to avoid a significant reduction in the scale and scope of humanitarian assistance delivered through NENTAD. A new business case should be developed in parallel to ensure continuity of humanitarian assistance post-NENTAD.	Business case Addendum for additional £25m submitted. to enable delivery of the humanitarian component of the FCDO Nigeria Business Plan.
FCDO should prioritise thematic areas for advisory focus to strengthen the overall humanitarian response, incl. strengthening centrality of protection and AAP.	Food insecurity and famine prevention, access, protection of civilians; returns; and AAP have been prioritised, supported by development of a workplan to organise work around these themes.
Further work is needed to broaden the VfM proposition in the business case and to develop measurable VfM indicators at partner level; the resulting analysis should inform the design of NENTAD’s successor programme.	AAH, TPM and UNICEF has been supported to develop and report on measurable VFM indicators. Design of NENTAD’s successor programme will consider this recommendation during the design. We shall be working with other IPs to develop VFM indicators in the coming year.
FCDO and IPs should review planning processes for the next review period to ensure agreed targets reflect the methodologies used to calculate results.	Logframe with key targets updated and finalised.
[Given Covid-19 and security risks] FCDO to work with all humanitarian partners to identify how response capacity can be sustained in the context of reduced field presence and access to deep field locations.	HNET promptly contacted each partner to understand actual/anticipated impact of Covid-19 on operations and mitigation measures; monitored regularly through meetings/calls. FCDO also with the Humanitarian Country Team and the INGO Forum to understand the impact on the response and where the UK may be able to assist (e.g., supporting flexibility in programming, advocacy to GoN on response policy and/lockdown measures).