## Log-Frame
Project name | Propcom Mai-Karfi: A rural market development programme in northern Nigeria
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1: end March 2019 | Milestone 2: end March 2020 | Milestone 3: end March 2021 | Milestone 4: end December 2021 | Notes and Assumptions
Sustained increases in the incomes of poor women and men engaged in selected rural markets in northern Nigeria. | Proportion of population below national poverty line for rural households in northern Nigeria. | Planned | 0 |  |  |  |  | NOTE: DFID to provide and track changes at Impact level using national, and possibly regional, statistics from national household surveys and other sources (including INGOs, etc.). Propcom's attribution stops at the Outcome level and the programme only contributes to any changes at the Impact level.
Achieved
Source: National statistics.
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Average increased income in rural households in northern Nigeria | Planned | 0
Achieved
Source: National statistics.
OUTCOME | Outcome Indicator 1.1a |  | Baseline | Milestone 1: end March 2019 | Milestone 2: end March 2020 | Milestone 3: end March 2021 | Milestone 4: end December 2021 | Notes and Assumptions
Selected rural market systems work more effectively for poor farmers and small scale rural entrepreneurs. | Number of poor farmers and small scale rural entrepreneurs recording net additional income change as a result of programme activities (% of women in brackets, Total / NE region). Cumulative | Planned (Overall) | 0 | 40,000 (15-30%) | 270,000 (15-30%) | 500,000 (15-30%) | 642,000 (15-30%) | 1. Those with higher incomes are better able to cope with and recover from shocks (economic, environmental, etc.) and are therefore more resilient. 2. Diversification of income generating activities also leads to improved resilience. 3. Farmers adopting appropriate climate smart agriculture (CSA) will be more resilient to climate change. 4. The volatile and unpredictable security situation in BAY and GBT states will allow market development and sustainable livelihoods to be supported resulting in discernible positive outcomes. 5. An intervention that fits within any of the 3 pillars of climate smart agriculture will be deemed climate smart: http://bit.ly/2JCu9kv. NOTE: The exchange rate to be used for Year 4 is £1 = ₦528. This needs to be reviewed every year and adjusted accordingly. (Source: oanda.com) The exchange rate used at the start of the project in 2012 was £1 = ₦254. NOTE: Direct impact from transition states will only be captured for the first year. Without programme presence for 2nd and 3rd years, only indirect impact attributable to the programme will be captured for these years.
|  | Achieved (Overall) |  | 190,198 (31%) | 429,414 (44%) | 630,891 (48%)
|  | Planned (North East) | 0 | 20,000 (15-25%) | 189,000 (15-25%) | 335,000 (15-25%) | 420,000 (15-25%)
|  | Achieved (North East) |  | 115,835 (32%) | 260,433 (52%) | 409,451 (55%)
Source: Propcom's MRM system.
| Outcome Indicator 1.1b (NEW INDICATOR) |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Percentage of poor farmers with at least 15% additional income change compared to the counterfactual. | Planned | 0 |  |  | 65% | 70%
|  | Achieved |  |  |  | 91%
Source: Propcom's MRM system.
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Aggregate net additional income among poor farmers and small scale rural entrepreneurs in selected rural markets as a result of programme activities (NGN/GBP). Cumulative | Planned (NGN) | 0 | 755490000 | 15109800000 | 25850000000 | 31000000000
|  | Achieved (NGN) |  | 10534994832.0553 | 20951926210 | 28131084491
|  | Planned (GBP) | 0 | 1500000 | 30000000 | 52116935.4839 | 63965530.1004
|  | Planned (GBP) |  | 21747326.9643 | 44137168 | 58531978
Source: Propcom's MRM system.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of farmers and small scale rural entrepreneurs with increased resilience to climate change as a result of the programme's CSA activities (% of women in brackets, Total / NE region). Cumulative [ICF Indicator 4] | Planned (Overall) | 0 | 60,000 (15-30%) | 315,000 (15-30%) | 520,000 (15-30%) | 735,000 (15-30%)
|  | Achieved (Overall) |  | 194,430 (33%) | 441,588 (45%) | 712,024 (46%)
|  | Planned (North East) | 0 | 30,000 (15-25%) | 220,500 (15-25%) | 350,000 (15-25%) | 505,000 (15-25%)
|  | Achieved (North East) |  | 117,627 (33%) | 269,755 (53%) | 483,364 (51%)
Source: Propcom's MRM system.
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Amount of investment leveraged through market players and key actors (NGN/GBP). Cumulative | Planned (NGN) | 0 | 503660000 | 5569548447.5099 | 9400000000 | 18000000000
|  | Achieved (NGN) |  | 5103093088 | 7782633983.4903 | 17880864473
|  | Planned (GBP) | 0 | 1000000 | 12000000 | 18951612.9032 | 37154214.4678
|  | Achieved (GBP) |  | 10530091 | 16254767 | 36928579
Source: Propcom's MRM system.
INPUTS (£) | DFID (£) |  | Govt (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1a |  | Baseline | Milestone 1: end March 2019 | Milestone 2: end March 2020 | Milestone 3: end March 2021 | Milestone 4: end December 2021 | Notes and Assumptions
Selected rural and agricultural market systems work more effectively for poor farmers and small scale rural entrepreneurs. | Number of partners and market actors that invest in pro-poor innovations that the programme helps to pilot (Total / NE region). Cumulative | Planned (Overall) | 0 | 12 | 18 | 68 | 70 | 1. Key market actors and partners (NGOs, INGOs) will respond to positive incentives unlocked by programme support, to provide better terms of trade, improved goods and services, increased rural access and more equitable rules of the game in their relationships with poor farmers and entrepreneurs. 2. Women's engagement in rural markets is hindered by cultural and other constraints. Because of this, women require tailored interventions in order to access markets and additional support is required to ensure this results in income benefit. 3. That other development programmes (Government and donor funded) do not result in significant market distortions which prevent market players from enacting positive and sustainable changes which benefit poor women and men in the long term. 4. That the security situation will determine the geographic footprint and scale of intervention activity in the NE region of Nigeria. Propcom Mai-karfi and partners can only operate in areas where the levels of security risk do not hinder their operational ability.
|  | Achieved |  | 31 | 63 | 70
|  | Planned (North East) | 0 | 6 | 10 | 50 | 51
|  | Achieved |  | 16 | 48 | 51
Source: Propcom's MRM system.
| Output Indicator 1.1b (NEW INDICATOR) |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Percentage of partners that have continued with the pro-poor innovation since the pilot started and/or made changes to the original business model. | Planned | 0 |  |  | 65% | 80%
|  | Achieved | 0 |  |  | 91%
Source: Propcom's MRM system.
| Output Indicator 1.2 (NEW INDICATOR) |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Percentage of surveyed market actors (who do not receive facilitation through Propcom) who report positive perceptions of relevant business models supported by Propcom (cumulative) | Planned | 0 |  |  |  | 65%
|  | Achieved | 0
Source: Propcom's MRM system.
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of poor farmers and small scale rural entrepreneurs who access new inputs, services, technology as a result of programme activities (% of women in brackets, Total / NE region). Cumulative [ICF Indicator 1] | Planned (Overall) | 0 | 150,000 (15-30%) | 375,000 (15-30%) | 580,000 (15-30%) | 821,000 (15-30%)
|  | Achieved (Overall) |  | 245,234 (35%) | 479,111 (44%) | 775,139 (46%)
|  | Planned (North East) | 0 | 75,000 (15-25%) | 262,500 (15-25%) | 390,000 (15-25%) | 570,000 (15-25%)
|  | Achieved (North East) |  | 144,384 (39%) | 288,855 (53%) | 523,635 (51%)
Source: Propcom's MRM system.
IMPACT WEIGHTING (75%)
INPUTS (£) ? (?)
| DFID (£) |  | Govt (£)
INPUTS (HR)
DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 (NEW INDICATOR) |  | Baseline | Milestone 1: end March 2019 | Milestone 2: end March 2020 | Milestone 3: end March 2021 | Milestone 4: end December 2021 | Notes & Assumptions
Adoption of CSA practises within selected rural and agricultural markets across N. Nigeria, including the NE region. | Hectares of land that have received sustainable land management practices as a result of the programme. [ICF Indicator 17] | Planned |  |  |  | 1000 | 10871 | 1. That the security situation will determine the geographic footprint and scale of intervention activity in the NE region of Nigeria. Propcom Mai-karfi and partners can only operate in areas where the levels of security risk do not hinder their operational ability. 2. That there will be no significant natural shocks (e.g. flooding, droughts, pest infestation, etc.) that will negatively impact the improving livelihoods of beneficiaries.
|  | Achieved |  |  |  | 10871
Source: Propcom's MRM system.
| Output Indicator 2.2 (NEW INDICATOR) |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of farmers that have adopted sustainable land management practices as a result of the programme. | Planned |  |  |  | 2000 | 5912
|  | Achieved |  |  |  | 5912
Source: Propcom's MRM system.
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of interventions targeting the North East region. Cumulative | Planned | 2 | 6 | 9 | 29 | 29
|  | Achieved |  | 12 | 27 | 29
Source: Propcom's MRM system.
IMPACT WEIGHTING (0%)
INPUTS (£) ? | DFID (£) |  | Govt (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1: end March 2019 | Milestone 2: end March 2020 | Milestone 3: end March 2021 | Milestone 4: end December 2021 | Notes and Assumptions
Private investors, government, non-government organisations and development agencies make changes in their approach to northern Nigeria as a result of programme influence. | Number of regulatory changes, policy reforms, or release of funds by state and federal government to facilitate activities that is supported by the programme. Cumulative | Planned (Overall) | 0 | 2 | 5 | 7 | 8 | 1. The security situation will determine the geographic footprint and scale of intervention activity in the NE region of Nigeria. Propcom Mai-karfi and partners can only operate in areas where the levels of security risk do not hinder their operational ability. NOTE: Influence can be of varying degrees ranging from initiating a discussion to bringing about radical institutional change. The project will only consider meaningful engagements leading to tangible outcomes as evidence of influence.
|  | Achieved |  | 4 | 6 | 8
Source: Propcom's MRM system.
| Output Indicator 3.2a |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of actors or organisations (non-government organisations, farmer organisations and trade associations) that have been supported or influenced by the programme (Total / NE region). Cumulative | Planned (Overall) | 0 | 6 | 12 | 19 | 30
|  | Achieved |  | 10 | 18 | 29
|  | Planned (North East) | 0 | 5 | 9 | 16 | 20
|  | Achieved |  | 8 | 15 | 19
Source: Propcom's MRM system.
| Output Indicator 3.2b (NEW INDICATOR) |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of collaborations with and support given to other development programmes and partners. Cumulative | Planned (Overall) |  |  |  | 4 | 5
|  | Achieved |  |  |  | 4
Source: Propcom's MRM system.
IMPACT WEIGHTING (10%)
INPUTS (£) ? | DFID (£) |  | Govt (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1: end March 2019 | Milestone 2: end March 2020 | Milestone 3: end March 2021 | Milestone 4: end December 2021 | Notes and Assumptions
Disseminate lesssons learned and produce knowledge products to document the programme's experiences. | Number of government, development sector, private sector, academia, and/or donor organisations attending lesson learning and communication events. | Planned (Overall) | 0 |  |  |  | 100
Achieved
Source: Propcom's MRM system.
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
| Number of knowledge products documenting PM's experiences. | Planned (Overall) |  |  |  |  | 1
Achieved
Source: Propcom's MRM system.
IMPACT WEIGHTING (15%)
INPUTS (£) ? | DFID (£) |  | Govt (£)
INPUTS (HR) | DFID (FTEs)

## Summary of changes
Date | Indicator No. | Change made | Rationale
2020-12-01 | Output 2.1 | Indicator removed | Removed as per FCDO's suggestion
2020-12-01 | Output 2.2 | Indicator removed | Removed as per FCDO's suggestion
2020-12-01 | Output 2.3 | Indicator removed | Removed as per FCDO's suggestion
2020-12-01 | Output 4 | Indicator removed | Removed as per FCDO's suggestion
2020-12-01 | Output 1.2 | Indicator moved from Output level to Outcome level. Now Outcome 3. | Indicator rearranged to better align with the logic of the programme
2020-12-01 | Output 2.5 | Indicator moved from Output level to Outcome level. Now Outcome 2. | Indicator rearranged to better align with the logic of the programme
2020-12-01 | Outcome 1.1b | Added to Logframe | Added to look at the depth of income change. It aims to look at the proportion of beneficiaries with at least a 15% increase in income compared to the counterfactual.
2020-12-01 | Output 1.1b | Added to Logframe | Added to look at the sustainability of business models/innovations introduced by the programme (also a systemic change indicator).
2020-12-01 | Output 1.2 | Added to Logframe | Added to look at the percentage of surveyed market actors who report positive perceptions of relevant business models supported by Propcom.
2020-12-01 | Output 2.1 | Added to Logframe | Added to look at the hectares of land that have received sustainable land management (SLM) practices. This correlates directly with ICF KPI 17.
2020-12-01 | Output 2.2 | Added to Logframe | Added to look at the number of farmers who have adopted the SLM practices promoted by the programme. Also in line with ICF KPI 17.
2020-12-01 | Output 3.2b | Added to Logframe | Added to count the number of collaborations with other development partners and organisations.
2020-12-01 | Output 3.2 | Renamed to Output 3.2a. Development projects has been removed from the list of actors and organisations influenced. | Development partners have been moved to Output 3.2b.
2020-12-01 | Output 1.2 | Target revised to 655,000 from 550,000 (increase of 19%) | Increased in line with the achievements of the programme.
2020-12-01 | Outcome 2 | Target revised to 545,000 from 440,000 (increase of 24%) | Increased in line with the achievements of the programme.
2020-12-01 | Outcome 1.1a | Target revised to 515,000 from 352,000 (increase of 46%) | Increased in line with the achievements of the programme.
2020-12-01 | Outcome 1.2 | Target revised to £55M from £9M (increase of 516%) | Increased in line with the achievements of the programme.
2020-12-01 | Outcome 3 | Target revised to £21.3M from £4.5M (increase of 374%) | Increased in line with the achievements of the programme.
2021-06-01 | Output 4.1 | Added to Logframe | Added to reflect the logic of the programe during the close-out phase.
2021-06-01 | Output 4.2 | Added to Logframe | Added to reflect the logic of the programe during the close-out phase.
2021-06-01 | Output 3.2 | Target increased from 20 to 30. | Increased in line with the achievements of the programme.
2021-06-01 | Output 2.3 | Target reduced from 30 to 29. | No new interventions are being added at this stage of the programme due to budgetary cuts.
2021-06-01 | Output 2.2 | Target increased to 5,912 | Increased in line with the achievements of the programme.
2021-06-01 | Output 2.1 | Target increased to 10,871 | Increased in line with the achievements of the programme.
2021-06-01 | Output 1.3 | Target increased to 821,000. | Increased in line with the achievements of the programme and the ToR for the 9-month extension.
2021-06-01 | Output 1.1b | Target increased to 80% from 70% | Increased in line with the achievements of the programme.
2021-06-01 | Output 1.1a | Target reduced from 52 to 51. | No new partners are being onboarded at this stage of the programme due to budgetary cuts.
2021-06-01 | Outcome 3 | Target increased to £37.15M. | Increased in line with the achievements of the programme.
2021-06-01 | Outcome 2 | Target increased to 735,000. | Increased in line with the achievements of the programme and the ToR for the 9-month extension.
2021-06-01 | Outcome 1.2 | Target increased to £63.9M. | Increased in line with the achievements of the programme.
2021-06-01 | Outcome 1.1a | Target increased to 642,000. | Increased in line with the achievements of the programme and the ToR for the 9-month extension.
2021-06-01 | Output 1 | Impact weighting increased to 75% from 55%. | Weights have been increased in line with the objectives of the programme during the close-out phase.
2021-06-01 | Output 2 | Impact weighting reduced to 0% from 15%. | No additional targets have been set for this output hence no impact weighting has been attached to them.
2021-06-01 | Output 3 | Impact weighting reduced to 10% from 30%. | Weights have been reduced because of the reduced importance of Output 3 indicators.
2021-06-01 | Output 4 | Impact weighting of 15% assigned to this new indicator. | Weights have been assigned to reflect the logic of the programe during the close-out phase.