ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	International Action Against Corruption (I-ACT) Programme
Country or region targeted	Global
Type of cost extension (if applicable)	N/A
Original project budget	£34.5m (includes £6m from the Prosperity Fund. / Current budget is £28m (£3m from the PF)
Original project start and end dates	1 August 2017 to 31 March 2021
Cost extension value (if applicable)	N/A
New project end date (if applicable)	31 March 2022
Business Case Document No	Vault number: 18108311

INFORMATION
What is the project’s purpose?
The International Action Against Corruption (I-ACT) programme delivers specialist Anti-Corruption technical expertise which is not available at country level and access to international partnerships to help tackle cross-border corruption. It works to shift incentives by better prevention, detection and exposure of corruption and recovery of stolen assets. I-ACT supports a range of implementing partners who provide experts, for example in financial investigations, anti-money laundering and asset-tracing, to help countries prevent and expose grand corruption.
What is the objective of the cost extension or other changes?
The programme extension end date is 31 March 2022. The objective of the changes to the programme is to continue funding components which have a strategic value to the UK and link to the UK Anti-Corruption Strategy commitments, while working with a reduced budget in FY 21/22. The five components which meet these criteria are: / Open Ownership (OO) / International Centre for Asset Recovery (ICAR) / U4 Anti-Corruption Resource Centre (U4) / Transforming Procurement Systems (TPS) / Extractive Industries Transparency Initiative (EITI). / All these components will allow the UK to continue implementing the FCDO’s Anti-Corruption priorities and commitments made at the London Anti-Corruption Summit in May 2016 and support other FCDO’s priority countries in meeting their related commitments. The UK will continue to be a world leader, for example, in the beneficial ownership and asset recovery arenas. The work of U4 will continue to educate Anti-Corruption (AC) actors and HMG staff in key areas of AC, including more recent publications on COVID related corruption. The funding of TPS will continue the successful work of the FCO’s Global Anti-Corruption Programme in increasing data standardisation and reducing corruption in public procurement. / We will maintain policy relationships with several of the I-ACT components who we are not funding in FY 21/22, such as, Transparency International or the Egmont Centre of Financial Intelligence Unit Excellence and Leadership (ECOFEL). This will ensure that the UK stays up to date on the Anti-Corruption global effort, and areas we may fund again in the future if the economic situation allows, and thereby allowing the UK to contribute to the overall partners approach in those areas.
What is the additional and total support the UK will provide?
The budget for FY 21/22 is £2.1m - funding which will ensure that the UK continues to lead in areas crucial to the UK Anti-Corruption Strategy, such as Beneficial Ownership and Asset Recovery. For example: / Open Ownership – will continue to drive effective implementation in more countries and leveraging learning and research to shape global policy debate to advance beneficial ownership transparency. / International Centre for Asset Recovery (ICAR) – FCDO’s funding to ICAR will support countries on asset recovery through training, long-term experts in-country and hands-on case advice. The work will also help developing country institutions to prevent and detect laundering of the proceeds of corruption and to recover stolen public assets. / U4 Anti-Corruption Resource Centre – work will assist to effectively address corruption challenges across a range of sectors. HMG and a range of Anti-Corruption actors will continue to have access to training materials and publications from U4 to develop their knowledge. / Transforming Procurement Systems – we will continue to build upon last year’s project success and results of the ex-FCO’s Global Action Against Corruption pilot. This will include building economic resilience by transforming the effectiveness of key transparency systems for procurement and beneficial ownership and breaking down silos between these reforms to foster a systemic and sustainable step change in transparency. / Extractive Industries Transparency Initiative (EITI) – will continue to fund the UK’s subscription to EITI to promote the public awareness about how countries manage their oil, gas, and mineral resources.
What are the expected results?
The expected key results include: / Open Ownership funding which will deliver normative change where beneficial ownership data is reliable, useable, and well used by governments, civil society, and business to deliver social and economic benefits including a reduction in corruption. The aim will be to increase the number of countries with public registers which contain structured beneficial ownership data, while developing new evidence and disseminating this to advance beneficial ownership transparency globally. / Asset recovery work will contribute to the building of Anti-Corruption chains that are better equipped to deliver sanctions and recover assets, and the development of stronger laws and international standards to make asset recovery more efficient. / Enabling the specialist Anti-Corruption Resource Centre to continue delivering key training materials and courses on AC which are not only used by AC actors but also by HMG staff. This will assist the UK’s effort in building knowledge on a wide range of AC areas etc.
What is the approach to implementation?
Beyond the FY 21/22 ODA budget cuts and commitments made in the UK Anti-Corruption Strategy, the approach to implementation this year was in part informed by the recommendation of FCDO’s external commissioned work of the Monitoring and Learning Agent. The decision to continue funding some elements was based on the analysis of which projects were highly performing, likely to achieve the greatest impact and value for money. To this effect, a more streamlined programme was constructed to focus on key aspects of the UK Anti-Corruption Strategy, such as asset recovery and beneficial ownership. The programme will also focus on capacity building with the Anti-Corruption Resource Centre and transparency with the extractives work. / We will continue to engage with non-funded partners on a wide range of policy areas, such as the Stolen Asset Recovery Initiative, the United Nations Office on Drugs and Crime on the illegal wildlife trade, and the Transparency International, to end the injustice of corruption by promoting transparency, accountability, and integrity. This will ensure that the UK will stay informed but will also feed into these areas of Anti-Corruption, which will help us gather evidence for potential future funding. Building on the former Global Action Against Corruption programme, funded by the Prosperity Fund, we will continue partnerships with established Anti-Corruption partners, for example, the use of data /digital tools to make the AC work in Mexico more sustainable. We will use this short-term project to learn lessons to inform future FCDO programme design and multi-stakeholders and international cooperation.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
Key changes from the original business case: / The context changes meant that the Theory of change was redesigned in November 2019 to include the critical monitoring and learning element, the tightening of assumptions to ensure understanding mechanisms of change and how individual components contributed to results. / COVID pandemic changed the political economy contexts of countries I-ACT worked in, with governments operating in a context of radical uncertainty, and faced with difficult trade-offs. Given the nature of the crisis was unprecedented, the FCDO like many other donors had to scale back some operations, explored and introduced other temporary or permanent, fiscal tools and measures to meet the operational challenges.