## AMAN 2-year logframe
Annex A
Logical framework 2020-2021 - Annual Report
Project No. 300611-103 - CASIP
PROJECT TITLE: 300611-103 | HMG CAPABILITY, ACCOUNTABILITY, SUSTAINABILITY AND INCLUSIVITY PROJECT (CASIP)
IMPACT | Impact Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
A more accountable, transparent and inclusive Palestinian Authority Security Sector (PASS) | Score of the Palestinian Security Sector Integrity Index | Deliver 2 Security Sector Integrity Index | Integrity Index score in SS 2018 was (55%) | 100% of the Index indicators and pillars developed | 0 | At least 40% of the index recommendations have been used to lobby PASS to enahnce the index scoring | Estimated Integrity Index score in SS 2019 at (58%) | Estimated 10% increase in Integrity Index Score in SS during lifetime of project | PASS is willing to make change, as well as is capable to make change so as to influence systems that frame their actions by adopting key recommendations and acting on them
|  | Achieved: milestone1 & 3 achieved, while mile milestone 4 not compltertly achieved.at the level of final score o fthe index. |  | Achieved |  | Achieved. | Partially Achieved Integrity Index score in SS 2020 was (55%). There is a significant improvement in the results of the index when it comes to Integrity and accountability in the SS, where the score of the Integrity and accountability pillars increased to 69 and 60 respectively compared to baseline, however the decline in transparency pillar to 38 had negatively impacted the final score of the Index
Source
Integrity Index (2018) in the SS report by AMAN/CPGSS published in 2019, Integrity Index (2020) in the SS report piblished in 2021
| Impact Indicator 2 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022)
| Percentage of citizens [m/f] who report trust in PA Security Sector | Deliver 2 opinion polls on security sector governance (ITA) | In 2020, 71.7% of polled citizens in WB expressed trust [M 65.6%/ F 77.8%] | 0 | 0 | 0 | 74% of polled citizens express trust. Estimated increase of 2% | Estimated 4% increase in polled WB citizens’ turst in PASS
|  | Achieved: .Milestone 4 not met. there are decrease in percintage of citzens expressed trust (68% of polled citzens express trust ( 65.8% males, 70.3% females). One opinion poll conducted during milestone 4 |  |  |  |  | Not Achieved 68% of polled citzens express trust ( 65.8% males, 70.3% females). One of the main factors that could have affected citizens perception is the Covid-19 pandemic effects on citizens and the way the government managed the crises and the state of emergencies
Source
Opinion Poll on Citizen Satisfaction with Governance of the Security Sector in the West Bank
OUTCOME 1 | Outcome Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
Strengthened and more engaged civil society, citizenry and media in holding PASS to account | Percentage of citizens [M/F] who say they understand their right and how to report a complaint | (1) 8 awareness campaign through various channels (social media, radio spots, ALAC) on rights to complaints, and (2) 2 opinion polls | In 2020, 66% of polled citizens reported understanding [67%M/65% F} | (1) campaign to enhance public' awareness on ITA related to Covid-19 and PASS | (1) campaign to enhance public' awareness on ITA in PASS' work | (1) campaign to enhance public' awareness on ITA in PASS' work | (1) campaign to enhance public' awareness on ITA in PASS' work (2) Opinion poll / 68% of citizen report understanding | Estimated increase (4%) of citizens reporting understanding of their right and how to make a complaint with minimum 65% of females reporting | assumptions: 1) Economic and security situation does not deteriorate to the extent that security sector governance becomes less of a priority for citizens and civil society actors; 2) International community continues to push for governance reforms within PASS; 3) Political will and government capacity to act on basis of evidence provided is secured. 4) PA/PASS are open to and willing to engage with citizens and civil society 5) Citizens are motivated to respond to knowledge and information made available to them 6) Citizens victims of corruption lodge complaints, and whistle blowers report witnessed corruption
|  | Achieved: Milestone1,2 &3 achieved, while milestone 4 partially achieved (the target of 68% of citizens report understanding was not . (3) social media and advocacy campaigns conduted during milestone 1. (2) campaigns (1 radio spots\1social meia) and 2 TV episodes were impleemented during milestone 2 . (1) radio spot campaign (1596 spots) and (1) social media campaign implemented during milstone 3 reaching 221,15 citizens. 2 opinion polls conductd. Only 65.5 % (68.8 males,62.3% females) of polled citzens reported understanding their right and how to report a complai |  | Achieved 3 social media awareness and advocacy campaigns conducted aimed at: 1) encouraging citizens to abide by PA and PASS instructions to tackle COVID-19 2) advocating for enhancing ITA in managing public afairs during the crisis 3) advocating enhancing ITA in forming & regulating local emergency comittees. | Achieved. 2 Campaigns tand 2 TV episodes conducted as followos: - one radio spot campaign (990 spots) implemented via 14 local radio stations encouraging citizens to report corruption includign corruption in PASS . - one social media campaign encouraging citizens to report corruption. The campaign reached 54000 citizens -2 TV episods produced and discussed the experience of the emergency committees during Covid-19 pandemic, and the role of the Civil Defence in the regulation of local volunteers during crisis/emergency state | Achieved -A radio spot campaign (1596 spots) was implemented via 14 local radio stations encouraging citizens to report corruption acts whether if witnessing it or being a victim for it. -a social media campaigns was implemented and have reached 221,15 citizens | Partially Achieved 2 campaigns seeking to raise citizens awareness on their rights and how to report a complaint conducted as follows: (1) one radio spot campaign (4154 spots) was implemented via 14 local radio stations . 2) one social media campaigns was implemented and have reached 300,000 citizens. 2 opinion polls conducted (The first one on ITA in Palestinian policie services and the second one on citizens satisfaction with the SS governance.. 65.5 % (68.8 5males,62.3% females) of polled citzens reported understanding their right and how to report a complaint
Source
AMAN Pre and post opinion poll analysis / "Opinion poll on security sector governance" for the years 2020, 2021 and 2022 / the indicator (and target if relevant) will be broken down by men and women
| Outcome Indicator 2 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022)
| Number of cases/policy recommendations adopted by PASS relating to internal policy/procedural system | 8 policy/procedural change recommendations adopted by PASS (complaints systems, internal audit, communication strategy, budget transparency). | 0 | 0 | 1 reports on PASS budget spending, with assessment to which the PASS complies with recommendations produced of CPGGS | 1 reports on PASS budget spending, with assessment to which the PASS complies with recommendations produced of CPGGS | 2 policy/procedural changes adopted by PASS | PASS Integrates ITA through 8 policy/procedural changes adopted in their functions and prcedures
|  | Achieved: Milestone 2 was met. two reports conducted. Milestone 4 not met. It could be attributed to current political context. |  |  | Achieved | Achieved | Not Achieved. AMAN and CPGSS have been active in providing inputs\recommendations to PASS to promote better governance reform in SS through the produced Integrity Index, policy papers, and diagnostics reports, which provide a tool for SS to analyze and improve their anti-corruption programme, however the current political context hindered any improvement at the level of adopting AMAN's recommendations.
Source
AMAN and CPGSS reports and PASS Reports
| Outcome Indicator 3 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022)
| Number of cases/policy recommendations adopted by PASS relating to gender inclusion | 2 policy\recommendations adopted by PASS re gender inclusion as a result of CPGGS interventions | 0 | 0 | 0 | 0 | 1 gender policy\recommendation | 2 gender policy\recommendation adopted
|  | Achieved: milestone 4 was not met. |  |  |  |  | Not Achieved. The COVID-19 and the lockdown caused a delay in the implementation of some major activities (i.e. the assessment on PASS complaints handling management, and the capacity buildings for the complaints units cadre which are the base for lobbying PASS to adopt policies for governance reform.
Source
AMAN' assessment and recommendation
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
WEIGHTING (60%) |  |  |  | 0 |  |  |  | 100%
OUTPUT 1.1: | Output Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
Improved institutional and programmatic capability for the CPGSS, media and civil society organisations to hold PASS accountable. | Number of standardised policy, procedural, and planning methodologies reviewed/developed by the CPGSS members | 4 policies, procedural, and planning methodology reviewed/developed and used by CPGSS | 0 | (1) CPGSS membership criteria and outsourcing strategy developed. (1) CPGSS bylaws reviewed and developed | (1) CPGSS 20-23 strategy developed. (1) PASS budget analysis and oversiting manual reviewed and developed | CPGSS implementation plan 2021 developed | 0 | At least 4 of CPGSS policies and bylaws are improved and the role of CPGSS to oversee the PASS is more sustainable. | 1) CPGSS member organisations are able to convene their general assemblies/revelent internal bodies to approve changes in policy documents/procedures in accordiance with their respective bylaws during the project's lifetime; 2) CPGSS member organisations' appetite and willingness to engage in the project does not diminish as a result of internal changes or other contextual factors. 3)AMAN has strong skills and judgement to select CSOs, provide quality support, mitigate risks, and manage the project efficiently and effectively.M37 4)The Secretariat of the CPGSS for Security Sector Governance (CPGSS) has strong institutional and programmatic levels for sustainability and understanding of the citizens’ needs. 5)The individual CSO members of the CPGSS mainstream ITA and anti-corruption in its strategies and workplans 6) Representatives of government and PASS are willing to engage with civil society actors; 7) Issues of ITA and anti corruption are of high priority to a critical mass in society; 8) Citizens are willing to freely participate in opinion polls and provide uncensored answers to poll questions; 9) Security situation does not hinder implementation of planned activities;
|  | Achieved: 4 policies, procedural and planning methodology reviewed \developed and used by CPGSS including (CPGSS internal bylaws, membership criteria, CPGSS 20-23 stratey and plan , PASS budget and analysis oversighting methodology. . |  | Achieved. The internal by-laws, membership criteria, work methodology, internal governance capacity, production and dissemination of knowledge and the media policy were reviewd and developed. | Achieved. The CPGSS 2020-2023 strategy and plan were developed and adopted by the platform members. - PASS budget and oversighting methodoloty was adeveloped and adopted by CPGSS members. | Achieved. CPGSS implementation plan 2021 developed
Source
CPGGS bylaws, strategies and workplan and procedural manuals ivity report, strategy and workplan
| Output Indicator 2 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022)
| Number of research (including perception polls) produced by CPGSS | (5) reports, 2020 and 2022 Integrity Index in SS , and implement (4) post polls | 0 | 1 report on ITA of PASS in responding to Covid-19 | 1 report on PASS compliance with recommendations produced by CPGGS | 1 report on PASS budget | 1 report on performance of complaints systems.1 Integrity Index. 2 opinion polls on PASS governance and on ITA | (5) reports, 2020 and 2022 Integrity Index in SS , and implement (4) post polls published and disseminated
|  | Achieved: Mileestones 1,2,3 &4 werer achieved. 4 reports , 2020 integrity index, and 2 opinion polls on PASS governance and on ITA were implemented |  | Achieved. 1 work guide for the local volunteer\emergency committees was developed. The aim of this guide is to frame and regulate the work of the emergency committees in a way that ensures integrity, transparency, and accountability in their work. | Achieved. Two reports prepared. One on PASS complies with the recommendations of SAACB. And one on PASS budget performance. | Achieved during milestone 2 | Achieved. 1 report on performance of complaints systems.1 Integrity Index. 2 opinion polls on PASS governance and on ITA
Source
AMAN pre and post training evaluation reports / This doesn’t explicitly feature in the milestones and target, only the number of reports produced
| Output Indicator 3 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022)
| Number of [m/f] trained, % of trainees who demonstrate improved understanding of mainstreaming ITA into their work, and % of trainined people express satisfaction that training met learning objectives. | 1) Train 12 (7 M/5 F) journalists from 10 media outlets on producing social accountability programs. 2) Train 12 (7 M/5 F) journalists to prepare investigative reports on security service. 3) Train 10 (6m/4f) CPGSS members on networking, advocacy, planning, and budget analysis. 4) Train 80 total (50m/30f) youth on social accountablity | 0 | 0 | 1) Trained 12 (7M/5F) journalists on social accountability programs. 2) Trained 12 (7M/5F) journalists to prepare investigative reports on security service. 3) 80% of trainees provided proposals for investigative reports. 4) 90% of trainees express satisfaction. 5) 30% of trained youth and journalists able to demonstrate their improved knowledge/skills | 1) 40 trained youth (25M/15f) on ITA and social accountability tools, 90% of trainees express satisfaction. 2) 10 trained CPGSS members (6m/4f) on networking, advocacy, planning, and budget analysis. 90% of trainees express satisfaction. 3) 45% of trained youth and journalists able to demonstrate their improved knowledge/skills | 1) 90% of the trained trained youth and journalists demonstrate improved understanding of topic and journalists produced fact sheets and investigative reports and implement social accountability initiatives covered in media | 1) 114 people attended training courses; and 85% expressed satisfation 2) 90% of trainees demonstrate improved understanding, knowledge and skill of the topic with minimum 40% of females participation
|  | Achieved: Milestone 1, 2,3, &4 werer met. 89.9% Of the trainees express satisfaction and assure that their knowledge related to ITA had improved. 2) 10 members of CPGGS were trained (5males,5 females). 95% express satisfaction. 3) 83.4% of trained (10F,14M) journalists demonstrate their improved knowledge/skills. 90% of trained youth improved understanding. 85% of journalists provided proposals for investigative reports. |  |  | Achieved : Two capacity building sessions were conducted via Zoom for 28 journalists and media editors to encourage them to take their responsibility in holding PASS accountable through preparing investigative reports and media accountability programs. The first sessionwas held in August for 15 journalist (8 females,7 males) and the other was held in September for 13 journalists (6 females ,7 males). 85% provided proposals for investigative reports. 79%trainees express satisfaction | Achieved: 1) 40 trained youth (20m/20F) 89.9% Of the trainees express satisfaction and assure that their knowledge related to ITA had improved. 2) 10 members were trained (5males,5 females). 95% express satisfaction 3) 83.4% of trained (10F,14M) journalists demonstrate their improved knowledge/skills | Achieved: 90% of trained youth improved knowledge. 85% of Journalists provided proposals for investigative reports.
Source
Publications by AMAN/CPGSS / AMAN pre and post training evaluation reports / AMAN's annual report, Attendance Sheet, AMAN satisfaction survey, AMAN/Sharek activity report, Pre and post training evaluation report and questionaire
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
WEIGHTING (30%)
OUTPUT 1.2 | Output Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
The public has more access to information and knowledge on how to complaints, identify and report corruption cases | Percentage of legal advice provided to victims and whistleblowers on suspected cases of corruption and/or number of people reached | 2 media and social media awareness campaigns; to encourage citizens to report corrupt practices by PASS . Provide ongoing legal advice to citizens through AMAN ALAC | 0 | 1 awareness campaign related to CoVID-19 and PASS performance | 1% increase in number of complaints related to PASS received by ALAC Ongoing legal advice to victims and whistleblowers | (1) media and social media awareness campaigns; (2) ongoing legal advice to victims and whistleblowers | Ongoing legal advice to victims and whistleblowers 2% increase in number of complaints related to PASS received by ALAC | 1) An increase 4% of citizen reporting on PAST corruption to ALAC | 1) Issues of ITA and anti corruption are of high priority to a critical mass in society; 2)Security situation does not hinder implementation of planned activities;
|  | Achieved: This target was met. A radio spot campaign (4154 spots) was implemented. Social media campaigns reached aproxmatly 300000 |  | 1.1 social media campaigns focused on 3 raising awareness campaigns aimed at encouraging citizns to following and adhere to the instructions issued by the Ministry of Health, and report corruption in PASS and the work of the local emergency committees. | 2% increase in the complaints Related to Pass received by ALAC compared to quarter 1. AMAN’s Legal and Advice Center (ALAC) received 95 contacts via different means (9 females, 85 males, 1 unidentified contacts). -A radio spot campaign (990 spots) was implemented via 14 local radio stations encouraging citizens to report corruption acts whether if witnessing it or being a victim for it. -a social media campaigns was implemented and have reached 54000 citizens -2 TV episods produced and discussed the experience of the emergency committees during Covid-19 pandemic, and the role of the Civil Defence in the regulation of local volunteers during crisis/emergency state | A radio spot campaign (1596 spots) was implemented between (1st of oct, and 31, Dec) via 14 local radio stations encouraging citizens to report corruption acts whether if witnessing it or being a victim for it. social media campaigns have reached 221,157 citizens AMAN’s Legal and Advice Center (ALAC) received 129 contacts via different means (13 females, 112 males, 2 unidentified contacts, 2 not applicable 7.75% in the number of complaints received related to security sector | Partially achieved Ongoing advice to victims and whisltleblowers provided. 1.16% increase in number of complaints related to PASS received by ALAC. ALAC database showed that 417 legal advice were provided, 7.19% of the received contacts cases were related to Security sector agencies, comparing to 6.03% in 2019.
Source:
Social Media Report, ALAC Data Base, Pre-Post Opinion Poll for the years 2020-2022 "Opinion poll on security sector governance"
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
WEIGHTING (30%)
OUTCOME 2 | Outcome Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
Improved internal systems, procedures and service-delivery of the PA Security Sector that better applies ITA values and principles. | Number of substantial improvements made by PASS to their internal accountability systems and procedures, inculding internal audit, budget controls, and complaints handling manegment as a result of CPGSS recommendations | 4 policy / procedural recommendations adopted by PA relating to ITA in PASS internal accountability systems and procedures, | 0 | 1 advocacy campaign related to CoVID-19 and PASS performance | 0 | 0 | At least 1 Policy/ procedural change recommendations made by CPGSS adopted by SS | 4 Policy/ procedural change recommendations made by CPGSS adopted by PASS during project lifetime. | 1) political will within PASS for reform; 2) budget and resources are available to support needed changes/reforms.
|  | advocacy campaign related to CoVID-19 and PASS performance achieved: Work under this outcome is planned for year two of the project. |  | Achieved The campaign included radio spots, social media campaigns, radio and TV episodes. People engagement were noticeable and they were able to define related bodies to reports violations |  |  | Not Achieved Work under this outcome is planned for year two of the project.
Source
AMAN and CPGGS reports, PASS reports
| Outcome Indicator 2 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022)
| Development of unified evidence based communication strategy | At least (4) recommendations made jointly to develop communication strategy related to Access to information, the right to hold PASS accountable, engagement of civil society in policy making. | 0 | 0 | 0 | 0 | 0 | A unified communication strategy jointly developed and approved by CPGSS and PASS
Achieved: (Precise language against the planned annual reporting)
Source
AMAN, media and CPGGS reports, PASS reports
INPUTS (£) | DFID (£)
WEIGHTING (40%)
Output 2.1: | Output Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
Improved knowledge/skills in key PASS institutions on complaints handling management that responds to citizens needs and expectations. | Number of [m/f] trained, % of trainees who demonstrate improved understanding in handling women complaints using gender sensitive approaches, and % of trained people express satisfaction that training met learning objectives. | 1) Train15 (10m/5f) officers from the complaints units in PASS complaints units. 2) Train (12) female police officers on ITA and handling women's complaints. | 0 | 0 | 0 | 1 assessment report on complaints systems | 0 | 27 [10m/17f] trained. 85% of trainees are satisfied with training objectives. (%) demonstrate improved understanding 70% of trainees applied the gained skills in their work | 1)political will with PASS is secured and change champions identified; 2) trained personnel are not rotated/replaced before new changes are adequately institutionalised; 3) trained staff have the support they need and are accountable to apply what they have learned.
|  | Achieved: This target was met, 1 assessment report on complaints systems conducted. |  |  |  |  | Achieved: Assessment report on complaints systems achieved in Q4
Source
AMAN Pre-post training evaluation report and follow up questionaire
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
WEIGHTING (20%)
OUTPUT 2.2 | Output Indicator 1 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
Knowledge/skills are improved within key PASS units (Internal Audit, Administrative and Financial, Communication and Planning), on effective integration of ITA' values and principles. | Number of [m/f] trained, % of trainees who demonstrate improved understanding in integrating ITA principles , and % of trained people express satisfaction that training met learning objectives. | Train 24 (16m/8f) from PASS internal audit units on ITA principles and values in service provision. | 0 | 0 | 0 | 0 | 0 | 24 [16m/8f] trained. 80% of trainees are satisfied with training objectives. 80% demonstrate improved understanding 70% of trainees applied the gained skills in their work | 1) political will with PASS is secured and change champions identified; 2) trained personnel are not rotated/replaced before new changes are adequately institutionalised; 3) trained staff have the support they need and are accountable to apply what they have learned.
Achieved: (Precise language against the planned annual reporting)
Source
pre and post training evaluation report and questionaires, Internal Audit Units Plans
| Output Indicator 2 | Planned | Baseline | Milestone 1 (June 2020) | Milestone 2 (Sep 2020) | Milestone 3 (Dec 2020) | Milestone 4 (March 2021) | Target (March 2022) | Assumptions
| Number of [m/f] trained, % of trainees who demonstrate improved understanding re national anti-courption strategy and ITA principles, and % of trained people express satisfaction that training met learning objectives. | Train 20 (13m7f) from PASS administrative, financial andplanning units on ITA and the national anti-cuorruption strategy | 0 | 0 | 0 | 0 | 0 | 20 (13m/7f) trained. 80% express satisfaction and imporved understading re; (i) ITA principles, (ii) The national anti-corruption strategy, and (iii) Abiltiy to integrating the national anti-corruption strategy in their respective units annual work plans. 70% of trainees applied the gained skills in their work | 1) political will with PASS is secured and change champions identified; 2)) trained personnel are not rotated/replaced before new changes are adequately institutionalised; 3) trained staff have the support they need and are accountable to apply what they have learned.
Achieved: (Precise language against the planned annual reporting)
Source
AMAN Pre-post training evaluation report and follow up questionaire, PASS Annual plans and strategy
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
WEIGHTING (20%)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1
2
3
4
5
6
7
8
9
10