Annual Review - Summary Sheet

Title: FINANCIAL INCLUSION PROGRAMME
Programme Value: £50.25 million		Review Date: 22nd August – 2nd September 2016
Programme Code: 1133311	Start Date: July 2008	End Date: March 2020

Summary of Programme Performance

Year	2008	2009	2010	2011	2012	2013	2014	2015	2016
Programme Score	N/A	67.5	55	75	A	A	A	A	A
Risk Rating	N/A	M	M	M	M	M	M	M	Major

Summary of progress since last review

Under the Financial Inclusion Programme (FIP) DFID has provided £50.25 million to the State Bank of Pakistan (SBP) to transform the financial market such that it provides equitable and efficient financial services to the poor. The main instruments through which this has been achieved are guarantee facilities[1] for Microfinance Providers (MFPs) and small and medium sized enterprises (SMEs), and institutional and regulatory reforms. Combined, these instruments have increased lending to underserved individuals and businesses.
[1] A guarantee is a way to transfer risk. The risk to the lender is lowered by guaranteeing repayment of part of the loan in the event of a default.

Key achievements since the last review include:

An increase in the flow of funds to the microfinance sector which are in turn lent to microfinance clients. Over the last year, the Microcredit Guarantee Facility (MCGF) issued seven guarantees, which supported five Microfinance Providers (MFPs) across Pakistan. This contributed to the cumulative figure of PKR 20 billion (£147 million[2]) available for lending since MCGF’s inception in 2008. This represents an increase of nearly 25% over the previous period when the figure stood at PKR 16 billion (£118 million).
[2] 1 GBP = 136 PKR

Agreement with the SBP’s FIP Steering Committee in June 2016 on the future of MCGF. MCGF has achieved what it set out to do by increasing banks’ lending to MFPs. Now that the DFID-funded Pakistan Microfinance Investment Company (PMIC) has been established to address the sector’s funding gap in a more sustainable, market-based manner, it is appropriate for MCGF to wind down.

An increase in lending to SMEs through the Credit Guarantee Scheme for SMEs (CGS). This year, the cumulative number of SMEs receiving a CGS-backed loan was 22,909 - an increase of 38% over the previous period.

Establishment of the committees and processes to implement the National Financial Inclusion Strategy (NFIS). Following a visit from Queen Maxima of the Netherlands, the United Nations Special Envoy for Financial Inclusion[3] in February 2016, seven technical committees were formed focusing on the seven priorities set out under the NFIS.
[3] https://en.wikipedia.org/wiki/Queen_M%C3%A1xima_of_the_Netherlands

The completion of twelve pilots to expand the scope and reach of financial services in Pakistan. These include value chain financing[4], warehouse receipt financing[5], and digital payments[6].
[4] Financial services, products and support services flowing to or through a value chain to address the needs and constraints of those involved in that chain e.g. in the dairy chain this could include tailored products for farmers, distributors, processors, wholesalers and retailers.
[5] Warehouse receipt financing improves lending to farmers and traders. A farmer or trader receives a receipt for their stored goods from a warehouse that has been approved by a bank. The bank then takes the receipt and lends to the farmer or trader against that receipt. The receipt essentially acts as collateral for the bank.
[6] A means of paying for goods or services electronically, instead of using cash or a cheque via post or in person.

The signing of an Accountable Grant (AG) with the Pakistan Microfinance Network (PMN) to support their services to the microfinance industry. This includes further strengthening of consumer protection practices in the industry; improvements to the policy environment for microfinance; industry research and knowledge sharing, and digitisation of microfinance to increase branchless microfinance services.

Summary of lessons learnt and recommendations for the next year

1. MCGF has played an instrumental role in not just increasing lending by £147 million to the microfinance sector, but developing relationships between MFPs and the banks. With a good credit history established through MCGF, banks are now willing to lend without a guarantee, on the basis of their balance sheets and portfolio performance[7]. This represents the ‘market changing’ impact of FIP, which has enabled the lending market to function without donor intervention or support. MCGF’s legacy should therefore be considered one of the programme’s primary achievements. This should be communicated more widely as the facility winds down in the coming year.
  [7] Tameer Bank and National Rural Support Programme (NRSP) are the most notable examples of microfinance providers that have been able to negotiate loans with commercial banks, based on relationships formed under MCGF.
2. The environment for SME lending is showing signs of improvement. The non-performing loan (NPL) rate[8] has decreased from 33.83% to 25.29% over the same period last year and the total amount of outstanding loans is now at PKR 305.1 billion (£2.24 billion) – a 6% increase from last year[9]. Moreover, CGS is starting to mature, showing an accelerated uptake of guarantees among banks.
  [8] The NPL rate reflects the percentage of loans in a portfolio that are in default or close to being in default.
  [9] SME Financing Review, State Bank Pakistan, December 2015
3. To capitalise on these positive trends, and to encourage banks to take more measured risks while expanding lending to the SME sector, SBP should consider moving CGS outside of SBP. The purpose of this would be to attract more private investment; allow CGS to develop a more independent image[10], and further hone its model to develop the market. It is therefore suggested that a detailed proposal be developed to transition CGS to a Public Private Partnership (PPP) company.
  [10] There is evidence that in some cases CGS has attracted safer loans as banks do not want to be perceived by SBP (the banks’ regulator) to have a high NPL rate. This is in conflict with the purpose of CGS which is to push banks’ risk frontier in the SME sector.
4. Given the uptick in usage of CGS, it should provide incentives for banks to target marginalised SMEs such as the under-collateralised, women-led businesses and businesses based in Khyber Pakhtunkhwa (KPK) and Baluchistan.
5. FIP’s Financial Inclusion Challenge Fund (FICF) and Technical Assistance (TA) components have delivered critical improvements to the financial system. This has included the establishment of the Credit Information Bureau for the microfinance sector; the drafting of the Secured Transactions Law; pioneering pilots for warehouse receipt financing; and the installation of Anti-Money Laundering software in Pakistan’s Financial Monitoring Unit (FMU). SBP and DFID should develop communications to highlight the significant achievements and lessons learnt from such initiatives.
6. This year the World Bank undertook two missions to design a Financial Inclusion and Infrastructure Loan Programme (FIIP) for Pakistan. Draft plans indicate an interest in building on the foundations that FIP has established, such as providing further funds to CGS as it expands, and funding strategic NFIS priorities. DFID should maintain close engagement with the team to ensure a complementary approach and similar aims.
7. The coming year is the critical transition year for FIP, as MCGF winds down and its funds are released for reprofiling against NFIS priorities. To prepare for this, DFID should work closely with SBP to ensure effective functioning of NFIS committees and processes (notably proposal development and monitoring and evaluation of projects). As a contingency, DFID should agree with its Finance and Corporate Performance Department a mechanism for receipt of unspent funds under FIP in the event that SBP is unable to effectively deploy funds released from MCGF.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-113331
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-113331/documents/

Outline of the programme

DFID is implementing a £50.25 million Financial Inclusion Programme (FIP) through the State Bank of Pakistan (SBP). The programme was introduced in 2008, at a time when 89% of the population did not have access to banking services. Further, while 60% of the population had access to mobile phones, no viable branchless banking solution existed. The number of microfinance borrowers was 1.2 million in 2008, the greater part of which were served by subsidised microfinance providers. The majority of the poor, particularly in rural areas, had no access to formal financial services. This limited people’s ability to save, apply for a loan and accumulate capital, and thus led to lower levels of resilience to shocks, and limited capacity to pursue entrepreneurial activities. More simply, it meant poor people had limited control over their lives and futures.

In this context, FIP aimed to transform the financial market and enable it to provide equitable and efficient market-based financial services to the poor and marginalised, including women.

Since its inception FIP has played an instrumental role in expanding the microfinance market, helping to increase the number of microfinance borrowers by over 230%. FIP has led on several national policy initiatives such as the National Financial Inclusion Strategy.

The programme has evolved significantly during its course of implementation and has been adjusted to respond to the emerging needs and changes in Pakistan. It was extended twice with the most recent no-cost extension to 2020 approved in 2014. The last five year no-cost extension was granted to consolidate the significant achievements of FIP and to maintain the momentum for reform in the sector. The extension was additionally important to ensure a seamless transition to DFID’s Enterprise and Assets Growth Programme (EAGR) which is the next phase of DFID’s support to microfinance and SME financing, based on market-based instruments. FIP’s extension to 2020 recognised that FIP would have loan guarantees outstanding over the 2015-20 time period, and that EAGR would take 3-5 years to fully deploy.

FIP is pursuing results relating to microfinance, small and rural enterprise lending, and better financial institutions and policy frameworks. DFID funds for FIP are allocated across five components indicated in the table below. The Government of Pakistan has also contributed PKR 300 million (£2.2 million) for CGS. In addition, the funds held by SBP as guarantee cover were invested in short term Government Treasury bills which have earned interest profit over the course of the programme, representing good value for money for DFID.
#	Component	DFID allocation
1	Microfinance Credit Guarantee Facility (MCGF) – to help microfinance providers borrow from commercial banks by covering up to 25% first loss / 40% partial loss (60% is offered for loans to tier II microfinance providers[11])	£15m
2	Credit Guarantee Scheme (CGS) – to help small and rural enterprises borrow from commercial banks by covering up to 40% of any losses incurred	£13m
3	Institutional Strengthening Fund (ISF) – for capacity building of microfinance providers. This fund was closed to new submissions in 2014.	£6m
4	Financial Innovation Challenge Fund (FICF) – grants to pilot innovative digital financial inclusion, rural finance and Islamic financing products and services	£10m
5	Technical Assistance (TA) – SBP capacity building and financial architecture investments on anti-money laundering, credit information bureau, Islamic finance, consumer protection and branchless banking	£6m
-	Programme Design Costs	£0.25m
Total		£50.25m
[11] The distinction between tier I and tier II microfinance providers (MFPs) relates to the maturity of the MFP: tier I refers to bigger, more established players and tier II refers to smaller, less established players. See Annexe B for more detail.

All amounts in £ millions
Including Government of Pakistan contribution of PKR 300 million (£2.2 million)

FIP is regarded by SBP and other donors as one of the most influential financial sector programmes currently under implementation in Pakistan. It has put DFID at the centre of most of the policy thinking related to inclusive financial sector development. DFID enjoys an excellent relationship with the SBP and is working closely with the World Bank, all major commercial banks, microfinance institutions, telecommunications operators and state agencies.

Acronyms

AG	Accountable Grant
CGS	Credit Guarantee Scheme (for Small and Medium Sized Enterprises)
EAGR	Enterprise and Assets Growth Programme
EOBI	Employees Old-Age Benefit Institution
FATF	Financial Action Task Force
FICF	Financial Inclusion Challenge Fund
FIIP	Financial Inclusion and Infrastructure Programme (World Bank)
FIP	Financial Inclusion Programme (DFID)
FMU	Financial Monitoring Unit
GLP	Gross Loan Portfolio
HBL	Habib Bank Limited
HMG	Her Majesty’s Government
IFC	International Finance Corporation
iNGO	International Non-Governmental Organisation
KPK	Khyber Pakhtunkhwa
LUMS	Lahore University of Management Sciences
MCGF	Microfinance Credit Guarantee Facility
MFB	Microfinance Bank
MFP	Microfinance Provider
MoU	Memorandum of Understanding
NADRA	National Database and Registration Authority
NFIS	National Financial Inclusion Strategy
NPL	Non-Performing Loan
NRSP	National Rural Support Programme (in this context a microfinance bank)
PAR	Portfolio at Risk
PCD	Procurement and Commercial Department
PKR	Pakistani Rupees (local currency)
PPP	Public Private Partnership
PMIC	Pakistan Microfinance Investment Company
PMN	Pakistan Microfinance Network
SBP	State Bank of Pakistan (Pakistan’s Central Bank)
SMEs	Small and Medium Sized Enterprises
TA	Technical Assistance
UNODC	United Nations Office on Drugs and Crime
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

#	Outcome Indicator	Baseline 2011	Progress 2015	Target 2016	Achieved 2016
1	SME credit size as % of GDP	1.66%	1.00%	1.10%	1.00%
2	% SMEs with loan from regulated entity	6.6%	4.76%.	6.0%	6.1%
3	Gross loan portfolio of microfinance sector	PKR 26.9bn	PKR 80.95bn	PKR 85bn	PKR 104.7bn
4	Number of microfinance borrowers	2.1m	3.5m	3.6m	4.0m
5	Number of transaction/ deposit accounts	28.7m	39.9m	42m	43.37m

Outcome Indicators 1 & 2

These outcome indicators reflect the strength of the financing environment for SMEs. Whilst the first indicator ‘SME credit size as a percentage of GDP’ is at 1% (narrowly below target) it is notable that the percentage of SMEs with a loan from a regulated entity has exceeded its target[12]. Moreover, the most recent data available from financial year 2015-2016 indicates that outstanding financing to SMEs stands at PKR 305.1 billion – a 6% increase from last year[13].
[12] It is evident from the outcome assessment table that both these indicators are below the baseline from 2011. This is reflective of the downward trend in lending to the SME sector in Pakistan over the last five years, largely attributable to heavy government borrowing which has crowded out lending to the private sector.
[13] SME Financing Review, State Bank Pakistan, December 2015. It is notable that both these figures are below the baseline from 2011. This is reflective of the downward trend in lending to the SME sector in Pakistan over the last five years, largely attributable to heavy government borrowing which has crowded out lending to the private sector.

This is an important achievement for a sector that has seen a negative trajectory over the last decade. Previous Annual Reviews have noted the continued tendency for heavy Government borrowing to crowd out lending to the private sector. As a result, the volume and value of credit to the private sector has steadily declined over time from 28.7% in 2008 to 15.4% in 2015[14] which has had a particularly adverse impact on SMEs which are perceived as high risk clients by the commercial banking sector.
[14] World Development Indicators, World Bank, 2015, http://data.worldbank.org/indicator/FS.AST.PRVT.GD.ZS

It is therefore welcome to see the indicators on SME financing starting to trend more positively. CGS has played an important role in helping banks manage risks associated with SME lending and thus to facilitate expansion in this area.

Outcome indicators 3 and 4

These outcome indicators reflect the growth and maturity of microfinance in Pakistan. This year, the target for the Gross Loan Portfolio (GLP)[15] of the microfinance sector has been exceeded by 19.7 billion PKR (£145 million), hitting PKR 104.7 billion (£770 million) versus the targeted PKR 85 billion (£625 million). Moreover, the outcome indicator for the number of microfinance borrowers has exceeded its target, reaching 4 million clients in Pakistan (over 50% women), representing an increase of 14% on last year.
[15] The outstanding principal balance of all outstanding loans, including current, delinquent, and restructured loans, but not loans that have been written off.

However it is important to see these achievements in the wider context of the industry’s target of reaching 10 million active borrowers by 2020[16] and the potential market size for microfinance which is 27 million clients[17]. There are concerns that such accelerated growth risks a delinquency crisis similar to that witnessed by fast growing microfinance markets globally in 2008. However, the institutional arrangements and practices of the Pakistani market – many of which have been developed or championed by FIP – reduce this risk. This includes a fully functional Microfinance Credit Information Bureau and a regulatory umbrella that in the last year was extended to cover not just Microfinance Banks but the non-deposit taking Microfinance Institutions. In the future, a continued focus on responsible finance and client protection initiatives are vital to ensure that the industry commits to the principle of ‘do no harm’ as it expands.
[16] Microfinance Growth Strategy 202, Pakistan Microfinance Network, 2015
[17] Thus the current penetration rate stands at approximately 15%. MicroWATCH, Issue 32, Qtr 2, 2014, PMN

Outcome indicator 5

This outcome indicator reflects the growth in bank accounts active in Pakistan. The indicator has exceeded the target of 42 million transaction / deposit accounts[18] active in Pakistan.[19]. However, it is important to note that this indicator captures the total number of bank accounts – not the total number of unique bank accounts. Therefore, this should not be read as 43 million Pakistanis hold a transaction account[20].
[18] December 2014 is the latest data available from SBP on this indicator.
[19] A2F Survey, Horus-Gallup, State Bank Pakistan, 2015
[20] Rough estimates from the State Bank assume that the number of bank accounts per person is around 2.2. Thus one could estimate 19.7 million of the population in Pakistan have a bank account.

Nevertheless, this indicator reflects the dramatic shift in financial inclusion since FIP’s inception in 2008. It is worth underlining the findings from the FIP-funded Access to Finance survey which were reported in last year’s Annual Review[21]. This survey indicated that between 2008 and 2015 the percentage of Pakistani adults with access to financial services offered by formal financial intermediaries increased from 12% to 23%[22]. The survey additionally confirmed that women are engaging more with financial services; the percentage of women banked increased from 4% to 11% over the same period (2008-15)[23].
[21] This survey was funded by FIP’s TA component and the draft results of the 10,000 sample survey were shared with DFID in August 2015, as a follow-up to the same survey undertaken under FIP TA in 2008.
[22] This includes providers of mobile money services.
[23] The A2F survey counts Benazir Income Support Programme (BISP) accounts as bank accounts. It is therefore important to note that BISP has played a significant role in positive movement on female held accounts.

Overall output score and description

Output	Output Statement	Output Rating
1	Increase in credit flowing to Microfinance Providers	A+
2	Increase in loan products utilised by SMEs across key sectoral clusters	A
3	Improved enabling environment and intellectual infrastructure for access to finance to agri and rural enterprises	A+
4	Efficient transition to NFIS priorities	B
Total		A

Output 1 The A+ score recognises that MCGF has been successful in increasing the flow of credit to microfinance banks. MCGF has exceeded the primary target for ‘Gross loan portfolio leveraged from MCGF through commercial sources to microfinance providers’ by PKR 3 billion or £22 million.

Output 2 The A score balances the significant over-achievement on indicators relating to the number of SMEs receiving a CGS-backed loan, with the notable under-achievement on the number of loans that can be classed as ‘sector specific’ which was one of the intended structural shifts for this year.

Output 3 The A+ score reflects the fact that all targets relating to the enabling environment have been met, with a slight over-achievement on indicator 3.2 whereby a cumulative total of 12 pilots for new financial products and models have been completed under FIP, against the targeted 11.

Output 4 The B score acknowledges the underachievement against targeted advances on the transition to NFIS. While only slightly below targets, the B underlines the importance of ensuring improvement in this high-risk output area.

Key actions

1. In line with agreements affirmed at the last FIP Steering Committee Meeting, SBP should wind down MCGF, by not issuing any new guarantees against MCGF within 14 calendar days from PMIC’s notification that PMIC is ready and capable to start its lending operation.
2. The CGS team should develop a full proposal for the establishment of CGS as a Public Private Partnership (PPP) company. In recognition of the technical knowledge required for this task, FIP funds should support the hiring of a consultancy to draft a detailed proposal for the PPP model, outlining the governance arrangements and operating model, and scoping equity shareholders from the banking sector.
3. CGS should develop a more targeted approach, offering higher guarantee cover for marginalised groups (e.g. under collateralised firms, women-owned firms, and firms located in KPK and Baluchistan).
4. SBP should convene a short working session with donors working on financial inclusion to agree on terms of reference and operating norms for a NFIS Donor Group.
5. SBP should ensure that fully costed proposals developed by the NFIS Technical Committees are first directed to the FIP TA committee for potential funding review, before receiving formal approval by the NFIS Steering Committee.
6. SBP should provide clarity on the staffing arrangements of the NFIS Secretariat and ensure that FIP funds are used to support the capacity of the Secretariat to function effectively. This will be particularly important in the coming year as the coordination, monitoring and evaluation demands of NFIS increase.
7. SBP and DFID should develop communications products to highlight the significant achievements and lessons learnt under FIP. Most notable achievements relate to MCGF’s role in shifting perceptions of the microfinance sector; providing grant risk funding to Pakistan’s first mobile money provider (EasyPaisa); establishment of the Credit Information Bureau for the microfinance sector; creation of an anti-money laundering data centre at FMU, and establishing the commercial case for warehouse receipt financing and a number of value chain financing models.
8. DFID should engage closely with the World Bank as they finalise their proposals for their Financial Inclusion and Infrastructure Programme (FIIP) in the coming year. This is important given that draft designs for the loan programme indicate support to or expansion of existing FIP components.

Has the logframe been updated since the last review?

Yes. The logframe has been updated to reflect the agreement to wind down MCGF in future years and the increased emphasis on transitioning to National Financial Inclusion Strategy (NFIS) priorities. Output impact weightings have also been updated due to a rationalisation of output areas. The previous logframe had two output areas relating to NFIS processes and priorities, and the development of an Exit Strategy for FIP, whereas this year’s logframe has combined these indicators in recognition of how closely they are related.

## C: DETAILED OUTPUT SCORING

Output Title	Increase in credit flowing to MFBs / MFIs (Microfinance Banks and Microfinance Institutions)
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		Y[24]	Impact weighting % revised since last AR?	Y
[24] All risks have been updated since last year to align with new guidance on risk ratings issued by DFID in February 2016.

Indicator(s)	Milestones	Progress
1.1 Gross loan portfolio leveraged from MCGF through commercial sources to Microfinance Providers disaggregated by 1st tier / 2nd tier MFPs	PKR 17 billion / PKR 16.5 billion first tier / PKR 0.5 billion second tier	PKR 20 billion / PKR 19 billion first tier / PKR 1 billion second tier
1.2 Value of funds released from MCGF for NFIS reprofiling (1000s)	SBP formal approval on MCGF closure	SBP formal approval on MCGF closure

Key Points
This output measures FIP’s contribution to loans provided to the microfinance sector through the guarantees offered under MCGF. This output has scored an A+ having exceeded its target for the Gross Loan Portfolio (GLP) leveraged through MCGF for both tier I and tier II MFPs[25].
[25] The distinction between tier I and tier II microfinance providers (MFPs) relates to the maturity of the MFP: tier I refers to bigger, more established players and tier II refers to smaller, less established players. See Annexe B for more detail.

Output 1.1
The Microfinance Credit Guarantee Facility transfers and diversifies risk. It lowers the risk to the lender by guaranteeing repayment of part of the loan in the event of default. MCGF met its target for this year by mobilising the cumulative figure of PKR 20 billion (£147 million) of commercial lending to the microfinance sector.

From the end of 2014, commercial banks were offered the option of higher risk coverage (up to 60% rather than the standard 40% that is offered to tier I MFPs) to encourage lending to the less established tier II players. This was a means of supporting diversified growth in the sector, encompassing those players catering to the very poor, as well as those driving the market in the slightly better off low income and microenterprise segments. The target for tier II loans has also been exceeded this year at PKR 1bn against the targeted PKR 500 million. This has been through the following loans:
- PKR 0.5 billion credit extended to BRAC bank by United Bank Limited (UBL)
- PKR 0.5 billion credit extended to U Bank by the Pak Oman Investment Company Limited

Output 1.2
The most striking development in the microfinance industry over the last year has been the establishment of the DFID-funded Pakistan Microfinance Investment Company (PMIC) as the primary vehicle for funding the sector in the future. PMIC will function as a market-based wholesale fund which will attract funds from commercial investors to increase the loans available to the microfinance sector. The company was incorporated in August 2016 and is expected to provide its first loan in October 2016.

In order for this new market-based institution to survive and not be subject to unfair competition from a subsidised facility, SBP and DFID agreed to wind down MCGF. This principle was formally established this year, with agreement reached in the FIP Steering Committee held on the 30th June 2016 that “MCGF will be closed down provided…PMIC has become fully operational and given two week notice to SBP and DFID, expected within one month from the date of its financial close”[26].
[26] Minutes, FIP Steering Committee, 30th June 2016, SBP

Recommendations
1. In line with agreements affirmed at the last Steering Committee Meeting, SBP should wind down MCGF, by not issuing any new guarantees against MCGF within 14 calendar days from the date of PMIC’s notification to SBP confirming its ability and readiness to start its lending operation.
2. The achievements of MCGF should be more widely shared with audiences both in Pakistan and within DFID globally. Demonstrating to banks that the microfinance industry is a viable and profitable lending market can be termed as one of the biggest successes of FIP as a sustainable, ‘market changing’ intervention.

Output Title	Increase in loan products utilised by SMEs across key sectoral clusters
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Number of SMEs gaining access to finance through a CGS-backed loan	20,000	22,909
2.2 Number of under-collateralised SMEs receiving credit from CGS backed loans	1,000	2,943
2.3 % share of sector-specific lending in CGS portfolio (by value)	30%	8%
2.4 Number of initiatives taken towards sustainable CGS governance arrangements	Commercial / PPP concept note approved by CGS Technical Committee	Commercial / PPP concept note approved by CGS Technical Committee

This output reflects the performance of CGS in increasing the flow of lending to the SME sector and in steering banks towards a more sector based approach to SME lending. The sector based approach is important as it allows banks to develop loan products better tailored to specific sectors (e.g. by tenure – the time duration for which a loan has been provided) which can help improve sector knowledge and risk management. This output has scored A, balancing the over-achievement on both the overall number of SMEs and number of under-collateralised SMEs receiving credit form a CGS-backed loan, and the missed targets on sector specific lending.

Key points

Output 2.1
Cumulatively, 22,909 SMEs have gained access to finance through a CGS-backed loan this year, exceeding the target of 20,000. This means 6,299 have been supported in the last year alone – a full 38% increase on 2015 figures. This re-affirms the positive trend witnessed in CGS’ utilisation rates which have been increasing at an accelerated rate over the last two years.

No. of SMEs receiving CGS backed loan

However, the negligible value and number of claims against CGS over its five years of operation also raises questions about how far CGS has encouraged banks to lend to riskier, credit-constrained SMEs. A credit guarantee scheme should encourage financial institutions to conduct responsible lending; but responsible lending does not equate to zero risk-taking and zero defaults. Moreover, Habib Bank Limited (HBL) dominates CGS with 63% of all CGS-backed loans (14,498 out of 22,909) originating with HBL. These concerns around additionality and diversity of partner banks have been raised previously but there has been limited capacity to investigate these issues in greater depth.

Output 2.2
It is a very positive sign that the target for under collateralised loans (those loans granted with less than 100% collateral) has been exceeded by almost 200%. This is a genuine shift in CGS’s operations as last year this figure stood at just 190 firms. This is important as the average collateral requirement from firms drawing credit is 113.7%[27]. CGS can therefore be seen to be driving down banks’ collateral requirements.
[27] Enterprise Survey Pakistan, World Bank, 2013

Output 2.3
The target relating to a sector specific approach has significantly under-performed. This target was based on the CGS Technical Committee’s agreement on a gradual shift to a sector-specific focus, with 30% of the CGS portfolio adopting a sector approach in the first year (this year), followed by 50% and 100% in the second and third year respectively[28]. This target has not been met. However, whilst the achievement since last year is 8% overall, the latest quarter for which data is available shows that 38% of CGS-backed loans are sector specific. This suggests the CGS portfolio is adjusting to the sector specific approach but that it is doing so more slowly than initially envisaged; we therefore judge that this does not pull the score down below A.
[28] CGS Technical Committee Meeting, April 2015

Part of the CGS Technical Committee agreement on the sector specific approach was that banks will be eligible to access up to 2% of the exposure limits[29] as a grant for technical assistance (TA) for designing and launching ‘sector specific products’. To date no bank has availed of this offer which explains part of the poor performance against this indicator. Further work is required to understand why, despite SBP’s outreach efforts, banks have not taken up this opportunity.
[29] Illustration: If bank ABC plans to lend PKR 100 million through sector specific deals, the CGS would provide a risk cover of PKR 40 million (assuming it is 40% for that deal). The bank will be eligible for up to PKR 2 million (i.e. 2% of exposure limit) as TA grant.

Output 2.4
In line with recommendations from last year’s Annual Review, an independent consultant was commissioned to review the operations of CGS and provide recommendations for its future. This work resulted in a recommendation to extend CGS beyond 2020, but with governance changes, combined with the introduction of some commercial elements.

This assessment was based on the strong development case for continuing CGS in Pakistan. SMEs remain largely un/underserved in the credit markets. Moreover, as it stands, CGS represents the major credit guarantee scheme focused on SMEs in the country and signalling termination of the scheme at this stage (in anticipation of a 2020 closure) might slow or substantially undermine short to medium term performance. At the same time, it was also noted that CGS contains no commercial elements such as fees for accessing guarantees and it is a wholly Government-donor led scheme.

In response to this assessment, SBP circulated a concept note to the CGS technical committee to convert CGS into a Company, based on Public Private Partnership principles (i.e. with some SBP ownership maintained alongside commercial players). On review of the brief concept note, the committee requested a more detailed, more thoroughly researched proposal for its consideration.

Recommendations
1. The CGS team should develop a full proposal for the establishment of CGS as a Public Private Partnership (PPP) company. In recognition of the technical knowledge required for this task, FIP funds should support the hiring of a consultancy to draft a detailed proposal for the PPP model, outlining the governance arrangements and operating model, and identifying equity shareholders from the banking sector.
2. The CGS team should hire the necessary resources to investigate the reasons for low default rates among CGS-backed loans and the dominance of HBL as a CGS partner bank.
3. In the context of an uptick in utilisation, CGS should develop a more targeted approach, offering higher guarantee cover for marginalised groups (e.g. under collateralised firms, women-owned firms, and firms located in KPK and Baluchistan).
4. SBP should seek to better understand barriers to use for the 2% TA offer and present its findings to the CGS technical committee.
5. DFID should maintain close engagement with the World Bank team that is designing a Financial Inclusion and Infrastructure loan Programme (FIIP) which is interested in providing financial support to CGS.
Output Title	Improved enabling environment and intellectual infrastructure for access to finance to agri and rural sectors
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 Number of mechanisms and academic centres developed to support the financial architecture for SME finance in Pakistan	3	3
3.2 Number of pilots completed through FICF (Financial Inclusion Challenge Fund) funds for new products and models	11	12
3.3 Level of consumer protection and empowerment in microfinance industry	Microfinance pricing transparency information disseminated to clients	Microfinance pricing transparency information disseminated to clients
3.4 Number of MFPs integrated within the payment ecosystem through Micro Payment Initiative (under PMN AG)	AG Signed with PMN to initiate this work	AG signed with PMN

Key points

This output tracks the number of institutions established to provide learning and research on topics such as Islamic Finance for the finance industry in Pakistan; consumer protection initiatives, and the number of pilots under FICF to improve the scope and reach of financial services in Pakistan. The output has scored an A+ having slightly exceeded the target for indicator 3.2 relating to pilots completed, and having met all other targets.

Output 3.1
Three Centres for Excellence in Islamic Financing were established across three provinces over the last year. These centres are housed in the Institute for Business Administration in Karachi, Sindh; the Lahore University for Management Sciences in Punjab, and the Institute for Management Sciences in Peshawar, KPK. All three centres are now offering graduate and post-graduate courses in Islamic Financing, alongside customised executive programmes and conferences for the banking sector. This is important as FIP-funded research on the subject identified that the most commonly reported factor contributing to the 18% incidence of voluntary financial exclusion was religion[30]. Further analysis underlined that a dearth of qualified professionals was a key barrier for growth in this sector. These centres therefore represent an important source of skilled professionals in this underexploited sub-sector.
[30] Knowledge, Attitude and Practice of Islamic Banking in Pakistan, Edbiz, SBP/DFID, 2014

The other ‘infrastructure’ item captured under this indicator and anticipated for future years is the new Anti-Money Laundering data centre in the independent Financial Monitoring Unit (FMU). Despite delays in procurement and shipping, the required hardware for the centre arrived at FMU’s Karachi base in September 2016 and the centre is on track to be formally launched by the end of 2016.

Output 3.2
A cumulative total of twelve pilots have been completed under the Financial Inclusion Challenge Fund, exceeding the target for this year. These pilots spanned initiatives related to both financially inclusive Government to Person (G2P) Payments (the focus of the first challenge fund launched in 2011) and agribusiness (the focus of the second challenge fund launched in 2014). An example from each round is provided below:
- The Employees’ Old-Age Benefits Institution (EOBI)[31] was awarded a grant to integrate its pension system with networks/transaction points of pension delivery agents such as banks. The project reached closure this year with both the Institution and its pensioners benefitting: pensioners can now withdraw pensions from any of the participating banks in Pakistan and the EOBI now has the ability to reconcile its accounts electronically.
  [31] A semi-autonomous institution which manages implementation and enforcement of the EOBI act which extends old-age benefits to insured persons or their survivors. The EOBI has registered more than 100,000 employers and provides coverage to more than 6 million employees. Currently, the number of pensioners exceeds 500,000. This act is applicable to all private sector firms.
- Faysal Bank was awarded a grant to test a “Rural Banking Franchising Model” by using third party service providers for extending lending in unbanked areas.  This project additionally developed an online loan application system to improve the turnaround time for its agri loans. This system has substantially reduced the turnaround time from loan submission to approval to 5 days against the previously reported 10-12 days.

Output 3.3
Consumer protection is a critical pillar of FIP’s work. The presence of responsible finance and client protection initiatives not only protects consumers from exploitation but it ensures that the industry expands while proactively managing delinquency risks. FIP has supported the Pakistan Microfinance Network (PMN) to undertake consumer protection initiatives through client awareness; basic financial literacy; pricing transparency; social performance data collection and analysis; promotion of social audits and ratings, and the development of a grievance redressal mechanism.

This year, in line with targets, the findings of the pricing transparency initiative were uploaded on the MFtransparency website, freely available for anyone to access[32]. Moreover, all the organisations that reported the pricing data were issued a seal of transparency by MFtransparency which some have displayed on their websites.
[32] http://www.mftransparency.org/microfinance-pricing/

Output 3.4
DFID Pakistan signed an Accountable Grant (AG) with PMN in August 2016. The AG not only supports PMN’s core work in knowledge dissemination, consumer protection and thought leadership but also provides funding for ‘digitising microfinance’. This work relates to the development of a system where electronic payments and settlement can happen across a network of institutions. This is critical at a time when the number of branchless banking accounts is increasing at an accelerated rate; the number of branchless banking accounts in the country is now well over 15 million[33] (from a base of 0 when FIP launched in 2008).
[33] Branchless Banking Quarterly Newsletter, SBP Issue 18, Q4 2015 (this is the latest report published at the time of writing this Annual Review).

Recommendations

1. SBP and DFID should develop communications products to highlight significant achievements and lessons learnt under FICF and the TA components. For DFID, this may include online ‘insight’ articles, knowledge sessions at the country office level and with the Private Sector Development cadre.
2. DFID should develop and implement a work plan to respond to recommendations contained within the Due Diligence Assessment of PMN which was completed and agreed with PMN’s senior management in advance of signing the AG. While the assessment revealed strong organisational systems and capacities overall, PMN has been recommended to develop policies and manuals on fraud, corruption and bribery, conflicts of interest, Human Resources (HR) and procurement.
3. Instigate quarterly review meetings with PMN to monitor progress and discuss developments in the microfinance sector.
4. Make arrangements for the launch of FMU’s Anti-Money Laundering data centre for November 2016. As the only active project across Her Majesty’s Government (HMG) that directly addresses the requirements of the Financial Action Task Force (FATF), it has support from the most senior levels in the Pakistan government.

Output Title	Efficient transition to NFIS priorities
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
4.1 Number of meetings held under NFIS Governance Structure / a) NFIS Steering Committee Meetings / b) NFIS Technical Committee Meetings	a) 2 Steering Committee meetings / b) 14 Technical Committee Meetings	a) 1 Steering Committee meetings / b) 14 Technical Committee Meetings
4.2 % of MCGF funds allocated to NFIS priorities	50%	0% / 100% (no funds released from MCGF)
4.3 Exit Strategy for FIP executed	Roadmap / Map of Options for FIP funds developed	Draft version of map of options developed

Key points

This output measures progress to winding down MCGF and putting in place the governance and processes to operationalise the National Financial Inclusion Strategy (NFIS). When MCGF ceases operations, existing guarantees will mature releasing funds for re-profiling under NFIS. It is anticipated that by June 2017 as much as PKR 1.7 billion (£12.5 million) could be available for NFIS priority initiatives until FIP's close in 2020, with further funds flowing from MCGF in subsequent years. It is therefore critical that the governance and processes for robust scrutiny of NFIS proposals and efficient redeployment of funds are in place.

Output 4.1
Since the start of this review period there has been one meeting of the Steering Committee in February 2016, coinciding with the visit of the United Nations Secretary General’s Special Advocate for Inclusive Finance for Development, Queen Máxima of the Netherlands. This catalysed the establishment of the seven NFIS Technical Committees relating to the priority areas outlined in the Strategy, namely (1) Digital Financial Services and Payment Systems (2) SME Finance (3) Micro, Agriculture and Housing Finance (4) Islamic Finance, (5) Insurance (6) Pensions, and (7) Financial Literacy and Consumer Protection. Since the last Annual Review, the Technical Committees have each met twice, totalling 14 meetings over the reporting period.

Output 4.2
The timing for the launch of the Pakistan Microfinance Investment Company (PMIC) has meant that this target was not met. When the logframe was updated this year it was anticipated that PMIC would already be operational with some funds released from MCGF. However, PMIC is now due to start operations in October 2016, beyond the scope of this Annual Review. It is important to note that the operations of PMIC were beyond the control of SBP and other FIP partners so this does not directly reflect the performance of FIP.

Output 4.3
The target relating to execution of the ‘Exit Strategy’ or ‘Transition Strategy’ for FIP has not been fully met. With the initiation of NFIS, SBP has collated and shared the list of proposals put forward by the NFIS Technical Committees which can be considered options for reprofiling. However, SBP has not developed a Transition Strategy with a detailed map of options despite the importance of this document for stewardship of DFID funds over the next four years of the programme. This can be partly explained by the slow start to the establishment of NFIS structures and systems, and partly explained by resourcing constraints within the NFIS Secretariat.

In recent months the DFID team has been working closely with SBP to agree on the technical requirements and organisational mechanisms through which NFIS funds will be reprofiled. These plans need to be formally expressed in a work plan which is approved by FIP’s Steering Committee.

Recommendations
1. SBP should develop a detailed work plan for NFIS transition agreed by the FIP Steering Committee by December 2016. This plan should set out how SBP will reprofile FIP funds to NFIS, to which timeline, and what the implications are in the event that funds are not effectively re-allocated.
2. SBP should convene a working session with donors operating in the financial inclusion space to agree on terms of reference and operating norms for an NFIS Donor Group by November 2016. This is in line with recommendations made at the last FIP Steering Committee.
3. SBP should provide clarity on the staffing arrangements of the NFIS Secretariat and ensure that it has sufficient resources to undertake its critical functions relating to the coordination and monitoring and evaluation of NFIS activities by December 2016.
4. SBP should ensure that fully costed proposals developed by the NFIS Technical Committees are first directed to the FIP TA committee for potential funding review, before receiving formal approval by the NFIS Steering Committee.
5. In order to develop fully detailed and costed proposals relating to NFIS priorities, SBP should hire an entity to function as a procurement agency for consultancy support on proposal development by December 2016.
6. As a contingency, DFID should agree with DFID’s Procurement and Commercial Department a mechanism for receipt of unspent funds under FIP in the event that SBP is unable to effectively reprofile FIP funds to NFIS priorities by June 2017.
7. DFID should immediately instigate monthly review meetings with SBP in recognition of the time sensitive nature of progress on the transition from MCGF to NFIS.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

FIP is an innovative programme which leverages public and private funds to provide equitable and efficient financial services to the poor. The cost drivers for the programme are calls on the two guarantee facilities and utilisation of the TA and challenge funds.

There is no external project management cost to DFID as SBP charges no administration fee for running the FIP Secretariat. Typically, a programme of this nature could expect to spend 5-10% of total funds on administration. Thus, SBP’s absorption of these costs represents a significant saving of up to £5 million. Further, there have been no defaults on loans in MCGF and negligible defaults under CGS which means that the guarantees were not called upon to the extent anticipated. As the funds used to provide the guarantees were invested, they have earned interest. Taken together these factors make FIP a very high value for money programme.

Guarantee Facilities

MCGF (£15 million) has resulted in commercial banks’ lending PKR 20 billion (equivalent of £147 million)[34] to microfinance providers. This amount is almost ten times DFID’s investment. The operational cost is minimal and is borne by SBP. There have been no calls on the guarantee funds to date[35].
[34] £1 = PKR 136
[35] It is worth noting that economic analysis would consider all costs, regardless of who incurs them. Thus, the fact that SBP does not charge DFID a fee does not mean that no costs are incurred.

Similarly, FIP’s £13 million CGS for small and rural enterprises has resulted in commercial banks’ lending to 22,909 small and rural enterprises. There have been few defaults and therefore calls on the guarantee have amounted to just PKR 14.5 million (equivalent £107,000) which is a relatively small amount. Again, operational costs are low and borne by SBP.

Further, the total funds held by SBP (£28 million) for both the MCGF and CGS guarantees are invested in risk-free securities and have accrued around £18.2 million[36] in interest since FIP’s inception.
[36] This is a direct conversion of PKR into GBP so this captures both the interest gains and the foreign exchange gains from the weakening of the pound (GBP) against the rupee (PKR) from June 2016.

Due to the nature of FIP’s design:
- MCGF has supported microfinance clients to gain access to over £147 million in loans at no programme cost to DFID; indeed with a net gain for DFID of £9.4 million.
- CGS has supported 22,909 SMEs to gain access to a loan at no programme cost to DFID; indeed with a net gain to DFID of £8.8 million.

Technical and Institutional Support

The three other components of FIP span the Institutional Strengthening Fund (closed to new submissions in 2014); the Financial Inclusion Challenge Fund, and a TA fund. The cumulative results of these three funds are summarised below:

The Institutional Strengthening Fund used £4.4 million to provide capacity building grants to microfinance providers, including support to two microfinance non-governmental organisations (NGOs) to transform them into licensed banks. The fund has additionally supported the Pakistan Microfinance Network (PMN) which acts as a policy and knowledge hub for the sector.

The Financial Innovation Challenge Fund has used £4.7 million to achieve a range of innovations relating to government to person (G2P) payments, agri-financing and Islamic finance.

FIP’s TA component has used approximately £6 million to build the broader enabling environment for access to finance, spanning a range of policies, legal reforms, infrastructure developments, research and networking. This has included the establishment of the Credit Information Bureau for the microfinance sector; the drafting of the Secured Transactions Law, and the installation of Anti-Money Laundering software in Pakistan’s Financial Monitoring Unit.

Across these three components, FIP has successfully invested in mobile banking in Pakistan. FIP provided grant funding for the establishment and early operations of EasyPaisa, the first mobile banking technology solution in the country, and held investment dialogues to help forge industry partnerships between banks and telecom providers, as well as providing innovation grants to a range of other mobile banking service providers. FIP is considered to have played an important role in facilitating the sector’s growth from 0 to 15 million accounts between 2008 and 2016[37].
[37] Branchless Banking Newsletter, Issue 18, State Bank Pakistan, October December 2015, the latest published report.

Economy

In assessing FIP’s performance against measures for economy implicit in the Project Memorandum, the programme is in line with expectations and in some cases exceeds them. The following economic measures were expected and have been fulfilled:

- SBP to provide administration and management at no direct cost to DFID. This has occurred for the duration of the project.
- SBP to provide additional funds to the project to at least the value of £1.5 million. SBP contributed PKR 300 million (£2.2 million) to the project for CGS.
- DFID to provide £50.25 million in grant funds to achieve the aims of the programme. £43 million has been spent to date and there have been no requests for additional funding for FIP.

One area that has exceeded the expected level of economy is on the funds remaining with FIP at this stage in the programme. It was anticipated that there would be some funds unused from the guarantee facilities that would be reprofiled to the other components of FIP, such as the TA component. However, it was expected that these funds would be needed for calls on the guarantees; after all, the non-performing loans to loans ratio of SME financing stands at 25%[38] in Pakistan so this could be reasonably anticipated for CGS. However, this has not occurred. As referenced above, calls on CGS have amounted to PKR 14.5 million (£107,000)[39], amounting to less than 0.01% of the guarantee funds, and there have been no calls on MCGF. In addition, these guarantee funds have been invested in Treasury bills and have earned interest. As a result, FIP is in the enviable position of having more funds than it started with, allowing it to support the next generation of services and market development through the NFIS.
[38] Quarterly SME Finance Review, IH and SME Department, State Bank Pakistan, December 2015
[39] As of 30th June, 2016, PKR 14.5 million have (£107,000) been claimed by the banks under the guarantee facility against the default of 114 cases booked under the scheme. However, out of that amount, PKR 6.02 million (£44,000) have been recovered.

Efficiency

In assessing FIP’s performance against measures for efficiency, there is a more nuanced picture.

On the one hand, FIP has not achieved the headline target: “Under the FIP, the Government of Pakistan has set a target of reaching out to 3 million microfinance borrowers by 2010 and 5 million by 2012”[40]. On the other hand, if considered as a cost per output or outcome, FIP has contributed to progress (an increase in microfinance clients from 1.2 million in 2008 to 4 million in 2016) at no extra programme cost to DFID. The £15 million for MCGF has not spent any funds – indeed the facility has grown in size. In addition, FIP has achieved its goal “to transform the microfinance sector from its reliance on state subsidies to market based, sustainable and inclusive financial services”[41]. As the Project Memorandum noted “It’s a big step for the Government of Pakistan” and yet this has been achieved through FIP. Importantly, this achievement has prepared the ground for the next generation of market-based growth which will be taken over by the Pakistan Microfinance Investment Company (PMIC) later in 2016.
[40] Financial Inclusion Programme, Project Memorandum, DFID, June 2008
[41] Financial Inclusion Programme, Project Memorandum, DFID, June 2008

Assessment of whether the programme continues to represent value for money

FIP has continued to demonstrate strong value for money for DFID over the years as the measures on economy and efficiency have continued to improve.

Quality of financial management

The quality of financial management was maintained on the basis of compliance to the reporting formats agreed with DFID. Financial management to date at SBP has been robust as indicated by the periodic independent audit reports and DFID reviews. Audit reports have been satisfactory and covered significant aspects of financial controls and compliance with rules and effective utilisation of public resources. In addition, the overall programme expenditure is acceptable against all components. These systems will continue to be maintained and strengthened further.

Moreover, SBP is covered by a Fiduciary Risk Assessment which was undertaken in August 2015. The assessment concluded that SBP provides high assurance of an effective internal control structure, with monitoring mechanisms in place and operational capacity to mitigate any fiduciary risk in FIP’s programme implementation.

For the PMN Accountable Grant, payments are clearly structured so that all the money spent is accounted for before any further money is released to PMN. PMN provides detailed project financial reports on a quarterly basis that set out actual expenditure to date against the approved project budget and a quarterly forecast expenditure for the calendar and financial year (ending 31st March). Further, based on the Due Diligence assessment undertaken on FIP this year, we are confident that their financial management systems are sound. Any grants received from FIP, managed by the SBP do not constitute part of PMN’s counterpart financing commitment.

Date of last narrative financial report	30/08/2016 Covering period ending June 2016
Date of last audited annual statement	24/02/2016 For the Year Ended June 2015

E: RISK

Overall risk rating:  Major

The programme’s overall risk rating is ‘major’, reflecting the importance of ensuring a smooth transition as MCGF winds down; funds are reprofiled to NFIS, and CGS transitions into a new PPP model. Outputs 2 & 4 have been rated ‘major’ respectively and will be monitored closely.

Output 1 – Credit flowing to MFBs / MFIs (Microfinance Banks and Microfinance Institutions) from MCGF	Moderate
Output 2 – Increase in loan products utilised by SMEs across key sectoral clusters	Major
Output 3 – Improved enabling environment and intellectual infrastructure for access to finance	Minor
Output 4 – Efficient transition to NFIS priorities	Major

The most pressing risks in the upcoming period are institutional, as follows:
- Slow development of costed NFIS proposals and delays in the approval process. This will be mitigated by hiring an external agency to procure consultants to develop detailed proposals. DFID and SBP have agreed on a structure for reviewing and approving the proposals in an efficient and timely manner. Under the proposed structure, proposals will be reviewed by NFIS technical committees and shared directly with the FIP TA Committee for shortlisting, following which they will be approved by the NFIS Steering Committee. DFID should work closely with SBP to ensure effective functioning of NFIS governance and processes as detailed under the commentary to output 4.
- Limited SBP experience in designing and managing a PPP which could adversely impact the future of CGS beyond FIP. DFID suggests hiring external consultants to design the CGS PPP model and encourages study tours for the SME Department staff to develop technical capacity and to learn from successful PPP models globally. SBP will need dedicated resources to set up and operationalise the PPP. This effort and the time it will take should not be underestimated.
- Weakening of partnership with SBP due to potential changes within senior management at SBP or the wind down of MCGF. To mitigate against this, it will be important for DFID and SBP to ensure that NFIS takes root such that it continues to play a central role in increasing access to financial services for the poor and marginalised.

Additional macro challenges related to an economic downturn affecting the SME and microfinance sector or potential instability in the run-up to the 2018 elections are tracked within FIP’s risk register and are monitored regularly.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

SBP operated to the agreed timelines in the previous year. While the majority of activities under the TA Fund and Financial Inclusion Challenge Fund (FICF) have been on track, SBP efforts on FIP transition into NFIS picked up only in the latter part of the year. Despite that, SBP has made good progress on designing and establishing the overall NFIS structure. The challenge of re-profiling MCGF funds to priority activities under NFIS over the 2016-20 period will remain in the coming year.

Performance of partnership(s)

SBP continued to demonstrate strong ownership of programme objectives and activities, engaging with financial service providers on all programme components. MCGF and CGS performed well because of SBP’s credibility and its commitment to facilitate financial inclusion in Pakistan. The majority of projects under the TA component have been completed and SBP continues to monitor the on-going projects closely, sharing progress on a quarterly basis. SBP’s performance on FIP’s transition to NFIS was initially slow but picked up during the latter part of the year as NFIS structures fell into place.

DFID signed an Accountable Grant (AG) with PMN in August 2016. The AG will support PMN’s core work in knowledge dissemination, consumer protection and provides funding for digitising microfinance. DFID completed a Due Diligence assessment of PMN prior to signing of the AG and based on the recommendations of the exercise, a work plan has been agreed with PMN to monitor progress.

Asset monitoring and control

The management and monitoring of programme assets is satisfactory. There are no fixed assets beyond the funds assigned to guarantee facilities and SBP reports on a quarterly basis to DFID on the status of these funds.

G: CONDITIONALITY

Partnership principles assessment

The new Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division at the federal level and text is shared every six months. The PPA was discussed most recently on 18 July 2016. The PPA sets out the Government of Pakistan’s commitment to the four partnership principles as demonstrated through its policies and actions: reducing poverty and achieving the Millennium Development Goals, now the Sustainable Development Goals. These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

DFID Pakistan’s assessment is that the government is demonstrating a credible commitment to the four principles. DFID can therefore continue to plan and deliver sizeable programming on-budget. Progress towards the Sustainable Development Goals and poverty reduction is proceeding, albeit slowly, given the challenges. Progress on human rights is mixed. On public financial management and anti-corruption the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels. Elite capture and its influence is often cited as a concern. Recent pressures on international non-governmental organisations (iNGOs) have led to a downturn on domestic accountability; but there is cautious optimism about a new registration process for iNGOs.

The majority of the UK’s investment in FIP is in non-sector budget support financial aid and technical assistance to the Pakistan Microfinance Network and the Financial Monitoring Unit[42]. Given the nature of FIP’s largest instruments (credit guarantees), the £40.75 million of financial aid has been disbursed and has achieved what it set out to achieve.
[42] The TA provided to support the Financial Monitoring Unit was channelled through an Accountable Grant with the United Nations Office for Drugs and Crime (UNODC) as the only provider globally of the goAML software. Owing to SBP’s procurement rules, the FIP Secretariat was unable to sign a contract directly with UNODC, hence a direct relationship with DFID.

H: MONITORING & EVALUATION

Monitoring
DFID receives a quarterly progress report from SBP which provides an update on all programme components as well as the financial position including the status of interest profits on funds held under the two guarantee schemes MCGF and CGS. This report typically comes six to eight weeks after the reporting period.

In addition to the Exchange of Letters (for non-budget financial aid) with SBP, DFID directly manages two other partnerships under FIP. First, a Memorandum of Understanding (MOU) with the United Nations Office on Drugs and Crime (UNODC) to deliver the Anti-Money Laundering data centre in FMU. For this, DFID receives a quarterly progress report from UNODC and currently holds monthly technical committee meetings to ensure close management of the project in its final critical stages. Second, DFID has recently signed an AG with the Pakistan Microfinance Network (PMN). The agreement requires PMN to deliver quarterly reports and arrange quarterly review meetings with DFID, the first of which is scheduled for October 2016.

Evidence and evaluation

There is a vibrant global debate as to the effects of microfinance and whether it offers an effective avenue out of poverty, leads to high wages, higher consumption, or whether it exploits poor people, leading to over indebtedness. Systematic reviews undertaken by DFID centrally have highlighted the mixed evidence on the topic, noting that microfinance is a complex industry, implemented in different development contexts and as a result “almost all impact evaluations of microfinance suffer from weak methodologies and inadequate data”.

This is an unsatisfactory conclusion. FIP has therefore invested in additional evaluations within the Pakistan context specifically. The is most notable through the Microfinance Impact Evaluation conducted by the Lahore University for Management Sciences (LUMS) commissioned under FIP’s TA component. This evaluation will measure the quantitative impact of micro-credit on consumption expenditure; schooling, women’s empowerment, assets and employment generation. The study will also identify practices that mediate the success and failure of micro-credit. The findings are expected to be finalised in the coming year.
Annex A: Microfinance Credit Guarantee Facility Utilisation, FY 2015-16

S #	MFB/MFI	Lender	Amount Sanctioned	Tenor	Option	Issuance Date	Max. Exposure	Current Outstanding Amount	Exposure on MCGF Funds
1	Tameer MFB	BAF	50.0	5 years	40% Partial	5-Oct-10	20.0	Loan Repaid	NIL
2	Tameer MFB	KASB	100.0	3.5 Years	40% Partial	5-Oct-10	40.0	Cancelled	NIL
3	Tameer MFB	JS Bank	100.0	3 Years	40% Partial	3-Nov-10	40.0	Loan Repaid	NIL
4	Kashf Foundation	MCB Bank	225.0	2 Years	40% Partial	14-Dec-10	90.0	Loan Repaid	NIL
5	NRSP	Consortium (HBL, NBP,ABL,MCB,UBL,AKBL,NIB & FBL)	1,200.0	3 Years	25% First Loss	29-Jun-10	300.0	Loan Repaid	NIL
6	Tameer MFB	ABL	100.0	5 years	40% Partial	28-Feb-11	40.0	Loan Repaid	NIL
7	Tameer MFB	Standard Chartered	600.0	2 Years	25% First Loss	17-Mar-11	150.0	Loan Repaid	NIL
8	Kashf Foundation	Silkbank Ltd	150.0	1 Year	40% Partial	5-May-11	60.0	Loan Repaid	NIL
9	Tameer MFB	MCB Bank	100.0	5 Years	25% First Loss	26-May-11	25.0	10.0	10.0
10	Tameer MFB	NBP	200.0	5 Years	40% Partial	17-Aug-11	80.0	25.0	10.0
11	Khushhali Bank	Soneri bank Ltd	100.0	3 Years	40% Partial	21-Sep-11	40.0	Loan Repaid	NIL
12	Tameer MFB	UBL	300.0	3 years	25% First Loss	14-Nov-11	75.0	Loan Repaid	NIL
13	Tameer MFB	FBL	100.0	5 years	25% First Loss	14-Nov-11	25.0	22.2	22.2
14	Tameer MFB	BoP	50.0	3 years	25% First Loss	10-Jan-12	12.5	Loan Repaid	NIL
15	Kashf Foundation	JS Bank	300.0	3 Years	40% Partial	18-Apr-12	120.0	Loan Repaid	NIL
16	NRSP MFB	JS Bank	500.0	5 years	40% Partial	4-Jun-12	200.0	150.0	60.0
17	Kashf Foundation	Silkbank Ltd	150.0	1 Year	40% Partial	27-Jun-12	60.0	Loan Repaid	NIL
18	NRSP MFB	Standard Chartered	650.0	2 Years	25% First Loss	20-Jul-12	162.5	Loan Repaid	NIL
19	Kashf Foundation	UBL	300.0	3 Years	40% Partial	10-Aug-12	120.0	Loan Repaid	NIL
20	NRSP MFB	POICL	100.0	5 years	40% Partial	12-Sep-12	40.0	40.0	16.0
21	Tameer MFB	BoP	50.0	3 years	25% First Loss	17-Sep-12	12.5	Loan Repaid	NIL
22	Tameer MFB	Redeemable Capital	500.0	13 months	40% Partial	25-Sep-12	200.0	Redeemed	NIL
23	Tameer MFB	Redeemable Capital	500.0	2 years	40% Partial	25-Sep-12	200.0	Redeemed	NIL
24	NRSP	BoP	500.0	1 year	25% First Loss	28-Dec-12	125.0	Loan Repaid	NIL
25	NRSP MFB	AKBL	400.0	5 years	40% Partial	28-Dec-12	160.0	160.0	64.0
26	Kashf Foundation	AKBL	400.0	3 years	40% Partial	29-Apr-13	160.0	66.7	26.7
27	Khushhali Bank	Soneri bank Ltd	300.0	4 years	40% Partial	14-May-13	120.0	Withdrawn	NIL
28	NRSP	BoP	500.0	1 year	25% First Loss	27-Mar-14	125.0	Loan Repaid	NIL
29	NRSP MFB	POICL	800.0	5 years	40% Partial	12-May-14	320.0	560.0	224.0
30	Kashf Foundation	JS Bank	400.0	4 years	40% Partial	26-May-14	160.0	327.3	130.9
31	Kashf Foundation	Silkbank Ltd	300.0	2 years	40% Partial	26-May-14	120.0	75.0	30.0
32	Kashf Foundation	UBL	300.0	3 years	40% Partial	11-Jun-14	120.0	150.0	60.0
33	FINCA MFB	JS Bank	400.0	1 year	40% Partial	8-Sep-14	160.0	Loan Repaid	NIL
34	Khushhali Bank	UBL	500.0	3 Years	40% Partial	12-Sep-14	200.00	300.0	120.0
35	FINCA MFB	NIB Bank	200.0	1 Year	40% Partial	15-Dec-14	80.0	Loan Repaid	NIL
36	NRSP	JS Bank	500.0	1 Year	40% Partial	30-Dec-14	200.0	Loan Repaid	NIL
37	NRSP	JS Bank	500.0	3 Years	40% Partial	30-Dec-14	200.0	333.4	133.4
38	Khushhali Bank	AKBL	400.0	3 Years	40% Partial	30-Dec-14	160.0	320.0	128.0
39	NRSP	BoP	500.0	1 year	25% First Loss	27-Mar-15	125.0	Loan Repaid	NIL
40	FINCA MFB	UBL	200.0	1 year	40% Partial	23-Apr-15	80.0	200.0	80.0
41	Khushhali Bank	Soneri bank Ltd	300.0	3 Years	40% Partial	6-May-15	120.0	300.0	120.0
42	BRAC	HBL	500.0	3 Years	60% Partial	6-May-15	300.0	500.0	300.0
43	ASA Pak	UBL	225.0	3 Years	40% Partial	5-Jun-15	90.0	225.0	90.0
44	NRSP MFB	Consortium (SBL, Pak Kuwait & Pak China)	900.0	3 Years	40% Partial	11-Jun-15	360.0	750.0	300.0
45	NRSP	UBL	300.0	3 Years	40% Partial	22-Jun-15	120.0	250	100.0
46	Kashf Foundation	AKBL	350.0	3 years	40% Partial	22-Jun-15	140.0	350	140.0
47	Khushhali Bank	JS Bank & AKBL (Syndicate)	1,500.0	4 years	40% Partial	30-Nov-15	600.0	1500	600.0
48	Kashf Foundation	UBL	500.0	3 years	40% Partial	4-Feb-16		500	200.0
49	FINCA MFB	NIB Bank	200.0	1 year	40% Partial	6-Apr-16	80.0	200.0	80
50	NRSP	JS Bank	500.0	1 year	40% Partial	6-Apr-16	200.0	500.0	200
51	NRSP	BoP	500.0	1 year	25% First Loss	10-May-16	125.00	500.0	125.00
52	Kashf Foundation	BAF	200.0	2 Years	25% First Loss	23-May-16	50.00	200.0	50.00
53	U MFB	POICL	500.0	3 Years	60% Partial	10-Jun-16	300.00	500	300.00
	Sum		20,000.00				7,412.5	8,531.2	3,520.1

Annex B: MFPs Tiering Criteria for MCGF

	MFBs/ MFIs (Tier I)	MFBs/ MFIs (Tier II)
Institutional Profile	Mature, financially sustainable, and large MFPs that are operational for 5 years or more	Small or medium sized, slightly less mature MFPs that are operational since 3 years or more
Size (Gross Loan Portfolio	> PKR 3,000 million	PKR 500 million or more
Sustainability	i) Positive RoA (Return on Assets) for the last year AND / ii) PAR (Portfolio at Risk) > 30 days should be < 10 %	i) Improving trend in RoA in last 3 years and RoA in last year should not be <-10% AND / ii) PAR > 30 days should be < 10 %
Transparency	Audited financial statements for at least the last 3 years	Audited financial statements for at least the last 3 years

Further details and the revised MCGF Guidelines issued by SBP are available at SBP’s website:
 http://www.sbp.org.pk/acd/2015/C1.htm
Annex C: Credit Guarantee Scheme FY 2015-16

Sr. #	Bank	Allocated Limit	O/S Amount as of 31-03-16 for all loans sanctioned up to 31-12-15	Available Limit	Sanctioned Amount during Q1-CY16			Number of Loans Sanctioned during Q1-CY16			Fresh Guarante-e Request
					General	Sector Specific	Total Sanctio-ned	General	Sector Specif-ic	Total Sanctio-ned
A	B	C	D	E	F	G	H	I	J	K	L = H * 40%
1	ADVANS	100.0	32.6	67.4	-	21.3	21.3	0	87	87	8.5
2	Allied Bank	450.0	69.5	380.5	-	3.0	3.0	0	1	1	1.2
3	Askari	30.0	11.0	19.0	-	-	-	0	0	0	-
4	Bank Alfalah	430.0	100.1	329.9	38.6	20.8	59.4	18	11	29	23.7
5	Bank of Khyber	500.0	181.0	319.0	46.0	-	46.0	55	0	55	18.4
6	Burj Bank	150.0	31.3	118.7	-	4.8	4.8	0	7	7	1.9
7	Faysal Bank	400.0	139.2	260.8	7.2	-	7.2	11	0	11	2.9
8	FINCA	100.0	73.4	26.6	-	11.4	11.4	0	39	39	4.6
9	Habib Bank	3,200.0	168.6	3,031.4	1,441.8	-	1,441.8	2,530	0	2,530	576.7
10	MCB	1,850.0	1,005.1	844.9	25.9	92.5	118.3	37	54	91	47.3
11	Meezan Bank	400.0	13.1	386.9	5.0	-	5.0	2	0	2	2.0
12	National Bank	300.0	120.3	179.7	2.0	15.5	17.5	1	6	7	7.0
13	Sindh Bank	100.0	-	100.0	2.0	7.0	9.0	1	2	3	3.6
14	Soneri	250.0	-	250.0	-	-	-	0	0	0	-
15	Tameer	200.0	51.3	148.7	-	148.5	148.5	0	566	566	59.4
16	UBL	21.0	8.0	13.0	-	-	-	0	0	0	-
Total		8,481.0	2,004.5	6,476.5	1,568.4	324.8	1,893.2	2,655	773	3,428	757.3