## Log Frame
PROJECT NAME | Punjab Economic Opportunties Programme - 113484
IMPACT | Impact Indicator 1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
Reduction in poverty in the PEOP districts | Poverty Headcount Ratio ‘Poor’ defined as those with consumption levels below $ 2 a day in the PEOP districts | Planned | 37.97% | Not Required |  |  |  | Reduction of 5% from baseline (i.e. 32.97%)
|  | Achieved |  | ]
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Impact Indicator 2 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Poverty Gap Ratio for the PEOP districts | Planned | 9.7 | Not Required |  |  |  | Reduction of 1% from baseline (i.e.8.7%)
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Impact Indicator 3 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Vulnerability Gap Ratio for the PEOP districts (‘Vulnerable’ defined as those with consumption levels between $2 and $4 a day). | Planned | 14.5 | Not Required |  |  |  | Reduction of 1% from baseline (i.e.13.5%)
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
OUTCOME | Outcome Indicator 1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumptions
Poor and vulnerable people actively engaged in productive economic activities in the 4 selected PEOP districts. | a) Per capita household consumption in the target population and b) per capita beneficiary consumption (Measured through RCT impact evaluation as the gap between treatment and control households based on tracker, midline and end line surveys] | Planned | Will be the same on average at baseline |  |  | a) 13% b) 5.5% | a) 14% b) 6.5% | a) 15% b) 7.5% | 1. The percentage of unemployed males is currently low i.e. at around 7%. 2. Other social factors do not adversely influence female participation in labor force. 3. Growth in regional (south Punjab) and Pakistan does not fall below 2.5 % per annum, generates jobs and returns to skills do not fall drastically. 4. Increase in livestock asset ownership will encourage household level economic activities 5. Increase in access to veterinary and extension services will improve animal health and help reduce economic losses 6. The law and order situation does not deteriorate.
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Outcome Indicator 2 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Index of Wellbeing (Measured through RCT impact evaluation as the difference between treatment and control households) [Based on tracker, midline and end line surveys] | Planned | Will be the same on average at baseline |  |  | 0.1 standard deviation increase in treatment versus control households | 0.1 standard deviation increase in treatment versus control households | 0.1 standard deviation increase in treatment versus control households
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Outcome Indicator 3 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Index of State Engagement (Measured through RCT impact evaluation as the difference between treatment and control households) [Based on tracker, midline and end line surveys] | Planned | Will be the same on average at baseline |  |  | 0.1 standard deviation increase in treatment versus control households | 0.1 standard deviation increase in treatment versus control households | 0.1 standard deviation increase in treatment versus control households
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Outcome Indicator 4 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Number of socially and/or economically marginalized women owning at least 1 small ruminant (goats/sheep) for livestock farming | Planned | All female target beneficiaries. |  |  | Increase of 4,000 women owning at least 1 small ruminant |  | Increase of 8,000 women owning at least 1 small ruminant
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Outcome Indicator 5 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Percentage of farmers accessing veterinary and extension services | Planned | As assessed during Phase I of the baseline Household Survey, the district-wise stats for farmers accessing government veterinary and extension services are: Bahawalnagar: 36.89% Bahawalpur: 46.25% Lodhran: 19.34% Muzaffargarh: 39.10% |  |  | Increase in access of farmers to veterinary and extension services by 2.5% | Increase in access of farmers to veterinary and extension services by 5% | Increase in access of farmers to veterinary and extension services by 10%
Achieved
Source: CERP Baseline Surveys, Tracker, Midline and End line Surveys.
| Outcome Indicator 6 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Percentage change in average milk yields amongst beneficiary livestock farmers. | Planned | Milk yields for cows=2.19 liters per day Milk yields for buffalos=2.92 liters per day. This is measured as the total number of liters produced per animal, summed over morning and evening milkings. |  |  | Average milk yields amongst targeted livestock farmers increased by 5%. | Average milk yields amongst targeted livestock farmers increased by 10%. | Average milk yields amongst targeted livestock farmers increased by 20%.
Achieved
Baseline established in 2012: Source: CERP Mid Term and Final Evaluation
INPUTS (£) | DFID (£) 30 million |  | Govt (£) | 25 | Other (£) | 0 | Total (£) 55 | DFID SHARE (%) 54.5
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Sustainable model for funding competitive training delivery | Level of Maturity of PSDF as an innovative model for skills financing | Planned | Nil | PSDF to be established as an independent corporate body | PSDF Funding Model Established and Tested (1st Generation products Tested) | PSDF Model refined for target population (use of research to design 2nd Generation Products) | PSDF consolidates its successful products | PSDF recognized as a successful skills financing model | 1. The turnover rate of PSDF and PIT professional employees is low 2. There are no frequent replacements of Board members.
Achieved
IMPACT WEIGHTING: 8% |  | Source: PSDF Annual Reports, Annual Reviews, Institutional assessment
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Skilled trainees | Number of persons trained in PEOP districts | Planned | 0 | 0 | 10,000 (40% female) | 40,000 (40% female) | 75,000 (40% female) | 80,000 (40% female) | 1. Competing Program with higher incentives are not offered to individuals from the target districts. 2. Adequate training capacity (physical infrastructure and trainers) are available in the market. 3. The turnover rate of PSDF and PIT professional employees is low. 4. There are no frequent replacements of Board members.
Achieved
IMPACT WEIGHTING: 30% |  | Source: PSDF Annual Reports, Annual Reviews, Institutional assessment
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Private Training places mobilized | Percent of private sector places created as a result of PSDF funding | Planned | Nil | 0 | 50% of total PSDF - funded training places | 60% of total PSDF - funded training places | 70% pf total PSDF funded training places | 80% of total PSDF funded training places | 1. Competing Program with higher incentives are not offered to individuals from the target districts. 2. Adequate training capacity (physical infrastructure and trainers) are available in the market.
Achieved
IMPACT WEIGHTING: 6% |  | Source: PSDF Annual Reports, Annual Reviews, Institutional assessment
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Access to yield enhancing practices, better healthcare and better animal nutrition available to livestock farmers | No. of farmers accessing veterinary and extension services, through PEOP | Planned | 0 | 0 | 5,000 farmers accessing veterinary and extension services, through PEOP | 50,000 farmers accessing veterinary and extension services, through PEOP | 100,000 farmers accessing veterinary and extension services, through PEOP | 150,000 farmers accessing veterinary and extension services, through PEOP
|  | Achieved |  |  | Total Farmers: 6,695 (Male: 4,872; Female: 1,823)
Source: PIT Reports; CERP's Assessment and 3rd Party Monitoring Report (where applicable)
| Output Indicator 4.2 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
| No. of animal health professinals and extension workers, trained through PEOP, in the target districts | Planned | 0 | 0 | 0.00 (NOTE: First initiative underway for VA assistants , expected to complete in 2013. Other initiatives for paravets to initiate in 2012-13) | 1,000 animal health professinals and extension workers, trained through PEOP (60% M; 40% W) | 5,000 animal health professinals and extension workers, trained through PEOP (60% M; 40% W) | 6,000 animal health professinals and extension workers, trained through PEOP (60% M; 40% W)
Achieved
IMPACT WEIGHTING: 30% |  | Source: PIT Reports; CERP's Assessment and 3rd Party Monitoring Report (where applicable)
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Livestock asset transfer to primary and secondary beneficiary marginalized women in selected 4 districts | No. of beneficiary women receiving livestock assets, directly or indirectly through PEOP | Planned | 0 | 0 | 0.00 (NOTE: Asset transfer initiative to initiate in 2012-13) | Transfer of livestock assets to 4,000 primary beneficiary women | Note: Since the first cycle is going to take some time and only the second round off springs will be given to secondary beneficiaries, therefore there is no milestone for this year. | Transfer of livestock assets to 8,000 primary/secondary beneficiary women | 1. Community groups will work well together for transfer of benefits from primary to secondary beneficiaries.
Achieved
IMPACT WEIGHTING: 5% |  | Source: PIT Reports; CERP's Assessment and 3rd Party Monitoring Report
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Feedlot fattening of animals for enhancing meat production | Percentage increase in price of fattened animals, measured through difference between treatment and control population | Planned | Village prices (from CERP's Baseline Survey): Young Cow: Rs. 13,000; Young Buffalo: Rs. 16,500; Young Goat: Rs. 2,500 | 0 | 0.00 (NOTE: Feedlot fattening initiative to initiate in 2012-13) | 10% increase in animal price of fattened animals | 10% increase in animal price of fattened animals | 10% increase in animal price of fattened animals | 1. Competing Program with higher incentives are not offered to individuals from the target districts 2. The turnover rate of PSDF and PIT professional employees is low. 3. Lack of awareness and customary practices prevent livestock farmers from engaging in modern productive practices.
Achieved
Source: CERP's Assessment
| Output Indicator 6.2 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
| No. of animals fattened through PEOP | Planned | 0 | 0 | 0.00 (NOTE: Feedlot fattening initiative to initiate in 2012-13) | 20,000 animals | 70,000 animals | 150,000 animals | 1. Competing Program with higher incentives are not offered to individuals from the target districts 2. The turnover rate of PSDF and PIT professional employees is low. 3. Lack of awareness and customary practices prevent livestock farmers from engaging in modern productive practices.
Achieved
IMPACT WEIGHTING: 5% |  | Source: PIT Reports; CERP's Assessment and 3rd Party Monitoring Report
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 7 | Output Indicator 7.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015) | Assumption
Policy and Regulatory Environment | Support to Government of Punjab for skills policy framework | Planned |  |  | Draft Scale up Strategy prepared - Request for TA for policy provided | Scaling up Strategy for PSDF - Request for Technical Assistance for Policy met | Request for Technical Assistance for Policy met | Improved policy and regulatory environment for skills | 1. Government is committed to policy reform
Achieved
Source: PSDF Annual Reports, Annual Reviews, Institutional assessment
| Output Indicator 7.2 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/03/2015)
| Appropriate policies and regulatory framework to enable the private sector to participate in livestock markets (liberalize livestock sale and purchase) | Planned | Rudimentary framework exists for auctioning livestock markets |  | Review of earlier reform work initiated | Review of earlier reform work completed | Regulatory framework drafted and submitted for approval of concerned quarters | Regulatory framework (policy, law, rules) in place and implementation initiated to allow farmers to fetch competitive prices, reflecting quality and weight of animals
Achieved
Source: PIT Reports, Annual Reviews
IMPACT WEIGHTING: 10%
| DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
DFID (FTEs)
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 8 | Output Indicator 8.1 |  | Baseline established 2012 | Milestone 2010-11 | Milestone 2011-12 | Milestone 2012-13 | Milestone 2013-14 | Target (31/10/2015) | Assumption
Knowledge Management & Sharing | Publication and sharing of Reports and Data | Planned | CERP Phase One Baseline HH Survey Reports (Skills and Livestock) Produced | CERP Phase-1 Baseline House Hold Survey Reports (Skills and Livestock) produced and disseminated | CERP Phase Two Baseline HH Survey Reports (Skills and Livestock) Employers Survey Report & Skill Providers Survey Livestock Supply Side Survey Report | RCT Impact Evaluation Reports giving immediate outcomes (Skills and livestock) | Midline RCT Impact Evaluation Report (Skills and livestock) | Final RCT Evaluation Reports Produced (Skills and Livestock) ( By October 2015) | 1. CERP technical input is provided as planned
Achieved
IMPACT WEIGHTING: 6% |  | Source: CERP Data; Operational Data (PSDF and PIT), SECP, donor and government documents, minutes of Board Meetings, News items, Facebook (likes) and blogs
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Note on B69: Sarah Saeed : After Jane's comments, we added a quality factor here. i.e. _-% of trainees to qualify a trade test of an accredited testing body.
Note on B157: Sarah Saeed : Jane wanted a quality indicator here as well. Could be "peer-reviewed reports".
Note on G20: Sarah Saeed : a) 6.5% b) 13%
Note on H20: Sarah Saeed : a)7% b)14%
Note on I20: Sarah Saeed : a)7.5% b) 15%

## Risk Analysis
Outputs | Risk (Description) | Probability (Low/ Medium/High) | Impact (Low/Medium/High) | Aggregate | Overall Risk Rating for an Output
Cross-cutting Risks | Deterioration in law and order situation | Medium | Medium
| Change in provincial boundaries | Low | Medium
| Change in political setup and reduction in political ownership of program | Medium | Low
| Corruption | Low | Medium
| Lack of required Technical and Program Design support needed to undertake successful RCTs to measure impact | Low | Medium
| Severe natural calamities such as floods, droughts, disease outbreak, etc., | Low | High
| Change in funding priorities of donor and government | Low | Medium
Output 1 | The Board of Directors is not given the independence in decision making. | Low | High | Low | Medium
| There are frequent changes in the Board’s Leadership | Medium | Medium | Medium
Output 2 | There is low level of take up of PSDF funded trainings because other skills training programmes in the same region give a very high level of stipend | Medium | High | Medium | Medium
Output 3 | The private and not for profit sector is priced out by the public sector entities in open competition | Low | High | Medium | Low
| Competing Skills Training programmes offer generous terms and rates to training providers on the basis of partnerships rather than open competition | Low | High | Medium
Output 4 | Inadequate supply of vaccines for PIT-related outputs | Low | High | Medium | Low
| Trained paravets do not opt to practice in target districts | Medium | Low | Low
| Willingness to pay of farmers for veterinary services remain low | Low | Medium | Low
| Low adoption of animal husbandry practices | Low | Medium | Low
Output 5 | Animal theft | Low | Medium | Low | Low
| High animal mortality due to disease outbreak, etc. | Low | High | Medium
| Community rifts preventing asset transfer | Low | Medium | Low
Output 6 | Low adoption rate | Low | Medium | Low | Low
| Low willingness to join community farms | Low | Medium | Low
| Low capacity to acquire animals | Low | Medium | Low
Output 7 | Lack of resources for new regulatory framework | Low | Medium | Low | Low
Output 8 | Problems with TC funding | Low | High | Medium | Low