## Sheet1
Final Results of PMDP Logframe (October 2018)
Updated version – Approved December 2017
PROJECT NAME | Palestinian Market Development Programme to strengthen the Private Sector in the Occupied Palestinian Territories (OPTs)
IMPACT RESULT | Impact Indicator-1a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone | CY 2016 Milestone | CY 2017 Milestone | CY 2018 Milestone | Target (date)
R1: Improved private sector-led growth in OPTs | Real GDP Growth |  | Planned |  |  |  | 8.2% | *3.8%
|  |  | Achieved | - | -2.5% |  | 3.5% | *4.7% | 3.1% |  | 3.1%
Source
PCBS:http://www.pcbs.gov.ps/site/512/default.aspx?tabID=512&lang=en&ItemID=1565&mid=3171&wversion=Staging
*http://www.pcbs.gov.ps/Portals/_Rainbow/Documents/Annual-ForecastingE.htm
http://www.pcbs.gov.ps/site/512/default.aspx?tabID=512&lang=en&ItemID=1294&mid=3171&wversion=Staging
http://www.pcbs.gov.ps/site/512/default.aspx?tabID=512&lang=en&ItemID=1892&mid=3172&wversion=Staging
http://www.pcbs.gov.ps/Downloads/book2371.pdf
| Impact Indicator-1b |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone | CY 2016 Milestone | CY 2017 Milestone | CY 2018 Milestone | Target (date)
| Extent of poverty: Proportion below national poverty line |  | Planned | For 2011: WB:17.2 , G:37.8 |  |  | 13%
|  |  | Achieved | - |  |  |  |  | 29.2% |  | 29.2%
Source
PCBS Poverty and living conditions in the Palestinian Territory 2009-2010 (www.pcbs.gov.ps).
http://www.pcbs.gov.ps/post.aspx?lang=en&ItemID=3115
| Impact Indicator-1c |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone | CY 2016 Milestone | CY 2017 Milestone | CY 2018 Milestone | Target (date)
| Jobs: Unemployment rate |  | Planned | WB:17.2 G:37.8 |  |  | 17.5% | *25%
|  |  | Achieved | - | 27% |  | 25.9% | *27.2% | 28.1% |  | 28.1%
Source
Data for OPTs as a whole from IMF reports (21% for Year 2011). Data for West Bank and Gaza from Palestine Central Bureau of Statistics (PCBS) annual Palestine in Figures (www.pcbs.gov.ps).
*http://www.pcbs.gov.ps/site/512/default.aspx?tabID=512&lang=en&ItemID=1565&mid=3171&wversion=Staging
http://www.pcbs.gov.ps/site/512/default.aspx?tabID=512&lang=en&ItemID=1848&mid=3171&wversion=Staging
http://www.pcbs.gov.ps/Downloads/book2371.pdf
OUTCOME RESULT (Output 1) | Outcome Indicator-1.1a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
|  |  |  | All Windows but B2B/B2M | [7 empty] | - World economy does not deteriorate further.
R1.1: Palestinian private sector (grantees) competitiveness improved | Number of enterprises reporting improved annual performance |  | Planned | 0 | 0 |  | 20 | 230 | 290 | 340 | 340 | - Movement & access restrictions remain as is or decrease.
[8 empty] | [45] | [98] | [119] | [119] | - PA finances remain viable.
|  |  | Achieved | - | 33 |  | 150 | 198 | 392 | 534* |  | - Firms/ beneficiaries are willing to share successes and best practice.
| [Women enterprises reporting improved annual performance by 2019 is 35% of the target] | [6 empty] | [46] | [95] | [186]
Source
Grantee annual survey
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
| Outcome Indicator-1.1b |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Number of enterprises reporting either increased exports or exporting for a first time |  | Planned | 0 | 0 |  | 8 | 75 | 105 | 120 | 120
|  |  | Achieved |  | 20 |  | 54 | 90 | 133 | 210* | 210*
Source
Grantee annual survey
*Results reported in 2018 cover the period from January till July 2018 only and not a full year.
| Outcome Indicator-1.1c |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
All Windows but B2B/B2M
| Number of jobs created (net) |  | Planned | 0 | 10 |  | 280 | 550 | 1000 | 1250 | 1250
|  |  | Achieved |  | 80 |  | 305 | 833 | 1159 | 1777* | 1777*
B2B/B2
|  |  | Planned | 0 |  |  | 300 | 1300
|  |  | Achieved |  |  |  | 807 | 1617 | 1451 | 1201* | 1201*
| Jobs for Youth (male and Female) target is 50% of the 2019 all jobs target |  |  | Youth (All Windows but B2B/B2M)
|  |  | Planned | 0 |  |  |  | 220 | 450 | 600 | 600
|  |  | Achieved |  |  |  |  | 386.5 | 512 | 993* | 993*
| Jobs for Women (of all ages including youth) target is 35% of the 2019 target |  |  | Women (All Windows but B2B/B2M)
|  |  | Planned | 0 |  |  |  | 150 | 325 | 415 | 415
| * Youth Women will be counted against youth and women targets |  | Achieved |  |  |  |  | 248 | 481 | 823* | 823*
Source
Grantee annual survey ) Over lab in results expected between youth & women in job creation for All Windows but B2B/B2M(
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
| Outcome Indicator-1.1d |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
All Windows but B2B/B2M
| Value of additional sales attributable to the Palestinian Market Development Programme (PMDP) (£m) |  | Planned | 0 | 0 |  | 1.4 | 30 | 55 | 75 | 75
|  |  | Achieved | - | 3.1 |  | 18.2 | 33 | 56 | 74.16* | 74.16*
B2B/B2M
|  |  | Planned | - | - |  | 7 | 30 | 55 | NA | NA
|  |  | Achieved | - | - |  | 14.7 | 41 | 56.9 | 57.1* | 57.1*
Source
Grantee annual survey ) B2B to be calculated as per the PMDP recommendation(
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
R 1.1.1: Grantees market penetration ability increased | Outcome Indicator-1.1.1a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
| Total number of new domestic and foreign markets entered |  |  | All Windows but B2B/B2M | [7 empty] | - World economy does not deteriorate further.
|  |  | Planned | 0 | 0 |  | 56 | 180 | 280 | 321 | 321 | - Movement & access restrictions remain as is or decrease.
|  |  | Achieved |  | 44 |  | 103 | 228 | 336 | 403* | 403* | - PA finances remain viable.
| Total number of new domestic and foreign markets entered (Back to Market window) |  |  | B2B/B2M | [7 empty] | - Firms/ beneficiaries are willing to share successes and best practice.
|  |  | Planned | 0 | 0 |  | 0 | 75
|  |  | Achieved |  |  |  |  | 140 | 147 | 150* | 150*
| Number of new domestic and foreign markets entered by women owned/managed firms (The 2019 targets are 35% of the value of indicator 1.1.1a) |  |  | Women (All Windows but B2B/B2M)
|  |  | Planned | 0 | 0 |  | 5 | 60 | 84 | 96 | 96
|  |  | Achieved |  | 7 |  | 17 | 66 | 135 | 169* | 169*
Source
Grantee semi-annual and annual survey
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
R 1.1.2: Grantees capacity in product development improved | Outcome Indicator-1.1.2a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
All Windows but B2B/B2M
| Total number of new or improved products or services developed |  | Planned | 0 | 5 |  | 32 | 200 | 420 | 470 | 470
|  |  | Achieved |  | 39 |  | 154 | 343 | 563 | 637* | 637*
| Total number of new or improved products or services developed (Back to Market window) |  |  | B2B/B2M
|  |  | Planned | 0 | 0 |  | 0 | 200 |  |  | 200
| Number of new or improved products or services developed by women owned/managed firms (The 2019 targets are 35% of the value of indicator 1.1.2a) |  | Achieved |  |  |  |  | 136 | 201 | 201* | 201*
Women (All Windows but B2B/B2M)
|  |  | Planned | 0 | 0 |  | 3 | 60 | 135 | 165 | 165
|  |  | Achieved |  | 10 |  | 31 | 90 | 152 | 247* | 247*
Source
Grantee semi-annual and annual survey
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
R 1.1.3: Grantees attitude towards the value of BSP enhanced | Outcome Indicator-1.1.3 |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Number of enterprises using own funds to pay for Business Development Services (BDS) |  | Planned | 0 | 0 |  | 15 | 60 | 100 | 115 | 115
|  |  | Achieved |  | 5 |  | 26 | 85 | 119 | 171* | 171*
| [Disaggregated by women] | [6 empty] | [23] | [35] | [58] | [58]
Source
Grantee semi-annual and annual survey (Number and % of Women enterprises using own funds to pay for Business Development Services (BDS) will be included in the report)
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
OUTCOME RESULT (Output 2) | Outcome Indicator-1.2.1a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
R 1.2.1: Positive behavioral change shown among the targeted group in analyzed market systems | Percentage of initiated interventions |  | Planned | 0 | 0 |  | 20% | 50% | 50% | 50% | 50% | - Market players willing to adjust their behavior as a result of studies, facilitation, observation, and personal experience.
| accepted and action taken by the targeted |  | Achieved |  | 0 |  | 40% | 74% | 85% | 93% | 93%
| group |  |  | Source
Annual Output 2 report
* Results reported in 2018 cover the period from January till September 2018 only and not a full year.
| Outcome Indicator-1.2.1b |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| # of beneficiaries/ customers using the new or improved services/products. |  | Planned | 0 | - |  | - | - | 212 | 483 | 483
|  |  | Achieved |  | - |  | - | - | 310 | 1305 | 1305
| [Disaggregated by women] | [7 empty] | [50] | [57] | [57]
Source
Semi-annual and Annual Output 2 report
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
| Outcome Indicator-1.2.1c |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Number of service providers adapting /adopting new practices/products offering. |  | Planned | 0 | - |  | - | - | 14 | 19 | 19
|  |  | Achieved |  | - |  | - | - | 22 | 48 | 48
Source
Semi-annual and Annual Output 2 report
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
OUTCOME RESULT (Output 3) | Outcome Indicator-1.3.1a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
R 1.3.1: PIPA capacity improved | Extent of improving PIPA's capacity |  | Planned | NA | 1 |  | 2 | 3 | 3 | 3 | 3
| The measuring unit is a scale from 1 to 5 , where 1 is " No change", 2 "Slight improvement" 3 "Moderate improvement" 4 "High improvement" and 5 "Very high improvement" |  | Achieved |  | 1 |  | 2 | 3 | 4 | 4 | 4 | - Political situation remains the same or improve.
Source
|  |  |  | PIPA scaling sheet (Annual) | [7 empty] | - PIPA and PA have political will to embrace change.
| Outcome Indicator-1.3.1b |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Number of Investments facilitated by PIPA * |  | Planned | 0 |  |  |  | 15 | 30 | 40 | 40 | -PA and Private sector willing to hire and pay for CTRs.
|  |  | Achieved |  |  |  |  | 14 | 41 | 81 | 81
|  |  |  | Source | [7 empty] | - Despite previous perception, Diaspora is open and willing to cooperate.
PIPA annual report
|  |  |  | * PMDP will report on the value of investments facilitated by PIPA in the quarterly report as achievements under Output 3 section (when applicable). | [7 empty] | - Private sector organizations willing to engage to address certain issues and gaps.
R 1.3.2: Well-functioning CTRs placed | Outcome Indicator-1.3.2a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Performance level of CTRs |  | Planned | NA | _ |  | _ | 2 | 3 | 4 | 4
|  |  | Achieved |  | _ |  | _ | 2 | 3* | 3** | 3**
| The measuring unit is a scale from 1 to 5 , where 1 is " Very low", 2 "low" 3 "Moderate" 4 "High" and 5 "Very high" |  |  | Source
CTR Scoring Sheet (Annual)
*This is the UK- CTR result
**This is the result of UK, Germany, USA, and Kuwait CTRs
| Outcome Indicator-1.3.2b |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Number of trade and investment deals facilitated by CTRs * |  | Planned | 0 | - |  | - | - | 3 | 14 | 14
|  |  | Achieved | 0 | - |  | - | - | 6 | 15 | 15
Source
CTR scoring sheet and CTR reports data
* PMDP will report on the value of trade and investment deals facilitated by CTRs in the quarterly report as achievements under Output 3 section (when applicable).
R 1.3.3: Diaspora Attitude towards trade, investment and know-how enhanced | Outcome Indicator-1.3.3a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Number of initiatives designed and launched by partner organizations as a result of PMDP’s support * |  | Planned | 0 | 0 |  | 5 | 7 | 11 | 13 | 13
|  |  | Achieved |  | 0 |  | 5 | 9 | 11 | 13 | 13
Source
Annual Output 3 reporting
* PMDP will report on the value of investment by diaspora in the quarterly report as achievements under Output 3 section (when applicable)
R 1.3.4: Increase in private sector investment due to positive change in business environment | Outcome Indicator-1.3.4a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Incorporating new enhancements to improve governmental and non-governmental bodies’ delivery of services. |  | Planned | 0 | - |  | - | 0 | 0 | 2 | 2
[10 empty] | [1] | [1]
| [Disaggregated by WAY] |  | Achieved | 0 | - |  | - |  | 1 | 5 | 5
[10 empty] | [2] | [2]
Source
Annual Output 3 reporting
R 1.3.5: Synergy between trade and investment organizations improved | Outcome Indicator – 1.3.5.a |  |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
| Partnership activities between trade and investment organizations held (without PMDP support) |  | Planned | 0 |  |  |  | - | - | 2 | 2
|  |  | Achieved |  |  |  |  | - | - | 1 | 1
Source
Annual Output 3 reporting
OUTPUT RESULT (Output 1) |  | Output Indicator-1.1.1.1a |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
R 1.1.1.1: Grantees assisted through grants programme |  | Total number of enterprises assisted | All Windows but B2B/B2M | [8 empty] | - Firms/ beneficiaries are willing to share successes and best practice.
|  |  | Planned | 0 | 30 |  | 138 | 314 | 445 | 494 | 494
|  | (Number of women owned/managed enterprises assisted. Target is 35% of total number of enterprises assisted) | Achieved |  | 73 |  | 221 | 329 | 465 | 620** | 620** | - Firms/ beneficiaries and BSPs are willing and able to invest in skills improvement and innovation.
B2B/M
|  | Total number of enterprises assisted (B2B/M) | Planned | 0 |  |  | 172 | 256 | 256 |  | 256 | - PMDP effectively reach out women, youth and disabled.
|  |  | Achieved |  |  |  | 172 | 256 | 264 | 264 | 264
Women (All Windows but B2B/B2M)
|  |  | Planned | 0 | 6 |  | 62 | 80 | 135 | 173 | 173
|  |  | Achieved |  | 13 |  | 48 | 93* | 143 | 219** | 219**
Source
Quarterly output 1 reporting
* Value reduced due to the new definition excluding B2B/M (Data collected in Annual survey 2016 for TA)
* Results reported in 2018 cover the period from January till September 2018 only and not a full year.
OUTPUT RESULT (Output 2) |  | Output Indicator-1.2.1.1a |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
R 1.2.1.1: Market system failure in specific sectors identified and addressed |  | Number of market system studies completed | Planned | 0 | 3 |  | 9 | 13 | 15 | 15 | 15 | - Market players willing to adjust their behavior as a result of studies, facilitation, observation and personal experience.
|  |  | Achieved |  | 3 |  | 10 | 14 | 15 | 15 | 15 | - Market players are willing to invest in addressing market system failures.
Source
Quarterly Output 2 reporting
|  | Output Indicator-1.2.1.2b |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of interventions based on completed market system studies conducted | Planned | 0 | 2 |  | 5 | 13 | 24 | 34 | 34
|  |  | Achieved |  | 3 |  | 10 | 19 | 30 | 43 | 43
Source
Quarterly Output 2 reporting
* Results reported in 2018 cover the period from January till September 2018 only and not a full year.
|  | Output Indicator-1.2.1.2c |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of products/ services improved/developed to address market failure. | Planned | 0 | - |  | - | - | 19 | 25 | 25
|  |  | Achieved |  | - |  | - | - | 22 | 51 | 51
Source
Quarterly Output 3 reporting
* Results reported in 2018 cover the period from January till July 2018 only and not a full year.
|  | Output Indicator-1.2.1.2d |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | # of individuals reporting an increase in knowledge and skills from services/ activities implemented as part of market interventions. | Planned | 0 | - |  | - | - | 267 | 377 | 377
|  |  | Achieved |  | - |  | - | - | 473 | 1063 | 1063
|  | [Disaggregated by women] | [6 empty] | [138] | [344] | [344]
Source
Quarterly Output 3 reporting
Results reported in 2018 cover the period from January till July 2018 only and not a full year.
OUTPUT RESULT (Output 3) |  | Output Indicator-1.3.1.1 |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | Assumptions
R 1.3.1.1: Supporting activities of PIPA conducted |  | Number of activities completed by PMDP within the framework of support provided to PIPA and key market institutions | Planned | 0 | 5 |  | 12 | 20 | 28 | 32 | 32 | - Political situation remains the same or improve.
|  |  | Achieved |  | 6 |  | 15 | 21 | 29 | 36 | 36
|  |  | Source | [8 empty] | - PIPA and PA have political will to embrace change.
Quarterly Output 3 reporting
R 1.3.2.1: Potential CTRs trained on trade and investment facilitation |  | Output Indicator-1.3.2.1a |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018) | -PA and Private sector willing to hire and pay for CTRs.
|  | Total number of people trained on trade and investment promotion | Planned | 0 | 0 |  | 0 | 10 | 30 |  | 30
[8 empty] | [2] | [6] |  | [6] | - Selected markets prove to be the right markets to target.
|  | [20% target for women] | Achieved |  | 0 |  | 0 | 0 | 30 |  | 30
[9 empty] | [14] |  | [14] | - Despite previous perception, Diaspora is open and willing to cooperate.
Source
|  |  |  | Quarterly Output 3 reporting | [7 empty] | - Ministry of National Economy and the other members of the Palestinian Export Council continue to meet and push the national export strategy forward.
|  | Output Indicator-1.3.2.b |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of CTRs placed | Planned | 0 | 0 |  | 0 | 2 | 6 | 6 | 6
|  |  | Achieved |  | 0 |  | 0 | 1 | 6 | 6 | 6
Source
Quarterly Output 3 reporting
|  | Output Indicator-1.3.2.1c |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of trade and investment leads facilitated by CTRs | Planned | - | - |  | - | - | - | 120 | 120
|  |  | Achieved | - | - |  | - | - | 18 | 381 | 381
Source
CTR Report
R 1.3.3.1: Diaspora engaging activities conducted |  | Output Indicator-1.3.3.1a |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of diaspora engaging activities conducted | Planned | 0 | 4 |  | 10 | 17 | 24 | 30 | 30
|  |  | Achieved |  | 6 |  | 13 | 18 | 25 | 34 | 34
Source
Quarterly Output 3 reporting
R 1.3.4.1: Enabling environment for investment and trade conducted |  | Output Indicator-1.3.4.1a |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of gaps and impediments identified based on (NES, Investor Needs Assessment, OII analysis) | Planned | 0 | _ |  | _ | 5 | 10 | 10 | 10
[8 empty] | [1] | [4] | [4] | [4]
|  | [Disaggregated by WAY] | Achieved |  | _ |  | _ | 6 | 10 | 10 | 10
[8 empty] | [2] | [4] | [4] | [4]
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.4.1b |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  |  | Planned | 0 | _ |  | _ | 1 | 4 | 6 | 6
|  | Number of gaps and impediments shortlisted for further engagements. | [5 empty] | [0] | [2] | [3] | [3]
|  |  | Achieved |  | _ |  | _ | 1 | 6 | 8 | 8
|  | [Disaggregated by WAY] | [6 empty] | [3] | [3] | [3]
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.4.1c |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of interventions implemented to address identified gaps (tools, research, training, resources, capacity building) | Planned |  |  |  |  | 0 | 2 | 4 | 4
[8 empty] | [0] | [1] | [2] | [2]
|  | [Disaggregated by WAY] | Achieved |  | _ |  | _ | 1 | 3 | 7(2) | 7(2)
[1]
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.4.1d |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of laws or Bylaws facilitated and TA provided to improve the regulatory environment | Planned |  |  |  |  | 1 | 2 | 3 | 3
|  |  | Achieved |  |  |  |  | 1 | 2 | 4 | 4
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.4.1e |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Building the action plan and Activation of the Doing Business Committees (Yes\No) | Planned | No |  |  |  | Yes |  |  | Yes
|  |  | Achieved |  |  |  |  | Yes |  |  | Yes
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.4.1f |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of TA provided to MoNE and other institutions to tackle doing business report related issues | Planned | 0 | _ |  | _ | 0 | 2 | 4 | 4
|  |  | Achieved |  | _ |  | _ | 1 | 4 | 4 | 4
Source
Quarter Output 3 reporting
R 1.3.5.1: Contribute to implementing recommendations of the NES |  | Output Indicator-1.3.5.1a |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Agree with Palestinian Export Committee (PEC) on action plan activities(Yes\No) | Planned | No | _ |  | _ | Yes |  |  | Yes
|  |  | Achieved |  | _ |  | _ | Yes |  |  | Yes
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.5.1b |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Strategy harmonization and integration of 2017 work plans conducted during 2016. | Planned | No |  |  |  | Yes * |  |  | Yes
|  |  | Achieved |  |  |  |  | No | Yes |  | Yes
Source
Quarter Output 3 reporting
* Strategy Conducted and work plan developed
|  | Output Indicator-1.3.5.1c |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Number of policy recommendations of the Palestinian Export Committee (PEC) plan implemented / in process | Planned | 0 | _ |  | _ | 0 | 2 | 3 | 3
|  |  | Achieved |  | _ |  | _ |  | 3 | 3 | 3
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.5.1d |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Branding pilot strategy developed (Yes/No) | Planned | No | - |  | - | No | Yes |  | Yes
|  |  | Achieved |  | - |  | - |  | Yes |  | Yes
Source
Quarter Output 3 reporting
|  | Output Indicator-1.3.5.1e |  | Baseline | CY 2014 Milestone |  | CY 2015 Milestone (cumulative) | CY 2016 Milestone (cumulative) | CY 2017 Milestone (cumulative) | CY 2018 Milestone (cumulative) | Cumulative Target (2018)
|  | Branding pilot implemented (Yes/No) | Planned | No | _ |  | _ | No |  | Yes | Yes
|  |  | Achieved |  | _ |  | _ |  |  | Yes | Yes
Source
Quarter Output 3 reporting