Type of Review: Annual Review

Project Title: Bangladesh Policy Fund

Date started: August 2007
Date review undertaken: July/August 2013

## Introduction and Context

What support is the UK providing?
The Bangladesh Policy Fund (up to £5m between 2007-2013) supports policy development and programming in Bangladesh in line with DFID’s strategic priorities and Operational Plan. It is a flexible resource that funds research studies, pilot projects and stakeholder consultations. The fund complements larger programmes by supporting activities that cut across traditional sectors and by responding quickly to emerging needs and opportunities. Projects are implemented with a wide range of partners from Government, the private sector and civil society.

What are the expected results?
The overall objective of the project is for development partners to implement pro-poor policy and reform in support of the Millennium Development Goals. The outcome of the project is research and policy interventions applied by the Government of Bangladesh and other stakeholders to develop pro-poor policy and reduce poverty, particularly for vulnerable and excluded groups. There are two lower-level outputs: 1) quality interventions, including studies, seminars and workshops that promote pro-poor policy change, 2) interventions designed and prioritised to ensure strategic added value. / The results will depend on the project proposals that are submitted by DFID Advisers and approved by the Senior Management Team. Examples of projects previously supported by the Policy Fund are summarised below to illustrate the types of activities and results that can be expected: / Bangladesh Human Security Assessment (£31k, 2007-2009) / Support Government of Bangladesh to Provide Evidence-Based Recommendations on Food Security (£125, 2008-2009) / Developing Innovative Opportunities for Private Sector Cooperation to Achieve Development Outcomes (£55k, 2009) / Mapping Nutrition Interventions in Operation in Bangladesh (£19k, 2009) / Promoting Financial Education through Mentoring Relationships (£111k, 2009-2010) / Bangladesh Food Security Investments Forum – Policy Options for Food Security Investments Plan of Bangladesh (£19k, 2010) / Support for the Proposed Investors’ Forum, Bangladesh (£8k, 2010-2011) / Supporting Civil Society Representatives to Attend UN General Assembly and Scaling Up Nutrition Global Events (£4k, 2011)

What is the context in which UK support is provided?
Bangladesh has made good progress on the Millennium Development Goals, particularly in terms of reducing income poverty, getting nearly all boys and girls enrolled in primary school and reducing child and maternal mortality. The country also has unquestioned potential: Goldman Sachs listed it in their “Next 11” economies with high potential to become one of the world’s largest economies in the 21st century. However, Bangladesh is a poor, populous and rapidly urbanising country, highly vulnerable to natural disasters and already experiencing the effects of climate change. High levels of poverty and inequality persist, with more than 4 in 10 people living on less than $1.25 per day and over three quarters of the population on less than $2 per day. / The 2011-2015 Operational Plan outlines DFID’s top priorities in Bangladesh: improving the provision of basic services such as health and education; supporting private sector development, jobs and skills as the foundation for growth over the longer term; and reducing and managing the risks to development, including those relating to governance and security, natural disasters and climate change. The majority of DFID’s funding in support of these priorities is channelled through large national programmes. However, it is important for the office to be able to support smaller, strategic activities and to be able to respond quickly to needs and opportunities as they arise. The Policy Fund provides this flexible resource. / Proposals to the Policy Fund must be consistent with DFID’s strategic priorities and not be eligible for support through another DFID programme. The fund is particularly useful for supporting research studies and stakeholder consultations to inform and influence policy development. A Business Case is being prepared that proposes to extend the Policy Fund for a further five years until 2018.

## Section A: Detailed Output Scoring

Output 1: Quality interventions i.e. studies, seminars, workshops promote pro-poor policy change to key policy makers in Government of Bangladesh and other stakeholders
Output 1 score and performance description: A (output met expectation) Each application form for the Policy Fund contains a section where the results of the project are scored after completion. Projects are scored on a scale of 1-5 (1 = purpose fully achieved, 2 = largely achieved, 3 = partly achieved, 4 = achieved only to a limited extent, 5 = not achieved at all).
Progress against expected results: / Indicator: number of interventions which score 1,2,3, 4 or 5 in project completion feedback score / The project has met the target for all completed projects to be awarded a score of 1 or 2. Five projects were supported by the Policy Fund over the last year, of which two were awarded a score of 1 and two a score of 2. One project, Bangladesh Bank Initiative for Financial Education, will be scored upon completion later in August 2013, but initial feedback is positive. 1. Independent Transparency, Accountability and Monitoring Mechanism for the Bangladesh Climate Change Strategy and Action Plan (£25k, June 2012 to March 2013, score 1) / The project supported a scoping mission to assess the options for a new mechanism to monitor implementation of the Government’s Bangladesh Climate Change Strategy and Action Plan (BCCSAP). It responded directly to a recommendation of the Independent Commission for Aid Impact in September 2011 to support monitoring of the BCCSAP by local and international civil society organisations. The mechanism that the project supported will improve public accountability of all funding for climate change adaptation in Bangladesh. The need for greater accountability and scrutiny of climate change financing is widely recognised, including by the Ministry of Environment and Forest and development partners. The project recruited two consultants to conduct a scoping mission, discussing the obstacles to more effective financing with key stakeholders in Bangladesh, and a desk review of international best practice. The consultants were selected through a competitive process managed by the Climate Change Adviser in DFID Bangladesh. The scoping mission identified a range of credible options for a transparency initiative, which have since been considered collectively by Government and development partners at the Local Consultative Group Environment and Climate Change Working Group. As of July 2013, the climate change team in DFID Bangladesh is designing a new programme to support transparency around climate change financing based on the findings of the report. The project also provided useful insights into climate financing, including around the political economy of climate change and the need to separate instruments for transparency from those of accountability and advocacy. Inputs from seasoned local and international experts was considered a key factor in the success of the project. / 2. Quarterly Macro-Economic Policy Briefings (£55k, June 2012 to March 2013, score 1) / The project sought to raise awareness of macro-economic reforms and help keep Bangladesh on track against its commitments under the International Monetary Fund’s reform programme (agreed in April 2012). Under the IMF programme, the Bangladesh Government is given access to a $1bn, three-year Extended Credit Facility tied to a reform programme with four pillars: improving fiscal policy, strengthening the central bank, improving governance of the financial sector, and reforms for improving the investment climate. These reforms are widely acknowledged as being crucial to long-term economic growth and stability in Bangladesh. The project funded the Policy Research Institute (PRI) to organise four quarterly roundtable discussions with policy makers, thematic experts and development partners to discuss the reform programme and challenges facing the Bangladesh economy. Each roundtable included presentations of four thematic policy briefs, which were prepared in advance and shared with Government, the media and civil society groups. The PRI provided written reports to DFID following each event. / The PRI was well-placed to manage the project as the leading Bangladesh policy research think tank on macroeconomic and fiscal issues. Bangladesh is on track against its commitments under the IMF reform programme. Whilst the pace of implementation will be due to a large number of exogenous factors, the project can be credited with making a modest contribution to this outcome. The project linked senior policy makers to international best practice, including through PRI’s presentations to the Minister of Commerce, Chief Economist at Bangladesh Bank and the Prime Minister’s Economic Adviser. The meetings also received significant press coverage, with their recommendations making front-page news. Lastly, the written reports that were produced following the meetings have been useful to DFID and HMG staff in discussions with Bangladeshi partners. 3. Supporting Social Protection Policy Reform in Bangladesh (£117k, September 2011 to August 2012, score 2) The project sought to strengthen government-donor collaboration on reforms to social safety nets and influence social protection policy in Bangladesh. Social protection is a high-profile issue among development partners in the country. Government spending on social protection amounts to around 15% of public expenditure and a plethora of donor-funded programmes have been established in recent years. However, support is fragmented and not always targeted at those most in need. The project supported a high-level conference on social protection in September 2011: Scaling-up Social Protection Reforms in Bangladesh: Building an Effective System of Social Ladders and Safety Nets. The conference, which was hosted by UNDP, brought together senior policy makers from relevant Line Ministries, donors and research institutions including the Power and Participation Research Centre and the Brookes World Poverty Institute. The conference led to a Government Communique outlining concrete commitments and a timeframe to reform social protection in Bangladesh. / The project also funded political economy analysis to support social protection policy reforms and inform Government-donor dialogue. The analysis built on the discussions at the preceding conference and made clear recommendations for reform. It later led to the development of a multi-donor programme of support to the Government on social protection reform, and is currently informing a new DFID Social Protection Programme, due to start later in 2013. 4. Addressing Violence Against Women and Girls in Bangladesh: from Evidence to Policy (£50k, November2011 to March 2013, score 2) The project sought to build the evidence base to support policies addressing violence against women and girls (VAWG). Levels of VAWG are particularly high in Bangladesh: a World Health Organisation study estimated that around 42% of ever-married rural women of reproductive age had experienced physical assault, and 50% had experienced sexual abuse within marriage. The local rights group Odikhar noted an increase in dowry-related violence in 2011, and the Acid Survivors Foundation recorded 84 acid attacks in the same year. Most literature on VAWG focusses on its consequences and coping strategies for abused women. The project sought to build on the limited evidence available on preventing VAWG, supporting the Government’s Multi-Sectoral Programme on Violence Against Women and National Plan of Action on Violence Against Women. The project did this by synthesising global evidence through a literature review, identifying individual and community risk factors for VAWG, mapping vulnerability to VAWG across different areas in Bangladesh and developing key policy recommendations. The lead Adviser in DFID Bangladesh considers the project report to be high-quality with robust and rigorous analysis. It made a number of conclusions and recommendations, relevant for both Government policy-makers and donors. The report will be launched in September 2013 at an event which is expected to be attended by the Minister for Women and Children’s Affairs, senior Government representatives. The research will also support civil society organisations to target their services more effectively and inform DFID Bangladesh’s next Operational Plan and programming to address VAWG. Lastly, it is intended to inform the development of pilot projects to establish what works in preventing VAWG in different types of communities in Bangladesh, as well as how best to engage men and boys to prevent and address violence. / 5. Bangladesh Bank Initiative for Financial Education (£121, March 2012 to August 2013) / The project is supporting Bangladesh Bank’s communication campaigns to improve financial literacy and consumer protection. The campaigns will improve understanding of basic financial issues and raise awareness of the benefits of banking, targeting groups including school children, women and small and medium sized enterprises. They will also help vulnerable groups to protect themselves from abusive financial practices and prevent them from being overburdened by debt. Project activities include developing a user-friendly website to explain basic financial issues and direct users to sources of consumer protection, broadcasting regular radio and television commercials to encourage responsible banking, and publishing messages in leading daily newspapers to raise awareness of the risks of transacting with non-licenced banks. / The project is due to finish later in August 2013; its performance and score will be assessed in the 2014 Annual Review of the Policy Fund. However, initial feedback is positive and Bangladesh Bank is hoping to continue and expand the project with DFID’s support. Useful lessons have been identified from the project, including around the inadequacy of media coverage of financial issues and the importance of bringing together financial regulators and companies to support financial education. / Recommendations: / Project managers should provide feedback and a recommended score to the DFID Corporate Business Unit (CBU) within three weeks of projects’ completion. The new application and evaluation form, introduced through the Policy Fund extension in August 2013, will allow CBU to record more detailed information on project performance. Impact Weighting (%): 60 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Interventions and designed and prioritised to ensure strategic value, gap filling, and significantly added value of Policy Fund mechanism
Output 1 score and performance description: B (output moderately did not meet expectation)
Progress against expected results: / Indicator: extent to which interventions fill gaps in strategic priorities for DFID Bangladesh and the Government of Bangladesh / The five projects assessed under output 1 all have clear links to strategic priorities in DFID Bangladesh’s 2011-2015 Operational Plan. The Policy Fund application form and checklist require applicants (DFID Advisers) to confirm that no other source of funding is available and to set out how the project is aligned with DFID’s strategic priorities. Applications for support are considered collectively by the DFID Bangladesh Senior Management Team, who are able to take a holistic view of Policy Fund activity and its fit with other programmes. However, a number of factors mean the Policy Fund is not currently fulfilling its potential in supporting the office’s strategic priorities: / Staff capacity to develop and manage Policy Fund projects is limited. Staff are focussed on managing large programmes that contribute to DFID Bangladesh’s headline results. As a result, the Policy Fund has been significantly underutilised (see section 2 on costs and timescale). / Awareness of the Policy Fund across DFID Bangladesh is limited, particularly among staff who recently joined the office. Staff are not always aware of how the fund can be accessed and which types of activities are eligible for support. / There is little follow-up work after projects are completed to assess their longer-term impact in informing and influencing policy development. / Recommendations: / The approval of the new Business Case presents an opportunity to raise awareness and improve understanding of the Policy Fund across DFID Bangladesh. The approval should be announced to all staff at a Sunday Morning Meeting. Presentations of Policy Fund projects at office In-Weeks could also by useful in raising awareness of the fund. The Corporate Business Unit (CBU) should develop guidance providing practical advice to staff on how to develop and manage projects, as well as setting out clearly the types of activities that are eligible for support. / A new policy and programme officer is expected to join CBU in autumn 2013. An important part of their role should be to support programme teams to develop proposals and manage projects. This should include meeting with all teams to discuss the process for using the Policy Fund and how it can support their strategic objectives. / The officer or Head of CBU should continue to attend British High Commission meetings of the Bilateral Programme Budget Board to ensure synergy between the two funds. The implications of new, central guidance on due diligence for the Policy Fund is unclear. The forthcoming visit of the DFID Risk and Control team should be used to clarify the due diligence requirements for implementing partners. It will be important that these requirements provide the necessary assurances but are proportionate to the size of Policy Fund projects so as not to discourage applications. / Impact Weighting (%): 40 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? N / No. The logframe was last updated in May 2010. / 1.2 Overall Output Score and Description: A (outputs met expectation) / 1.3 Direct feedback from beneficiaries / Feedback on the Policy Fund was sought from DFID staff to inform the development of the new Business Case. The value of having a relatively small, strategic and flexible fund was widely recognised. There were mixed opinions on whether the fund should be outsourced, which would reduce the administrative burden on DFID staff but risk making the fund less responsive to DFID’s needs and priorities. Feedback also revealed misunderstandings around the purpose of the fund and its eligibility criteria. / Events to disseminate research findings and inform policy-making received positive media coverage. In particular, the roundtable events organised through the Quarterly Macro-Economic Policy Briefings project received significant press coverage. Feedback from participants and implementing partners was also positive, including from Bangladesh Bank on the Financial Education project and from economists who participated in the economic roundtables.
1.4 Summary of overall progress / The Policy Fund supported five high-quality projects over the past year that were aligned to DFID’s strategic priorities. Of the four projects that were completed in this period, two were awarded a score of 1 (purpose fully achieved) and two a score of 2 (purpose largely achieved). Feedback from the lead DFID Advisers on these projects was very positive and identified useful lessons for future projects and programming. However, the fund was significantly underutilised, largely due to limited staff capacity and a lack of awareness of the fund across the office. Improvements brought about by the new Business Case, communications to raise awareness of the fund and the increased capacity from a new staff member in the Corporate Business Unit will help to address these issues.
1.5 Key challenges / There are two key challenges, described in greater detail in the assessment of output 2: / DFID staff capacity. The priority given to managing large programmes means there has been limited staff capacity for developing relatively small, strategic interventions. / Lack of awareness of the Policy Fund, including around how the fund can be accessed and the eligibility criteria for support.
1.6 Annual Outcome Assessment / Outcome: Policy Fund supported research and policy interventions used and applied by Government of Bangladesh and other stakeholders to develop pro-poor policy and reduce poverty, focussing on vulnerable and excluded groups / The Policy Fund’s outcome statement is on track to being achieved. Feedback from DFID Advisers upon project completion shows that interventions are informing national policy and programming, although it is not possible to attribute changes to the Policy Fund alone. Projects over the past year directly addressed issues relating to poor and excluded groups in Bangladesh, including vulnerable women and girls, groups vulnerable to climate change and those in need but without access to social protection. The expanded application and evaluation form, expected to be introduced by the new Business Case in August 2013, will capture more detailed information on the performance and longer-term impact of completed projects to inform the outcome assessment.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N The Policy Fund is significantly underutilised (see assessment of output 2). As of 24 July 2013, £108,333 had been disbursed from a budget of £800,000 in 2013/14. The underutilisation is largely due to limited staff capacity across DFID Bangladesh to develop and manage projects. Programme teams were also encouraged to ensure value for money during their negotiations and most of the projects came in under the original estimate. However, the nature of the fund as a flexible resource that can respond quickly to emerging needs and opportunities means it is difficult to accurately forecast spend. It is important that the size of the fund is greater than likely need, taking into account the importance of realistic forecasting, to ensure DFID Bangladesh has the flexibility to capitalise on strategic opportunities as they arise throughout the year. / 2.2 Key cost drivers / Projects are funded by the Policy Fund on an ad hoc basis as needs and opportunities arise. Spend is expected to increase in 2014 under the new Business Case and as greater capacity is dedicated to supporting projects and raising awareness of the fund. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There have been no changes to evidence. 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level The risk is low. Risk is assessed for each proposal before being submitted to the Senior Management Team for approval.
Risk of funds not being used as intended / The risk is low. The Policy Fund does not support large-scale procurement or long-term activities where the risks are greater. The lead DFID Adviser is responsible for monitoring fiduciary risk and project progress. Central guidance introduced earlier in 2013 requires DFID to conduct due diligence assessments for all new partners. These assessments will provide further assurances that implementing partners have the capacity to effectively manage DFID funds. / 4.4 Climate and Environment Risk / The Climate and Environment Risk is rated C (low). There will be some international travel for conferences and consultancy, but lead Advisers should seek to minimise waste and carbon footprints. The Policy Fund can support activities to improve climate change policy and programming, such as the Transparency Mechanism project supported over the past year.

5. Value for Money
5.1 Performance on VfM measures / The Policy Fund constitutes around 0.4% of the DFID programme budget in Bangladesh. The VfM of the Policy Fund is based on its potential to leverage significant policy and programmatic change through relatively small, strategic investments. The fund supports VfM by saving staff time that would otherwise be required to develop disproportionately detailed Business Cases for small interventions. / VfM is also assessed at the project level for each intervention. For example, the manager of the “Macro-Economic Policy Briefing” project sought to minimise costs for activities other than research: seminars were hosted at the Policy Research Institute to minimise travel and hosting costs, and 87% of the budget was assigned for the development of research papers and policy briefs. The application forms for other projects did not explicitly set out the VfM cases of the proposals, but since April 2012 the application form now makes this a requirement (see section 5.2 below). The new Business Case (August 2013) assessed the case for outsourcing management of the Policy Fund to a third party. It concluded that keeping management in-house was the most cost effective and responsive way for DFID Bangladesh to influence and support policy development, avoiding the costs associated with using a managing agent. / 5.2 Commercial Improvement and Value for Money / As of April 2012, the application and evaluation form for individual projects requires Advisers to set out the VfM case and any financial savings that have been made. / 5.3 Role of project partners / Project partners are identified on a case-by-case basis for each intervention. Over the past year, all implementing project partners are considered to have performed well. However, one partner did not allocate sufficient human resource for the work resulting in several delays. This underlines the importance of due diligence and careful selection of project partners. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A. The UK’s conditionality only applies to financial aid directly given to partner governments.

7. Conclusions and actions
Output 1 Project managers should provide feedback and a recommended score to the DFID Corporate Business Unit (CBU) within three weeks of projects’ completion. The new application and evaluation form, introduced through the extension of the Policy Fund in August 2013, will allow CBU to record more detailed information on project performance. Output 2 / The approval of the new Business Case presents an opportunity to raise awareness and improve understanding of the Policy Fund across DFID Bangladesh. The approval should be announced to all staff at a Sunday Morning Meeting. Presentations of Policy Fund projects at office In-Weeks could also by useful in raising awareness of the fund. The Corporate Business Unit (CBU) should develop guidance providing practical advice to staff on how to develop and manage projects, as well as setting out clearly the types of activities that are eligible for support. / A new policy and programme officer is expected to join CBU in August or September 2013. An important part of their role should be to support programme teams to develop proposals and manage projects. This should include meeting with all teams to discuss the process for using the Policy Fund and how it can support their strategic objectives. / The officer or Head of CBU should continue to attend British High Commission meetings of the Bilateral Programme Budget Board to ensure synergy between the two funds. The implications of new, central guidance on due diligence for the Policy Fund is unclear. The forthcoming visit of the DFID Risk and Control team should be used to clarify the due diligence requirements for implementing partners. It will be important that these requirements provide the necessary assurances but are proportionate to the size of Policy Fund projects so as not to discourage applications.

8. Review Process
The review was conducted by DFID Bangladesh’s Corporate Business Unit between 21 July and 1 August 2013. It involved consultations with DFID Advisers who had managed Policy Fund projects over the past year. The review also drew on the assessments in project application and evaluation forms.