Type of Review: Annual Review

Project Title: AAWAZ Voice And Accountability Programme, Pakistan

Date started:	May 2012	Date review undertaken: May 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing up to £34.3 million over 5 years (May 2012 to May 2017) in programme resources and technical assistance. This includes an Inception Phase that ran from May 2012 - February 2013, during which piloting of activities began in 7 districts. / DFID Pakistan is closely involved in the development of the AAWAZ . In addition, DFID has also funded two Annual Reviews and two Beneficiary Assessments

What are the expected results?
The stated outcome for the programme is that: democratic processes in Pakistan are more open, inclusive and accountable to citizens. / Four different areas will be addressed to arrive at this outcome: / Helping women and excluded groups to participate safely in politics and in public spaces at federal, provincial and local levels / Building the skills of citizens and communities resolve disputes peacefully, work together for common solutions and be more tolerant towards minority groups and women / Facilitating women and other excluded groups to engage with government to improve responsiveness and accountability and demand improved delivery of services / Generating and synthesising improved evidence and communicating/championing this to political leaders and the elite / The project will achieve its aims by working through four experienced local NGOs this by working with in 45 Districts in Punjab and Khyber Pakhtunkhwa Provinces, directly engaging with 4500 grassroots communities. / In addition, advocacy and communications initiatives at District, Provincial and national levels will strengthen the legislative and policy environments for participation by women and excluded groups and change attitudes towards women and excluded groups.

What is the context in which UK support is provided?
The overall context for support to the AAWAZ Voice and Accountability programme include DFID's Strategic Vision for Girls and Women, which highlights the need to create an enabling environment that frees girls and women from the constraints that perpetuate exclusion and poverty; and DFID's long term commitment to Making Governance Work for the Poor. The approach taken by AAWAZ of working through local organisations also fits well with the recommendation of the International Development Committee of the UK Parliament regarding the need to "look for opportunities to support home grown reformers from all quarters in Pakistan; working with civil society groups and progressive parliamentarians striving for equitable political, social and economic development."[1] / At national level, the vision in DFID-Pakistan's Operational Plan 2011-2015 gives importance to: empowering women and girls, so they can safely participate in decision-making, access essential services including justice, and enjoy equal rights; making democracy work and improving governance / and greater involvement in electoral processes, especially by women and excluded groups; and ensuring the government responds to its citizens’ needs through the effective delivery of public services, especially health and education. / The AAWAZ project aims to increase the participation of women and excluded groups in decision making in public and political spheres as well as ensuring their active engagement in governance advocacy that will not only access key services but also to promote a more constructive, responsive and accountable relationship between government and citizens. Its work to protect and increase democratic space also includes the active promotion of tolerance and the peaceful resolution of conflict. / The project is being implemented in a very difficult context characterised by poverty insecurity, extreme gender inequality and deteriorating human rights. The country faces significant social, economic and security challenges. In 2012, Pakistan ranked 146 out of 176 in the UN Human Development Index. Poverty is increasing and the gap between rich and the poor is widening. Provision of basic services falls far short of international norms and many groups, including women, are excluded from access to services. As a result, over a third of Pakistanis remain poor, and under-educated. / Last year (2013) Pakistan was ranked second from bottom (135 out of 136) in the World Economic Forum's Gender Gap Index. Women in Pakistan face extreme levels of violence, discrimination and inequality in almost every aspect of their lives. It is the 3rd most dangerous country in the world for women and many women live in an atmosphere of fear, their lives guaranteed only in exchange for obedience to social norms and traditions. More than 70% are thought to have suffered some form of domestic abuse with the most visible cases including honour killings, gang rapes, and acid attacks. 7,1 million girls are out of school and half of all women are illiterate, rising to 70% in rural areas. / Violence against women takes place against a background of general insecurity and violence. Pakistan ranks 157th of 162 countries on the Global Peace Index. And, according to the Global Terrorism Index, no other country, apart from Iraq, has been so badly affected by terrorism in recent years. Tolerance of difference seems to be decreasing at the same time space for democratic debate is narrowing. Human rights violations, including murders targeting liberal elements in society, are largely ignored by government and the police. This creates a creeping atmosphere of fear that creates a culture of caution and curbs freedom of speech and action. / Governance lies at the heart of Pakistan’s economic and social problems. Over many years the dominance of military, bureaucratic and political elites has distorted governance and resource distribution. Weak capacity and accountability, a reliance on connections to get things done as well as open corruption undermines public confidence in the state and the rule of law. / Donor experience over the last decade has demonstrated that top-down governance reform programmes do not on their own produce concrete, positive benefits for citizens. In addition to a positive legislative environment that supports greater transparency and reform, this requires a strong demand side. The AAWAZ project aims to create an active citizenry - including both women and men as well as usually excluded groups - that will engage in constructive governance advocacy that calls government to account and institutionalises responsive and consultative relationships with the state. . / Reversing this situation requires the active involvement of women, excluded groups and their communities in constructive governance advocacy with government to improve services and create a culture of accountability and responsiveness. In addition, ordinary women and men need to join with more influential citizens and sympathetic politicians to create a legislative environment that supports reforms and change.
[1] International Development Committee, Summary, Tenth Report, Pakistan, printed 26 March 2013, House of Commons, UK Parliament: http://www.publications.parliament.uk/pa/cm201213/cmselect/cmintdev/725/72503.htm

## Section A: Detailed Output Scoring

Output 1: : Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab
Output 1 score and performance description: Score is A / This output has already delivered some significant changes for women at community level in terms of their participation in public life. Working with allies it has influenced the adoption of legislation that improves the status and legal rights of women including positive reforms of the Local Government Acts in KP and Punjab.
Progress against expected results: / Output Indicator 1.1: Cumulative number of formal engagements (as defined in output manual) on gender issues between AAWAZ forums and political representatives at local, provincial and federal levels / AAWAZ has defined formal engagements on gender issues to mean the number of CNIC and voter registration campaigns which achieved a minimum of 500 CNICs and registration of votes for women. / As such it has exceeded the target of 12 engagements and reported 18 such campaigns. / It has helped 60,193 people to get CNIC registration (36,625 women) and 39,569 votes (23,364 women). / Consortium partners have a presence on the Commissions on the Status of Women at the national level and at the provincial level in Punjab and KP as well as the national Economic Advisory Committee of the Government. / Although not captured anywhere in the output indicators, at village level women are not only represented in each forum but AAWAZ has ensured that they are also holding key posts The team also found that one of the two top positions in each forum was occupied by a woman. In several villages visited by the review team, women reported that this was the first time they were participating with men in such forums. / These AAWAZ forums are themselves ‘public spaces’ and, in the Pakistan context, women's active participation at forum meetings represents a very significant change. The fact that women recognise their right to be present in a public space, to express their views publicly, and to participate in politics at multiple levels is a major achievement. As is the fact that male forum members also acknowledge this right. / Women's public and political participation has included rallies, lobby meetings with local government, politicians and political parties, and Khuli Katcheri,[2] sessions at some of which gender issues have been raised directly. During one field visit, a an MNA[3] reported that although public meetings had been held in the past, before AAWAZ started work, women were never present. / AAWAZ provincial and national level forums bring together a diverse group of stakeholders and are facilitating the development of a shared understanding on key issues affecting women’s safe public and political participation and helping to build a single, powerful women's voice. In Punjab, MPAs[4] said the AAWAZ provincial forum had helped them form a cross party women's caucus. / AAWAZ and its allies held a series of meetings with the Department of Women's Development to finalise the draft for the Punjab Commission on the Status of Women 2014 which was passed in March 2014. Forum members also helped MPAs, NGOs and activists reach consensus on the Domestic Violence Bill, allowing them to speak with a united voice for the first time. In addition, AAWAZ was closely involved in the lobbying that resulted in the Punjab Government adopting the Women’s Empowerment Package, 2014, and Punjab Women Fair Representation Act, 2014. The latter reinstated a 33% reservation of seats for women after the Constitution (18th Amendment) Act 2010 had reduced this to 35 out of a total of 183 seats. / Output Indicator 1.2: Cumulative % men/ women reporting reduced acceptance of violence against women in programme districts over the previous year / As there have been no concerted district wide campaigns with the objective of reducing acceptability of violence against women, it is unlikely that AAWAZ has made any significant progress against this indicator. During field visits some successful interventions by forum members in cases of domestic violence were reported at village level, as were local radio programmes on different gender issues including domestic violence. However, it is difficult to gauge the achievements as there is no credible baseline or subsequent survey to enable measurement against this indicator. / NOTE: There is a need for AAWAZ monitoring to make links across outputs, e.g. number of peacefully resolved disputes that address violence against women. / Output Indicator 1.3: % increase in participation of women in decision making processes at public community institutions (HMC/AAWAZ Forums) in programme districts. / AAWAZ’s achievement of having 40 per cent of the key posts in AAWAZ forums occupied by women is a highly commendable step in the right direction. These forums can play the role of ‘incubators’ for women’s leadership if in the future clear strategies are put in place for developing women’s leadership. / However, there is a conceptual confusion in this indicator as it has been conceptualized as a district level indicator for ‘public community institutions’ which would include institutions such as School Management Committees (SMC) and Health management committees (HMC) notified by the government but not community institutions formed by a programme. Therefore progress reported against this district level indicator in terms of women’s representation in decision-making forums created by AAWAZ is problematic. There is anecdotal evidence to suggest some re-vitalizing of School Management Committees under Output 3 activities but whether more women were included has not been reported on. / Output Indicator 1.4: a) % increase in decision making positions held by women within political parties b) Percentage of women in legislative bodies at local, provincial and national levels / A significant achievement has been made against this indicator in terms of the increase in the number of reserved seats for women and minorities in local government at the Union Council level. The AAWAZ Utha campaign on local government was launched in August 2013 by consortium partners for changes in the Local government bills in KP and Punjab. In Punjab, the number of seats for women in a UC were increased from 1 to 2 (out of 13 total members) and due to the campaign and one seat for minorities reserved in every UC as opposed to the initial plan. In KP, 20% seats for women and 5% seats each for youth and minorities have been ensured. While precise attribution is difficult to establish, there is no doubt about the major contribution made by AAWAZ. / All partners also reported their efforts in helping women at the local level file their nomination papers for elections in the local government elections. 1441 women were mobilised in Punjab to file nomination papers and 421 women were finally able to do this. The postponement of local body elections in the Punjab meant that the women were not actually voted into these positions. In KP the dates for the elections were not announced which meant no one could file their papers. Because local elections were postponed at the last minute, there is no achievement in terms of positions actually held by women at this stage. This is due to factors beyond the control of the programme. / Many civil society organisations are working on the issue, but AAWAZ played a significant role in increasing the number of reserved seats for women and excluded groups in Union Councils. For example, initially religious minorities were to have reserved seats only where they had at least 200 community members. In Punjab, one seat for minorities is now reserved in each UC regardless of numbers. Consortium partners also are working directly to influence political parties. There is evidence of partners successfully lobbied for inclusion of women in the political parties in some areas. For example, in Haripur district, lobbying by the AAWAZ district forum formed by consortium partner Sungi, resulted in PTI creating a women section in 17 of the District's Union Councils, with plans to extend coverage to all Union Councils over time. / Issues: / A clear strategy for addressing the structural, cultural and personal barriers to women’s increased safe participation in public and political spaces is needed. To date, an over-arching behaviour change communication strategy to challenge gender discrimination at multiple levels is missing. / The capacity building on gender sensitisation needs significant improvement especially at district level and below where training sessions were far too short and not designed the different specific audiences. / A strategy for engaging with young women and young men is needed. These can be agents of change and definitely are the key to the future. / A clear plan of action to ensure Agahi resource centres achieve their potential of becoming centres of knowledge for women is needed. This is recognised by AAWAZ district staff who would like to see the "focal persons" who run the centres given proper training and a larger honorarium that reflects their responsibilities. To create a women-friendly environment, the Agahi centres need to be better resourced with many more visual materials suitable for non-literate audiences. Ideally, if funds permit, computers with internet connections would give women access to the outside world. In addition, a strategy needs to be in place to ensure women's access and use where there is a strong possibility of the space being taken over by men. / Recommendations: / A behaviour change communication strategy to challenge norms that lead to gender discrimination and social exclusion needs to be developed and implemented. / AAWAZ needs to develop a strategy for engaging effectively with young women and men as agents of change. / A new strategy and accompanying revised budget is needed urgently to guide the effective functioning of Agahi centres. This should clarify, amongst other things: / key areas in which the centres would provide knowledge, / effective ways of communicating with (illiterate) women, / capacity building and remuneration for Agahi focal persons / how priority access for women to these centres would be ensured so that these centres become key centres of knowledge and empowerment for women. / It is recommended that AAWAZ consults its District Coordinators when drawing up the strategy and learns from Shirkatgah’s experience of establishing women-friendly spaces. / AAWAZ needs to develop plans and guidelines for supporting women to contest elections that includes building their skills in public speaking and running their campaigns as well as facilitating access to information. / The programme should prioritise and focus its advocacy on a few high impact laws while giving equal attention to ensuring existing laws that have the potential to deliver significant changes are implemented for the benefit of citizens at district, provincial and national levels. / Impact Weighting: 25% / Revised since last Annual Review? NO / Risk: Low / Revised since last Annual Review? Yes - the AR 2013 rated the risk as medium
[2] Literally "open court". An official meeting where government departments meet communities to listen and respond to service issues, etc.
[3] Member of the National Assembly, Pakistan's federal parliament.
[4] Member of the Provincial Assembly

Output 2: Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab
Output 2 score and performance description: Score is B / Performance against this output is uneven across consortium partners and districts. Intervening in disputes is very sensitive in any context but in Pakistan is fraught with difficulties. It takes place against in a context where local disputes rapidly deteriorate into violence and a background of lawlessness, insecurity, intolerance, corruption and rising extremism in which the relationship between citizens and the police, judiciary and the state is one of deep mistrust. / In these circumstances, before staff, partners and forum members engage in dispute resolution they should receive extensive, high quality training. According to staff themselves, this has not happened but, driven by targets, they are intervening in a wide range of disputes. Staff and partners with pre-existing skills in this area have done well. Others have struggled and there is a risk that they may cause unintended harm. / Progress against expected results: / Output Indicator 2.1 Cumulative no of community level disputes identified, pre-empted and peacefully resolved by the communities themselves or through government notified Alternative Dispute Resolution (ADR) mechanisms / Targets Achieved / Identified 10,000 1,233 / Pre-empted 7,000 5,631 / Resolved 7,000 2,578 / The project has not met its targets for this indicator. In part, this may be due to the fact that the expansion into new communities continued until the first months of 2014. Newly formed forums need to be trained and develop relations of trust within the community before anyone will bring disputes to them. Attending a big peace mela is one thing (see below) trusting a group with a personal dispute is quite another. / Output Indicator 2.2 Cumulative number of excluded group households participating in AAWAZ Forums’ local level peace building initiatives (DFID accepted definition is that this means as no less than 50% participation of women and excluded groups in peace building initiatives) / NOTE: This definition of this output indicator is confusing and needs revision. The target is clearly designed to measure a number of households, while the definition to make sense requires a target that counts the number of peace events and the percentage of women and individuals from excluded groups attending those events. When the revision is made, it would be helpful to divide the 50% so that there is a percentage for women, and a separate percentage for individuals from minority groups. This is necessary to track the project's progress in working with excluded groups and individuals more closely. / In the event, AAWAZ states that it has recorded the number of individual women and members of excluded groups participating in peace events. It is not clear where these number has come from but it is almost certainly a very large under-estimate as explained below. / Target Achieved / 1,000 8,860 / During the last year AAWAZ organised 2735 peace events that brought from people from different backgrounds together around a shared interest, value or common cause. Even if it is assumed that only the members of the local forums attended these events, which we know is wrong, that would mean a total of 54,700 participated, with 50%, or 27,350 of these being women or individuals from excluded groups. In fact, these "melas" took a variety of forms including, for example, sports matches, peace walks, baking contests, handicraft contests, music events, theatre, public speak competitions, and appear to have been universally successful in attracting large and diverse crowds. / Many consortium partners have arranged public celebrations of minority festivals or holidays. The results have been impressive. For example, Christmas Day was publicly celebrated in Swabi and Attock Districts for first time in the history. And in Attock the AAWAZ District Forum scored another first by holding a public celebration of the ancient folk festival of Lohri which is most closely associated with Hinduism. In an astonishingly rare expression of tolerance Muslim, Sikh and Christian community members also participated in the ceremony. / Interestingly, older women are taking an active part in conflict resolution in some communities, able to do this because of their different status. In general, the conflicts addressed by women relate to domestic disputes and to those related to marriage. According to the Beneficiary Assessment Feedback, older women have however, resolved more complex conflicts related to debt settlement and Swara (giving girls to settle disputes). Issues of property, dispute among men and other’s related to public goods are seen as men’s domain. / Some specific achievements include: / In Sargodha, the district team helped strengthen linkages between district forums and Masalehati (Reconciliation) Committees and Bar Associations. The District Bar Association formed a legal committee to provide free legal aid, especially for AAWAZ UCs. / An MOU was signed with the Department of Sociology at BZ University in Multan to engage youth in enhancing tolerance and channeling positive energies / In three districts Christian graveyards were protected / After months of continuous effort, the district forum resolved a sectarian conflict in Kyushu. / In a number of districts, official District Peace and Reconciliation Committees have invited AAWAZ forums to be engaged in their work / Output Indicator 2.3 % of people in programme districts who consider AAWAZ community cohesion mechanisms to be credible and effective / NOTE: AAWAZ figures refer to the percentage of women in programme communities, not people in districts. / Target Achieved / 5% 15% of women / The source for the figures are the Rapid Surveys 1 & 2 which interviewed women in selected villages/settlements from 13 AAWAZ districts asking if community cohesion mechanisms of AAWAZ are credible and effectively helping them resolve disputes and encourage social cohesion.
Issues: / Setting targets for resolving disputes has created a risk of reinforcing patriarchal values and customary practices and losing focus on AAWAZ’s primary stakeholders, women and excluded groups. Without proper training it is inevitable that communities will slip back into traditional dispute resolution customs. That this is happening is clear from the examples of dispute resolution in the quarterly reports that frequently note the involvement of jirgas or panchayats in resolving conflicts. / These traditional councils are dominated by local elders and rather than following due process, they base decisions on a combination of religious edicts, patriacharchal values and prevailing cultural norms which discriminate violently against women and go against the law of Pakistan. / While both review team field visits and case studies demonstrate instances of women and minorities being successfully supported by AAWAZ in disputes, the team also came across one AAWAZ peace committee which included panchayat members. This committee was happy to speak about a criminal case where a woman had been forced to swallow acid by her husband, which after local negotiations it was about to settle out of court through wani - a custom whereby young girls are forcibly married or simply given into another clan or household to resolve a fued. / Capacity building on conflict resolution has been weak. Mediation, negotiation, dispute resolution and peace building skills are not developed in a few hours, nor without the opportunity for extensive practice in safe settings. This is especially true when their use needs to be guided by a focus on gender, inclusion and democratic process. / The output manual seems to understand this and lists 15 essential output 2 topics that need to be covered in trainings (the first topic alone could easily consume five days). It also states that before work begins, a cadre of trained consortium partner staff should be developed. This cadre was supposed to field test its learning and skills before developing and deliver training to district level staff and civil society organisations. Once trained, district level staff and partners would cascade the training to AAWAZ forums at all levels of operation. And finally the village forums themselves would conduct comprehensive training programme with community members. / Quarterly reports also recognise this issue: "The most sensitive part of the programme at village level is developing the skills of local communities to identify, pre-empt and resolve disputes... (forums) require extensive input from district teams of partners to learn and accept a framework for conflict resolution that is not based on a subjective understanding of the prevailing cultural norms but is in line with the state laws." / Nevertheless, in practice the quality of the training held at the national level was very weak and its duration insufficient for a training of trainers. The consensus view amongst district staff is that the training on this output was both insufficient and of poor quality. The model for cascading the training suffered from the same constraints as the training in the other outputs – the top layer of staff expected to condense the district level training into half the number of days, with further condensations at all levels below this, meaning there were negligible inputs at the level of the village forums. / Given the negligible capacity building by AAWAZ on output 2 issues, questions of attribution are inevitable. How realistic is it to claim that simply creating a peace committee and asking women and men to focus on dispute resolution has in and of itself resulted in more disputes being resolved or resolved in keeping with AAWAZ objectives. It raises the concern that disputes that would have been resolved as a matter of course are being attributed to AAWAZ. / To date, compared with other outputs, advocacy on this area seems weak but must be an essential element in the future if Province-wide milestones are to be reached. / Despite the development of a reporting mechanism to track local disputes and resolution processes. Qualitative data analyses that could guide and troubleshoot glitches in the processes and make sure that women and excluded groups are not being victimised because of cultural norms have not been carried out. This was not a failure of output 2 staff but a result of the poor performance of the partner responsible for PARR (see output 4 below). / Recommendations: / As a matter of urgency, AAWAZ should review and restate to staff and implementing partners its policy of not involving jirgas, panchayats and other similar bodies in dispute resolution. At the same time, it should prepare guidance notes for how staff, partners and forums can avoid doing this without attracting a hostile reaction from these bodies. The attitudes of these traditional structures conflict with AAWAZ's commitment to women's rights and excluded groups and to democratic processes and the rule of law. / AAWAZ should review its emphasis on dispute resolution. The review team believes that a better less risky way to achieve its objectives could be to focus on: / prevention through peace-building activities, interfaith dialogues, the joint celebration of religious festivals by women and men of different faiths, gender-sensitisation and promotion of non-violence through creative means / advocacy at district and provincial levels informed by experiences from district and community work but also by a sophisticated understanding of effective national and international alternatives. The issues suggested in the Output Manual to advance and improve citizens' rights to protection and justice including establishing provincial level human rights commissions alongside active Citizen-Police Liaison Committees, Union Public Safety Committees and Musalihat e Anjumans, etc. are in place. / develop and implement sustained campaigns at district and/or provincial levels rooted in persuasive communication (or another attitude change theory) to promote tolerance, non violence, alternative forms of dispute resolution, etc. / To support the future direction of Output 2 an improved, properly resourced capacity building plan must be developed that ensures acceptable amounts of time are devoted to training at all levels. This must be accompanied by a user friendly manual with specific training sessions designed for different types of audience, including non literate village audiences. It should be assumed that village level forums need as much or more training than HQ staff / Impact Weighting : 25% / Revised since last Annual Review? NO / Risk: High / Revised since last Annual Review? NO

Output 3: Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab
Output 3 score and performance description: Score is A / The purpose of this output is to equip forum members and their communities with the skills and tools to engage with government to foster mutual accountability and improve their daily lives. The aim is to break the traditional patron-client, and or kinship (biradari) relationships through which deals are done and services delivered by working through state and legal mechanisms. / Given the emphasis on the involvement of women and excluded groups and on the need for genuine democratic process, this output demands a specific form of governance advocacy. This is likely to mean that results are slower to be seen but the faster alternative - using community bigwigs and traditional patronage routes - while delivering services, undercuts any attempts to move away from business as usual. / A project that aims to empower women and excluded groups, promote rights and democratic processess and build social capital to promote and protect tolerance can attract hostile attention from extremists. Although it is not the output's main purpose, its apparently non contraversial nature - getting government to provide services - helps to protect the project and its stakeholders from excessive attention and aggression.
The 2014 Beneficiary Feedback Assessment report states that the highest impact of the AAWAZ programme is felt in the area of rights awareness and improvement in governance/service delivery, especially in the areas of education and health. And that "In all areas, the forum members mentioned an improvement in service delivery including quick redress of complaints and increased teachers/health officials’ attendance in schools and BHUs. Beneficiaries also mentioned that communities were resolving local level issues like sewerage, cleanliness at local level and they were contributing financially to the efforts." [5] / Progress against expected results: / Output Indicator 3.1 Number and types of issues raised by the local communities through AAWAZ Forums with increased participation of women, girls and other excluded groups / Milestone Achieved / 2,000 4,754 / AAWAZ reports that approximately 40,960 forum members were engaged in this process. The composition of the forums meant an automatic and significant increase in the participation of women, girls and other excluded groups. It estimates a further 281,000 or so community members were involved in advocacy activities to hold local government and politicians to account. / During the last year, orientation was given to forum members in all districts that raised community levels of awareness regarding the processes through which local priorities are incorporated in District budgets. This covered the rights of citizens to basic services, their role in holding government departments to account, the different channels available for lodging formal complaints against corrupt officials/ departments, advice on data collection and in some districts how to lodge a Right to Information request. / The orientation prompted a host of grassroots and district level advocacy initiatives and increased the range of social actors engaged in political life. Forum members and their communities are learning the value of a united voice and the benefits of using data and dialogue as well as protest when building relationships with district and local authorities. Collaborative engagement with government has increased mutual respect, accountability and access. Women forum members told the review team found that their involvement in these activities has given them new confidence and increased their self esteem. / Output Indicator 3.2 Number and types of service delivery outlets improved in the areas of health, education and other priority areas benefiting women, girls and other excluded groups / Education/health issues addressed / Milestone Achieved / 900 1,011 / Other issues addressed / Milestone Achieved / 450 358 / Other issues addressed included safe water supplies, irrigation, rubbish collection and similar problems with the village environment. / In line with the AAWAZ focus on education, many village forums held meetings with School Management Committees and Parent-Teacher Associations. The issues discussed included teachers not present or behaving irresponsibly, high dropout rates, lack of basic facilities including drinking water, toilets for girls, and unhelpful attitudes of police departments. / Some selected achievements of individual forums regarding education include: / In Bhakkar, school development plans for 60 schools were based on assessments provided by AAWAZ forums and reflected forum's and priorities and targets for improvement. / In Okara the district forum set up enrolment camps in 10 union councils which its members say resulted in the enrolment of some 3000 children from poor communities. / In Jhok Sikandar village, (D I Khan), no primary education was available to girls. The forum, along with local notables, lobbied the Education Department to either open a girls' primary school or allow local girls to enrol in the boys primary school and provide additional teachers to cope with the extra numbers. The Department approved the enrolment of girls in the boys school and appointed three additional teachers. This was an impressive accomplishment and also brought about a positive change in local attitudes regarding co-education. / Also, in DI Khan a Right to Information application and follow up advocacy eventually resulted in the re-opening of a school that had been closed for 30 years . / In Attock district, the laboratory in the Government Boys’ High School, Golra was re-opened with the support of the DLO, and two vocational centres were opened in UC Golra. / Output Indicator 3.3 Percentage of women and other excluded groups satisfied with the quality of services has improved in result of AAWAZ accountability initiatives / Milestone Achieved / 5% 41% of women / The source for the 41% comes from the Rapid Survey 1 and 2 which asked women in selected villages/settlements from 13 AAWAZ districts if they thought that social services (education, health, water and sanitation) had improved over last 12 months. / Issues: / A strong focus on targets for ‘demands met’ combined with communities' desire for tangible results risks preference for advocacy through those who are influential. The targets for ‘demands met’ combined with an understandable community desire for immediate results tilts the balance in favour of getting the more influential community persons or the implementing partners to take the lead. While initial accompaniment by such bigwigs is acceptable, without a clearly articulated inclusive, people-centred approach to advocacy and a long term capacity building programme, it is unlikely that AAWAZ's primary targets, women and the excluded, will be able to independently develop robust and effective relationships with political representatives and government departments need to be addressed. Instead they will remain as participant bystanders. / Inclusive and participatory decision making has a cost. For the poorest households, the loss of earnings involved in attending village or UC level meetings can be prohibitive. Although, during the inception phase, citizens had eagerly participated and decided their development priorities in their communities, there was feeling that participation could be a luxury for some people which they could not afford to do this on long term basis. / Travel costs for women, poor and excluded groups are an issue about which district staff feel strongly. Noting that forum members with low or no incomes are very reluctant, or simply unable, to afford the fares needed to reach UC and lobby meetings, they point out that AAWAZ needs to recognise that the result is that poverty is acting as a barrier to inclusive membership of UC forums. This point is also made by beneficiaries themselves.[6] / Capacity building on advocacy has been weak. The training for this output at the national level was of poor quality and too short for a Training Of Trainers. As with the training for other outputs, staff were expected to cascade the training into progressively shorter sessions for district staff and AAWAZ forums without the support of either customised training for different levels or good quality manuals. The result is that capacity-building for advocacy has been negligible where it is most needed – at the village level / AAWAZ reporting on this output is failing to do it justice. Monitoring of output 3 needs to improve and include quantative and qualitative indicators that capture the less tangible but significant changes that are happening. / Recommendations: / AAWAZ should reinforce the need for implementing partners to mentor and guide the AAWAZ forums and facilitate their direct engagement with line agencies and public agencies as opposed to playing that role themselves. / It is essential that expectations are carefully managed, especially at village and UC forum levels. When communities know that using their new, AAWAZ facilitated, links with local notables could achieve things more quickly, persuading them that using more democratic means to achieve their objectives will be worth it in the long term, will not be easy. AAWAZ should provide guidance for district staff and partners on the most effective ways to get the message across. / Having clear, measurable goals regarding opening democratic space, establishing dialogue with government, etc. will be useful in this regard. / AAWAZ also needs to discuss with DFID the trade off between long term improvements in governance and immediate results, so that the issues involved are fully appreciated. / The Programme Management Committee (PMC) should address the issue of poverty preventing participation and find workable solutions. In other programmes, solutions have included scheduling meetings and trainings so that they take place outside working hours, and, for women, do not clash with key household responsibilities like meal times. Serious consideration should be given to reimbursing actual travel costs for the poorest forum participants but only as part of a long term plan that gradually transfers these costs to the forum itself. This could be part of a move towards long term sustainability of village and UC forums as it might encourage them to engage in creative community level fundraising. / The MO and consortium partners need to develop and resource a plan for high quality advocacy capacity building of women and socially excluded groups at the grassroots, with a strong emphasis on people-centred advocacy approaches. Local advocacy specialists with a strong understanding of people-centred/grassroots advocacy should be contracted to implement the plan and create materials suitable for use at village level and in Agahi centres. / Advocacy training should also be provided to district staff and implementing partners that gives them a strong conceptual framework for this work. Training should emphasise the implications for short and long term results of employing different approaches and methods. It should also address communications work, including the use of new media and technologies, as part of the advocacy toolbox. / The Steering Committee should explore the reasons for weak reporting and monitoring on this output and take remedial action. Monitoring must capture changes in democratic participation, government responsiveness and governance related improvements that already can be seen. / Impact Weighting: 25% / Revised since last Annual Review? NO / Risk: Low / Revised since last Annual Review? YES - AR 2013 rated it medium
[5] See Viqar, F et al, AAWAZ Voice and Accountability Programme, Pakistan, Beneficiary Feedback Assessment Report, May 2014, DFID Pakistan
[6] See Viqar, F et al, ibid

Output 4: Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa and Punjab
Output 4 score and performance description: Score is B / Team Observations: / Performance on Output 4 remains the weakest area in AAWAZ and both its constituent functions, PARR and Monitoring and Evaluation (M&E), are the most troubled in the Programme. However there are clear signs of revival in PARR after its restructuring, with the formation of the Strategic Learning Unit (SLU) whose promising early performance and sense of direction pull Output 4 score up to B. This is not the case with M&E which has stagnated badly owing to continuing conceptual problems stemming partly from programme design and partly from the poor performance of the former implementing partner the Sustainable Development Policy Institute (SDPI); this has been exacerbated by the reluctance of both DAI/MO and the remaining Consortium partners to take ownership for M&E. The recent withdrawal of SDPI from AAWAZ however, clears the way for a radical overhaul of M&E. / BACKGROUND / PARR and M&E were all the responsibility of "Consortium B" was to be managed by SDPI with assistance from overseas partners that never materialised[7]. / i) when there were problems with initiating PARR, the research effort stumbled badly in terms of quality and timeliness and the monitoring effort never got going; / ii) conceptually the Consortium A partners as well as the MO regarded monitoring as the responsibility of a third party and never took ownership of the AAWAZ monitoring function (as distinct from the partner organisations own, widely differing monitoring systems) - this was very much the case when the AR 2014 Team began work. / Surprisingly for a highly experienced organisation, SDPI showed considerable passivity and lack of initiative in addressing its problems. This included a failure to support the AAWAZ programme with sufficiently well qualified technical expertise. / Consistent shortcomings in Output 4 results meant a very critical report and rating from the 2013 Annual Review team. This led to SDPI/PARR being put on a Performance Improvement Plan (PIP). The PIP required SDPI to deliver a steep improvement in performance and achieve rapid results. Regrettably SDPI failed to do this, as recorded in the dismal September 2013 PIP Progress Report. / These last needed further examination which led to the AAWAZ Programme MONITORING, EVALUATION AND PARR Independent Review and the PARR Restructuring Plan. / The latter's main recommendations were to merge the Consortia bringing in SDPI with the same status as Con A partners with a set of clear functional deliverables and responsibilities to the AAWAZ programme.; establish a Strategic Learning Unit (SLU) which would incubate PARR functions (except policy analysis and research, which was to remain in SDPI); Bring the Response Fund into the MO and find an external body to carry out M&E. / Currently: / i) SLU was created and has begun work well; / ii) SDPI continued to underperform and has now left the Consortium / iii) Monitoring was not a central concern of either the Independent Review or the PARR Restructuring Plan and remained neglected by AAWAZ
Progress against expected results: / Outcome Indicator 4. % No of policy changes/reviews successfully advocated for with provincial and decision makers, national legislators and politicians. / Baseline 2013-14 2014-15 2015-16 2016-17 / Planned / KP / Punjab / National 0 / 0 / 0 2 / 2 / 2 4 / 4 / 4 6 / 6 / 6 8 / 8 / 8 / Achieved / KP / Punjab / National 2 (in-progress) / 2 (in-progress) / 3 (in-progress) N.A N.A N.A / This indicator represents commencement of continuing engagements with legislators at national and provincial levels for policy changes ("advocacy under way" in AAWAZ terminology). It is too early to judge the efficacy of these processes. / Output Indicator 4.1: / a) Cumulative no of quality evidence-based policy studies shared with politicians and decision makers / b) Cumulative number of quality media initiatives undertaken by PARR aiming to create mass awareness and mobilisation on laws and policies specifically on gender equality, tolerance and inclusion in political processes. / Baseline 2013-14 2014-15 2015-16 2016-17 / Planned a) / Planned b) / TV / Radio / Print 0 / 0 / 0 / 0 2 / 12 / 12 / 12 8 / 36 / 36 / 36 14 / 60 / 60 / 60 25 / 84 / 84 / 84 / Achieved a) / Achieved b) / TV / Radio / Print 7 (3 SLU + 4 SDPI) / 8 / 45 / 16 / Target a) which is fairly modest would appear to be overachieved but in the rush to utilise funds and meet targets, SDPI produced a number of sub-standard studies. SLU was given the task to "repair" these and produce some of their own briefs. The following briefs are fit for purpose: / 1) Role of Political Parties in raising Women's Political Participation (prepared by SLU) / 2) Accountable provincial-local partnerships for improving service delivery (prepared by SLU) / 3) Traditional forms of ADR - The Case for Proscription (prepared by SLU) / 4) Partial Disclosure of Polling Data (prepared by SDPI under SLU supervision) / 5) Removing Roadblocks to Electioneering and Election Day (prepared by SDPI) / 6) Issues of Service Delivery and Citizen's Complaint Redress (prepared by SDPI) / The following brief was not of acceptable quality: / ADR and Women's rights in the local sphere (prepared by SDPI). / While the target for the year was (to prepare six policy briefs) was met, this was a result of an entirely new body (SLU) being formed to address the continuing shortcomings in PARR. / The target is met albeit with SLU intervention / As to Target b) while the Team was not in a position to judge the television appearances, a sampling of the 45 half-minute radio spots (produced by Consortium Partner SPO) appeared to be quite effective and the print articles sampled, most of which were of the op-ed type varying from 700 to 1000+ words each also appeared acceptable. / Thus: TV target is partially met; Radio target is overachieved; Print target is overachieved; despite the shortfall in TV appearances, overachievement in radio and print mean / The target is met / Output Indicator 4.2: Cumulative no. and types of quality advocacy campaigns initiated by AAWAZ partners, consolidated, synthesized and analysed by PARR / Baseline 2013-14 COMMENT / Planned 3 6 Baseline figure not understood. / Only three advocacy campaign reports were made available to AAWAZ, one of which is not acceptable and being "worked on" by SLU. / Target not met / Achieved 3 4 / Detail: Of the three advocacy campaign reports, the ones on "16 Days of Activism" and Report on Local Government Elections Campaign were fit for purpose, while the AAWAZ Consolidated Elections Report was not of acceptable quality. This last is being rewritten by SLU. / Target not met / Output Indicator 4.3: Number of organizations capacitated and commissioned in carrying out quality research and advocacy initiatives to inform AAWAZ and other programmes on selected themes / Baseline 2013-14 COMMENTS / Planned / Commissioned / Trained Orgs. 8 / 0 16 / 4 Commissioned: Target not met but all PARR activities are on hold / Trained: Claimed met but see below. / Achieved / Commissioned / Trained Orgs. 8 / 0 0 / 4 / DFID and MO decided to pause activities relating to the Response Fund until PARR restructuring is complete and SLU is able to commission quality research. / The "trained organisations" refers to the two-day "AAWAZ Training Workshop on Political Economy Analysis Through a Gender Lens" delivered by SDPI. Regardless of the quality of the training about which the Team cannot comment, a two day training delivered as late as May 2014 cannot validate AAWAZ's claim having trained its partners. / Targets not met or on hold / Issues: / The current situation regarding output 4/PARR requires serious and immediate thinking from the Steering Committee and MO about what is needed from this output in the future and how its future success can be guaranteed. / While AAWAZ has a rudimentary monitoring system this does not systematically collect and reference back-up data, there is no way to assess whether achievements claimed are real or whether numbers stated actually represent meaningful change. This situation, when added to other failures of PARR, could lead to a situation where AAWAZs' very real achievements in the field are never captured. In turn this means that no lessons from the work will be available to be shared amongst partners or with the outside world. / There is an urgent need to develop a robust monitoring system that takes a strategic approach to gathering information that will create an evidence base in relation to AAWAZ objectives and logframe as well as capturing less tangible changes using both quantitative and qualitative indicators. / Difficulties in finding a solution may be increased by the potentially troublesome and apparently contradictory views of the consortium partners implementing outputs 1, 2 and 3. Partners have expressed reluctance to be monitored by "outsiders" while at the same time being unenthusiastic about the MO taking on an expanded monitoring role. The rationale behind this thinking was not shared with the review team. / These factors and the urgency of the situation make it critical for the MO and the consortium partners to take immediate ownership of the M&E functions for AAWAZ as an integral part of their collective responsibility. / In the view of the review team searching for another external partner is unlikely to be the best solution at this point. AAWAZ would have little control over the quality of personnel actually deployed in the field. And would need an oversight team to check the monitoring operation. Being less attuned to the requirements of the AAWAZ programme, the external agency will be forced to move slowly in the early stages. The expense is also likely to be considerable. / Recommendations: / M&E / The Steering Committee should give the future of M&E urgent and thorough attention and come to conclusions that all members are committed to make work. A clear strategy and immediate plan of action should be agreed and implemented without further delay. This must include a decision regarding the location of any new M&E entity and should receive the active support of all Steering Committee members. / The Review Team believes that the best solution would be to create a strong and technically capable in-house M&E Unit located within the MO and under the direct management of the MO Team Leader who should take personal responsibility for its success. The unit should be supported by external STTA expertise as required. This would have a mandate to build capacity of consortium and implementing partners and to set up a robust AWAAZ M&E system. / Given the urgency and complexity of the above task, it will be essential to recruit new highly qualified, specialist M&E experts, one with senior management experience in this role, if possible in designing and mainstreaming M&E systems in similar large organisations. Others with proven track records of successful implementation of M&E programmes in complex organisations. The involvement of DFID or its nominated experts in the recruitment process is desirable. / There should be no dual, additional or "temporary" charges assigned to staff involved in M&E and all M&E staff should be fully capable of discharging the duties entrusted to them. / Given the urgent need for effective monitoring to begin without further delay, we recommend that while recruitment of such a unit takes place, the Team Leader of the MO in consultation with the consortium partners and DFID, should contract one or two senior M&E specialist consultants, ideally persons already familiar with the AAWAZ programme, to begin designing the new system. These consultants would / work closely with SLU and the monitoring experts in the consortium partners; / provide support with recruiting the new Unit's staff; / be managed by the MO Team Leader who would have responsibility for the timely delivery of their outputs / The Team has been informed that SDPI has resigned from the AAWAZ Consortium and the MO on the direction of the AAWAZ Steering Committee is are currently executing a disengagement plan with them. The disengagement plan should be executed as swiftly and cleanly as possible and DFID should track the process closely. / SLU / From this point on, SLU must change its focus and use its talents to deliver new, high quality deliverables of its own. / The Research Advisory Group must be formed in practice as opposed to on paper and must begin its work immediately. / The SLU's scope of responsibilities should be carefully defined to avoid overload. Ideally these should include responsibility for knowledge management and learning, shared with the entity responsible for M&E. / An urgent priority for SLU is to design and commission of a credible baseline to collect, inter alia, the data required for measuring logframe targets. / Too many diverse tasks should not be heaped on SLU's shoulders. / If SLU needs further qualified personnel or other resources to meet the requirements of their work, these should be made available. Unqualified staff should not be forced on SLU. / It would be desirable for SLU staff to regularly spend a week or so with different consortium partners in order to familiarise themselves with AAWAZ's operating procedures and fieldwork. / Impact Weighting : 25% / Revised since last Annual Review? NO / Risk: Medium / Revised since last Annual Review? NO
[7] A fuller background is available in Appendix 1 PARR to the AR 2014 Narrative Report

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Yes / It was updated after the last Annual Review incorporating some but not all the review's recommendations. Further improvements are needed to clarify exactly what is being measured. And to measure changes in women's status and in community relationships with government. / 1.2 Overall Output Score and Description: A / AAWAZ has been scored against output deliverables and progress over the 12 months since the last Annual Review. The project has achieved a series of impressive achievements, especially in relation to outputs 1 and 3, both of which scored A. Major transformations have taken place in the lives of thousands of women, in how they relate to local government and politicians, and in the services that are available for them to use. Performance against output milestones is uneven but the under achievements are compensated for by large over achievements in other areas / The difficulties with the way output 2 is being implemented (discussed in Section A) meant it scored B. However, the review team believes with a shift of focus, this output could play an important role in the promoting tolerance and peaceful debate in a context where these are under constant threat. / The problems with output 4, and the fact that the PIP did not result in the changes needed, meant that for 9 months AAWAZ suffered from a lack of quality research and M&E. Hence the B grade. However, the new Strategic Learning Unit formed in March gives cause for optimism. Nevertheless, AAWAZ must act urgently to ensure a top quality M&E unit is formed and a new, more strategic M&E system is up and running as soon as possible. / 1.3 Direct feedback from beneficiaries / A comprehensive beneficiary feedback study took place in April and May 2014. It's key findings fit with those of the review team. For example, regarding women's participation at all levels in the social and political spheres and men becoming sensitised about girls and women's rights; service delivery improving and government becoming more responsive; increases awareness of women and men on rights to services and holding officials accountable; etc. The report states that social capital is developing more strongly than expected at community level due to: the effective organisation of community women and men in the village forums with a defined purpose, focused interventions and a place to gather; and increased networking and development of linkages between people already active, especially at village and Union Council levels. / Recommendations include: reinforcement of representation of excluded groups in AAWAZ forums and regular gender sensitisation of all AAWAZ forum members; strengthening district staffing resource for engagement with AAWAZ forums where it is weak; increased training and awareness raising; and flexibility re the focus on education and health in order to be able to respond to other community priorities. / In addition, the report recommends more cross learning between consortium and implementing partners; having a strong M&E and Learning system; more regular and systematic flows of information from Islamabad to the field offices; better gathering of information from field level that is fed into policy debates; and developing an understanding of the impact of different implementing partner approaches to community engagement and replicating the most successful. / Finally, responding to comments that there is very little direct engagement via field visits between the DAI Management Organisation and the beneficiaries, the report recommends the Managment Organisation should create a direct beneficiary feedback mechanism.
1.4 Summary of overall progress / Overall, progress to date has been good. Over the last year, the AAWAZ programme has expanded to all 45 programme districts and established village, union council, tehsil and district forums in more than 90% of the target area. This is an impressive achievement in its own right, given the often difficult context. / Women members of AAWAZ village, UC and district level forums recognise their right to be present and express their views in public spaces including rallies, lobby meetings with local government and politicians, and Khuli Katcheri (open court) sessions. They report having increased confidence and self esteem as a result. / AAWAZ has supported 36,625 women to obtain CNIC registration, the basic building block of citizenship in Pakistan, and helped 23,364 move to the next step of being registered as voters. / In the Punjab of 1441 women were encouraged to file nomination papers for local government positions and 421 were able to do this, before the elections were cancelled. / Working with allies, the project has influenced the adoption of legislation that improves the status and legal rights of women including positive reforms of the Local Government Acts in KP and Punjab. / More than 2700 peace events have been held across the AAWAZ Districts bringing people from different backgrounds together. Even more impressive is the fact that some AAWAZ partners have organised public celebrations of festivals belonging to minority religions in which all other faith groups in the area have participated. This is unheard of in the current context and is a remarkable example of increased tolerance. / A host of grassroots and district level advocacy initiatives have increased the range of social actors engaged in political life with communities learning the value of a united voice and the benefits of using data and dialogue to build relationships with district and local authorities / With a future focus on deepening and strengthening the implementation over the coming 12 - 18 months, it can achieve much more.
1.5 Key challenges / In addition to the challenges regarding the internal workings of the AAWAZ programme, there are a series of external challenges to be faced. / The continuing absence of local government and no dates set for elections in Punjab or KP will make women's participation in formal politics very difficult to achieve. It is extremely unlikely that village women could stand, let alone be elected, to provincial level political bodies. AAWAZ needs to reflect on this and discuss with DFID alternative paths to their political empowerment. Any changes must be reflected in logframe indicators. / The security situation in KP remains a serious concern. AAWAZ staff are sometimes denied permission to travel (NOCs) by the security services and the overall space for development initiatives is shrinking, along with tolerance and the space for democratic debate. Work on the rights of women and excluded groups is especially sensitive. In addition, the province is characterised by harsh weather and harsh terrain, poor infrastructure and transport services, poverty and in some areas entrenched extremism. Nevertheless, consortium partners and their staff are determined to continue operating. As they rightly claim, it is precisely in these areas that the need is greatest. However, it is essential that all partners working in KP and the MO make very regular assessments of the security situation and are careful to minimise the risks to themselves, the communities they work with and the AAWAZ programme, in whatever ways are necessary.
1.6 Annual Outcome Assessment / The outcome of the project is: Democratic processes in Pakistan are more open, inclusive and accountable to citizens. / This is a very ambitious outcome given the extremely poor state of governance in Pakistan. It is unrealistic to expect any single project to achieve improved democratic processes across the whole nation in five years. However, AAWAZ is well placed at provincial level not only to protect the democratic space that exists but also to expand it through work at vilage, district and provincial levels. As reported, accountability between local line agency officials and politicians has already increased in districts where AAWAZ is working. There is no reason why increased openness and inclusiveness should not also be achieved. / For a bigger impact, the project will need to develop imaginative advocacy and communications strategies that seek to influence opinion on a much larger scale. Clearly there will be risks in becoming widely known as an organisation promoting inclusive change. This will demand a very careful assessment of potential issues and the vehicles through which this type of influencing takes place.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / So far the AAWAZ programme has spent about 33% of its total programme budget in 42% of the programme period. ( The inception phase was completed in nine months instead of 12 months and the project is currently in its sixth quarter from a total of 16 quarters during the implementation phase.) / An analysis of the expenditure pattern shows that the project has spent 80% of its total allocation from the start of the project up to April 20th, 2014. This level of expenditure is better than normal for similar projects at this stage of their development. Figure 1 below illustrates the actual expenditure and projected trends if the current trends continue. However, it is expected that the expenditures will be made more-timely now that the major items to be procured have been acquired. / Table1 Expenditure Pattern and Projected Trends / An analysis of the expenditure pattern by partner, by output and by category of expenditure was also conducted. An analysis of the budget by output shows that Output 1 was able to utilise 87% of its budgeted funds during this period compared with 77% for Output 2, 61% for Output 3 and 78% for Output 4. Output 1 costs include the overall cost of community mobilization through establishing the forums at the various administrative tiers which is the institutional anchor for the other outputs. / The Aurat Foundation was given the largest share of the budget, consistent with its area of responsibility, with Sungi having the smallest share because of its lower district outreach. From among the Consortium partners, Aurat Foundation has had the lowest spend so far at 71%, followed by Sungi at 78%, SPO at 80% and SAP-PK at 88% (Table 2). The MO has a high utilization rate of 87% which was to be expected given that its funds are mostly being used for management fees, technical back-stopping and salaries of staff at the head office. / 2.2 Key cost drivers / A review and analysis of overall inputs and costs as presented in the AAWAZ accounts revealed that personnel costs consume the largest share of the budget, with fees comprising 48% and operations 15% of the total. This ratio of overhead to programme costs is very high compared to other DFID funded projects. / However, in empowerment and governance programmes, people are the project and it is normal practice for all field staff as well as advocacy staff to be included under the programme budget, something that has not happened in this case. / The review team notes that the costs analysed and presented in figure 1 below exclude the fees and costs of services provided by DAI International (as opposed to the MO). These were unavailable to the team on the grounds of commercial confidentiality. Without knowing the size of the charges made by DAI's international[8] for its support to the MO and the AAWAZ project it is not possible say how these compare to similar organisations supporting similar project, nor to assess whether these costs represent good VFM. We believe it would be useful for DFID to review DAI international fees, costs and charges made against the project itself before reaching final conclusions on ratios. / 2.3 Is the project on-track against original timescale: Yes and No / Outputs 1, 2, and 3 are on track but Output 4 is behind schedule due to the problems with the consortium partner. This partner has now formally disengaged from the project. Part of output 4's remit has been taken over by a newly formed Strategic Learning Unit. But the project still has some catching up to do in terms of establishing a high quality M&E unit. The review team has prepared a Programme Action Plan to ensure this happens without delay. / As soon as this has happened the M&E issue is in train, the project should address the issue of establishing an effective knowledge management and learning (KML). This is present in individual consortium partners but not operational for the project as a whole.
[8] DAI London and Washington plus any technical support from offices located elsewhere

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The latest version of the AAWAZ Theory of Change (ToC) improves on previous editions but it still needs more work. The current ToC has a partial analysis of the obstacles to change then jumps straight to what it wants society to look like. Only the "strategy" side bars give any indication of the steps the project might take to move towards societal goals but these are not linked to specific change pathways. / The review team has recommended that a team made up of representatives from all the partners should prepare a revised theory of change with clear pathways that demonstrate how AAWAZ activities generate the desired changes and what assumptions are made about context and behaviours at every stage. And that an external expert is brought in to facilitate this process. / The external evidence regarding effective social marketing (aka behaviour change communications) that appeared in the last Annual Review template is still relevant and should inform AAWAZ's future work in this area. / New external evidence includes a paper by Bicchieri and Mercier is a useful and relevant addition to the literature on changing social norms (Cristina Bicchieri and Hugo Mercier, Norms and Beliefs: How Change Occurs, February 2014 available at: http://www.academia.edu/1596868/Norms_and_Beliefs_How_Change_Occurs / They argue that: / One of the reasons that tackling a relatively central belief often entails a prolonged process is that many peripheral beliefs have to be modified first. / Social norms are supported by shared normative beliefs. Therefore the process of belief change has to be a collective one. People, in other words, have to change their mind together. / Legislative driven change is most successful when it takes small steps that keep it close to the prevailing soccial norms rather than trying to achieve a major change all at once. If the size of the change is too big, it is unlikely to be accepted or enforced. / Discussions and deliberations often allow people to change their normative beliefs and, therefore, the normative expectations related to an old norm that has to be challenged. Still, even the disappearance of the previous normative expectations may not prove sufficient / Group discussion, as opposed to individual discussion, is important because, if a group is confronted with a persuasive argument, and people see others accept it, then they may feel free to accept the argument themselves. Accepting an argument and changing behavior, however, are two different things. / Deliberation is the best tool to induce belief change, but it doesn’t scale up very well: Studies show that as groups grow larger, pre-play communication aimed at inducing cooperative behavior breaks down more easily, as it becomes more difficult to create the trust necessary to support commitments to cooperate / The difficulties highlighted mean that deliberation cannot be the only means through which a norm can change when large numbers of people are involved. Activists understand this very well, and so they rely on a variety of other media to effect norm change, from ad campaigns to spreading new words that encapsulate a normative statement (such as “homophobic”). / The greater the loss (for example, damage to the daughter’s reputation) resulting from a failed effort to shift to a new norm, the more people need to be sure that a sufficient number of people in the community will together act to adopt the new alternative. All must see that all see that there is change. / Progress is very slow at first, as a few people gradually start to adopt a new norm. But when the tipping point is reached, change can be very sudden. It should then be expected that a slow and steady change in attitudes may not be immediately accompanied by an equally slow and steady change in behavior. On the contrary, behavioral change may be sudden and quite dramatic, and difficult to predict / 3.2 Where an evaluation is planned what progress has been made? / An evaluation was scheduled for midway through the project, i.e. half way through the coming year. Given the difficulties with output 4, the review recommends this is postponed until the beginning of year 3 when an evaluation will be able to make a more accurate judgement of the the future trajectory of the project, as well as an assessment of its past work.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Output 1 - Low / Output 2 - High / Output 3 - Low / Output 4 - Medium / 4.2 Assessment of the risk level / No local government; conflict areas barred; extremist takeover of districts or country;
Risk of funds not being used as intended / The project has robust financial systems, stringent procurement mechanisms, accounting controls, compliance mechanisms and internal and external audit procedures. The review team believes that fiduciary risk is minimal. / 4.4 Climate and Environment Risk / The project work involves only an insignificant impact on carbon emissions. / There is a risk of flooding, earthquake and other natural disasters. If these occurred in project districts they could interrupt or temporarily divert attention away from the main aims of the project.

5. Value for Money
5.1 Performance on VfM measures / The value for money assessment of AAWAZ was attempted based on the data available from project records, tabulating the results from the case studies and interviews with some members of the AAWAZ Forums at the different levels during the Annual Review. However, this assessment was hampered by the fact that much of the data and analysis required was missing. / VFM is not yet a core value for the AAWAZ programme. The project has adopted a narrow, economic view of Value for Money and has not yet fully integrated the concept into its work in a way that could inform choices about programme design, implementation and financial management. / During the current review an attempt was made to examine the different categories of programme expenditure for a better analysis of the specific ways in which the funds were being allocated and used. Within the programme budget, the main activities include group formation, orientation and training, meetings, conferences, advocacy and media campaigns, melas or festivals, establishment of Agahi centres and staff training, etc. The breakdown of the budget is presented by output, by year, by partner, by district. When all the disparate elements which fit into one-broad category are grouped together, it shows the opportunities for much more strategic utilisation of some of the funds and the potential synergies that could be captured for more cost-effective utilisation of funds with higher impact. / Table 1: Programme Budget and Expenditure (Year 1 to Year 4) / Programme category £ (%) Share of Programme Expenditure / Forum and Committee Formation 1,173,309 16.21% / Awareness/Orientation/Training 1,888,994 26.09% / Media and Advocacy Campaigns 1,328,092 18.34% / Festival / Mela 525,709 7.26% / Agahi Centre 669,953 9.25% / Meetings/conferences 97,608 1.35% / Exposure Visits 49,324 0.68% / Staff Orientation / Training 438,530 6.06% / M&E Activities 69,393 0.96% / Shadow Report 208,484 2.88% / Technical Assistance 25,871.61 0.36% / Administrative support to ADF 1.27% / Other 672,824 9.29% / Total 7,240,324 100.00% / The cornerstone of the AAWAZ implementation strategy is the establishment of forums at various tiers from the village to the district level. The forums are reported to have a total membership of about 88,500 of which roughly 48% are women and 75% are active. This means that from the 13 million households (94 million people) in the 45 districts, the programme has organised less than 1% as forum members. The extent to which the programme is able to extend its outreach to other households at the village, Union Council and district level depends upon the nature and scope of its activities. / Establishing village organisations and creating an apex structure at the Union Council level has been used by rural support programmes (RSPs) for the last two decades. The review team benchmarked AAWAZ costs against two other organisations (see Figure 2 below).[9] However, the costs are not directly comparable because the nature of the forums that are being created by AAWAZ are different from those created by the RSPs which operate only at community level and have a larger membership. Also, the costs of these programmes include the management costs for follow-up and supervision for a given period while the AAWAZ costs do not. Once AAWAZ partner and operations costs are included its costs may come to the same level as other programmes. / Figure 2: Average Cost of Community Mobilization (Rs) / 5.2 Commercial Improvement and Value for Money / As noted, the AAWAZ Management Organisation keeps a close eye on costs and a firm control on budgets in order to manage internal costs. Procurement rules are also strictly applied with centralised procurement for many items used regularly by the consortium partners and the use of Crown Agents for large purchases. / 5.3 Role of project partners / With the exception of the partner involved in Output 4 which has now disengaged from the project, the review team did not have time to undertake a thorough assessment the performance of individual consortium partners or their implementing partners or their delivery of VFM. / The apparent lack of a comprehensive picture of the lack of information regarding the roles and responsibilities of the large number of small implementing partners operating in AAWAZ districts, nor how they are supervised in terms of quality control, HR policies and security issues has been identified by the review team. Without a better understanding of the implications of working through a wide variety of implementing partners it will be impossible to assess whether this is more, or less, efficient and effective than working directly through staff. / 5.4 Does the project still represent Value for Money : Yes / Despite the lack of data needed to provide a full VFM analysis, the strong emphasis on economy within the project and its achievements to date indicate that it provides good value for money. / 5.5 If not, what action will you take?
[9] The World Bank (Second Poverty Alleviation Fund Project to Support Participatory Development through Social Mobilization. Report No. 40863-Pk September 14, 2007. World Bank) provided USD 75 million for the formation of 50,000 community organizations and 500 Local Support Organizations. This roughly comes to about Rs 90,000 per Community Organization (The total cost of USD 75m has been divided by 50,000 at the prevailing exchange rate of that time which was Pk Rs 60.) Another programme financed by the International Fund for Agriculture Development in the Punjab budgeted Rs. 45,000 for the creation and supervision of village organizations. In comparison, the cost of the initial formation and orientation of the AAWAZ Forums at the Village and Union Council level is Rs. 30,000 (This has been calculated by dividing the relevant budget categories with the number of forums at these levels).

6. Conditionality
6.1 Update on specific conditions / Not relevant to this project as it does not constitute financial aid.

7. Conclusions and actions
AAWAZ has already delivered significant achievements in the areas where it works: / The 2014 Beneficiary Feedback Assessment report states that the highest impact of the AAWAZ programme is felt in the area of rights awareness and improvement in governance/service delivery, especially in the areas of education and health. / A host of grassroots and district level advocacy initiatives have increased the range of social actors engaged in political life with communities learning the value of a united voice and the benefits of using data and dialogue to build relationships with district and local authorities. / Women members of AAWAZ village, UC and district level forums recognise their right to be present and express their views in public spaces including rallies, lobby meetings with local government and politicians, and Khuli Katcheri (open court) sessions. They report having increased confidence and self esteem as a result. / AAWAZ has supported 36,625 women to obtain CNIC registration, the basic building block of citizenship in Pakistan, and helped 23,364 move to the next step of being registered as voters. / In the Punjab of 1441 women were encouraged to file nomination papers for local government positions and 421 were able to do this, before the elections were cancelled. / Working with allies, the project has influenced the adoption of legislation that improves the status and legal rights of women including positive reforms of the Local Government Acts in KP and Punjab. / More than 2700 peace events have been held across the AAWAZ Districts bringing people from different backgrounds together. Even more impressive is the fact that some AAWAZ partners have organised public celebrations of festivals belonging to minority religions in which all other faith groups in the area have participated. This is unheard of in the current context and is a remarkable example of increased tolerance. / All the above represent major achievements and have transformed the lives of many women and excluded groups in a context where the barriers to their participation and freedom of movement are enormous. / Working with allies it has influenced the adoption of legislation that improves the status and legal rights of women including positive reforms of the Local Government Acts in KP and Punjab; the Punjab Women’s Empowerment Package, 2014, and Punjab Women Fair Representation Act, 2014. The latter reinstated a 33% reservation of seats for women after the Constitution (18th Amendment) Act 2010 had reduced this to 35 out of a total of 183 seats. / AAWAZ and its allies held a series of meetings with the Department of Women's Development to finalise the draft for the Punjab Commission on the Status of Women 2014 which was passed in March. Forum members also helped MPAs, NGOs and activists reach consensus on the Domestic Violence Bill, allowing them to speak with a united voice for the first time. In addition, / This is impressive progress for a project that has completed only 18 months of full implementation. / Rapid expansion has resulted in some problems. The review team recommend no further expansion into new communities or districts. Instead the emphasis should be on quality not quantity. / Areas that need attention include: / Village, UC and district forums. Greater conceptual clarity is needed about the composition and role of village, UC and district forums and the processes they should follow to ensure transparency, accountability and responsiveness in all their work. / Barriers to women's safe participation in public life. A clear strategy for addressing the structural, cultural and personal barriers to women’s increased safe participation in public and political spaces is needed, that recognises that simply having women present is insufficient. / Excluded groups. The Beneficiary Assessment describes AAWAZ work with excluded groups as weak and the review team agrees. A review of the barriers to greater inclusion would be a useful basis for moving forward. / Dispute settlement and peace building. This is the weakest of the three main programme outputs. AAWAZ claims re successes in dispute resolution are not backed evidence and are difficult to verify. Field visits indicated this area of work was uneven at best, unacceptably weak at worst. Staff report that capacity building was inadequate and of poor quality. A rethink by the Steering Committee is a priority recommendation from the review team. / A strategy for involving youth. This was identified as a missed opportunity by the review team and also was a strong recommendation from district staff. / Capacity building. The inverted pyramid whereby forums at village level, whose need is greatest, receive the shortest, least well targeted capacity building, while HQ staff receive the longest and best, needs to be turned upside down. It will be essential to take a more professional approach to training, bringing in specialists are required and ensuring that all sessions are tailored to their specific audiences with appropriate materials to match. / The review team has developed a Programme Action Plan to guide the work of the AAWAZ steering committee in relation to priority issues. These include: / Resolving the M&E issue is the top priority in a programme action plan recommended by the review team. It is essential that SLU and M&E are accompanied by a well thought out and properly staffed knowledge management and learning strategyProblems with PARR meant that monitoring and evaluation (M&E) service to the programme were inadequate. The proposed solution - to contract an external agency to be responsible for M&E - has not worked out. / Immediate action must be taken to ensure a credible baseline for monitoring is in place / Create a strong and technically capable in-house M&E Unit with a mandate from SC to build the capacity of consortium and implementing partners and to set up a robust AWAAZ M&E system / Support from STTA should be brought in as required / Unit to be located in MO with Team Leader taking personal responsibility for high quality and timely delivery of outputs / Unit to be staffed by new highly qualified, senior M&E specialists, ideally with a track record of designing and mainstreaming successful monitoring systems in organisations of a similar size. / Appropriate remuneration should be available for the right candidates. / AAWAZ cannot afford another mistake re M&E, so recruitment of right people for Unit key. SC to take joint responsibility for this. Alongside the MO Team Leader, a head of M&E from a consortium partner, plus a representative from SC and DFID should be part of selection panel. / Given the urgent need for effective monitoring to start as soon as possible and because recruitment takes time, contract one or two STTA senior M&E specialists, ideally persons already familiar with the AAWAZ programme, to begin designing the new system, / Output 2 needs review and revision / As a matter of urgency, the SC should delegate to the PMC the task of reviewing the policy and current realities re the involvement of traditional jirgas, panchayats, etc. in AAWAZ dispute resolution processes and make recommendations. At the same time, the PMC should prepare guidance notes for how staff, partners and forums can avoid involving these traditional structures without attracting a hostile reaction. The review and guidelines should be referred to the SC for final decisions and action. / The review team recommends that rather engaging in dispute resolution a better, less risky way to achieve its objectives could be to focus on: / prevention through peace-building activities, interfaith dialogues, the joint celebration of religious festivals by women and men of different faiths, gender-sensitisation and promotion of non-violence through creative means / advocacy at district and provincial levels informed by experiences from district and community work but also by a sophisticated understanding of effective national and international alternatives. The issues suggested in the Output Manual to advance and improve citizens' rights to protection and justice including establishing provincial level human rights commissions alongside active Citizen-Police Liaison Committees, Union Public Safety Committees and Musalihat e Anjumans, etc. are in place. / develop and implement sustained campaigns at district and/or provincial levels rooted in persuasive communication (or another attitude change theory) to promote tolerance, non violence, alternative forms of dispute resolution, etc. / To strengthen forums and agahi centres, a strategy needs to be developed in line with a revised theory of change that is based on an evaluation of AAWAZ’s experience to date and actively involves AAWAZ district staff, that clarifies and elaborates on the following: / role and key objectives for AAWAZ forums / implications of different membership formations and how members are chosen / differentiated strategy for more conservative areas / role of implementing partners at district level / guidelines for supervising and monitoring the performance of implementing partners / steps to ensure the effective functioning of Agahi centres / Capacity Building for Quality not Quantity / Capacity building plans for all four outputs must be developed within an overarching framework that includes amongst other things: / criteria to guarantee training content and trainers are good quality / sufficient time is allowed for training sessions at all levels It should be assumed that village level forums need as much or more training than HQ staff / each training is designed for its specific audience, including non literate audiences / a system for deciding priority areas for training / to prevent "training overload" establishes a centralised schedule of capacity building events that covers all outputs and subject areas. / To support the future direction of Output 2 an improved, properly resourced capacity building plan must be developed. / Capacity building plans for implementing partners should be developed as a priority since their work is key to the success of the project / Training on advocacy, especially people-centred and governance advocacy should be provided to both district staff and to forum members from the village upwards to increase the success of governance advocacy initiatives. / This should provide a shared framework for advocacy that, inter alia / prioritises direct involvement of women and excluded at all levels / explores the implications for short and long term results of employing different approaches and methods / gives equal value to “soft” and “hard” objectives / addresses communications work, including the use of new media and technologies as part of the advocacy toolbox / All capacity building should be accompanied by user-friendly manuals and materials to support and stimulate learning. These should include plenty of visuals and audio visual items for use with non literate participants that can be part of the resource collections in Agahi centres / Building on the work already completed by the MO and consortium partners, the final costed workplans for the coming year must be sufficiently flexible to meet the needs of different contexts and approaches and to respond to innovations. Greater flexibility in district budgets would be useful. / The MO should organise a thorough review and revision of the costed workplans to ensure these facilitate rather than constrict the programme. / The number of separate activities needs to be reduced, possibly by clubbing those that fall into the same overall thematic area or category together. / Some level of discretionary spending should be made available to District Coordinators / This need not involve any relaxation in the reporting, accounting and procurement rules. / The PMC should review the budgets for districts and consider whether and how to respond to reasonable requests from staff for additional personnel vehicles/transport and personnel. If no budget is forthcoming it should provide the SC with suggestions regarding how problems due to transport shortages might be resolved. / The MO should review district budgets and provide guidance to the SC on the implications of increasing resources for programme purposes including the development Agahi centres, participation of poorer forum members, running of District forums, etc. / AAWAZ should re-assign all field and advocacy staff to programme budget heads in line with normal practice. Other fee and operations costs should be reduced to a level to be agreed between AAWAZ and DFID. / The complete set of recommendations can be found in the Narrative Report.

8. Review Process
Preparations for the Annual Review began in late April with onsite research taking place between 6th and 23rd May 2014. Reporting took place between 26th May and 18th June. The review team members were: Hilary Coulby, Agha Imran Hamid, Shazreh Hussain and Maliha Hussein, all independent consultants. / Meetings were held with a wide range of staff at the MO, staff teams from the five implementing partners (plus separate meetings with one head and one deputy), a group of sixteen District Coordinators, the women staff from the consortium partners and MO leading on gender issues, a groups of staff leading on advocacy, a group of staff whose roles include or potentially could include knowledge management and learning, team leaders of two other projects funded by DFID (SNG and STAEP), the authors of the Beneficiary Assessment Report, members of the Punjab AAWAZ provincial forum, including women MPAs, lawyers and journalists, and staff of DAI's office in London. In addition the team visited 4 districts in Punjab and 3 in KP where they met with village, UC and district level forums.