## Sheet1
PROJECT NAME | PAKISTAN EDUCATION TASK FORCE
IMPACT | Impact Indicator 1 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
Improved basic educational outcomes for an increased number of Pakistani Children | Children in primary education | Planned | 56% | 58% | 60%
|  | Achieved |  |  | 68% M69% F 68% | 61% M61% F 63% | n/a | n/a
Source: Pakistan Bureau of Statistics; Pakistan Social and Living Standards Measurement Survey 2011-12 Indicator: Net Enrolment Rate at primary level (age 5-9) (excluding karachi class) http://www.pbs.gov.pk/sites/default/files/tables/summary_of_key_indicators_0.pdf
OUTCOME | Outcome Indicator 1.1 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
Increased capacity of governments and the private sector to implement education reforms | A high level UK/Task Force set up to address poor delivery of public education | Planned |  | TF meets every two months and exerts influence delivery process evidenced in federal provincial actions and budgets
|  | Achieved |  | Taskforce met every two months,
Source: TCF SDU Progress reports
| Outcome Indicator 1.2 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Increased financing of education | Planned | 2.1% of GDP | 2.35% of GDP
|  | Achieved |  | 2.4% | 2.2% | 2.2% | n/a | n/a
Source: PM Secretariat Summary. TF Reports, http://data.worldbank.org/indicator/SH.XPD.PUBL.ZS?page=1
| Outcome Indicator 1.3 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Number of budgetary analyses, research studies and informational materials increased | Planned | 0 |  |  |  | 15 | 16
Achieved
Source: Pakistan Economic Survey 2008/9
| Outcome Indicator 1.4 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Improved education provision in low cost private schools | Planned |  |  |  |  | % Grade 1 | 0
|  | Achieved |  |  |  | % of children in class 1 who can read at least letters 83% % of children in class who can at least do division 63% % of children in class 1 who can recognize at least numbers (10-99) 53% % of children in class 5 who can read at least a story 55% | % of children in class 1 who can read at least letters 81% % of children in class who can at least do division 61% % of children in class 1 who can recognize at least numbers (10-99) 52% % of children in class 5 who can read at least a story 53% | 0
Source: TCF SDU Progress reports http://www.aserpakistan.org/document/aser/2013/reports/national/ASER_National_Report_2013.pdf http://aserpakistan.org/document/aser/2012/reports/national/National2012.pdf
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
Establish an Education Task Force | Priorities endorsed by IPEMC | Planned |  | Priority goals reflected in delivery chains
|  | Achieved |  | Priority goals not reflected in delivery chains
Source: Minutes of iPEMC
|  |  | Baseline |  |  |  | 2013 | 2014
| Output Indicator 1.2 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Capacity building report prepared | Planned |  | IPEMC approves report
|  | Achieved |  | No report prepared
Source: I-SAPS reports
| Output Indicator 1.3 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Roles and responsibilities of federal and provincial departments mapped | Planned | 0 | Implementation plan agreed
|  | Achieved |  | No implementation plan agreed
Impact Weighting (34%) |  | Source: Minutes of iPEMC
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
Availability of knowledge and evidence on education spending increased and policy makers engaged for improvements in education budget utilisation | Number of budgetary analyses, research studies and information materials increased | Planned | 1 set of budgetary analyses is available |  |  |  | 15 research based reports and materials produced and widely disseminated | 1 research based report(s)/materials produced and widely disseminated
Achieved
Source: I-SAPS reports
| Output Indicator 2.2 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Parliamentarians, policy makers and political leaders sensitised on education budget issues and provided with evidence for informed debate and discussions | Planned | 0 |  |  |  | 90 | 60
Achieved
Source: I-SAPS reports
| Output Indicator 2.3 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Number of policy dialogues on education budgets conducted | Planned | 0 |  |  |  | 6 | 0
|  | Achieved | [5 empty] | 0
Source: I-SAPS reports
Impact Weighting (33%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
TCF School in a Box developed (primary school "kit") and tested in the field | Guidelines for administrative, financial and academic operations developed | Planned | 0 |  |  |  | 3 | 0
|  | Achieved |  |  |  |  | 3 | 0
Source: TCF reports
| Output Indicator 3.2 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| Assessment tool to measure school standing (quality and management) developed | Planned | 0 |  |  |  | 1 | 0
|  | Achieved |  |  |  |  | 1 | 0
Source: TCF reports
| Output Indicator 3.3 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| No of schools mapped | Planned | 0 |  |  |  | 250 | 0
|  | Achieved | 0 |  |  |  | 250 | 0
Source: TCF reports
| Output Indicator 3.4 |  | Baseline | 2010 | 2011 | 2012 | 2013 | 2014
| No of education providers trained (including teachers and head teachers) | Planned | 0 |  |  |  | 30 | 0
|  | Achieved |  |  |  |  | 73 | 0
Source: TCF reports
INPUTS (£) | DFID (£)
Impact Weighting (33%)