Type of Review: Annual Review

Project Title: Sector Wide Approach to Strengthen Health (SWASTH) in Bihar
Date started: June 2010

Date review undertaken: 15 to 18 July 2013
Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
DFID is providing grants up to a maximum of £145 million over a period of six years (2010-11 to 2015-16). Following a request from the Government of Bihar (GoB), £20 million was transferred from the Financial Aid (FA) component to Technical Co-operation (TC). The revised allocations under the two components are FA £100 million and TC £45 million. DFID has engaged a consortium of firms (Care, Options, and IPE Global) to provide technical assistance to the programme implementing agencies (Department of Health and Family Welfare, Department of Social Welfare, and Public Health Engineering Department). Additionally, DFID has also contracted Population Council for a study on Violence Against Women (VAW), KRAN consulting to provide software for drugs procurement and inventory management, DFID has accountable grant agreements with Jhpiego to support Government of Bihar to strengthen the pre-service nursing education and with Intrahealth to strengthen the human resources for the Health department.

What are the expected results?
Output: DFID grants will support five outputs under the SWASTH programme: / Increased scale and functionality of nutrition, health and water and sanitation services / Community level processes established to manage, demand and monitor services / Systems strengthened for improving efficiency and effectiveness / Capacity to work with non-government actors enhanced / Quality and use of monitoring and evaluation systems improved / Outcome: The achievements of the above outputs are expected to “increase use of quality, essential nutrition, health and water and sanitation services especially by poorest people and excluded groups”. This outcome will show up in the achievement of the following indicators: / Indicators Base line 2015-16 / Deliveries taking place in health facilities 32% 45% / Women who have received complete ANC 5% 25% / Children aged 12-23 months fully immunized T 33% / F 27% T 60% / F 60% / Children breast fed within an hour 16% 60% / Children (6 to 23 months) given complementary feeding (breast milk and semi-solids) 23% 50% / Number of people with sustainable access to clean drinking water sources 46.4 million 66.8 million / Number of people with sustainable access to an improved sanitation facility 16.8 million 40.0 million / ANC: Ante Natal Care T: Total F: Female / Impact: SWASTH programme is expected “to improve the nutrition and health status of people in Bihar, particularly the poorest and excluded”. The programme will impact on the following five indicators[1]: / Indicators Base line 2015-16 / Maternal Mortality Ratio 312 229 / Pregnant women age 15-49 with anaemia 60% 50% / Under Five Mortality Rate T 77 / F 81 T 58 / F 60 / Contraceptive Prevalence Rate 29% 45% / Under-weight children (0-5 year) T 55% / SC 70% T 46% / SC 57%
[1] Following this annual review the logical framework of the SWASTH programme will be revised, to take into account more recent data that was not available at the time of design, and which can both provide more accurate baseline figures and more appropriate and stretching targets.

What is the context in which UK support is provided?
Despite impressive economic growth in recent years, Bihar continues to be among the poorest states in the country. For more than a decade in the 1990s/2000s Bihar suffered from poor governance. Investment in health services was low, and public health facilities suffered from a lack of drugs, personnel and infrastructure. The accession by the current Chief Minister of Bihar has ushered in a period of improved governance, with a focus on basic service delivery, and more concerted attempts to improve the impact of publicly funded schemes. / Since the launch of the National Rural Health Mission (NRHM) in 2005 investment in health has grown, and Bihar has focused on operationalizing the primary care level of its health service, as well as significantly strengthening medical and nursing training capacity across the state. Nursing colleges which had been dormant for over a decade are now taking in new students, and the state has plans to upgrade existing nursing schools to full nursing colleges. As well as two new medical colleges, GoI has also opened a new All India Institute of Medical Sciences in Patna district. / As a result, in recent years the health and nutritional status of Bihar’s population has improved markedly. Infant Mortality Rates (IMR) have declined significantly (from 64/1000 live births in 2004 to 43/1,000 in 2012), as has the Maternal Mortality Ratio (MMR) (from 312/ 100,000 live births to 261/ 100,000, live births in 2010-11), although it continues to be much higher than the national average[2]. However, a key area of concern for the state remains child malnutrition. It is estimated that about 5 million children in the state are currently suffering from chronic malnutrition[3]. / A very small proportion of the population has access to piped water supply and the majority of the population uses tube wells or bore wells as source of drinking water. The state is faced with severe problems of ground water contamination with excess arsenic, fluoride and iron in several districts, a high disease burden linked to poor quality water, and depletion of ground water level due to excess withdrawal. A huge number of people in the state (some 60 million) still continue to practice open defecation. / A number of other development partners are active in the state. In health, key partners include the Bill and Melinda Gates Foundation (BMGF), UNICEF, Norway, and UNFPA; and in nutrition the World Bank. Development partners coordinate through sub-sectoral coordination groups, including an agreed division of labour to support GoB in implementing the Government of India’s strategy for Reproductive, Maternal, Newborn, Child and Adolescent health (RMNCH+A). The Gates Foundation is the overall lead for the RMNCH+A roll-out, but with significant support from DFID and SWASTH. The State has also initiated its own campaigns for improving maternal and child health and nutrition, involving development partners to support these efforts. In general coordination is good at state level.
[2] Select health indicators of the state: Indicators	Source	Bihar	India Total Fertility Rate	SRS 2011	3.6	2.4 Infant Mortality Rate (per 1,000 live births)	SRS 2012	43	42 Neo-Natal Mortality Rate (per 1,000 live births)	SRS 2011	29	31 Early Neo-Natal Rate (per 1,000 live births)		25	24 Under Five Mortality Rate (per 1,000 live births)		59	55 Maternal Mortality Ratio (per 100,000 live births)	SRS (2007-09)	261	212
[3] The calculation is based on population data of Census 2011. Source: B-TAST

## Section A: Detailed Output Scoring
Output 1: Increased scale and functionality of nutrition, health and water and sanitation services
Output 1 score and performance description: / Score: A (met expectation) / Progress against expected results: / Output Indicators Milestone (2012-13) Progress Score / Number of district hospitals (DHs) providing comprehensive obstetric, abortion and child care (as per GoI standards) Provision of quality services in 10 DHs as per GoI standards. (As per 2013-14 the target is for 19DHs (10 in 2012-13 and 9 in 13-14), / Additionally 46 facilities upgraded to FFHI. 10 DHs providing quality services as per GoI Standards. / Up-gradation plans for 36 DHs developed for certification framework / FFHI rolled out in 82 facilities against the additional target of 46 A+ / Facilities facing stock-out of essential drugs and other supplies <30% As per HMIS data, there was no stock out of OPD drugs in 19 of the 38 districts (50% of districts) B / Number of Nodal AWCs (NAWC) functional At least 3,000 nodal AWCs functional in 9 priority districts Approval for Uddeepika position was delayed hence the nodal AWC could not be made functional. 1,731 Uddeepika positions have now been approved by the state and the recruitment process initiated (posts advertised)- / Plans for up-gradation including reference materials and kits approved. B / 1,500 nodal AWCs beyond the 9 priority districts providing quality VHSND services While monitoring mechanisms have been established, the quality parameters / and specific interventions through TA/FA are yet to be defined C / Number of children reached with nutrition services 3.7 m 7.11 m A++ / Additional habitation with access to clean drinking water through: A+ / Arsenic/Fluoride treatment units and/or surface water 500 571 / Number of rehabilitated bore wells 20,000 28,487 / New water storage 250 254 / Key achievements and challenges: / There have been significant achievements in improving the quality of maternal, newborn and child health services through the implementation of the Family Friendly Hospital Initiative (FFHI) in 14 districts. The FFHI system generates a certification which will be awarded every 3 years to facilities that meet standards focusing in particular on Maternal and New born Health (MNH) services. The State Health Society (SHS) has identified 178 facilities for FFHI certification in this year, as well as a further 46 for higher level accreditation (ISO and NABH). ISO and NABH look at the quality of services beyond MNH generating a drive for quality across the entire health system. Field visits for the annual review identified that there were visible improvements in patient amenities, sanitation measures in labour room and wards and staff behaviours, although these improvements await verification through MIS data collection and other evaluations. BTAST will do a robust impact evaluation on the FFHI process. Particular achievements include: / FFHI quality improvement process rolled out in 82 facilities (10 District Hospitals, 6 Sub Divisional Hospitals, 9 Referral Hospitals, 52 Primary Health Centres, and 5 First Referral Units). The certification of 28 facilities will be achieved by Aug 2013. / Regular monitoring and hand holding support provided in the facilities through FFHI consultants. / District Quality Assurance Committees activated, operationalized, and meet regularly. / 30 Maternal and Child Health Centres (MCH) centres in Level-1 facilities operationalized and made functional as delivery points / Assessment of labour rooms of 742 facilities in the state completed and report submitted / SWASTH has made less progress on plans for upgrading the facilities and infrastructure of 36 District Hospitals. An assessment was carried out in each District Hospital last year and detailed up gradation plans were developed. However, the state is yet to take a decision on implementation of the plans or on a certification process for the district hospitals. / The state has made impressive strides on improving public procurement of infrastructure, equipment and drugs through the newly established Bihar Medical Supplies and Infrastructure Corporation Limited (BMSICL). SWASTH has supported the BMSICL with the software used for drug supplies. In addition, BTAST has supported the state government to revise the state Essential Drug List (EDL) to streamline drug availability. The BMSICL was finalising its first tender for drugs at the time of the annual review. It will be important to ensure this tender goes smoothly, by engaging the district programme officers of SWASTH to support monitoring of drug availability at facility level. There is currently no data for measuring the facility level stock out of drugs as per the indicator in the project milestones, although this should be available from HMIS data sources. / GoB with SWASTH support has prepared a roadmap for the management of severe acute malnutrition (SAM) in children. This is based on scaling up the successful model piloted by Medicines Sans Frontiers in Darbhanga district. The state plans to expand this model to the whole district, for which it has secured funds from the National Rural Health Mission. However questions remain over how technical assistance will be provided for this effort. / GoB has convened a committee consisting of government officials and representatives from development agencies to formulate a health policy for the state. This work is being led by UNICEF. BTAST is simultaneously leading on work around a new policy for human resources for the state. / Nutrition / There has been a delay in implementation of Nodal Anganwadi Centres (AWC), primarily due to delays in approval from the state government on recruitment of additional worker Uddeepikas. The nodal AWCs will be funded under financial aid. / Notification of 1,731 Nodal AWCs in 9 priority districts has been completed. / Posts of Uddeepika for 1,731 Nodal AWCs approved by the Finance Department, recruitment guidelines approved by Social Welfare Department, and recruitment process initiated through advertisement of the posts. / Plan for up-gradation of Uddeepan Kendras approved by the department and fund transfer to districts initiated. / Reference materials for Uddeepika and kits (furniture, equipment, weighing machine, growth chart, hand-washing kits, etc.) for Uddeepan Kendra approved by the department. / Impact assessment of pilot nodal AWC concept in 2 districts completed. / Village Health Sanitation and Nutrition Days (VHSNDs) have been strengthened in priority districts through supportive supervision and handholding with TC support. However, more attention is needed for monitoring and to ensure the completeness and quality of the services provided, as well as the quality of behaviour change efforts and messages given on the days. / While monitoring mechanisms for VHSNDs have been established, the quality parameters / and specific interventions through TA/FA are yet to be defined / In the last 6 months (Jan –June 2013) of the total 16633 VHSND planned; 15904 were conducted in the 9 priority districts. (95.64%) (Source: ICDS MPR; cross validated through District Project Officer monitoring visit reports) with significant improvement in participation of frontline workers and supervisors from the three depts. (Source: Report of DPO monitoring visits in 122 AWCs during Jan-March and 127 AWCs during April-June). / Dashboard for VHSND and monitoring checklist along with software for data analysis developed, and data collation and compilation underway. / District level trainings of Front Line Workers (FLWs) and Village Health Sanitation and Nutrition Committee (VHSNC) members completed by the Master Trainers (63 Master Trainers empanelled and trained). / An eco-friendly, low cost AWC has been established and operational in Jehanabad district with TC support. Cost data indicates the model is more economic than current building designs. / The design and budgets for construction of 44,000 Anganwadi Centres have been developed and submitted for approval by the Building Construction Department. / WASH / Standard Operating Protocol developed and rolled out for Operation and Maintenance (O&M) of mini-pipeline schemes attached with treatment units for Arsenic, Fluoride and Iron. / Developed water quality monitoring & surveillance mechanism for assessing and strengthening the disinfection system and its integration with on-going interventions. / A Detailed Project Report (DPR) has been developed for piped water supply schemes in 5 model Gram Panchayats and shared with the department. The implementation of the DPR will be undertaken by the department. / For development of mini water supply scheme, 100 Mahadalit dominated habitations have been identified and approved by the Cabinet, and ‘no objection certificate’ obtained. Tentative site has been identified with district authorities for 96 schemes. The commissioning will be taken up under FA fund. / Four Mobile Water Quality Laboratory procured (under FA) and working in four zones. / Strengthening of all 38 districts PHED Laboratories (being done under FA, to be completed by August 2013). / Construction of 100 model integrated water and sanitation complexes in schools. Work order for all 100 complexes given out. / Recommendations: / Health / BTAST should agree a timetable for expediting plans for district hospital up gradation, which could also utilise financial aid allocations for the department. / Good progress has been made through the FFHI initiative on improving quality of care. However, the BTAST team could support stronger embedding of Quality of Care (QoC) into on-going monitoring, through: / Relevant FFHI related indicators should be included in the dashboard monitoring system of the state. These could include indicators that reflect QoC across the system (coverage, facility readiness, utilisation, service content). / It will be important to review how quality indicators could be used more at a district level, especially for the District Quality Assurance Committee (DQAC), to measure the ‘readiness’ of facilities for FFHI certification. / Funds are available to support QoC at facility level and a regular analysis of the utilisation of the Rogi Kalyan Samiti (RKS) (patient welfare committee) fund and the type of activities it is being used for may be a useful and occasional TA/project management tool. / The stock-out indicator in the logframe needs to be better defined, and BTAST needs to ensure that data is available to report against this indicator. The team might want to consider using tracer drugs for MNH. Data should present stock out at facility (not medical store) level, and draw on data available from the HMIS system. This needs to be in place by the time of the mid-year review. / In the small sample of facilities that we visited women were discharged after delivery with antibiotics as a preventative measure. The team might want to consider how more rationale use of antibiotics could be addressed through the FFHI. / Oxytocin is not being stored as recommended in a fridge. The BTAST team should consider how this could be facilitated. Financial aid could be used for a procurement of fridges for all delivery points in the state. / Nutrition / Nutrition Monitoring Unit (NMU): BTAST to support SWD on NMU recruitments through a hiring agency. State recruitment to be expedited, all recruitments to be completed by October 2013; and Induction to be completed by Dec 2013. Performance management framework for NMU to be developed and agreed with SWD by Oct 2013. / Nodal AWC: a) BTAST to support SWD on Uddeepika recruitments through hiring agency. Recruitment and induction to be completed by Nov 2013. At least 80% Nodal AWC functional in 9 priority districts by Dec 2013. Baseline for Impact Assessment of Nodal AWC including cost per beneficiary / per Nodal AWC to be established by Nov 2013. b) Disseminate findings of the pilot Nodal AWC with GoB and Minister of Women and Child development by Nov 2013. c) Second phase approvals/work for the remaining 29 districts to be initiated by Dec 2013. / Quality parameters for VHSND services to be defined and agreed with ICDS by August 2013. Specific TA/FA inputs towards improving quality to be agreed and steps taken to implement by August 2013. Skill building of AWWs on Growth Monitoring to be prioritized as one of the key inputs to the VHND in 9 priority districts. / A sustainability and exit plan that aligns with the ICDS restructuring to be developed by June 2014 / WASH / BTAST to update the current habitation level data with Census 2011 population as well as with the data of Rural Development Department in order to better assess gaps in service level. / Need to integrate the framework for water quality monitoring & surveillance (WQMS) mechanism with the on-going WQMS programme of the department, and aligning the same with the on-going blanket testing of sources by the department in arsenic and fluoride affected habitations. / BTAST to support the scale-up of the development of piped water supply schemes in model Open Defecation Free (ODF) villages and engaging community in the planning and implementation phase. / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Community level processes established to manage, demand and monitor services
Output 2 score and performance description: / Score: A (met expectation) / Progress against expected results: / Output Indicators Milestone (2012-13) Progress Score / Level of awareness amongst women and men (age 15 to 49) about: Level of awareness/ knowledge amongst women and men (age 15 to 49) about: / Pregnancy and delivery care / Family planning method used / Infant and child feeding practices / Management of diarrhoea / Management of ARI / Hand washing / Child's stool disposal 25% increase over baseline The baselines were not established as planned, therefore the data from concurrent Monitoring – phase 1 will be considered as the baseline. The concurrent monitoring data reflects : / Safe delivery- 58.2%; 3+ANC- 65.1%; 83.6% Iron/ Folic Acid tablets consumption; and 73.6% have taken 2 Tetanus injections / FP- 76.1% / infant feeding practice- 30.1%- / Diarrhoea Management.- 82.4% / ARI - 79.8% / Hand washing- 29.8% / (Source : Concurrent Monitoring – phase 1; DLHs, preliminary data) B / Number of SHGs mobilized for health, nutrition, water and sanitation 3,000 6,750 A++ / Number of districts with comprehensive program for Violence Against Women (VAW): 3 Trainings and helplines in all 38 districts; Community interventions VAW in 2 districts and scaling up to 5 more districts A+ / Protection officers trained (at least 2 trainings) Four training programmes conducted for Protection Officers and other stakeholders / Help lines streamlined (as per the revised guidelines) Detailed action plan rolled out for streamlining helplines / Community interventions for VAW Community mobilisation to address VAW piloted in 4 blocks in two districts, and scale up initiated in another 5 districts / Number of Open Defecation Free (ODF) Panchayats (Nirmal) 266 267 A / In 9 selected districts, functioning of: / RKS (disaggregated by Dist Hospital, CHC, Civil Hospital and PHC; underserved areas) At least 15% of 1970 RKS ( 295) graded as functioning satisfactory and above. (Governance; Financial management; Patient welfare) Scoring system developed and piloted in 14 FFHI districts. / Of the 602 RKS in the 14 FFHI 240 (40%) were assessed to be satisfactory. / Based on this result, it can be assumed that 40 % RKS is satisfactory across the state. A / VHSNCs At least 15% VHSNCs graded as functioning satisfactorily and above 47% of the VHSNCs performing satisfactorily / Key achievements and issues: / Behaviour change communication / Although all sector teams (health, nutrition and WASH) are working on behaviour change issues the SWASTH programme does not have a clear strategy and roadmap for behaviour change communication, which incorporates the work being done with training of front line workers; strengthening Village Health, Nutrition and Sanitation Days, operationalizing nodal anganwadi centres and improving quality of care in health facilities, as well as some work on mass media (under the PHED). As a result opportunities for cross learning and cooperation between the different elements of work have not been identified. It was agreed that the BTAST team would develop a behaviour change strategy to guide the work of the team in the second half of the programme period. / Although the preliminary results from the concurrent monitoring survey indicate high levels of knowledge about key health behaviours, since this was the first round of concurrent monitoring it has not been possible to establish the trend in knowledge and awareness. Therefore we have scored this indicator at B. There is a need to review the milestones and targets against this indicator, as we have agreed to use the data from concurrent monitoring report as the baseline. / Health / The state has made progress in improving governance of health facilities through operationalizing the patient welfare committees (RKS). A total of 1,952 RKS have been registered under Society Registration Act, bank account opened, and fund has been transferred. In FFHI districts the RKS funds have been used to support needed improvements in facilities, such as improved cleanliness, privacy and comfort of delivery rooms. / The State has also improved the management of Kala Azar (visceral leishmaniasis) through public health facilities and outreach workers. / A total of 5,387 FLWs (5,221 ASHAs in 49 PHCs and 166 ANMs in FFHI facilities) trained on Kala Azar by DPO-BTAST & FFHI consultants, and outcome assessment of training of ASHAs completed and recommendations submitted to the State Health Society. / Advocacy under the SWASTH programme led to training of 13,200 FLWs by the start in 33 endemic districts, and Quality Assurance study of those trainings conducted and the report with recommendation submitted to the State Health Society. / A tracking mechanism has been established to ensure availability of Kala Azar drugs (Miltefosine) and Rapid Diagnostic Kits at 11 (out of 14) endemic FFHI facilities. / Nutrition/Community Based Approach (CBA) / With BTAST support, the Social Welfare Department has taken initiatives to enhance the interpersonal communication and counselling skills of frontline workers in the ICDS system. / Learning Games to strengthen counselling skills have been developed and pilot tested by training around 100 AWWs from one block each in two districts (Aurangabad and Purnia). A baseline and end line survey has been completed and the learning games are due to be rolled out. / An action plan for roll out of the BBC Media Action developed Mobile Kunji tools has been prepared and shared with the NMU. This initiative will be rolled out to more than 20,000 FLWs in 2013-14. / The SW department, with support from BTAST has also made significant progress in the implementation of Gram Varta Plus to mobilise self-help groups and communities for improved health, nutrition, and WASH. Progress includes: / Successfully piloted in Maner block of Patna district: 103 Self Help Groups (SHG) mobilised, 20 Participatory Learning Action (PLA) meetings completed, and end line survey nearing completion. / Scaled up in 11 Women Development Corporation (WDC) blocks since December 2012 and 6750 SHGs mobilised in the first phase through BTAST district teams. / MoU signed with Jeevika and scale up processes initiated in two districts (this partnership will reach out to around 36,000 SHGs in 5 priority districts of SWASTH). / Partnership with Mahila Samakhya for scaling up Gram Varta underway (this partnership will reach out to another 2,400 SHGs in the 5 priority districts). / Significant progress has been made on implementing a package of interventions to reduce violence against women: / Four training programmes have been conducted on PWDVA Act, Gender, roles and responsibilities under the act conducted for Protection Officers, Counsellors of Helplines ,Training Officers of Short Stay Homes. / Detailed action plan rolled out for strengthening helplines (procurement process completed, SOP developed and implemented in 3 pilot districts). / Community mobilisation to address VAW piloted in 4 blocks in two districts, and scale up initiated in another 5 districts. / Special Cell for women established in all blocks of Patna district, counsellors hired, and procurement of equipment completed / Population Council, CEDPA and London School of Hygiene and Tropical Medicine under the VAW research facility (direct contract by DFID) have entered the implementation phase and are implementing robust evaluations of a suite of interventions, some through randomised controlled trials and some through quasi experimental design. / WASH / Over the last decade since the Nirmal Gram Puraskar (NGP) for open defecation free panchayats was initiated by Government of India, 217 Gram Panchayats in Bihar were made Open Defecation Free (ODF) and awarded NGP till 2011. Various studies on the current status suggest that the majority have slipped back and are no longer ODF. Poor community mobilisation leading to behaviour change was one the main reason cited among others. However, with the Community Led Total Sanitation (CLTS) approach initiated under SWASTH, there has been a substantial quality improvement in the way ODF has been achieved with community mobilisation and instituting community monitoring leading to behaviour change. Hence, there is much lower chances of slip back to open defecation in villages/ panchayats achieving ODF through CLTS approach. / BTAST has supported the Department to integrate the (CLTS) approach into the sanitation program of the PHED in 6 districts and a capacity building programme conducted for PHED and associated sector agencies. In addition, a detailed manual for CLTS and a step-by-step guide for toilet construction developed and submitted to the department. / However, CLTS triggers and makes the village ODF though supporting immediate make shift toilets which are susceptible to being destroyed by rain and storms. It is therefore important to help convert the make shift toilets into properly constructed toilets with the help of Govt incentives. Developing a mechanism for advancing incentive money to build toilets will be important to sustain ODF. / Comprehensive capacity building of the Village Health, Nutrition and Sanitation Committees (VHSNC) has been implemented by incorporating and coordinating WASH activities with interventions of the health and nutrition sectors and piloted in 2 districts. / Community based O&M of hand pumps through women’s SHGs implemented; 671 women hand pump caretakers and mechanics trained and providing services in Shibsagar & Dobhi blocks of Rohtas and Gaya respectively. / A framework for mass media campaigns on sanitation and hygiene has been developed and rolled out through the department. / Recommendations: / Behaviour Change / It is critical that BTAST work to develop an overall behaviour change strategy for the SWASTH programme, which sets out how the various pilot activities (learning games, frontline worker training, mass media, use of the mobile kunji, among others) will be brought together in a comprehensive and coherent way, and the links between them will be made. The strategy should set out targets for comprehensive behaviour change programming in the SWASTH high focus districts. The strategy should set out key behaviours and messages. This should be drafted by October 2013. / Community Based Approach / Appropriate staff, systems and mechanisms to ensure the roll out of the Gram Varta participatory learning and action work across the 9 priority districts ( including 20,000 SHGS) to be agreed and operationalized with Jeevika, Mahila Samakhya and WDC by October 2013. / A steering committee to be established in the Women’s Development Corporation (WDC) for regular review meetings between B-TAST, WDC, Jeevika and Mahila Samakhya to ensure timeliness and quality of implementation of the PLA set up by September 2013. / The roll out of Inter Personal Communication (IPC) training using the Mobile Kunji tool to reach 20787 front line workers to be initiated by September 2013. / Scale up of VAW interventions through multi-sector engagement in seven districts to be initiated by September 2013. / WASH / BTAST to support PHED to scale up successful interventions through CLTS as an integral part of on-going NBA program for adoption of sustainable sanitation practices. This will integrate varied community mobilization and facilitation approaches such as participatory theatre, Gram Varta under the on-going NBA. It should be described in the recommended behaviour change strategy. / Rolling out multi-media (radio, TV, mobile, print, street theatre etc.) BCC campaign for hygiene and sanitation promotion and integration with Dus Ka Dum developed under the NRHM. / Current progress of the NBA is assessed on the basis of the earlier baseline mentioned in the Project Implementation Plan (PIP). The PIP needs to be updated/ revised as against the current number of households, so as to identify the revised targets for 12th and 13th five year plan. / Develop mechanism for advancing incentive fund for toilet construction to community (both SHG and non-SHG members) to improve sustainability. / District and Social Group Analysis / BTAST Social Development Team to undertake gender and social group equity analysis of programme coverage and progress against the key indicators of the overall SWASTH programme and share with DFID on a regular basis. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Systems strengthened for improving efficiency and effectiveness
Output 3 score and performance description: / Score: A (met expectation) / Progress against expected results: / Output Indicators Milestone / (2012-13) Progress Score / % vacancies amongst sanctioned frontline staff A+ / a) ANM 17 23 / b) AWW < 5 24 / c) ICDS Supervisor 50 14 / d) PHED Engineers – JE 55 50 / e) Nurses 65 60 / f) Anaesthetists 55 13 (against IPHS norms) / g) Lab technicians 42.5 data not available / h) Contractual NRHM 45 8 / i) Contractual PHED (TSC) 37.5 24 / % staff trained / % staff with adequate knowledge on management of essential health, nutrition and WASH. 17% increase over baseline (ICDS functionaries) / Induction training conducted for 390/534 NBA block coordinators / 20% increase over baseline 15% of tested frontline staff demonstrate adequate knowledge Some trainings conducted but progress against the milestones cannot be reported, for want of : / Baseline / Capacity building plan across 3 sectors/ cadre/ levels/ needs assessment plan / Source of data / Assessment report of trainings C / Up-gradation and setting up of nursing schools (ANM, GNM and BSC Nursing) Up-gradation underway; business plan for new school approved. Assessment of the current status of nursing schools has been conducted. / Plan for up gradation has been developed. / IN addition, the medical corporation is developing DPR for two new nursing schools in Buxar and Banka districts through PPP. B / State health budget allocation Rs. 2,150 crores Rs. 3,121 crores A+ / % Utilisation of funds of central schemes A+ / a) NRHM 50% 84% / b) National Rural Drinking Water Programme 60% 80% / c) Nirmal Bharat Abhiyan 55% 53% / Number of FRA benchmarks assessed as substantial or high risk for DoH/SWD/PHED 6/5/5 8/8/6 (all ratings are substantial)* / Highlights of achievements and challenges: / Overall, the programme has made some progress on development of specific trainings for key cadres of staff within the three departments, and on conducting a training needs assessment for key trainings. However, the overall capacity building strategy of SWASTH is in need of further development, on the basis of the capacity building plan which was developed earlier by BTAST. A more systematic structured training across cadres/ sectors / levels against the baseline and needs assessment is required. In particular the three departments should be supported to develop comprehensive training plans which also maximise the possibility for synergy, for example by using the same pool of master trainers. / * The recently conducted FRA has revised the risk from ‘Medium’ in FRA- 2009 to ‘Substantial’ in FRA-2013. This should not be viewed as change in risk environment. Risk assessment in FRA-2009 was based on system/process introduced/prevalent at state level without any reference to practices at district/ block level. / The overall Fiduciary Risk Assessment for the three departments is : / Department of Health : “Substantial‟ with a bias towards “Moderate‟ as there have been several measures taken by the department towards improving internal controls, modernization of procurement system, preparation of sector medium term expenditure framework etc. Eight out the fifteen benchmarks have a positive trajectory of change showing that effective steps are being undertaken to improve and strengthen the Public Financial Management (PFM) system. / Social Welfare Department : “Substantial‟ with a bias towards “moderate‟ as there are positive measures taken by the department towards improving accountability of officials through better reporting and rigorous monitoring. Eight out the fifteen benchmarks have a positive trajectory of change showing that effective steps are being undertaken to improve and strengthen the PFM system / Public Health Engineering Department: “Substantial‟ with a bias towards “Moderate‟. The department has taken several measures towards bringing in transparency in the procurement process through modernization of the procurement system. Nine out the fifteen benchmarks have a positive trajectory of change showing that effective steps are being undertaken to improve and strengthen the PFM system. / Health / Some progress has been made in this year to support a stronger human resources management function within the Department of Health. A human resources and organisational development (HR and OD) task force has been constituted to develop health workforce strategy for retention, rationalization, deployment, and career path development. / BTAST with Intrahealth have established an IT enabled human resources database (HRIS) system for use for managing transfers and rationale deployment of staff. Data on health cadres (doctors, nurses) has been gathered, and validated. The system is now being used to generate analytical reports on gaps in human resources capacity. Further work to support an interface with the District Health Management Information System and to take data on training is underway. / Quality of care and HR/skills. BTAST is supporting the Government of Bihar in establishing four skills labs designed to provide a 3 day competency based training for in-service and pre-service training for staff involved in delivering MNH services. Two skills labs have already been established (in Muzaffarpur, and Bhagalpur) with two other in the pipeline. Although the skills labs are well managed and providing strong skills based aspect to training in these nursing colleges, there remain some questions about the extent to which they are in line with national guidelines. / In addition, since many aspects of skills training in the state still appear to be week (for example field visits identified that many staff trained in skilled birth attendance were not clear on the use of the partograph) then broader attention to the quality of skills based training is required. / The project steering committee for the SWASTH programme had previously identified the need to build the capacity of the State Institute for Health and Family Welfare. BTAST has supported the state health society to develop plans for strengthening both the infrastructure and the faculty of the Institute. / Nutrition / Social Welfare Department with BTAST support has made progress on training of key cadres under the ICDS programme: / Training of Child Development Project Officers (CDPO)/Lady Supervisors (LS) /Frontline Workers (FLW) in 9 priority and 2 Commuinty Based Approaches (CBA) districts (Gaya and Jehanabad): / 235 CDPOs, 575 LS, and 532 District Mobile Training Team members trained. / 4,915 AWWs, 4,439 Anganwadi Helpers (AWHs), and 4576 ASHAs trained. / Trainings initiated in 91 projects of 9 priority districts. / Dashboard (enlisting leadership actions and key indicators) introduced at the project level and CDPOs and LS trained in pilot blocks. / A total of 211 NMU positions have been approved by the Finance Department and the recruitment process initiated. / State level workshop on revised management information system (MIS) of ICDS organised, which was attended by Master Trainers from Jharkhand, Himachal Pradesh, Uttar Pradesh, and Bihar. / WASH / PHED Department has adopted direct incentive transfer to beneficiaries for toilet construction, and has also piloted e-payments to individual beneficiaries for the toilet incentive in one district. / A capacity building plan for the Executive Engineers and above prepared and submitted to the department. / Human resource support provided to the department (1 at the PHED headquarter and 2 in identified districts) for strengthening accounting functions. / Regularity of appointment of Chemists and Lab Technicians in district labs out of TA funding. / E-procurement systems fully functional. / Recommendations: / BTAST to update the capacity building matrix to reflect the current status of trainings across the three departments and to emphasise the sharing of resources between the three departments, by October 2013. The CB matrix should clearly articulate the type of trainings, theme, for whom (staff/cadre/level), at what frequency, baseline and sources of data. / Health / In the pre-training skills lab tests and from visiting L1 facilities in the state, it is clear that some areas of basic care are missing – such as use of the partogram, accurate use of weighing machine, cervical dilation. A more detailed assessment of the current SBA training and both trainers and trainees competencies should be undertaken. / The skills lab is based on acquiring practical knowledge and skills and the skills may be difficult to maintain when trainees return to their place of work. It is worth considering how on-going support could be institutionalised post training, with more formal roles for supervision. This should be added to the capacity building plan. / BTAST should review the complications case load for ANMs in L1 facilities and if quite low for some complications then designing strategies for ANMs to have more frequent refresher training or placements in busy tertiary facilities to ensure that their skills are kept up-to-date. / Nutrition / Provide technical support to the department in conceptualisation and implementation of Integrated Performance Management System (IPMS). / System to track trainings and assess knowledge and skills of participants to be established by Nov 2013. / Develop comprehensive training calendar; map the CB activities by the department (SWD) as well as by other Development Partners to ensure cohesiveness and greater efficiency of resources. / Develop plan to strengthen institutional capacity of the state training institutes MLTCs and Anganwadi Training Centres (AWTCs) (based on gap analysis/needs assessment) to undertake training of ICDS functionaries by Nov 2013. / ICDS Supervisory in-service training to be conducted for 15 days (preferably in capsules)- instead of 26 days. / Assess the impact of learning game (pilot); The initiative needs to be accordingly dropped or integrated with on-going capacity building efforts for the service providers / WASH / Develop a framework for the achievement of targets under the Mission Manav Vikas for urban and rural drinking water and sanitation in the state. / Strengthen accounting functions in all districts. / Streamline e-procurement through electronic transfer of tender document cost and Earnest Money Deposit. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 4: Capacity to work with non-government actors enhanced
Output 4 score and performance description: / Score: B (moderately did not meet expectation) / Progress against expected results: / Output Indicators Milestone / (2012-13) Progress Score / Proportion of private sector providers registered under the Clinical Establishments Act. 15% of the estimated facilities registered State yet to pass the clinical establishment act, which will provide the basis for registration. C / Number and scale of PPP arrangements in health, nutrition and sanitation functional (includes Demand Side Financing/Results Based Financing initiatives) DHFW 10 / PHED 1 DHFW - 14 / PHED – No Progress B / Highlights of key achievements and challenges: / Overall this has been the slowest moving output of the SWASTH programme. Despite official recognition and statements of the importance of the private sector in supplementing public sector services, particularly in the health sector, there has been little movement in introducing the appropriate regulatory frameworks to support effective public private partnerships in health. Specifically the State has yet to pass the state level clinical establishment act which would provide the regulatory basis for the mapping, and registration of private health facilities. / BTAST has supported the state government both on advocacy and capacity building around private sector partnerships, including the following: / An investor’s conference was held in the state to attract private investors in healthcare, jointly with the Confederation of India Industry Bihar chapter. The meeting attracted a high level of government participation, including the Deputy Chief Minister, and a number of large (mainly hospital) private sector health companies. / Recruitment has taken place for a PPP cell within the State Health Society. However, the cell is still not fully recruited and has not yet been built up in terms of its capacity to design, oversee, and contract PPPs. / Terms of reference have been developed for an evaluation and assessment of current PPPs in the health sector, and contracting of this review is in process. / For PHED, Mahila Samakhya (SHGs) has been involved in hygiene and sanitation promotion in villages as well as for mitigation of domestic violence against women. / Recommendations: / BTAST to finalise terms of reference for the review of current PPPs in the health sector, with the support of the consultant on PPPs in the resource pool, and to contract by end September. / BTAST to agree on a capacity building plan for the PPP cell in the state health society, and identify suitable technical support for this. / Under PHED, to strengthen cooperation and capacity building of SHGPIs like WDC, Jeevika and Mahila Samakhya for promotion of improved sanitation services through SHGs and federations / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 5: Quality and use of monitoring and evaluation systems improved
Output 5 score and performance description: / Score: A (met expectation) / Progress against expected results: / Output Indicators Milestone / (2012-13) Progress Score / Availability of valid and reliable data for planning and delivery 1st round of concurrent monitoring and provider's survey completed Survey of more than 50% Blocks (318) conducted and data validation underway B / Annual report on status of nutrition, health and water & sanitation published and discussed within government and with CSOs. Annual Report published; discussed with CSO (within 3 months of the publication) Annual report published and available in public domain. B / Use of scientific studies and impact evaluations At least 1 RCT designed and initiated 3 RCTs designed and initiated. A+ / Highlights of key achievements and challenges: / Health / The availability of information for decision-making has improved significantly in the state, with significant support from BTAST to gather, validate and present the data. / District information consultants have been placed in all 38 districts providing onsite support for quality data generation and validation. / BTAST, through district level staff has supported data collection and validation for health management information system (HMIS) human resources information system (HRIS) and the maternal and child tracking scheme. Data has been collected and validated at state and district level and presented at the monthly CS review meeting. / Data has been presented in the form of a dashboard set of indicators to monitor differential progress between districts. The human resources information system is beginning to demonstrate good quality data for reporting and for strategic decision making on HR for health. / Nutrition / The Concurrent Monitoring Survey has been conducted in more than 50% of blocks and data validation is underway, to ensure the quality of the data. / A pilot mobile based monitoring system for the ICDS system has been implemented in Jehanabad district. Learning from the pilot will be fed into the newly conceptualised Integrated Performance Management (IPMS) system for which a concept note has been developed. / The design of a Conditional Cash Transfer (CCT) pilot to investigate the impact of CCTs on nutrition outcomes has been approved by the state government and implementation has been initiated in Gaya district. / WASH / The PHED Reforms Support Unit (RSU) Cell has been agreed and manpower support provided. / ICT (Information Communication Technology) based monitoring of hand pumps through SMART Water system has been piloted and a framework for scaling up submitted to the department. / Recommendations: / Health / BTAST to continue to support the state to improve the interoperability of data systems, particularly the DHIS and the HRIS systems, so that joint reporting and data analysis can be performed. / BTAST to support the state to develop capturing of real time data to strengthen the Mother Child Tracking System through mobile based data uploading. / Strengthen capacity of block level officials, especially Block Health Managers, for improved monitoring and use of data in planning at local level, including through BTAST district level staff. / Nutrition / BTAST to finalise the concurrent monitoring survey, ensuring the quality of the data, and of the reporting. / Quality assurance of data to be completed by August 2013, data analysis and dissemination to GoB by Dec 2013. / Score cards for 9 priority districts needs to be developed and shared by Dec 2013. / Cash Transfer (CT) / Baseline to be completed; implementation to be initiated in full scale by Dec 2013. / The CT design to ensure that beneficiaries who are not availing the Take Home Ration /Supplementary nutrition program are also able to register. / Integrated Performance Management (IPM) / BTAST to support the SWD in actively procuring the services of an agency for implementing IPM. The agency needs to draw on lessons/best practices from the existing work of other Development Partners in the state as well as ensure that the IPM software is aligned with the new ICDS MIS and the web based MIS being planned under World Bank supported ISSNIP programme in Bihar. / WASH / Carry out an assessment of the mini pipe water supply systems being implemented by the department for quality affected and water scarce habitations. / Undertaken an assessment of the sustained sanitation behaviour in terms of usage of toilets, localised solid & liquid waste management, hand washing and school & Anganwadi sanitation. / BTAST should pilot smart water system with smart chip/ sensors to monitor down time and repair. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.
1. Progress and results
Has the logframe been updated since last review? Y/N / No. However, the logframe will be revised on the basis of newer data sources that have become available since the programme design, to ensure that baselines best reflect the true situation at the commencement of implementation and provide the most appropriate targets for the remainder of the programme period (by December 2013).
Overall Output Score and Description / Score: A (met expectation) / Out of five outputs, four outputs are rated A (with cumulative impact weightage of 90%) and only one rated B (with impact weight of 10%). / Output Impact weight Score / Output 1 30% A / Output 2 25% A / Output 3 20% A / Output 4 10% B / Output 5 15% A / Overall score A / Direct feedback from beneficiaries / Beneficiary Feedback / Health / Mrs Nigam Devi, pregnant woman who delivered at PHC (Uda-Kishunganj) This is the place where anyone can plan delivery without any out of pocket expenditure and irrespective of caste and religion. / Mr Rakesh Mahto who used OPD Service at PHC (Uda-Kishunganj) I am satisfied with the consultation by the Doctor, who has given me enough time for medication and also I got all the medicines free at Medicine distribution counter / Biwi Mahsina, a woman who arrived in DH Madhepura for Routine Immunization for her child I am really happy by immunizing my child through second dose of Routine Immunization. As soon as I entered the staff nurse greeted me. / Bhola, a rural old person suffering from kala-azar and admitted since last one day in District Hospital Madhepura I am fortunate to be here because it’s the only place in Madhepura where there is no charge for consultation and medicines. The hospital environment is hygienic and the nurses are caring. / Mrs Sulekha Devi, mother of a child who availed IUCD Insertion Family Planning Service at PHC Singheswar I availed this service free of cost and the staff nurse was very co-operative and made me confident. / Nutrition / Shanti Devi (community woman participant, Mochi Tola, Sadikpur village, Maner block, Patna) Gram Varta meeting is an empowering process in itself; it has led to our understanding that mother’s milk contains sufficient water and minerals and external water/substitute is required for the baby even during summer. / Babiya Devi, (President, Maner Federation, Maner, Patna) Through our meetings, we have learnt that overall health expenses by federation and SHG women have reduced over the recent past and we cannot attribute this to anything else but our participation in Gram Varta meeting and learnings from it. / Khushbu Kumari, Ganagasagar, Makhdumpur block, Jehanabad) I attend the Gram Varta meetings regularly. I am 4 months pregnant and have realised the importance of weighing of children, TT injections and complete ANC check-ups. Inspired by Gram Varta learning, my husband has been accompanying me during my visit to the AWC for weighing of my one-and- half year old daughter and to the health centres for ANC check-ups. / Ms Arti, Project Manager cum Protection Officer , Women Helpline, Gaya The regular trainings provided under the SWASTH project have proved to be very useful and we have been able to help our clients well. / Ms Pramila Kumari, Project Manager cum Protection Officer, Women Helpline, Patna Earlier, we worked on the issue of domestic violence and other gender related issues as part of helpline services. Post trainings and exposure visits received through SWASTH support, we have been able to understand the overall perspective on PWDVA, 2005. Understanding the Act has helped the team to link victims to legal aid. / Station in charge, Gandhi Maidan Mahila Thana, Patna Training programmes that we have attended earlier were routine and mundane. Through this orientation workshop for police officials, we have received inputs on gender issues, the issue of domestic violence, and related legislations. We hope to receive regular trainings which will help us in our work. / WASH / Sunita Singh, Nigrani samiti member, Sarvodayapuri, Atiya gra Panchayat, Bodh Gaya block, Gaya The triggering made us realise the ill effects of open defecation not just in terms of privacy for women folk but also leading to the bad health of our children; we realized that having a toilet is as easy and in our hands instead of waiting for subsidies from the government. / Bibha Chobey, Mukhiya, Lakhora Gram Panchayat, Chanpatia block, West Champaran Initially it seemed to be an uphill task to achieve, but with the good support from B-TAST and the help of the committed youths from the Panchayat, Lakhora attained the status of ODF within 21 days and is the first GP to have become ODF. The support from the DM, DDC and the entire district administration for construction of pucca toilets is overwhelming. / Rajendra Prasad, Secretary- Tetariya village, Jal Gram Prabandhan Vayalagam, Tankuppa block, Gaya The development of Oorani has not only improved the ground water level, but also resulted in water availability in nearby hand pumps & well. The water from oorani is not only clean but also tastes good. / Rita Devi, SHG member and HPCM, Village Karmauni, Nawadih Gram Panchayat,, Dobhi block, Gaya After the training for handpump repair, I have repaired more than 25 handpumps and earned more than Rs. 5,000/-. Now I am financially stable, also constructed a toilet in my house and have enrolled my children in a private school for their better education. Not only this, my work has earned me a good social status and respect in my village and amongst my clients. / Maya Ram Sada, Nepal tola, Dahma Khari Kutaha panchayat, Alouli block, Khagaria Prior to construction of the Phaydemand shauchalay, we faced the negative impacts of defecating in the open. Now, the shauchalaya has not only resulted in improvement of our health. But also saved money on fertilizers for cultivation.
Summary of overall progress / SWASTH has made good progress on some key programme strategies and areas of programme delivery during the project period, particularly the following: / Work on improving the quality of care available in public facilities through the FFHI process, and in mainstreaming Kala Azar management within the health system. FFHI has been rolled out in 82 facilities and 28 facilities will be certified by November 2013. Some other important initiatives include: operationalization of 30 MCH centres in Level-1 facilities; training of 5,387 FLWs on Kala Azar in in endemic districts; establishment of tracking mechanism to ensure availability of Kala Azar drugs and diagnostic kits; development of web-based drugs MIS for regional warehouses; increase in NRHM contractual posts; and establishment of IT-enabled HRIS. / Scaling up community mobilisation for improved health, nutrition, sanitation and hygiene with a significant expansion of work with self-help groups across priority districts. / Agreeing the nodal anganwadi structure, human resources requirements for its implementation, and progress on recruitment. Significant progress has been made in establishment of Nodal AWCs through notification of 1,731 Nodal AWCs, and approval of posts of Uddeepika and release of advertisement. The review year has also witnessed several other achievements such as: construction of one model AWC using low-cost, eco-friendly technology; launching of community incentive pilot in two blocks in Gaya and Jehanabad; development and pilot testing of ‘modules of learning games’ for enhancing IPC skills; action plan for rolling out of ‘mobile kunji’; training of FLWs, LS, and CDPOs; establishment of dashboard at project level; and several initiatives undertaken to push forward VAW package interventions. / The key achievements during the review year under WASH include: development and roll out of standard operating protocol for O&M of mini-piped water supply schemes; development of water quality monitoring and surveillance mechanism; govt. approval for development of mini water supply scheme in 100 Mahadalit dominated habitations; implementation of community based O&M of hand pumps through women SHGs; integration of CLTS approach with the sanitation programme of the department; development of manual for CLTS; provision of human resource support (accountants, chemists, and lab technicians) out of TA funds; making e-procurement system of the department fully functional.
Key challenges / Despite the progress against key programme strategies, there remain a number of issues which constrain programme progress, including the following cross cutting areas: / Utilisation of FA has been slow across all three sectors, and particularly in the Social Welfare and PHED departments. However, given the progress in implementation of the Nodal Anganwadi strategy outlined above, and agreement of key strategies in PHED, it is expected to catch up over the next 3-6 month period. The key achievements in FA for PHED has been the four Mobile Water Quality Laboratory procured and working in four zones; strengthening of all 38 district Public Health and Engineering Laboratories (to be completed by August 2013); construction of 100 model integrated WASH complexes in schools. The major FA utilisation expected over next few months include commissioning of 100 model mini-pipe water supply schemes; and blanket testing of all water sources (about 4 lakhs sources) in quality affected habitations. / The programme has made good progress on scaling up the community mobilisation element under the Gram Varta strategy. However, the other elements of the community based approach outlined in the programme design (including behaviour change communications, strengthening of village health and nutrition days) have yet to be fully mainstreamed across all CBA blocks. The programme could make more effort to work from the FFHI facilities and the newly operationalized L1 delivery points (additional PHCs) as a platform for strengthening the support to village health and nutrition days. / A key priority for the programme is to develop a clear behaviour change communications strategy, which includes the various elements of behaviour change (learning games, IPC training for frontline workers and Gram Varta) and adds in additional elements (such as job aids for frontline workers) where required. The behaviour change strategy should be developed by the end of 2013. / The programme needs to make a clearer strategy for monitoring and evaluation. There is a tremendous amount of piloting going on across the three sectors, yet the systematic gathering of data on those pilots, including evidence that could be used for advocacy and scaling up needs to be reflected in a programme wide monitoring and evaluation strategy. / The programme had developed a draft capacity building strategy. However, insufficient progress has been made in embedding that strategy into the work of the three departments and identifying clear entry points for working across the departments to develop clear, measurable and monitored training plans. This should be developed by the end of 2013. The health team also need to put more advocacy effort, with DFID support, into operationalizing the human resources task force, which has been constituted but is not yet playing a strong role in guiding human resources policy. The state institute for health and family welfare is still under-capacity, but plans to strengthen it have not yet been adopted by the state. / Good progress has been made in operationalizing the Bihar Medical Supplies and Infrastructure Corporation. The corporation is now floating a tender for the provision of drugs, and legal impediments to that have been overcome. BTAST needs to ensure on the ground capacity to monitor the roll out of the first tender for drugs to ensure that there are no stock outs as the state moves from a decentralised drug procurement system to a more centralised one. / The Social Welfare Department had identified a major objective as the development of an integrated performance management system for ICDS Directorate. BTAST needs to ensure that adequate support is given to this initiative, tracking it and ensuring that good practice from other partners across the state is fed into its development. / Finally, at the annual review it was agreed to develop systematic scorecards for demonstrating progress in priority districts. Since other players in Bihar are also scaling up their district level presence, there also needs to be a comprehensive review of the job descriptions of district level staff so that opportunities for synergy and co-location can be identified. / Annual Outcome Assessment / Outcome Score: A / Impact Score: A / Bihar is well on track to achieving the outcome and impact indicators as evident from the latest available data given in the tables below. / Outcome Indicators Milestone / (2012-13) Progress / Deliveries taking place in health facilities 39.5% 46%1 / Women who have received complete ANC 13.5% 5.9%2 / Children aged 12-23 months fully immunized 52.5% 64.5%3 / Children breast fed within an hour 40% NA / Children (6 to 23 months) given complementary feeding (breast milk and semi-solids) 35% NA / Number of people with sustainable access to clean drinking water sources 52.4 million 53.35 million / Number of people with sustainable access to an improved sanitation facility 25.0 / million 25.36 million / 1 Source: DHIS-2 (2012-13) / 2,3,4 Source: AHS (2010-11) / 5,6 Source: PHED / ANC: Ante Natal Care NA: Not Available / Impact Indicators Milestone / (2012-13) Progress / Maternal Mortality Ratio 245 2611 / Pregnant women age 15-49 with anaemia 58 NA / Under Five Mortality Rate 68.5 642 / Contraceptive Prevalence Rate (any modern method) 38% 37.63 / Under-weight children (0-5 year) 51.5% 404 / 1 Source: SRS (2007-09) / 2 Source: SRS (2011) / 3 Source: AHS (2010-11) / 4 Source: Hungama Survey 2010-11

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The project is not currently on track in respect to the financial forecast, but it is expected that the rate of financial utilisation will increase in the coming months. Till date, £54 million has been disbursed, over three years. Overall FA utilization under the department of Social Welfare and Public Health Engineering is low. However with the recent approvals on NMU, Uddeepika and cash transfer, the expenditure is expected to pick up. Utilisation of TC funds has been largely on track. Over the three year period (2010-11 to 2012-13), BTAST utilised 91% of deliverables based contract value and 96% of the total sub-contracting budget. Some of the sub-contracts (e.g. sub-contracts on ‘conditional cash transfer pilot’ and ‘concurrent monitoring’) would spill over to next year and beyond. / 2.2 Key cost drivers / The planned activities under the SWASTH programme are the cost drivers of FA, which among others include payments for salaries/honorarium (e.g. salaries of support unit to the concerned department; honorarium of additional worker at Gram Panchayat level Anganwadi Centre; salaries of nursing skill lab), purchase of equipment, civil constructions, up-gradation of facilities, training, monitoring and supervision, mobility costs, etc. / TA sub-contracting spend over the last three years (2010-11 to 2012-13) were driven by different requirements of programme support such as short term consultancy, community intervention, monitoring and evaluation, research/study/survey, training and capacity building. / 2.3 Is the project on-track against original timescale: Y/N / Yes. Barring deferment or substitution of few activities, the project is on-track against the original timescale.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Early evidence from Gram Varta Plus: The pilot of Gram Varta (a community based approach of ‘participatory learning and action’ (PLA) through a cycle of 20 community meetings) in Maner block in Patna district has been completed and early evidence (pending completion of the end line survey) shows tremendous potential of PLA in bringing about change in behaviour and practices related to health, nutrition, hygiene and sanitation. The evidence also shows that Gram Varta is an effective tool to leverage on ‘social capital’ for undertaking activities such as construction of individual household toilets and creating awareness among the larger community. The experience of successful completion of pilot has led to scaling up of Gram Varta Plus through three SHG promoting institutions (Women Development Corporation, Bihar Rural Livelihoods Promotion Society, and Bihar Mahila Samakhya). / Integrated approach for fluoride management: The pilot initiative in Khaira village, Munger has recommended several actions such as, monitoring of drinking water source is neededat least twice a year; screening of inhabitants for assessing the extent of skeletal and non-skeletal fluorosis; alternative supply of drinking water from safe sources; and community or household level treatment systems. / Development of 24x7 water supply through community involvement: The development of piped water supply scheme through intensive community dialogue and involvement has provided good insights, such as: / As an executive arm of Gram Panchayat, Village Water and Sanitation Committee (VWSC) is required to provide all the necessary support for implementation of water supply scheme in the village. / Women’s role is pivotal in planning for suitable water facilities, or deciding on reliability of sources, or distribution schedules. / Members of VWSC, field workers, ASHA, ANM, AWW, and school teachers need to be trained on subjects such as operation and maintenance, sanitation, drainage, solid and liquid waste management, water quality, hygiene, cleanliness, etc. / Operation and Maintenance of the water supply scheme may be carried out initially by a contractor for about 5 years and thereafter VWSC of Gram Panchayat. / 3.2 Where an evaluation is planned what progress has been made? / Several evaluation studies have been commissioned during the review period as given under: / Evaluation of the impact of the Family Friendly Hospital Initiative on improving the quality of care for maternal, new born and child health. / Involvement of SHGs for malnutrition reduction using a participatory learning and action approach / Concurrent monitoring of village level health, WASH and nutrition services / Conduct trial and evaluation of the nodal AWC strategy / Monitoring of ICDS services/facilities through mobile sets / Mahila Samakhya work on community mobilisation (VAW)

4. Risk
Output Risk Rating: Low/Medium/High / The programme is judged to be of medium risk with the potential of high return. / Assessment of the risk level / The key risk factors are assessed as given under: / Key risk factors Status Risk rating / Fiduciary risk Department of Health – Substantial / Social Welfare Department – Substantial / Public Health Engineering Department - Substantial Substantial / Staff turnover Risk of short tenure of senior officials in the implementing departments continues. High / Political Reforms in the health, nutrition, and water and sanitation sectors continue to be high on political agenda. / The Chief Minister of the state himself visits and takes stock of implementation of various programmes at the grass root level. Low/ Medium / Implementing capacity The vacancies of ICDS supervisors, PHED engineers (JE), nurses, anaesthetists, contractual staffs under NRHM and TSC have been reduced, thereby improving service delivery capacity. / Despite shortage of staffs, service deliveries by the concerned departments have improved significantly. Medium / Staff obstruction to reform The implementing departments have undertaken several initiatives for transparency in procurement, strengthening of financial management, and for improving monitoring and control systems. / So far there has not been any resistance from the departmental staffs. Low / Continued exclusion of disadvantaged areas/groups The risk mitigation measure of tracking the progress in the underserved areas and for underprivileged/excluded people has not yet been put in place. Medium / Risk of funds not being used as intended / At the state level, there is no risk of diversion of DFID grants for programmes other than SWASTH programme. DFID funds are allocated to each of the implementing departments through a separate budget line. / At the departmental level, the risk of funds not being used as intended under the SWASTH programme is rated to be low. Each implementing department is required to spend funds as per its plan of activities duly approved by the Project Steering Committee. Use of DFID funds is subject to statutory audit. / Climate and Environment Risk
The SWASTH programme interventions will have no adverse impact on climate and environment. Rather, some of the interventions will reduce the risks. For instance, successful completion of construction of an eco-friendly AWC with muds and brick technology has opened up the potential for up scaling such construction, which in turn will have positive impact on environmental balance due to less use of cement and steel. Similarly, application of CLTS has already made 25 Gram Panchayats ‘open defecation free’. Scaling up of CLTS initiatives will contribute in mitigating environmental risks by reducing faecal contamination of surface and ground water in the state.

5. Value for Money
5.1 Performance on VfM measures / The VfM performance at this stage of implementation of SWASTH has been assessed in terms of UK Treasury’s ‘3 Es’ viz. ‘economy’ (in procurement of inputs), ‘efficiency’ (in delivery of outputs), and ‘effectiveness’ (in achieving the intended results). / Economy / The FA/TA inputs are procured following the procurement guidelines of DFID or the Government of Bihar whichever is applicable. Economy in procurement is achieved through competitive bidding and negotiations (see next Section 5.2 for further details). Besides, various programme activities have been carried out carefully to achieve value for money as evident from the following examples. All these examples require further analysis to see whether the strategies employed are fully effective. / Construction cost of model AWC: A model AWC has been constructed at Dhanerai in Jehanabad district using eco-friendly, mud and bricks technology. The centre has built-up area of 825 sq. ft., covered veranda with grill and gates, multipurpose hall for counselling of women and children, separate toilets for children and staff, covered courtyard with hand pump, well-ventilated semi-open kitchen with smokeless agro-waste chullah, and separate store room for grains. The construction cost of the centre is estimated to be 21% cheaper than conventional construction cost[4]. / Outreach cost of Gram Varta: Gram Varta involves ‘participatory learning and action’ through a cycle of 20 community meetings. A local woman from the community is recruited as ‘facilitator’, and she receives training and support for conducting PLA. On the average, she conducts PLA with 5 SHGs having a total of 65 women members, and conducts (20 x 5 =) 100 meetings to complete one cycle over 19 months. The SHG members, in turn, reach out to the larger community. The average cost per meeting conducted by a facilitator is estimated to be Rs. 260 and cost of reach out to women members of SHG works out to be a negligible amount of Rs. 4 per member[5]. However, the efficacy of the training cannot be ascertained at this point since comprehensive evaluation on the outcome of PLAs has not yet been carried out. / Cost of training ASHA on Kala-Azar: BTAST has taken initiatives to improve knowledge and skills of ASHA on Kala Azar in endemic districts. The training is imparted by the District Project Officers of BTAST in selected PHCs on ASHA Diwas (held once in every month). DPOs themselves have undergone a one-day training conducted by the health team and Kala-Azar consultant of BTAST. On the average, 85 ASHAs have attended the half-a-day orientation programme conducted by a DPO at each PHC. The training cost is estimated to be Rs. 25 per ASHA which represents only 15% of the departmental cost for the same purpose[6]. However, it should be noted Governments training programme for ASHA’s are full day/ residential programme which includes travelling and subsistence costs for ASHAs. The efficacy and assessment of the training yet to be ascertained. / Efficiency / Management of public finances: Utilisation of NRHM funds increased from 45% in 2011-12 to 52% in 2012-13. The total expenditure on health has increased over the years and public health expenditure of Bihar is around 1.8% of GSDP which is significantly higher than all India average of 1.2% of GDP. State allocation to health has also steadily increased and now stands at Rs. 3379 crores in 2012-13 which is 18% higher than 2011-12. Though the per- capita public health expenditure and per capita drug expenditure has increased over the years and presently (2012-13) it is Rs. 450 and Rs. 12 respectively. However, in absolute terms these figures are among the lowest in the country and well below national average which is Rs. 675 (2011-12) and Rs. 43 (2010-11). / On WASH, the utilisation rate has fallen both for national sanitation and water programmes. Regarding NBA (for sanitation), funds utilisation has decreased from 67% in 2011-12, to 53% in 2012-13 due to ambiguity of incentive transfer related to construction under MNREGS. The spending is expected improve after direct transfer of incentives to the beneficiaries. Spending on NRDWP the national water mission, the utilisation rate has also fallen compared to 2011-12 and the utilisation rate is around 44% in 2012-13. High level of vacancies of engineers are affecting execution of schemes and resulting in low utilisation rate. / Management of human resources: As noted in Output 3, vacancies in anaesthetists, ICDS supervisors, and contractual posts under NRHM and NBA have been drastically reduced. However, the vacancies for front line workers (ANM and AWW) still continue to be significantly higher than the milestones of the review year. In the case of PHED, vacancy in engineers is still around 2012-13. In 2012-13, though the number of sanctioned posts of Doctors has increased but the total number of available doctors has marginally declined. The vacancy for Doctors in 2012-13 is still 48% against sanctioned post. Vacancy of staff nurses and ANMs have remained same as of 2011-12. / Procurement: Bihar Medical Services and Infrastructure Corporation has been fully functional and currently engaged in the procurement of drugs, equipment, and works. The service of the corporation is not limited to DoHFW; it is now procuring kits for AWCs (which primarily consist of medicines) on behalf of the SWD. The Corporation has recently received a request from the Rural Development Department for purchase of equipment for schools. / PHED has fully operationalized e-procurement systems. At present, all procurements above Rs 25 Lakhs are done through e-procurement only. / Service delivery: The delivery of health, nutrition, and WASH services in the state have improved significantly as evidenced from the illustrative list given below: / The number of outpatients visiting the government hospitals has increased, from 63 million in 2011-12 to 72 million in 2012-13 –an increase of 14% , / The inpatient numbers have remained same as 2011-12 at around 3.9 million. Inpatient bed occupancy ratio is 21% for PHSc, 40% for CHc and 89% for DH/SDH. / There has been significant increase in Institutional deliveries from 2009-10. However, this growth has remained stagnant in the last two years. Institutional delivery was 1.42million in 2012-13 compared to 1.43 million in 2011-12, estimated to be around 47% of total deliveries in 2012-13. / Complete immunization of children aged 12-23 months currently stands at 64.5% (AHS-2011) as compared to 18% in 2005.Authentic data is not available for the project period. / Most of the AWCs function regularly and nutrition services now reach to over 4 million children in the state. However, the estimated number of children 0-6 age group in Bihar will be around 16-17m so the number of children reached through the existing centres is significantly less (25%) / Number of people with sustainable access to clean drinking water sources increased from 58% in 2008-09 to 83% as on 14-03-2013[7]. / Number of people with sustainable access to an improved sanitation facility increased from 14% in 2008-09 to 41.6% as on 08-07-2013[8]. / Improved VHSND service delivery: BTAST monitoring and support has led to regular holding of VHSND and greater participation of frontline workers and supervisors. / Currently no data is available comparing FFHI facilities to non FFHI facilities. Disaggregated or aggregated data on FFHI hospitals is still not available. BTAST will develop an evaluation strategy for FFHI which will provide this data. / Effectiveness / SWASTH may be credited with several achievements that reflect programme effectiveness. These include the following: / CLTS making villages ODF: Response to CLTS among the community members, especially among the women, has been overwhelming. Following CLTS interventions, 25 Gram Panchayats (GPs) across 3 blocks (viz. Jalalgarh in Purnia, Chanpatia in West Champaran, and Bodh Gaya in Gaya) have become ‘open defecation free’ (ODF). The effectiveness of CLTS can be gauged from the illustrative case study of Jalalgarh block in Purnia district where 10 GPs have become ODF. At the initial stage, 26,172 kachha (temporary) toilets were constructed within a short period of 2-3 days. Subsequently, pucca toilets were constructed for 4,408 individual households with funding support from PHED. About 88% of these households are now using toilets, reflecting a definite change in sanitation practice among the community members. / Gram Varta strengthening social capital: As mentioned earlier, apart from bringing about change in behaviour and practices related to health, nutrition, hygiene and sanitation, Gram Varta has become an effective tool to strengthen ‘social capital’ of the community. To give an example, four SHGs - Devi, Aarti, Kaali and Shanker (from Sadikpur, Harangi Tola, Yadav Gali, Maner block) attended all the 20 meetings of a PLA cycle starting from September 2011. Inspired by PLA, the group members mobilised community contributions for installation of three tube wells at a cost of Rs. 30,000 per tube well. They also succeeded in installation of four tube wells using PRI funds and two more tube wells sourcing funds from a NGO. To cite another example, six SHG members (three each from Durga and Laxmi SHGs) and four non-SHG women attended a complete cycle of PLA and being motivated by participatory learning joined hands together to construct toilets for their own houses. Each one of them contributed Rs. 2,400 for purchase of bricks and the rest amount sourced from PHED. Not only that, at their requests, the PHED contractor addressed the community and said “by having your own toilets, you could prevent your daughters and daughter-in-laws from going outside for open defecation and this will not only prevent them from illness but also from any kind of physical and sexual assault.” / Cost effectiveness of the programme: The programme effectiveness cannot be calculated based on DALY because data on IMR/ MMR is not available for project intervention period. / Overall VfM Assessment / SWASTH has performed reasonably well in terms of all the three VfM measures. However it is to be noted that DFID’s FA spend remains below expectation. / 5.2 Commercial Improvement and Value for Money / For improving effectiveness and efficiency in programme delivery in PHED, it is necessary to improve the bottom up planning and budgeting process , strengthening of accounting practices, recruitment and capacity building of staffs . This will lead to better utilisation of central funds and increase coverage and maintenance. / On health, it is important to improve the utilisation of NRHM funds and improve the procurement system. Though BMSICL has been set up, FRA studies revealed that there has been no direct evidence of preparation of procurement plans, incidence of stock out at facilities level and inability to purchase certain items even in emergency, delays in vendor supplies, stocking of drugs without any clear relation to actual demand. Moreover along with improvement of quality it is also necessary to focus on increase in infrastructure facility and human resources. Many of the indicators like doctor to population ratio or bed to population ratio is one of the lowest in the country and below Indian average. Otherwise, the demand generation programmes like JSY, Gram varta, VHSND, won’t translate to significant improvement in health or nutrition outcomes. / TA procurement by DFID under SWASTH programme was based on competitive bidding in the open market. The TA contract payment has been linked to ‘output based deliverables’ ensuring maximum value for money. / In 2012-13, TA budget under SWASTH programme including sub-contracts by BTAST represented an average daily fee rate of £152, which is 10% lower than the previous year’s average fee rate. Moreover, around 92% of TA was delivered by Indian nationals enhancing sustainability and knowledge transfer within the country. / The sub-contracting by BTAST has followed good procurement procedures complying with DFID guidelines as given under: / The Terms of Reference (TOR) for the subcontract activity is approved by both GoB and DFID. / Contracting of TA inputs is subject to DFID approved procurement procedures. / Regular reviews of TA work is conducted by GoB and DFID linked to Monthly Progress Reports / Six monthly procurement review and sample check of subcontracting is conducted by DFID procurement group. / The value for money was maximized over the last three years (2010-11 to 2012-13) through procurement of subcontracts in the open market. In terms of contract value, about 67% procurement had been through competitive tendering process. In the case of small value direct contracts, which represented 33% of the total contract value, BTAST could save through negotiations 17% (£234,808) of the original quotations. / Further cost savings were achieved by using government facilities for trainings, meetings, etc. / 5.3 Role of project partners / SWASTH programme has been implemented in partnership with DoHFW, SWD and PHED. At present, DFID is the only external donor providing financial assistance to all these three departments. BTAST is engaged by DFID to help implement planned activities under SWASTH programme. Other technical agencies like UNICEF, UNFPA, NIPI and BMGF are also providing technical support on maternal child health, family planning, nutrition, and on WASH issues and they all work in close collaboration with BTAST and the state government. / DFID India has also ensured alignment of BTAST with the DFID’s other regional projects - SPUR (for urban reforms; working in close collaboration with the Urban Development Department) and Governance and Administration reforms project. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?
[4] The details of cost estimates are as given under; Type of construction	Built area / (sq ft)	Rate / (Rs./sq ft.)	Total / (Rs. lacs)	Savings (Rs. lacs)	(%) Traditional construction of AWC	825	1,400	11.55 Model AWC	825	1,100	9.08	2.5	21
[5] The training cost per facilitator is approximately Rs. 7,000 and a facilitator is paid a total honorarium of Rs. 19,000 @ Rs. 1,000 per month for 19 months. Thus, cost per meeting over each cycle of PLA is estimated to be [(7,000+19,000)/100=] Rs. 260. The average cost to reach out to a woman member of SHG works out to be (Rs. 260 ÷ 65 =) Rs. 4 only.
[6] The half-a-day salary of DPO and transportation cost adds up to direct training cost of Rs. 2,134 per orientation programme. Taking into account that on the average 85 ASHAs attend per programme, the training cost works out to (2,134 ÷ 85 =) Rs. 25 per participant. The state has recently sanctioned a training budget of Rs. 1,32,000 to orient 400 ASHAs. Per participant rate per day is (1,32,000 ÷ 400 =) Rs. 330. The rate comparison on a full-day basis shows that training cost of BTAST is [(25 x 2 ÷330) x 100 =] 15% of the regular training cost of the department.
[7] Source: Hon’ble Minister’s speech for Demand for Grant in the Legislative Assembly (p2)
[8] Source: www.tsc.gov.in

6. Conditionality
6.1 Update on specific conditions / For SWASTH programme, DFID has not specified any specific policy conditions for GoB. However, reforms in the health, nutrition, and water and sanitation sectors continue to be high on the political agenda of the state government. / According to the Project Memorandum, the state government is required to ensure that SWASTH funds are provided as additional to: (i) state share of national government schemes; (ii) expenditure required by the XII and XIII Finance Commission and Supreme Court judgements; (iii) the state’s plan contribution. These conditions are fully met. / The Project Memorandum also specifies that DFID funds will be itemised under budget heads following standard GoI and state government rules and procedures. GoB has complied with this condition.

7. Conclusions and actions
Conclusion: During the period under review, implementation of SWASTH progressed with satisfactory achievements of programme outputs, outcomes, and impact milestones. There were visible improvements in health, nutrition, and WASH services. The beneficiary feedback gathered from the field was quite encouraging. SWASTH implementation also achieved Value for Money. However, a disquieting fact was poor utilization of FA. / Actions: The Year 4 milestones should be drawn up taking into account spillover activities from the previous year and the recommendations made against each output. More emphasis is required inter alia on scaling up of community based interventions and promoting public-private-partnership for expanding infrastructure and facilities and delivery of health, nutrition, and WASH services. It is also imperative that all the three departments take appropriate measures for effective utilization of FA.

8. Review Process
The joint Annual Review was undertaken during July 2013 (15 - 18 July). The review included field visits and state level presentations and discussions. The field visits were conducted in Gaya, Bhagalpur and Banka districts. / The review participants included DFID team, officials from DoHFW, SWD, PHED and representatives from the Government of India. Technical agencies such as UNICEF, UNFPA, NIPI, BMGF, Intra Health and JHPIEGO also participated in the review. / The Annual Review Report is informed by independent sources of survey data like DLHS, SRS, AHS as well as Government MIS. Detailed progress documentation on BTAST outputs, presentations by the Government of Bihar, and findings of various surveys and reports were reviewed to support the conclusions.