Annual Review – Summary Sheet

Title: Innovative Ventures and Technologies for Development (INVENT)
Programme Value: £38m		Review Date: September 2016
Project Code: 202927	Start Date: 4/08/2013	End Date: 31/07/2019

Summary of Programme Performance
Year	2013/14	2014/15	2015/16
Programme Score	B	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
The INVENT programme was approved in August 2013 to invest up to £38m over 6 years to support technological and business innovations for the benefit of the poor in the low income states of India and in developing countries in Africa and South Asia. This programme is funded both from the DFID India bilateral budget (henceforth referred to as DFID India), and the DFID India Global Programme (henceforth referred to as Global). This is the third annual review of the programme.

The focus for the third year of the programme was on strengthening partnerships and implementation of project components which were already approved within DFID and/or by the Government of India. The main components of the programme are as follows:

Ideate (Global)
£1.6m technical assistance to share and replicate proven innovations from India to developing countries.

Incubate (DFID India)
£6m Support to incubators which will nurture innovative inclusive business ideas leading to 50 ‘investment ready’ businesses.

Invest-Scale (DFID India)
- £18m returnable capital for replication and scale-up of commercially proven innovative businesses in India’s low income states (LIS).
- £3m Strengthening ecosystem for inclusive innovations and impact investments.

Propagate (Global)
- £3.3m technical assistance to support knowledge-sharing on inclusive innovations between India and developing countries.
- A £2.1m DFID contribution to a pooled fund to test and pilot innovations between India and developing countries.

The main achievements under each component of the programme were as follows:

Ideate
Global Grand Challenges (GC) launched its third call on GC for TB Control, supported by USAID and DFID. Subsequently GC has released 3 pilot awards, for scaling Indian Innovations at a global level. Following selection the three awardees are: 1) Everwell Health- in Burma 2) Operation ASHA- in Afghanistan and 3) ZMQ Development- in Uganda. The first two pilots have started implementation in early August 2016. ZMQ Development was given the award in June 2016 and they are in the process of finalising their target patient population. They will start implementation in August 2016.
Incubate
This component is being implemented by DFID India in partnership with Technology Development Board (TDB). This component was delayed due to reasons including vacancy or confusion over the post of Secretary at Technology Development Board (TDB) for over a year. During the review period, Dr. Bindu Dey assumed the post of Secretary at TDB and the agreement between the Implementing Agency (Villgro) and TDB was signed on 1st October 2015.
- The governance structure for managing the program with a Steering committee and a governing council was agreed with TDB.
- Villgro selected 4 incubators in the LIS (IIT Kanpur at Kanpur, Startup Oasis at Jaipur, IIM Calcutta Innovation Park at Kolkata and KIIT TBI at Bhubaneswar) to support under the INVENT program. Agreements have been signed with all the 4 incubators.
- Virtual Incubation: www.startupwave.com - during the review period over 303 entrepreneurs used the Pre-incubation platform and benefited from the content, structured process and mentor connects. 41 enterprises graduated from Pre incubation to incubation phase and 38 mentors have come on board.
- The incubation phase of StartupWave was launched in October 2015. The Steering committee agreed the financial sustainability plan for the platform.

Invest-Scale
Funds: £18m Development Capital Investment (DCI):

Of the three potential Go owned/sponsored funds identified during the second annual review, two partnerships viz. Rajasthan Venture Capital Fund (RVCF) and IL&FS Tara Fund IV were finalised. DEA final approval for RVCF and IL&FS partnerships was received during May and June respectively. The funds were formally launched during the SoS visit in Aug 2016.

The commercial terms including the alignment with INVENT objectives were agreed during the review period. The team contracted consultants to conduct due diligence of the partners using DFID India framework and to ratify the legal terms. The recommendations were agreed/negotiated with the fund managers.

Eco-system: Building an effective social venture ecosystem in India

NESTA partnership on UK-India Innovation exchange:

- Research report on framework for ‘Good Incubation in India’ with strategies for supporting social enterprises in challenging contexts was launched in February this year
- Capacity building workshop was conducted for 40 Incubators in India in February this year.
- Partnership with Indian Impact Investors Council in hosting a lecture with Sir Ronald Cohen, founding-chairman of Big Society Capital. Sir Ronald is widely regarded as the father of Impact investments. He spoke about the potential of Impact investments in India.

- S.H.E Initiative:
  - In the last year, the pilot phase of the S.H.E initiative (a multi-stakeholder platform that promotes collaborative action to address safety, health education and employment of women and girls) gained momentum with 13 corporates joining as signatories to S.H.E. Compact.
  - The lessons from this pilot fed into the larger initiative for engaging with corporates for mobilising private sector resources for social impact. Phase 2 of S.H.E. is also included in this imitative. A consortium led by Think Tank Consultancy, FICCI and IPE Global was awarded the contract for this initiative.

Propagate

Connect to Grow (CTG) completed its 3 month Inception period in November 2015. The programme design and approach builds on the original concept of DFID’s Innovation Knowledge Exchange Facility. CTG supports enterprise growth, using the mechanism of innovation transfer and partnership. During the Inception Phase, systems and processes to manage the partner enterprises, as they progress, were laid down. A team of partnership managers with experience of working in over 150 Asian and African countries have now been recruited. To date 450 enterprises (Indian, Asian and African) have registered for partnership on the CTG website.

Millennium Alliance (MA)
During the review period, DFID supported Rounds 2 and 3 of MA. Out of 62 enterprises selected under MA, 12 have been supported under INVENT for exclusive South- South collaboration. While the round 2 awardees (6) are working in agriculture and health sectors, round 3 awardees (6) will additionally working on water and sanitation issues. Round 2 is under implementation in Ethiopia, Rwanda, Kenya, Uganda, Nepal, Bangladesh and Afghanistan. Round 3 awardees are yet to start implementation. They have recently received their first grant.

MA Global window caught the attention of PM Modi when the MA led a delegation of 7 companies (supported under the DFID India Global Programme) from the MA to join the FICCI’s Business and Innovation delegation to Nairobi from 10-11 July 2016.The delegation was led by Dr. Bindu Dey, Secretary, Technology Development Board from the Department of Science and Technology, Government of India. PM Modi interacted keenly with the delegation to know more about the UK contribution to development initiatives in Africa.

Summary of Lessons Learnt
- There is a visible opportunity to align with GOI’s Start up India programme.
- There is very high potential of XHMG working especially with Department of Science and Technology.
- Due Diligence of proposed partners is crucial to the final selection outcome of the awardees.
- Partnerships take a long time to materialise as alignment of interests across multiple investors takes time.
- Incubators need to evolve their sustainability plans over time.
- A number of enterprises registering interest from Africa and South Asia are at too early a stage to consider an international partnership opportunity
- It has been challenging to get enterprises and Connect’s Partnerships Managers to think through the logic between the market opportunity, the enterprise’s corresponding needs, and the opportunity for partnership.
- There is need for more coherence within different components of the programme.

Summary of responses to last year’s annual review

Outputs	Recommendations	Status
Output 1	In order to ensure that we don’t face any further bureaucratic challenges in the coming year a strong ‘Advisory Board’ needs to be constituted after TDB signs the MoU with the management agency.	Agreed with TDB to constitute Advisory Board by October 2016
	StartpWave is having greater traction and impact than envisaged. It was designed to be subsumed within the TDB partnership but because of the delay in TDB partnership, SW started early integrating various players and having a greater impact at the startup ecosystem. Therefore it is recommended that it deserves a separate output in the log frame.	Added an output indicator for StartpWave
	Unconvention/L will require hand-holding in a low touch, pre-incubation form of support to reach a level of maturity at which they can be incubated	Most of those identified through Unconvention/L are linked to StartupWave
Output 2	While there is a clear gap in the market in terms of very early stage of impact investments (pioneer and small ticket), the government fund managers that we identified have little understanding and appetite in this stage of investments. This is proving to be tough but the team should ensure our role as ‘Market maker’ and being ‘Additional’.	Two DCI funds signed off aligning fully with INVENT objectives (Pioneer, Small ticket and LIS
Output 3	MA to set up an advisory board with experts in the sector and the impact investment space to ensure that they can feed into the application format, tweak the appraisal process and criteria for efficiency, etc., which is now in place.	This Advisory Board was set up but was dissolved when FICCI discovered that some members had conflict of interest There are plans of reconstituting it as soon as some rules and regulations for board membership are finalised

Summary of recommendations for DFID, for the next year

Ideate

Grand Challenge (IKP)
Monitor implementation of DFID-funded projects supported under the call on TB (jointly with USAID).

Incubate

- Increase the visibility of the program to align with GoI’s Start up India action plan by engaging Niti Aayog and Department of Industrial Promotion and Policy (DIPP) in the delivery of the program. Team to agree action plan by September.
- There’s greater potential of working x HMG in some of the areas relevant to INVENT especially with Science and Innovation network (SIN) promoted NEWTON fund UKTI promoted Tech Rocketship awards. Now that all the INVENT partnerships are in the implementation phase, the teams should agree on areas of mutual collaboration.

TDB
- Villgro to have an efficient team in place (by Sep 2016) at TDB and Incubators to increase the pace of the program.
- Agree end to end business plan by Oct 2016
- Agree on a monitoring and reporting plan with Villgro and TDB

Virtual Incubation platform
Monitor the sustainability plan of the platform and critically examine the path to sustainability through the steering committees

Invest-Scale

- Actively help the funds source the right set of investment pipeline enterprises aligning with INVENT objectives.
- Since both the funds are pooled funds with multiple investors, greater coordination is required to ensure DFID INVENT objectives are achieved. Where necessary ‘the excuse’ clause agreed with both funds could be activated.

Ecosystem
Follow on engagement with NESTA as part of UK offer in Tech Summit planned in November.

Propagate

Millennium Alliance
- Work with USAID to support awardees in networking, monitoring & evaluation and capacity building.
- Work with TDB, FICCI and MEA to establish and promote ADITI (African Development through Indian Technology and Innovation) Fund as India’s Platform to transfer proven innovations from India to Africa for development impact.
- Continue the dialogue with UN Economic and Social Commission for Asia and Pacific (UNESCAP) on an approach to regional innovation platform and set out next steps by September 2016.

Connect To Grow
- Ensure engagement in South Asia (where effort has been weaker compared to Africa) remains a focus area for Connect.
- Focus on creating knowledge products, and make links to the planned evaluation of INVENT Global
- Ensure learning from Connect helps in designing ADITI (Ongoing)

Evaluation of Global component of INVENT
Work with identified partner to support delivery and generation of early lessons as well as final report.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	3881771
DevTracker Link to Log frame:	3899054

Introduction: Why is the intervention needed?
Despite high levels of innovations targeting the poor nationally, India’s social entrepreneurial activities are unevenly spread, with significantly lower levels in the low income states. A recent report notes that only 16% of enterprises benefiting the poor operate within India’s low income states, notwithstanding the fact that these states constitute more than 60% of India’s population. There is a need for increased investment to develop and pilot new ideas and approaches as well as to take proven concepts to scale or to new markets.

Providing quality healthcare and education; improving agricultural productivity and quality of livelihoods; and increasing access to energy continue to be amongst the most pressing current problems facing India and low income countries. Inclusive innovations in such sectors have substantial developmental impacts on the lives of the poor.

Such inclusive Indian innovations have demonstrable potential to benefit the poor not just in India but also in other developing countries. However, several challenges remain in sourcing, nurturing, scaling and adopting such solutions both in India and from India to other developing country settings. This is a gap that INVENT aims to address.

Different components of the programme address different challenges across the innovations lifecycle in order to better deploy India’s entrepreneurial and technological capabilities for the reduction of poverty in low income states and developing countries.

Outline of the Programme: What Support?
The three main elements in the programme are to:

i. Pilot and nurture innovative business ideas in order to build a pipeline of projects for future impact investing and scale-up:
- ‘Grand Challenge’ Funds in health, to help generate new solutions for specific problems in these sectors that are relevant to developing countries;
- Support to incubators which will nurture innovative inclusive business ideas leading to 50 ‘investment ready’ businesses.

ii. Support the scale-up of innovative enterprises in the low income states through:
- Direct patient capital investment in commercial innovations that benefits poor;
- Providing capital to a Fund of Impact investment Funds that in turn invests in commercial innovations that benefits poor;
- Strengthening ecosystems for inclusive innovations.

iii. Support knowledge-sharing on inclusive innovations between India and developing countries through technical assistance for:
- Supporting a network of potential investors and investees from India in other developing countries;
- Technical Assistance and roadmaps for exchange, adaptation and adoption of at least 5 inclusive innovations developed for up to 3 developing countries;
- Support evaluation studies undertaken on the adaptation and adoption of inclusive innovations.

Expected Key Results
The programme is expected to support technological and business innovations to benefit up to one million poor people belonging to lower income segments (BoP), as producers, consumers, employees and suppliers in India’s poorest states and in developing countries.

- At least £25m investment mobilized for inclusive innovations;
- Over 7,500 new jobs created;
- Over £30m increased taxes generated ;
- Up to 50 viable business ideas/enterprises provided training and technical assistance;
- Up to 25 inclusive innovation pilots supported in developing countries;
- Exchange, adaptation and adoption of up to 5 (of the above 25 pilots) inclusive innovations in up to 3 developing countries, focused in health and agri-food sectors;
- At least 1 research and evaluation study undertaken.

Fit with DFID & UK strategic priorities
The project contributes to the Prime Minister’s vision of development which aims to make poorer countries attractive to invest in and remove the barriers that hold prosperity back. Furthermore, the project contributes directly to achieving the DFIDI’s Operational Plan objectives and aligns well with the transition of the DFID India programme away from large resource transfers to focus on small-scale TA, private sector investment through DCI and engagement with India on global development challenges.

The project will contribute to the HMG prosperity agenda by building links with the private sector, and improving the overall environment for innovative businesses. Innovation is an important theme within the HMG-India relationship. The project responds to several priorities agreed at the recent Ministerial-level UK-India Science and Innovation Council meeting: better understanding of innovation metrics and collaboration; boosting interaction with SMEs; helping innovative businesses and academia to collaborate; and a focus on priority sectors, e.g., food and health.

## PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

This is the third annual review for INVENT. The third year was dedicated to: (a) agreeing terms with new partnerships (b) implementing existing programme partnerships while (c) addressing operational issues.

No.	Outcome Indicators	Milestone year 3 (2015-16)	Progress
	No. of innovative solutions introduced in LIS+LIC	21	The number of innovations introduced in LICs and LIS clearly surpasses the milestone number: / Connect has completed its Inception Phase and awarded its first partnership grant in Ghana. / The 4 incubators selected / 41 enterprises graduated from Pre incubation to incubation / The Contribution agreement has been signed with two fund managers RVCF and IL&FS. / 6 MA awards have been given in Asia and Africa / Three GC awards given in Burma, Afghanistan and Uganda.
	Additional individuals/households obtaining significantly improved access to affordable and efficient basic services and products in agreed priority sectors in India and in LICs	50,000	Due to the delay in kick starting some of the partnerships and the associated delay in identifying and piloting innovations, quantification of the number of people impacted by each innovations and the aggregated total is not ascertained. / This should be taken as a priority for next Annual Review.

DFID’s vision for the program is to work closely with GoI and contribute to their Start up India mission. This can happen both from the private sector and Global program components of INVENT.The emergence African Development through Indian Technology and Innovation (ADITI) represents good evidence of how DFID’s programming and dialogue around INVENT has catalysed new action and commitment from GoI. In addition, DFID has worked with United Nations Economic and Social Commission for Asia and the Pacific (ESCAP) on a concept note for a UK-India-UN partnership to stimulate policy makers across the region, to drive greater sharing and uptake of inclusive innovation.

Overall output score and description

Output number	Output Description	Impact Weight (%)	Output Performance
1	Identify, pilot and nurture inclusive innovations in LIS & LICs	40%	Outputs moderately exceeded expectation (A+)
2	Support the scale up of innovative enterprises in low income states	40%	Outputs moderately did not meet expectation (B)
3	Support Knowledge sharing on inclusive innovations between India and low income countries	20%	Outputs moderately did not meet expectation (B)

Key Lessons
The components of INVENT directly contribute to GoI’s Startup India mission and the various initiatives the GoI has under Startup India. With the transitioning of UK-India bilateral relationship, it will be a missed opportunity if DFID India doesn’t leverage INVENT’s objectives and results with that of GoI’s vision for Start ups.

There is greater potential working x HMG in some of the areas relevant to INVENT especially with Science and Innovation network (SIN) promoted NEWTON fund. Now that all the INVENT partnerships are in the implementation phase, the teams should agree on areas of mutual collaboration.

Incubation
- For Social impact focussed incubators, it is hard to get to sustainability only from revenue generating activity; incubators will almost always need some grant money as well.
- There are a range of different business models available to incubators, one size fits all approach will not work.
- Often the right revenue model emerges only after incubator reaches some level of maturity.
- In considering different ways to generate revenue, incubators need to prioritise activities that generate steady revenue while aligning with their core mission.

Start-up wave
- Virtual tools and resources can enhance capacities of incubation staff to provide support in stage and sector-appropriate ways
- Cohort-based incubation is more efficient than staggered support for start-ups because it allows
- StartupWave team to align efforts from Demo Day to Demo Day
- Demo Days aligned with industry convening create a much larger and more beneficial platform for startups

MA
- There should be cross learnings between each of the three Global INVENT components. This will help to maximise the gains and minimise/avoid duplication of resources
- Under Connect and MA the need for capacity building and mentorship of entrepreneurs has clearly emerged as a need and a precursor to the implementation of partnerships.
- Early lessons learnt, need to be incorporated into the evaluation of Invent.

Connect to Grow
A number of enterprises registering interest from Africa and South Asia are at too early a stage to consider an international partnership opportunity. Most South Asian African enterprises who have registered are not at the point of doing what they do well enough. It has been challenging to get enterprises and Connect’s Partnerships Managers to think through the logic between the market opportunity, the enterprise’s corresponding needs, and the opportunity for partnership.

Grand Challenge
Due Diligence of proposed partners is absolutely crucial to the final selection outcome of the awardees. For example when IKP conducted the due-diligence of one shortlisted partner they found that the ground realities were vastly different from what was being claimed in the bid document. Pilots that bidders were projecting as successful did not have adequate evidence data to support it.

Business Engagement
Continuous engagement and follow up is essential with corporates and technical agencies to achieve tangible results in influencing development outcomes of CSR spends.

Key actions
- Agree DFID representation in the Steering committees of RVCF by Sept
- Agree DFID representation in the Advisory board of IL&FS TARA fund by Sep
- Constitute an Advisory board for TDB partnership by October 2016
- Increase the visibility of the program to align with GoI’s Start up India action plan by engaging Niti Aayog and Department of Industrial Promotion and Policy (DIPP) in the delivery of the program. Team to agree action plan by September.
- Agree end to end business plan of incubators by Oct 2016
- As the CTG programme evolves we should ensure that we respond to needs on the ground.
- Continue the dialogue with UNESCAP on approach to regional innovation platform and set out next steps by end October.
- Monitor the sustainability plan of the virtual incubation platform and critically examine the path to sustainability through the steering committees

Has the logframe been updated since the last review?

NO. However it is recommended that Indicator 3.3 under Output 3 should be removed for subsequent review due to policy change and discontinuation of funding to Sankalp Africa

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Pilot and nurture inclusive innovations in Low Income States (LIS) and developing countries
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
1.1 Pilot and test new solutions in developing countries to tackle global problems in key sectors	Yr 1: 0 / Yr 2: 5 / Yr 3: 6	In year 3 of implementation, MA awarded 6 grants under Round 2. All 6 started implementation in the review period. The progress on all 6 is detailed below. / In addition MA has selected and awarded 6 grants under Round 3 this year, achieving the output target. All the 6 grantees have received the first tranche of grants. / During this review period 3 calls under Grand Challenge have been awarded grants. All 3 will be in implementation phase by August 2016.
1.2 No.of Business ideas/ early stage start ups graduating from Pre-incubation support to receive Incubation/Acceleration support / Incubators; Mentors; Corporate partnerships on boarded	25	Output exceed the targets for this year / Under StartpWave, 41 enterprises graduated from Pre incubation to incubation phase and 38 mentors were on boarded / In addition in partnership with TDB, 4 incubators have been selected to incubate social enterprises in 8 LIS
1.3 No.of Business ideas/ early stage start ups graduating from incubation support to receive first round of investments in LIS	10	20 enterprises showcased to investors - (Includes 14 startups showcased at Demo Days and 6 other startups were put in touch with IAN and I3N for evaluation / 6 enterprises in conversations with 9 investors

Key Points

Incubation

Villgro was appointed as the lead incubator for the Innovative Ventures and Technologies for Development (INVENT) program of Technology Development Board, Government of India (TDB), supported by the DFID in December 2013. The agreement between TDB and Villgro was signed on 1st October 2015, following which the programme commenced.

Villgro selected 4 incubators in the LIS (IIT Kanpur at Kanpur, Startup Oasis at Jaipur, IIM Calcutta Innovation Park at Kolkata and KIIT TBI at Bhubaneswar) to support under the INVENT program. Agreements have been signed with all the 4 incubators.

The kick-off meeting between TDB, DFID, Villgro and all the 4 selected incubators was held in Delhi on 9th June 2016. Critical issues such as building pipeline, due-diligence, portfolio management, building an effective mentoring program, defining and measuring social impact, technology and MIS, virtual incubation and using StartpWave, reporting and reviews were discussed in the meeting. In addition, each incubator made a presentation on their current operations and implementation plans for INVENT.

Villgro has started identifying social enterprises through its current pipeline so that it can start incubation of enterprises that fit the INVENT mandate. One of the enterprises identified as per selection criteria (agreed between DFID, TDB and Villgro) is Carmel Organics which will be incubated at Startup Oasis, Jaipur. Details are in Box 1.

Box 1: Carmel Organics / Carmel Organics is working in LIS and is involved in contract production, processing and trading of organic products. They focus on small and marginal farmers who use organic farming practices. The incubation agreement has been signed between Villgro and Carmel Organics, following which Carmel received funding of INR 10 lakhs (£10,000). / Innovation: / Carmel Organics promotes organic herb farming and encourages farmers to grow hundreds of different medicinal herbs organically and get higher income from their produce. Carmel supports farmers by, providing seeds and inputs along with extension services through its expert agriculture team and has a buyback arrangement for their produce at fair price. / Problem: / Farmers have limited crop options to grow on their farm which limits their income. Farmers do not have access to information on diversifying their cropping. Other alternative to improve farm earnings is to grow commercial crops fruits/vegetables and polyhouse production which requires huge investments not possible for small and marginal farmers. / Impact: / Carmel organics helps farmers grow herbs organically and get more income on herb produce and a premium on prices if quality is good. The farmers’ income increases from 50% to 200% after producing herbs.

StartupWave

Since its launch in April 2014, 600+ entrepreneurs have signed up for StartupWave support towards building/refining their business models with the support of serial entrepreneurs, VCs, angel investors,
Incubators, and the like, and are now on the pathway to establish successful enterprises. SW supports
entrepreneurs in 3 ways:
- work with idea-stage entrepreneurs validate their ideas and build out business models
- work with newly launched startups to help them build minimum viable products and prepare for fund-raising
- showcase high-potential startups to investors, corporates, and other strategic partners

During the review period:
- Over 303 entrepreneurs used the Pre-incubation platform and benefited from the content, structured process and mentor connects.
- The incubation phase of StartpWave was launched in October 2015.
- 20 enterprises showcased to investors - (Includes 14 startups showcased at Demo Days and 6 other startups were put in touch with IAN and I3N for evaluation
- 6 enterprises in conversations with 9 investors

Box 2 Examples of Enterprises supported by StartpWave / Donate Items / Connects Donors and NGOs through web and mobile platforms to boost in-kind donations. The platforms are integrated with e-commerce, curated to NGOs’ needs that donors can use to identify / products suiting their interest to donate. / Jeevtronics / Improve design of and access to defibrillators by creating a hand cranked defibrillator for India and / other low and middle income countries. / TatvaGyan / Provides tablet-based high quality affordable pre-school program for kids in the 3-6 years age range, by working on a personalized approach to track a child’s learning pattern. TatvaGyan also conducts / after-school programs to bridge the learning deficits of children in a short duration. / Actozen / A healthcare solution that adopts technology to improve doctor discovery, consultation, doctor-patient interaction and medical history repository rolled into one. / IndiPV / Early stage company developing automatic, water less, Photo Voltaic (PV) panel cleaning systems for Solar PV power plants ranging from roof top plants to large scale installations. / MilkyWay / Addresses issues in the dairy value chain so as to boost supply and provide high quality, affordable unadulterated milk and milk products. / Inclov / Inclov is the world’s first matchmaking app focusing on people with disability and with health disorders to find love. / Paarking / Trusted community marketplace for people to list, discover and book unique parking space nearby the / required destination - online or from mobile.

Millennieum Alliance

The review period saw all awardees under Round 2 in implementation. During this time calls for Round 3 were also announced and subsequently 6 awardees selected. They have received their first tranche of grant and will soon start implementation. There are some early lessons coming out of the selection and implementation process and the Global INVENT learning Evaluation planned for this year, will look into this in detail. MA has also completed selection of awardees for Round 3 and 6 awards have been given. The awardees in round 2 are detailed below in Box 3.

Box 3: Awardees under Millenium Alliance, Round 2 / AFIYA (by ZMQ) in Uganda and Afghanistan (Details of programme given in previous review ) / ZMQ is adapting the Mobile Integrated Resources for Aurat (woman)(MIRA)model, which is a mobile phone channel designed to help poor pregnant women and adolescent girls with information on pre-natal care, child immunisation, family planning and adolescent health. Baseline surveys have been completed in both countries and implementation has started. / Forus Health in Ethiopia / Forus Health is running a pilot in Ethiopia to demonstrate a sustainable eye screening model using the Fundus camera they have manufactured. They have identified “Beyond Eye Care “mission in Ethiopia as their partner. Sites have been identified and training of operators completed. The initiative aims to screen 10,000 patients in multiple sites and analyse the prevalence of multiple eye diseases in select districts of Ethiopia. / Sustainable Sugarcane Initiative (SSI) in Kenya / AgSri from India aims to develop, test and demonstrate the system of Sugar Cane Intensification in Kenya. AgSri has conducted a detailed study of sugarcane cultivation in the country and finalised West Kenya Sugar Company as partner. A training programme has been conducted for 450 sugarcane growing farmers. The project is well into implementation with capacity building, training, demonstration and early stage crop management. / Cropin in Kenya / Cropin from India will pilot their mobile–based platform for real-time farm management, monitoring and traceability in Kenya. They have scoped out potential partners, and contextualised technology to Kenya. 300 farmers have already been enrolled and the number is expected to reach 1000 by year end. Early learnings are positive and farmers are getting the benefit through timely intervention and support for their needs. DFID Kenya is helping them to connect to Kenya Market Trust. / Bhungroo in Bangladesh / Bhungroo technology by Naireeta in India is a water management system that injects and stores excess rainfall underground and lifts it out for use in dry spells. The massive underground reservoir can hold as much as 40 million litres of rain water. It harvests water for about 10 days per year and can supply water for as long as seven months. Artificially recharging aquifers by adding rainwater to underground water reservoirs enables the communities to continue farming for more than half of the year. The project was delayed due to certain legal requirements. 10 site units have been selected and training of local partners have been completed. Expected results include erection of 10 units of Bhungroo for 100 farmers, freeing 50 acres of land in each monsoon every year without any extra cost, guaranteed irrigation to approximate 200 acres of land and increased adaptation to climate change. / Farms and Farmers (FAF)- in Nepal / Under this initiative FAF will pilot the Indian approach of DeHaat (initiated in Patna, India) through mobile technology to provide end-to-end agri services to small and marginal farmers- from crop selection to market linkages in Nepal. Youth will be targeted for operations as potential change makers / service provider at the DeHaats. A detailed baseline survey of 600 plus households in 19 villages of 2 districts has already been done. 10 micro entrepreneurs have been trained and 5 Dehaat centres will have been set up by end August.

The emergence of ADITI represents good evidence of how DFID’s programming and dialogue around INVENT Global has catalysed new action and commitment from GoI, building on DFID-supported mechanisms. The Global team will continue to work with India’s Technology Development Board (TDB), Federation of Indian Chambers of Commerce and Industry (FICCI) and the Ministry of External Affairs (MEA) to establish and promote ADITI (African Development through Indian Technology and Innovation) Fund as India’s platform to transfer proven innovations from India to Africa for development impact.

In addition, DFID will continue the dialogue with UNESCAP on an approach to regional innovation platform and set out next steps.

Grand Challenges (IKP)

Three organisations in Afghanistan, Burma and Uganda have received awards for piloting and scaling up their work on TB diagnostics, compliance and adherence. Each of the three countries have identified their target ‘patient group’ and all will be in implementation stage by the end of August. Some early results from the pilot in Burma are expected in October 2016. The details of the awardees are in Box 4.
Box 4: Awardees under Grand Challenges / 99 DOTS/Everwell Health (Burma) / Everwell Health is using augmented packaging and mobile phones to monitor and improve adherence to anti-Tuberculosis medication in Burma phones. Using 99DOTS, each anti-TB blister pack is wrapped in a custom envelope, which includes hidden phone numbers that are visible only when doses are dispensed. Population Services International (PSI) and their Sun Quality Health Network (SQH) is the partner in Burma. The program encompasses over 900 private practitioners who are enrolling TB patients; who together report about 20% of the TB cases in the country. The goal is to enrol 100 patients in the first two months, as a proof of concept and learning opportunity before expanding the program. Pending success of the pilot, 100-500 patients a month will be enrolled, and the total numbers not to exceed 5,000 patients, by the end of 2017. Both pulmonary and non-pulmonary TB patients are enrolled. / Operation ASHA (Afghanistan) / Operation ASHA (OpASHA) delivers high quality healthcare services with a focus on tuberculosis and has a presence in 9 states in India and 7 countries worldwide. In Afghanistan the objective is to pilot the eCompliance and eDetection technology and study the impact of the pilot on TB patients and study the success and challenges of global technology transfer and adoption. OpASHA aims at developing a model of sustainability for the project in Afghanistan by partnering with Afghan Community Research & Empowerment Organization for Development (ACREOD). / ZMQ Development (Uganda) / ZMQ development was awarded the GC-TBC Call III award on June 30, 2016. They are in the process of finalizing their target patient population and their engagement in Uganda.

Recommendations

- Participating in the Investment committee of Incubators will give insights into the governance structure agreed with Incubators.
- Expedite Constitution of the Advisory board for TDB partnership to ensure the program achieves the set objectives in addition to offsetting the GoI bureaucracy. For closer alignment to GOI’s Start –up India Mission, TDB should invite participation from Niti Ayog in the Advisory Board
- Ensure alignment of interest from downstream investors with each incubator as it will incubators provide appropriate incubation services to entrepreneurs. This is likely to attract downstream investors to take interest in mentoring and subsequently investing in such enterprises.
- All incubators need to present their achievements against milestones to the Steering committee once in a quarter. This will also help in learning from each other.
- The collective strengths of Mentors in the four incubators, Villgro and StartpWave could be leveraged for larger DFID investment programs. Team should explore this opportunity with respective fund managers
- The current level of coordination between StartpWave and TDB partnership in leveraging partnership strengths are inadequate. Villgro and Intellecap should agree action plan for future engagements.

Output Title	Support the scale up of innovative enterprises in low income states
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
2.1 No. of viable business enterprises supported for scale up into LIS through patient risk capital investments	6	The contribution agreements for the 2 funds have been signed and funds formally launched in Aug 2016 / The funds will now start identifying the enterprises to invest in.
2.2 Strengthening ecosystem for inclusive innovations and impact investments	*Management Agency identified for BE work / * *Impact incubation capacity strengthened for identified incubators	Management Agency identified for Business Engagement work / Incubation for Social impact workshop was organised to strengthen incubators. / Report on Good Incubation for Social Impact launched.

Key Points

Funds
The milestone for the year (6 investments) is not met as the team under estimated the time it takes to agree partnership terms with three Fund managers simultaneously. The time required to get a sign off on contribution agreements with partner fund managers was much more than expected. The difficulty in agreeing partnership terms with three fund managers (RVCF, IL&FS and MPIF) simultaneously posed a challenge to the team. The issues/activities which required buy in from partners and government approval which are outside the influence of DFID took more time than envisaged.

Due Diligence for RVCF and IL&FS was completed in November and January this year respectively. The DEA approvals for RVCF and IL&FS came in March and June respectively. The negotiations on commercial, Environment Social Governance (ESG) and legal terms with the funds took considerable time and efforts from the team. One of the major achievements of this process was agreement on adoption of ESG parameters across the fund and not only for DFID funded investments. This is a first step forward in mainstreaming in responsible investing practices in established funds. The RVCF and IL&FS funds were launched during SoS visit to India in August 2016.

Ecosystem
All the milestones for the year have been achieved

Nesta
Nesta organised a one-and-a-half day summit on incubation for social impact, bringing together 57 participants, representing a wide range of organisations from across India and beyond. This event provided a valuable opportunity for participants to enhance their knowledge on incubation, network, link up with other organisations, learn about upcoming projects, and realise the value of collaboration between similar initiatives.

The Incubation for Social Impact Summit was the final deliverable within the Nesta-DFID India partnership. The event was designed to support DFID’s objectives for INVENT by engaging incubator managers in thinking about how they can support social enterprises in low-income states.

In order to reach incubators and make sure the content was useful to those groups, Nesta built relationships and co-organised the event with three partner organisations in India: the Indian STEP and Business Incubator Association (ISBA), Aspen Network of Development Entrepreneurs (ANDE) and GIZ, the German agency for international cooperation. Nesta also worked with Bethnal Green Ventures to design and deliver the event.

We also organised the Sir Ronald Cohen event in April 2016 in partnership with Indian Impact investors Council that attracted approx. 150 participants. The event highlighted the potential of Impact investments in Indian context and provided ways to explore new instruments like Social or Development Impact Bonds in India.

Business Engagement:
- In the last year, the pilot phase of the S.H.E initiative (a multi-stakeholder platform that promotes collaborative action to address safety, health and education and employment of women and girls) gained momentum with 13 corporates joined as signatories to S.H.E. Compact.
- The lessons from this pilot fed into the larger initiative for engaging with corporates for mobilising private sector resources for social impact. Phase 2 of S.H.E. is also included in this imitative. A consortium led by Think Tank Consultancy, FICCI and IPE Global was awarded the contract for this initiative.
- This initiative aims to deepen engagement with both Indian Corporates and UK Businesses in India, strengthen the call to action initiative – S.H.E and policy advocacy.

Recommendations

Investments
This is the first time DFID India will be investing in a pooled fund vehicle where DFID India will be one of many investors. There is risk of DFID objectives getting diluted though DFID’s interest have been ring fenced through the terms in contribution agreement. Therefore it is highly recommended that the team have close engagement with fund managers during the investment process.
- The first few investments are crucial in giving signals to the fund managers on the type of investments DFID will be interested in.
- Where necessary DFID can use the ‘Excuse clause’ to abstain from investing in an enterprise though it is approved by the investment committee

Ecosystem
There is need for setting up a networking group/platform – potentially across thematic/sector groups – to allow incubators across sectors to keep in more regular contact. This could be led and managed by TDB which has a long-term interest in and commitment for supporting incubators.
Impact measurement in social enterprises both from impact investors and incubators remains a big challenge. Support to investees needs to be provided for impact measurement. This also needs to be included in the evaluation plans for the fund.
Business Engagement:
Continuous theme based engagement and follow up essential to retain interest of signatories. TA support and networking needs to be need based and specific to on board more signatories.

Ensure that potential and expertise of selected consortium on CSR, industry networks, programme management is fully utilised to set up a relevant facility to engage corporates for lasting development impact.

Output Title	Support knowledge sharing on inclusive innovations between India and developing countries
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
3.1 Evaluation Studies/Operational Research Studies undertaken	1	TORs have been developed, and signed off by SEQAS, for the evaluation of the Global Component of INVENT. The tendering process will begin as soon as the new framework arrangement (expected in early September) is in place.
3.2 New Partnerships for replication, adaption and adoption of inclusive innovations developed in developing countries	2	MA identified 5 new partnerships in Africa and Nepal under Round 3. Description given below. / CTG has made its first investment in a partnership between a Ghanaian enterprise Agromite, and two Indian enterprises, Redlands and Bansuri for Agricultural mechanisation. / A total of 7 new partnerships have been formed in the review period.
3.3 No. of innovators targeting BoP receiving business development services (BDS) and technical assistance in developing countries	4	None. Funding to Sankalp Africa has been discontinued because of policy changes. Therefore it is recommended that this indicator is removed for the subsequent reviews.

Key Points

Connect to Grow
The programme completed its Inception Phase in November 2015. The programme design and approach builds on the original concept note of DFID’s Innovation Knowledge Exchange Facility (IKEF). Process and procedures for the programme have been laid down and a team of partnership managers (with experience of working in 150 Asian and African countries) have been recruited. To date, almost 450 enterprises (Indian, Asian and African) have registered on the Connect website. As mentioned in the progress section above the first partnership has been established in Ghana. If the pilot is successful, the partnership will look at assembly and manufacture of machinery in Ghana

One of the early learnings of the programme is that the number of enterprises registering interest from Africa and South Asia are at too early a stage to consider an international partnership opportunity. Most South Asian/African enterprises who have registered are not at the point of doing what they do well enough. It has been challenging to get enterprises and CTG’s Partnerships Managers to think through the logic between the market opportunity, the enterprise’s corresponding needs, and the opportunity for partnership. There are no other initiatives in India or elsewhere helping SMEs create partnerships in the same way as CTG i.e. real partnership where both partners undertake a venture together and share the risks and reward in same way. This has resulted in a need for CTG to provide counselling to enterprises from a very early point, and only taking forward those which demonstrate potential.

Due to the large number of early stage enterprises in Asia and Africa as opposed to more established high growth SMEs, CTG has worked through intermediaries. Intermediaries have been happy to reach out to their network of enterprises for free. Whilst this has been successful there may be a need to attract specific intermediaries who may require payment.

There has been greater demand in agriculture than health. In all of the countries the number of Agriculture enterprises far outweighs the number of health enterprises do the pool is generally much smaller.

CTG is currently running slightly behind schedule, largely in the number of enterprises that have been given a travel grant to connect with enterprises in India. The journey of enterprises for developing an international partnership has taken longer than anticipated, largely because of the amount of support the prospective enterprises needs. This opportunity is new for most of the enterprises in partner countries.

MA

In Round 3 we have identified 5 new Innovators who will be replicating and adapting their work in partner countries in Africa and Nepal. Each of them have identified local partners.

Waterlife in India is partnering with the Government of Rwanda to provide sustainable and affordable safe drinking water through Community Water Systems. A family can get 20 litres of safe water at less than 20 cents. With more that 60% of people in Rwanda with no access to safe water there is high incidence of infant mortality and waterborne diseases. Waterlife through their business model will provide Economic, Social and Environmental sustainability of solutions for the scarcity of potable water. Additionally they will provide education and awareness to bring in behavioural changes and prevent waterborne diseases.

Aakar Innovation’s will partner with Zana Africa, Village volunteers-Zigbira-common ground Africa, mpegi-banapads in Nairobi and Kisumu IN Uganda to establish affordable sanitary napkin manufacturing unit ,in the community which is run by the local women. They produce high quality affordable sanitary napkins. Under this model, women take the ownership to run the unit. They design the strategy for production, sales and marketing. This unit makes the women socially and economically empowered at community level, they openly discuss about menstrual hygiene management at community level.

Science for Society (also known as S4S) will partner with HPR and AEPC in Nepal to reduce post harvest loses by introducing the innovative solar conduction dryer technology. Solar Conduction Dryer (SCD) is an electricity free solar powered food dehydrator that reduces moisture content in agro-produce so that farmers and rural women can preserve their produce up to 1 year without using any chemicals and earn additional income through the sale of dehydrated products. SCD converts agro-produce into value added dehydrated products. Dehydrated products can be sold at high value and can also be used by farmer families throughout the year.

Science for Society will partner with Nairobi University, Macro consultant consortium and IFAD project to improve processing and marketing of Cassava (in Moranga – Kenya) which is one of the high value traditional crops with the ability to withstand adverse climatic conditions and an important food security crop for resource poor households. More than 70 % of cassava farmers in the Africa and Asia are women and are almost entirely responsible for the processing and marketing of cassava and its by-products. Household processing is labour intensive operation and requires 90 man-hours to process 100 kilograms. The operations account for significant wastage as the cassava tuber is not processed immediately, and the product's shelf-life is limited. Micro- processing at village level offers a solution but at a very high cost. Traditionally these units are run on diesel and /or electric power generators, and cost $15-20,000. Daily operational costs of approximately $20 per 200 kilograms further reduce the profit margin by 40-60 percent.

Agventures Corporation will partner with Meriadeg Le Cadre in Burkina Faso to introduce the portable backpack solar cotton picking machine to harvest cotton lint. The invention deploys the use of solar energy to run a cotton picking machine. During usage, the portable battery stores the extra power that is generated by the solar panel. The stored power can be used in the evening by farmers to light their homes and run home appliances. The circuits behind the solar panel are designed to convert solar power to electricity at the required levels to drive the cotton picking machine; and to store the additional power generated in a battery for later usage at home. Cotton harvesting in India & Africa is done by hand and is labour intensive, tiresome and ergonomically challenging. Due to the staggered blooming characteristics of Indian cotton hybrids and small sized farm holdings, the large fully automated cotton harvesters used in the US are not considered suitable for Indian farming conditions. Many villages in India & Africa have acute power shortage or have no electricity at all. This necessitated a harvesting solution without the use or electricity or AC recharged batteries.

Recommendations

There has been more focus on Africa than Asia and this needs to be balanced out in the coming year. We will be working closely with CTG on this.

Through on-the-ground insights, refine approach, creating more clarity in CTG team members’ roles, responsibilities as well as the overall approach taken to support enterprises through the process. Both CTG and DFID India will ensure that as the programme evolves we will ensure that we respond to the needs on the ground.

Indicator 3.3 of output 3 is no longer relevant so this review recommends that it should be removed from reporting.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

All implementing partners financed from the DFID India Global Programme (MA, IKP and CTG) have ensured that they have selected awardees or entrepreneurs who can maximise impact as well as provide Value for Money. All 3 have a set selection process and a Selection Committee / Steering Committee which reviews the awardees before they are selected for partnerships. DFID India was involved in the selection of awardees for Round 3 under the MA partnership. The team ensured that every single bid which came in was closely reviewed and that costs were appropriate to the tasks. In many cases the costs were reduced to reflect this.

Under CTG for example, to date 450 enterprises (Indian, African and South Asian) have registered on the website. An initial review revealed that out of this only 190 African/ South Asian and 100 Indian were found suitable to make it to the CTG market place. A further review showed that only 52 out of the suitable ones had a clearly articulated need. In the next step of assesment only 16 have been found suitable to make an initial connection with prospective partners. To date only one partnership grant has been awarded. The sifting process followed shows the rigour to achieve focus, impact and value for money.

When GC announced their call on TB last year, 55 applications from around the country were received. Out of which only 13 were shortlisted to present in front of the selection committee. Further only 4 out of 15 were selected for due diligence. Out of these four, three were given grants.

TDB: Though the project delayed was by more than a year, it was agreed with the Implementing Agency that the management fees and other terms agreed while procuring the MA will hold good for future engagement. As the management agency was hired by TDB which followed the GoI procurement process that mandates the lowest economic bidder of the top 3 technical bidders wins the contract. With the procurement of this MA, the fee of the management agency (Villgro) came down by 85% as Villgro managed to bring in a partner (Lemelson Foundation) who can bear the remaining cost as their objectives aligned with INVENT objectives.

Intellecap: INVENT incubation component includes Virtual incubation, StartupWave. The platform has supported close to 400 entrepreneurs with a small contract from DFID and GIZ. DFID is now supporting the second phase of Virtual incubation that will provide end-to-end support to startups Partners are committed to develop and scale the platform, and also make it sustainable.

RVCF and IL&FS: DFID is approximately contributing 15% of these funds leveraging the remaining 85% from other investors such as SIDBI, LIC and foreign investors However the fund practices will be governed by DFID’s polices for responsible investing such as ESG, LIS and innovation focus. The success of these funds is likely to attract more investments in early stage enterprises in LIS investments.

VfM performance compared to the original VfM proposition in the business case

As envisaged in the Business case, the partnership interventions and results represents an effective use of DFID resources as it delivers high impact and potentially market transforming innovations in under invested regions of India and other LICs in Africa and Asia. Across partnerships, there are clear evidence of leveraging additional private sector resources, and using returnable capital, allowing for it to be used for greater developmental impact ensuring good value for money in the delivery of this programme.

Assessment of whether the programme continues to represent value for money

The programme is progressing well to meet its objectives despite delays and delivered its objectives as set out in the logframe and the business case, and continues to represent value for money. All partnerships leverage private resources at least at 1:1. Already concluded, on-going and new partnerships such as NESTA, Intellecap, NextGen, Villgro, TDB, ILF&S and RVCF, Millennium Alliance, IKP and CTG have gathered pace (compared to previous years).

All partnerships under MA and GC reveal that Indian enterprises and institutions/organisations are working with local partners in South Asia and Africa. This makes the initiatives cost effective and contributes to sustainability, scalability, transfer of knowledge/ technology as well as capacity building of the recipient partners. Under MA there have been instances where FICCI (implementing partners for MA) have connected the Indian enterprises further with prospective Investors in India as well as in other countries. For example when MA led a delegation of 7 enterprises (supported under the DFID India Global programme) to participate in FICCI’s Business and Innovation delegation to Nairobi in July 2016.

Quality of financial management

For all the three components of the Global INVENT programme forecasts are updated on a monthly basis. Regular conversations/ meetings and conference calls with the 3 partners help us to make the forecasts as accurate as possible. All invoices are scrutinised well before payments are reimbursed to ensure that the money is spent for the intended purposes. No payments are made in advance.

DFID India is constantly in touch with partners to refine and make its forecasts as accurate as possible. All partners DCI partners, TDB, Villgro, Intellecap, FICCI, IKP and CTG are well aware of the DFID requirements for Due Diligence and are practicing it diligently to ensure VfM and high quality financial management.

Forecasting and monitoring of all components are done on a monthly basis. Financial statements are received by DFID on a regular basis. Annual Workplan and budget are agreed at the beginning of each year. DFID keeps a tight vigil on the spend on a monthly basis and ensure that the forecasted budget is spent at the end of the financial year.

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk
The overall programme risk continues to be moderate as the sector context has not changed much both in India and developing countries. The new government has proven to be pro-innovation and enterprise development so we concluded that the overall programme risk remains moderate.

Bureaucratic delays in Incubation work even after signing the contract remains a risk. Early lessons suggest key to avoiding bureaucratic delays is to develop trust and involve TDB in every operational aspect of the program. However this is work in progress. Villgro need to quickly deploy personnel to liaise with TDB closely. In selection of the PMU team to involve Villgro, TDB and DFID. Monthly Steering committee to clear backlogs and a constitution of an independent advisory board to mitigate delays in decision making.

Incubation and Investment Component:

RISKS	MITIGATION	Impact/Probability
Investment in the two DCI funds do not meet DFID INVENT objectives as DFID is one of many contributors in the fund	IL&FS: Agreed a process where DFID will have veto power in investments related to INVENT objectives before it goes to IC. / RVCF: Agreed with Fund manager to be part of 2 ICs planned	High/Moderate
Bureaucratic delays in kick starting the Incubation work even after signing the contract	A Steering committee constituted that will fast track decision making / Advisory Board being set up.	High/Minor
Lack of pipeline of investible projects for impact investments	Nurturing investible pipeline through StartpWave / Active networking with other impact investment funds to explore co-investing opportunities / Sourcing through organisations carrying out social business plan competitions	Medium/Moderate
Inability to identify viable incubates that deliver social outcomes	Initial pipeline already sourced from Unconvention/L and will follow multiple channels in sourcing the pipeline.
Stakeholders fail to appreciate the risk of failure inherent in innovation investments (including economic returns) and criticise the project for not delivering	Risk of failure will be clearly mentioned in the project documents. Project team to ensure this aspect communicated clearly along with possible benefits. In addition the team will ensure partners adopt systems and processes that will balance innovation risk vs returns.	Medium/Minor

Ideate and propagate Component

RISKS	MITIGATION	Impact/Probability
Cut in DFID resources threatens programme viability	This risk has become real, requiring some streamlining to the programme. Reduce number of calls in Grand Challenge programme while maintaining support as a knowledge partner. Challenge partners to find alternative funding (e.g. GoI support for Millennium Alliance). No further support to Sankalp, but maintain dialogue with Intellecap.	High/Severe
Turnover of staff: risk to capacity and institutional memory.	Detailed handover to new DFID programme lead. Negotiation of draw-down capacity from David Elliott for CTG. Capacity of Connect to Grow and Millennium Alliance teams boosted.	High/Minor
Slow or limited take-up of innovations in developing countries: One of the primary risk of INVENT’s global component remains that there may be limited or slow uptake of the Indian innovation INVENT supports in developing countries.	Focus on developing country needs – e.g. CTG narrative on boosting enterprise growth in LICs. Stipulation that Indian innovators should have a developing country partner, building buy-in and lasting capacity. Development of learning and evaluation activity will use external service provider to identify opportunities for improvement and course correction.	Medium/Moderate
HMG Support eroded: perceived competition with UK commercial interests.	Close discussion with UKTI, SIN and visiting UK trade delegations. Consistent feedback that INVENT not competing with UK commercial interests: UK business not focused on affordable innovation for poor communities.	Medium/Moderate

Outstanding actions from risk assessment
None

Due Diligence actions

Due diligence has been conducted on two agencies for Rajasthan Venture Capital Fund and IL&FS (Development Capital Investment) component before signing the agreement. All recommendations have been addressed. It has been agreed that ESG safeguards and the due diligence of the potential investee companies will be carried out regularly by the Fund Managers.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme overall is delivering as planned. Most of the output indicators are well on track except for few partnerships. The TA contract has been signed in October 2015. Progress has been slow as TDB is ensuring that all government of India procedures are adhered to to implement this programme. The approvals are fairly time consuming due to internal procedures.

Performance of partnership(s)

TDB: Over the years, the partnership between TDB/DFID/Villgro and other stakeholders has evolved/matured. DFID and TDB along with the Management agency are having regular formal and informal interactions on the programme progress, challenges and issues and take corrective measures to address those issues to set the programme rolling. Contract milestones were reviewed this year to align with programme priorities and ensure ease of measurement. The Steering Committee has been set up post October 2015 to address any bottlenecks and take key decisions for the programme implementation. The Steering Committee has been an integral part and TDB, DFID and Villgro are committed to this forum. The SC meetings are held every alternate month and will now be held on a quarterly basis.

RVCF and IL&FS: With two new funds launched in partnership with RVCF and IL&FS, DFID will closely work with its partners to further strengthen its partnership to deliver programme objective

All 3 components financed from the DFID India Global Programme are performing well. They are ensuring that all the DFID criteria including high impact and value for money are maintained when they further enter into partnerships. The Global team is in regular contacts with all 3 components through phones and meetings and are aware of the progress at any point of time. For example Under MA we have monthly meetings where progress is presented and views of donor partners are considered and taken on board.

Asset monitoring and control

No asset has been purchased till date by the implementing partner. However, arrangements have been set in the MoU/contracting agreements that any asset procured under the programme will be recorded in the Asset Register and get updated each time a new asset is purchased. Partner will share updated asset list inventory every six months. Arrangements will be made to carry out spot checks to manage programme assets and proper guidelines will be agreed for their handling and disposals.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

There were no conditionalities attached to this programme. DFID has ensured adherence to the four principles to support poverty reduction and the MDGs, human rights and international obligations, public financial management, good governance and transparency, and domestic accountability to all development partnerships where possible.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In year 3 of implementation, the theory of change remains unchanged and has no implication for the programme. Regular monitoring throughout the review period has continued to be maintained.

Incubation and Investment component: The evaluation agency could not be appointed due to delays in signing of the contract with PMU under the TDB and DCI component. Contribution Agreement has been recently signed with Rajasthan Ventures Capital Limited (RVCL) and IL&FS thus paving the way for the implementation of all the components of the programme. Team intends to appoint an evaluation agency within next 3-4 months and to ensure that the baseline report is available before the next Annual Review.

Ideate and Propagate Components: TORs have been developed for a learning evaluation of the Global Component of INVENT and signed of by SEQAS. We will be starting the tendering agreement as soon as the new framework arrangement is in place.

Monitoring progress throughout the review period

Programme is monitored regularly through various mechanisms in place: Steering committee meetings with TDB, Millennium Alliance and Connect to Grow, monthly review meetings with management consultants along with partners, Representation in Investment committees and Advisory councils in DCI partnerships, monthly reporting, mid-year and annual Review assessment. Various field visits were conducted by the programme team as part of monitoring progress on ground.

Under Global INVENT the programme is monitored very regularly through direct interaction with partners, phone calls, monthly meetings and conference calls. As most of the initiatives on ground are showing up early results, DFID India plans to visit at least one programme of each of the 3 components in the forthcoming months.

Annex 1

Annual Review – Summary Sheet

Title: Innovative Ventures and Technologies for Development (INVENT)
Programme Value: £38m		Review Date: September 2015
Project Code: 202927	Start Date: 4/08/2013	End Date: 31/07/2019

Summary of Programme Performance
Year	2013/14	2014/15	2015/16
Programme Score	B	A
Risk Rating	Medium	Medium

The INVENT programme was approved in August 2013 to invest up to £38m over 6 years to support technological and business innovations for the benefit of the poor in the low income states of India and in developing countries in Africa and South Asia. This is the second annual review of the programme. After a slower than expected start for some components of the programme for a variety of reasons, the programme now appears to be well positioned to achieve the desired outputs, outcomes and impact.

The main focus in the second year of the programme has been mainly on strengthening partnerships and implementation of those components which were already approved within DFID and/or by the Government of India. These efforts are already beginning to show fruit.

In undertaking the Annual review, we have taken the opportunity to update the log frame and delivery plans. The main changes in the log frame are to move some outputs back by one year reflecting the delayed start and to strengthen several of the indicators. The Delivery Plans have been aligned with the revised log frame and what is now known about the issues in implementing the various components. The revised log frame is attached for approval.

The main components of the programme are as follows

Ideate
£1.6m technical assistance to share and replicate proven innovations from India to developing countries.

Incubate
£6m Support to incubators which will nurture innovative inclusive business ideas leading to 50 ‘investment ready’ businesses.

Invest-Scale
- £18m returnable capital for replication and scale-up of commercially proven innovative businesses in India’s low income states (LISs)
- £3m Strengthening ecosystem for inclusive innovations and impact investments

Propagate
- £3.3m technical assistance to support knowledge-sharing on inclusive innovations between India and developing countries.
- A £2.1m DFID contribution to a pooled fund to test and pilot innovations between India and developing countries.

The main achievements under each component of the programme were as follows:

Ideate: £1.6m support to ideate through Grand Challenge Funds
The ideation component of the programme (Grand Challenge) has been established and the mandate definition meeting for the first call was held on August 26th.
Incubate: £6m Support to incubators:
- This component was delayed due to reasons including not filling or confusion over the post of Secretary at Technology Development Board (TDB) for over a year. With a new Secretary at TDB and agreement on the objectives and plans for the programme, the agreement between the Managing Agent, Villgro, and TDB is expected to be signed by 31st August 2015.
- In the interim period, to cover the gap between signing the contract between TDB and Villgro, DFID signed a contract with Villgro to kick-start the pre- work of sourcing the enterprises for the Incubation component. 12 enterprises were identified through this process.
- Virtual Incubation: www.startupwave.co/ the virtual incubation platform launched at the Sankalp Global Summit in April 2014 in partnership with GIZ and Intellecap entered the phase 2 of building the platform. The incubation phase is due to launch in September 2015. The long term plan is to develop and scale the platform, and also make it financially sustainable.

Invest-Scale: £18m Development Capital Investment (DC!):
- As per the decision following on from the first Annual Review, INVENT team carried out a scoping exercise to explore alternative options for Development Capital Investment (DCI) component. Three potential GoI owned/sponsored funds emerged from this scoping exercise: They are Rajasthan Venture Capital Fund (RVCF), IL&FS Sustainability Fund and MP Innovation Fund.
- The team agreed the above alternative options with Head of Office and has received ‘in principle‘ approval from DEA to carry out formal negotiations and appraisal of IL&FS and RVCF funds and await progress on the proposed MP innovation fund. Due Diligence and discussions are underway with all three funds

£3m strengthening the ecosystem for inclusive business and impact investments:
NESTA partnership on UK-India Innovation exchange:
- Capacity building: Development Impact & You Workshop: Two bespoke one-day workshops on Development Innovation and You (DIY) toolkit was organised for the key ecosystem players.
- Building an effective social venture ecosystem in India: Research work on framework for successful social incubation in India; Dissemination of the research is being planned.
- Samhita CSR TA pilot concluded and lessons shared: This pilot project was described in the ICAI review as an ‘effective model of using TA to support CSR. The team concluded the pilot review in May 2015 and shared the learnings including input into DFID India’s future Business Engagement Strategy.
- S.H.E Initiative: Over the past year, the pilot phase of the S.H.E initiative (a multi-stakeholder platform that promotes collaborative action to address safety, health and education and employment of women and girls) has gained momentum with 11 corporates (2 UK, 8 Indian and 1 MNC) now on board as signatories. The target is to reach 25 corporates by the end of the current pilot ending January 2016.

Propagate: £3.3m technical assistance to support knowledge-sharing
The demand-led instrument for sourcing innovations – the Innovation Knowledge Exchange Facility (IKEF) – has been established after successfully completing the OJEU process. The design phase for the same is ongoing and scoping visits have been conducted in 4 developing countries.

£2.1m contribution to the Millennium Alliance (pooled fund)
- 6 Indian innovators have been extended support to be introduced in developing countries and have started implementation of these pilots.
- INVENT also supported Sankalp Africa 2015 held in Nairobi in February 2015 focusing on the ‘investing for women’ theme. Sankalp Forum expanded into Africa with DFID and Shell Foundation’s initial support in 2013. The idea was to accelerate enterprise growth and building a South-South corridor between India and Africa.
Key Lessons

As an innovative and experimental programme, lesson learning and adaptive flexibility in overall management are important aspects of the programme

Ideate
- It has taken longer than expected to establish the partnership for the ideation component of the programme. This was primarily because the initial partnership was being scoped with the Government of India (BIRAC) and was almost finalised when we hit an operational barrier. Since the ideation piece concentrates on taking innovations to Africa and South Asia, GoI could not do so in compliance with the Foreign Contribution Regulation Act (FCRA). Hence we had to start the process of scoping partnerships again.
- Within the programme, there was a discussion around the additionality of the Grand Challenge. The team discussed this with HQ, external stakeholders and internally and came to the conclusion that it would be good to use 3 different approaches for taking innovations to Africa and South Asia – a challenge fund with broad sectoral focus (Millennium Alliance), a Grand Challenge approach of sourcing innovations for a very specific global concern (like TB diagnostics) and a demand-led innovations sourcing instrument (IKEF). The planned evaluability assessment will help us identify the evidence for the benefits of each approach.

Incubate
- Responses to services provided by StartupWave validated some of key hypotheses of this component of the programme, notably the blending of in-person touch-points with online support.
- Many of the entrepreneurs who surfaced at Unconvention/L will require hand-holding in a light touch, pre-incubation form of support to reach a level of maturity at which they can be incubated.

Invest-Scale
- While there is a clear gap in the market in terms of very early stage impact investments (pioneer and small ticket), the government fund managers that we initially identified have little understanding and appetite for this type of investment. This provides reassurance that our role as ‘Market maker’ and our activities are ‘Additional’ rather than competing with existing investors
- There are new funds with which we could work and we are currently evaluating three of them with a view to potentially invest. Investing in all three would be administratively stretching for the team and we are exploring ways to manage this effectively.
Business engagement
The TA is directed towards creating common CSR platforms for companies to participate rather than assisting individual companies. This requires more time for decision making but leads to more effective outcomes.
Ecosystem
Discussions with stakeholders during the preparation of the research report being prepared by NESTA revealed a strong interest in learning how incubators can operate effectively in second and third tier cities, and more generally in building incubators’ capacity in India. We anticipate a wide audience for the report when it is finalised and released.

Propagate:
- The 6 innovators awarded under Millennium Alliance were delayed in starting implementing the pilots due to working out compliance with FCRA. DFID along with the Federation of Indian Chambers of Commerce and Industry (FICCI) wanted to ensure that the awards are made in compliance with FCRA which took time in consulting both legal and FCRA experts.
- The call for proposals under Millennium Alliance (MA) has to be further tweaked for the next round (to be announced by December 2015) to be able to get better informed bids. DFID suggested MA to set up an advisory board with experts in the sector and the impact investment space to ensure that they can feed into the application format, tweak the appraisal process and criteria for efficiency, etc., which is now in place.