Annual Review - Summary Sheet

Title: Punjab Education Support Programme (PESP) II
Programme Value: £420.5 million		Review Date: January 2016
Programme Code: 202697	Start Date: 22/02/2013	End Date: 31/03/2019

Summary of Programme Performance
Year	2013/14	2014/15	2015/16
Programme Score	A	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
PESP II[1] is DFID’s largest bilateral programme globally and a major contributor to results. The programme is unique because of its whole system reform approach; strengthening government systems, building institutions, and focusing on access, quality and management of the education system. Combined with a budget to back up this ambition, PESP II has the potential for a transformative impact on the education sector in Punjab. In 2015, the Independent Commission for Aid Impact underlined the need for long-term, predictable support to bring about the transformational change needed to build institutions and systems to deliver results[2].
[1] A list of acronyms can be found on page 5 of the document
[2] http://icai.independent.gov.uk/wp-content/uploads/ICAI-report-DFIDs-approach-to-Delivering-Impact.pdf

PESP II works with the School Education Department and related institutions (Punjab Monitoring and Implementation Unit, Punjab Education Foundation, Department of Staff Development, Punjab Examination Commission, Punjab Curriculum and Text Book Board and the Special Education Department) to provide system-wide support and bring improvements across the education sector.

The key components of PESP II are: Sector Budget Support which provides funds to the Government of Punjab (GoPb) to improve access to education and improve quality in government schools; a school infrastructure component to upgrade facilities and provide additional classrooms in existing government schools; building the capacity and quality of Punjab’s low-cost private sector through the Punjab Education Foundation (PEF); piloting an access to finance component, focusing on expanding the low-cost private schools (LCPS) in under-served areas (on hold since the last Annual Review); targeted support through Civil Society Organisations (CSOs) to tackle social exclusion and inequality; a scholarship programme for higher education and girls’ higher secondary education to target the poorest, creating role models, and demonstrating the value of education to communities; a system-wide impact evaluation and research component; and a technical assistance component to underpin delivery of the other seven components.

PESP II is closely aligned to and complemented by the Punjab Roadmap for Education. The Roadmap analyses real-time, robust data across the province against a range of education indicators, tracks progress, and supports policy reforms and decision-making to improve delivery. The Roadmap approach has strengthened monitoring systems and the transparency of reporting, and ensures that senior officials are held to account for progress. PESP II provides technical assistance to support both the Roadmap process and the institutional strengthening work under the PESP II Results and Activities Framework (RAF). The Chief Minister (CM), Shahbaz Sharif, and the UK Special Representative for Education in Pakistan, Sir Michael Barber conduct bi-monthly stocktakes to assess progress. The RAF has five result areas and targets are also monitored through the bi-monthly stocktake process. This has driven the ambition and pace of change and deepened political commitment to reform. The sustainability of the approach or the ability for it to drive longer-term reforms in quality remains to be seen.

In January 2016, the CM, through the Roadmap process, set out an even higher level of ambition through a set of 2018 goals to improve learning outcomes for the complex Punjab public and low-cost private education system; while continuing to push for getting the remaining out-of-school children into school.

The new 2018 goals for a refreshed Roadmap from January 2015 are:
1. High-quality teaching and learning in the classroom which supports: teachers training and support; and classroom-level monitoring to ensure quality lesson delivery and regular assessment of pupils.
2. Strong leadership and accountability to assist the GoPb develop a better system of selection, training and accountability of district and sub-district level managers and teachers.
3. A conducive learning environment which provides remedial support to primary and lower secondary classes to improve learning levels and ensure no child falls behind.
4. Enhancing the learning environment through improved school infrastructure and reducing the incidence of multi-grade teaching.

The last Annual Review of PESP II took place in November 2014 and was approved in February 2015. In April 2015, the Secretary of State agreed a major cost extension of £70 million to the sector budget support component of PESP II. Good progress has been observed in four of the five outputs of the programme, while the other output (a better learning environment) has performed below expectations.

Key achievements over the past year are:
- Expansion of an improved performance management system across all 36 districts.
- Expansion of student learning assessments to a further 11,000 students (through the Punjab Education Foundation (PEF) and other primary schools).
- An additional 62,000 out-of-school children enrolled in new schools in four pilot districts through the priority districts’[3] component.
  [3] The selection of priority districts was done on the basis of key education indicators (participation rates, enrolment rates) at the time of the PESP II Business Case design. Eleven low-performing districts were identified in Punjab - mostly Southern Punjab where indicators were very low. The term priority districts is now used instead of low-performing districts.
- An improvement in overall school environment, with an average of 95.5% functioning basic facilities: boundary walls, drinking water, toilets and electricity (previously 93.7%).
- A further 8,500 higher secondary and 61 tertiary scholarships awarded to students under the Punjab Education Endowment Fund (PEEF) from the poorest districts of Punjab, other provinces and areas[4].
  [4] Azad Jammu and Kashmir (AJK), Federally Administered Tribal Areas (FATA), Gilgit-Baltistan and Islamabad Capital Territory (ICT).
- New products to address the quality side of education have been developed including: revised textbooks; quality teacher guides; a strengthened examination system; an early grade assessment system; and, increased school-level monitoring and mentoring.

The Technical Assistance and Management Organisation (TAMO – DFID-funded technical assistance team) is working well across the education sector in Punjab and has built significant buy-in at the most senior levels. A more participatory approach with some departments would assist in the long-term success of institutional strengthening.

The integrated support for quality led by TAMO has laid down the foundations for a good system. It focuses on improving learning outcomes, the development of quality teaching and learning materials and a range of assessment initiatives. Early results from learning assessments suggest the quality of education is beginning to improve. There is a need, however, for sustained effort as it will take some time before the actual impact is realised at a system-wide level. Linkages between the key institutions for quality like the Directorate of Staff Development (DSD), the Punjab Examination Commission (PEC) and the Punjab Curriculum and Textbook Board (PCTB) need to be strengthened.

The programme has made particularly good progress on the district governance workstream and monthly pre-District Review Committee (DRC) meetings are improving decision-making. The Punjab Inclusive Education Programme (PIEP) and PEEF scholarships programme targeting children with disabilities and girls are also showing promising results.

The school infrastructure component has been slow to perform. This was due in part to a delay in legal registration of IMC Worldwide (the international private sector implementing partner) in Pakistan. Unit costs have also risen dramatically since the last Annual Review and work is behind the original schedule. The quality of construction in the classrooms that have been completed is encouraging.

Lessons learnt
1. In order to create a greater sense of ownership by the GoPb of the PESP II programme and especially the Results and Activities Framework (RAF), DFID and TAMO should ensure that the government’s needs and DFID’s support are regularly discussed and that the needs are properly reflected in the development of support. The planned introduction of a six-monthly PESP II Steering Committee would ensure that the government has an oversight of the whole DFID support in education beyond the technical assistance supporting the stocktakes and achievement of the Roadmap goals.
2. A continued focus on ensuring quality of and consensus around data is essential, as is rigorous monitoring of all interventions.
3. Effective technical assistance for institutional strengthening needs the support of the relevant institution head as well as strong relationships with other levels of management. This helps to ensure capacity goes deeper than senior management and protects capacity building efforts from staff turnover.
4. TAMO should ensure that beneficiary organisations are content with the balance between generalists and technical experts in TAMO including education, equity, governance and public financial management.

Summary of recommendations for the next year
Programme outputs
DFID must ensure that the Roadmap stocktakes continue to drive improvements and that its conduct ensures continued buy-in from key stakeholders who attend. The focus on the stocktake should not, however, distract from other priorities under PESP II, which are not assessed at the stocktake such as the institutional strengthening of the Education Department, improvements to public financial management, and delivering on the inclusive education components of PESP II. The plan for transition of the Roadmap to the GoPb’s Special Monitoring Unit (SMU) should be implemented to ensure sustainability of the reforms. This does not however mean wholesale transfer of PESP II to sit within the oversight of the SMU.

The quality agenda is a core part of PESP II and should continue to be a focus. TAMO should review its technical expertise to DSD to strengthen the current teaching and learning model/approach and rebalance emphasis from monitoring to actual coaching and/mentoring. DSD and PEC need strengthening and linkages should be developed between them and other related organisations such as PCTB to maximise results.

TAMO should continue to develop linkages between the different assessments conducted at various intervals and strengthen the feedback system back to DSD so that assessment results are incorporated into the teacher training and Continuous Professional Development (CPD).

DFID should maintain close scrutiny of the school infrastructure component to reduce the risks of any further cost escalation and time delays and ensure that high construction standards are met.

DFID should review the Lahore University of Management Sciences (LUMS) National Outreach Programme (NOP) scholarships programme to improve its focus on gender and the most disadvantaged.

DFID should step up its engagement with PEF and, working with TAMO, ensure the pace and depth of technical assistance is improved. Assistance should support PEF to finalise an institutional strengthening plan and a long-term strategy reflecting the additional risks and demands anticipated from expansion. This should include clear plans to strengthen PEF’s identification, payment and monitoring processes.

DFID should continue discussions with PEF and other GoPb stakeholders on teacher pay in PEF schools and advocate for progressing improvements to PEF’s policy and practices that support the payment of fair wages.

TAMO and DFID to ensure dedicated technical assistance resources to support the roll-out of District Education Authorities (DEAs) following the elections of local bodies besides ensuring clarity on roles and responsibilities among SMU, Roadmap teams, TAMO and School Education Department (SED), through clear transition planning.

The work being carried out on the priority district component by Civil Society Organisations (CSOs) should be closely monitored to ensure that lessons learned from the pilots are fully captured and that, together with the findings from the Third Party Validation (TPV), they are used to inform any future expansion of their activities.

Programme management
Due to the complexity and size of the programme, all components should have a clear DFID lead and support staff, and ensure that they are empowered with the appropriate levels of responsibility and authority.

As part of TAMO Year 3 contract amendment discussions, DFID should conduct a review of TAMO’s workplan and bring it in line with the logframe and RAF. The review should happen in consultation with the relevant government departments to address their reservations about supply-driven assistance.

List of Acronyms

AEO	Assistant Education Officer
BRAC	Bangladesh Rural Advancement Committee
CCSI	Community Committees for School Infrastructure
CM	Chief Minister (Punjab)
CPD	Continuous Professional Development
CSO	Civil Society Organization
CTSC	Cluster Training and Support Center
DCO	District Coordination Officer
DDEO	Deputy District Education Officer
DEO	District Education Officer
DFC	Divisional Field Coordinator
DFID	Department for International Development (UK)
DLI	Disbursement Linked Indicator
DRC	District Review Committee
DSD	Directorate of Staff Development
DTE	District Teacher Educator
EA	Education Ambassador (LUMS)
EDO	Executive District Officer
EVS	Education Voucher Scheme
FAS	Foundation Assisted Schools
GDP	Gross Domestic Product
GET	Ghazali Education Trust
GoPb	Government of Punjab
GRCC	Government Reform Coordination Cell
HDI	Human Development Index (UN)
HR	Human Resource
IMC Worldwide	International Management Consultants Worldwide
KSM	Key Supplier Management
LCPS	Low Cost Private Schools
LND	Literacy and Numeracy Drive
LUMS	Lahore University of Management Sciences
MEA	Monitoring and Evaluation Assistant
MIS	Management Information System
MTBF	Medium Term Budgetary Framework
MVF	Mentoring Visit Form
NOP	National Outreach Programme
NSB	Non-Salary Budget
NSP	New School Programme
OPM	Oxford Policy Management
PFM	Public Financial Management
PIEP	Punjab Inclusive Education Programme
PITB	Punjab Information Technology Board
PESP	Punjab Education Sector Programme
PCTB	Punjab Curriculum and Textbook Board
PC-1	Planning Commission - 1
PD	Professional Development
PEC	Punjab Examination Commission
PEEF	Punjab Education Endowment Fund
PEF	Punjab Education Foundation
PFM	Public Financial Management
PIEP	Punjab Inclusive Education Programme
PMIU	Programme Monitoring and Implementation Unit
PMS	Performance Management System
PPBP	Parho Punjab, Barho Punjab (Learn Punjab, Prosper Punjab)
PR	Participation Rate
PRAP	Portfolio Risk Assurance Programme
Pre-DRC	Pre-District Review Committee
PSLM	Pakistan Social and Living Standard Measurement
RAF	Results and Activities Framework
QAT	Quality Assurance Test
RISE	Research on Improving Systems of Education
PWC	Price Waterhouse Coopers (Auditors)
SBAP	School Based Action Plan
SBS	Sector Budget Support
SCWG	School Council Working Group
SED	School Education Department
SLO	Student Learning Outcomes
SMU	Special Monitoring Unit
SNG	Sub-National Governance
SOP	Standard Operating Procedure
SPO	Strengthening Participatory Organization
TACE	Technical Assistance for Construction and Engineering
TAMO	Technical Assistance and Management Organization
TCF	The Citizens Foundation
TOR	Terms of Reference
TPI	Transparency for People Initiative
TPV	Third Party Validation
UNICEF	United Nations Children’s Fund
WB	World Bank

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/

Outline of the programme
PESP II supports the GoPb to reform and transform the delivery of education in Punjab. The overall goal is to improve enrolment, retention and performance of students in Punjab so that more children are in school, staying longer, and learning more. Through a range of innovative interventions with the government, private sector and CSOs, the programme will deliver equitable access to better quality education across the whole province.

The overall budget is £420.5 million including £170.2 million for sector budget support over six years between June 2013 and March 2019. The programme includes the following components:

A sector budget support component providing funds to the GoPb to improve access to education and quality in government schools (£170.2 million).

A school infrastructure component focusing on building additional classrooms in existing government schools and providing a limited number of missing facilities such as boundary walls, washrooms, electrics, and water and sanitation facilities. This is managed through the Humqadam project, implemented by IMC Worldwide (£104 million).

Support to PEF to build the capacity and quality of Punjab’s growing low-cost private sector and increase access through an Education Voucher Scheme, New Schools Programme and Foundation Assisted Schools programme (£68.6 million).

An access to finance initiative focusing on improving the availability of access to finance for low-cost private schools (LCPS) to help them fund infrastructure needs and provide quality education services (on hold since the last Annual Review) (£9 million).

Targeted support through CSOs to tackle social exclusion and inequality by identifying and enrolling out-of-school children in eleven priority districts (£10.8 million).

A scholarships programme for higher secondary girls from southern Punjab, other provinces and areas, and university level scholarships for girls and boys through PEEF (£10.9 million).

A scholarship programme for tertiary level students (girls and boys) through the LUMS NOP scheme to enable the poorest to enter higher education and create role models to build aspirations among people from disadvantaged areas (£18.2 million).

A technical assistance component – TAMO – comprising Adam Smith International (ASI) and McKinsey has been contracted by DFID to provide support to the GoPb and other partners in the PESP II programme. Technical Assistance to the Roadmap through McKinsey and TPV for the infrastructure component are also provided through this component (£39.7 million).

A system-wide impact evaluation and research component. This component has not moved forward to implementation phase (£2.5 million) and the evaluation element will be re-designed.

Education context in Punjab
Punjab is Pakistan’s biggest province and home to over 100 million people (around 56% of the country’s population) and currently contributing 58% of Pakistan’s Gross Domestic Product (GDP). As a result of its size, Punjab has the highest number of out-of-school children aged 6-16 years (estimated in 2014 by Alif Ailaan to be 13 million, of which 6.8 million are girls), and the highest number of children with low learning levels in Pakistan. Pakistan cannot hope to end its education emergency without a substantial and sustained increase in both the access to and quality of education that children receive in Punjab.

Expected results
The UK’s support to the GoPb will have a significant impact on driving reform and improving the quality of teaching and learning outcomes. Structural reforms will impact positively on future cohorts of children in schools across Punjab. PESP II accounts for over 90% of DFID’s forecast results for primary school children benefiting from DFID support. All government school children (6 million primary, 4 million secondary) and PEF school children (around 2.2 million) will have benefited from UK support in Punjab by March 2019. Children attending government schools will benefit from improvements in the way the sector is resourced and managed in terms of budgets and quality human resources at the provincial and district level, as well as improved teaching quality and materials leading to better learning outcomes.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The outcome of PESP II is “more children in school, staying longer, and learning more”.

Indicator No.	Indicator(s)	Milestones 2015/16	Progress (Dec 2015)
Outcome Indicator 1	Participation rate for primary school aged population (ages 5-9) / Participation rate for primary school aged population (ages 5-9) in 11 priority districts	Punjab average: / Girls: 88.5%, Boys: 91%	Punjab average: / Girls: 88.9%, Boys: 91.8% / Priority districts: / Girls: 81.1%, Boys: 86.8% / [Nielsen Survey: June 2015 - December data delayed]
Outcome Indicator 2	Participation rate for secondary school aged population (ages 10-16) / Participation rate for secondary school aged population (ages 10-16) in 11 priority districts	Punjab average: / Girls: 80%, Boys: 84%	Punjab average: / Girls: 80.5%, Boys: 83.9% / Priority districts: / Girls: 67.9%, Boys: 76.9% / [Nielsen Survey: June 2015 – December data delayed]
Outcome Indicator 3	Student learning outcomes: / Average scores by subject for March and September six-monthly assessments (grade 3 students)	Percentage of grade 3 students that achieve specific Student Learning Outcomes (SLOs) for each subject English, Maths, and Urdu / Maths: 65% / English: 59% / Urdu: 56%	Govt PEF TCF CARE / Maths 68% 80% 78% 77% / English 57% 69% 56% 66% / Urdu 57% 77% 74% 68% / Overall 61% 75% 69% 70% / [September 2015 assessment]
Outcome Indicator 4	Student attendance	90% attendance rate maintained every month / (90% boys’ schools; 90 % girls’ schools)	90.4% / No gender breakdown available / (Jan - Dec 2015 rolling average)

Student participation rates measured in June 2015 show the 2015/16 targets for primary and secondary schools to be largely met, although the December survey data is not yet available to confirm whether this trend has continued. The six-monthly student learning assessment shows a higher proportion of grade 3 children have achieved standard learning outcomes in Maths and Urdu than expected, while fewer have achieved English standard learning outcomes.

Since September 2014, overall government school assessment scores have improved slightly (from 58% to 61%). This was due to improvements in Urdu (50% to 57%) and Maths (65% to 68%), while English scores dropped slightly (59% to 57%).

Assessments were introduced in PEF schools in February 2015 and repeated in September 2015. The latest PEF assessments showed lower learning outcomes than previously (Maths: 92% to 80%; English: 74% to 69%; Urdu: 87% to 77%). However this is to be expected, given new grade 3 students are tested in September, while in February the grade 3 students tested will have had six more months of education.

Overall output score and description
Overall the programme outputs scored an A: outputs met expectation.

Output	Score	Impact Weight	Summary
1. Better managed, more accountable education system	A	15%	All 3 targets met.
2. Better teacher performance and better teaching	A	30%	4 of 5 targets met. / 1 target moderately not met.
3. Better learning environment	B	15%	2 of 3 targets moderately not met. / 1 target substantially not met.
4. Improved access to schools, especially in priority districts	A	30%	2 of 3 targets met. / 1 target moderately not met.
5. Enhanced demand for education	A	10%	All 3 targets met.

Has the logframe been updated since the last review?
Yes. The previous Annual Review recommended revising the PESP II logframe. After a series of consultations, it was approved by the acting DFID Head of Office in August 2015.

In November 2015, the PESP II team reduced the infrastructure-related milestones for 2015-16, reflecting challenges encountered in that component over the past year.

Summary of responses to issues raised in previous Annual Reviews (where relevant)

Recommendation 2014/15 Annual Review	Response
Short-term: The logframe should be reviewed as soon as possible and consensus reached on the indicators and milestones to ensure that all stakeholders are working towards agreed goals. Progress against the logframe should be built into routine meetings throughout the year. The logframe review should also consider: / a) increasing the overall impact weighting of output 1 to acknowledge its importance in delivery of long-term reform; / b) revising output 1.3 to measure the effectiveness of school councils; / c) ensuring indicators under output 2 are closely aligned with the GoPb vision for education in 2018; and, / d) increasing the risk rating of outputs 3 and 4.	The logframe was reviewed and refined jointly by DFID and TAMO. A series of stakeholder alignment meetings were held with the PESP II delivery partners: SED, Programme Monitoring and Implementation Unit (PMIU), DSD, PEC, Punjab Information and Technology Board (PITB), PEEF, PEF and LUMS) for alignment on goals and targets.

## C: DETAILED OUTPUT SCORING

## C: DETAILED OUTPUT SCORING

Output Title	Better managed, more accountable education system
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015/16	Progress (Dec 2015)
1.1 Number of districts with effective and targeted system-wide performance management system	Performance Management System (PMS) expanded to cover all 36 districts entailing regular monthly Pre-District Review Committee (DRC) and re-aligned/ re-structured DRC meetings covering new metrics and Literacy and Numeracy Drive (LND) scorecard. / Pilot of re-engineered business processes in two districts commences June/July 2015 and implemented by May 2016.	Met expectation / PMS initiative expanded to all 36 districts including holding of regular Pre-DRC meetings. / Re-engineered business processes being piloted in two districts.
1.2 Frequency of MEA visits and better reliability of data collected	90% school visit rate maintained every month. / Tablet-based real-time data collection system rolled out in all 36 districts. / Data verified (for sufficient robustness and quality). / As a test for quality of collected MEA data, the maximum variation between audit data from District Field Coordinators (DFC) spot-checks or TPVs and collected MEA data for the same schools should be within +/-10%.	Met expectation / 96.1% (12 month rolling average to December 2015). / Tablet-based real-time data collection rolled out in all 36 districts. / 2015 audit shows that margin of error is within +/-10% for 3 of the 4 indicators: / Student attendance: 10.7% / Teacher presence: 3.6% / Functioning facilities: 2.4% / Administrator visits: 3.1%.
1.3 Functional primary school councils as measured by: / Regular meetings held / Actual utilisation of funds	Incremental increase of 5% over baseline[5] for both components of the indicator (regular meetings held and actual utilisation of funds)	Met expectation / School council meetings: / 18 non-NSB districts[6]: 66% schools meeting on monthly basis; / 18 NSB districts: data not available. / Fund utilisation: / 18 non-NSB districts: 52% utilisation; / 18 NSB districts: 82% utilisation / Overall weighted indicator: 70% functional schools (compared with baseline of 33% in 2012/13).
[5] Weighted indicator constructed to capture percentage of school councils holding regular meetings and percentage of funds utilised by school councils.
[6] NSB districts refer to those districts in 2014/15 that received the new ‘Non-Salary Budget’ (NSB) grant for school councils. As of financial year 2015/16, all districts are receiving the NSB grant.

Key Points
This output supports the GoPb to better manage the education system and increase government accountability with the aim of improving the quality of education. The achievement of this output is chiefly supported through sector budget support. The Roadmap helps to maintain high-level political commitment and momentum needed for reform.

Output Indicator 1.1
This output milestone has been met. It has two components: efficient follow-up routines (pre-DRCs) and re-engineered business processes in the education district offices.

The PMS was introduced in 2014/15 to cover 33 districts and has now been expanded to all 36 districts and is led by SED. It includes the establishment and conduct of monthly pre-DRC meetings. These meetings are chaired by the Executive District Officer (EDO) and are used to review progress against district targets, take decisions and prepare for the monthly DRC meetings with the District Coordination Officer (DCO).

The initiative has been expanded to all 36 districts in Punjab. A set of routines for the effective management of districts is in place and TAMO, through its network of Divisional Field Coordinators (DFCs), is supporting the districts to implement and refine the processes. Meetings are held regularly and minutes are issued. The indicators under review have also been expanded to include scores from the Literacy and Numeracy Drive (LND) tests. The system appears to be working well so far and provides a systematic approach to reviewing performance at all levels of the school system: at the provincial level by the Secretary SED and his recently established reform unit; at the district level by the DCO and EDOs during their monthly DRC meetings; at the markaz level (the lowest level of education management comprising a cluster of around 40 schools at the sub-district level) by the EDO during the pre-DRC meetings; and, at the school level by the Assistant Education Officers (AEOs). The real impact of the initiative will however require further monitoring of actions taken as a result of these meetings and an assessment of their effect on school performance.

AEOs measure and document the performance of each school they visit based on a checklist of standard indicators (student attendance, teacher presence, enrolment, retention, teaching quality, learning outcomes, overcrowding and multigrade teaching). This checklist enables AEOs to track and drive progress on each of the core areas of reform. The EDO is able to review the AEO’s performance in driving improvements in school results by cross-checking the checklist against independent district data reports provided by the PMIU. The Secretary holds EDOs accountable through the data analysis conducted by his reform unit. The Secretary follows up with the EDOs at monthly workshops, during which EDOs are also provided with coaching to improve their performance.

The pilot of re-engineered business processes is underway in two districts: Hafizabad and Rahimyar Khan. The pilot involves the automation of human resources information including information on transfers, postings, promotions and disciplinary proceedings. The Transparency for People Initiative (TPI) is designing the software. The aim behind the pilot is to provide a management tool to the EDO to facilitate teacher management. While this looks like a good technical initiative, it is not clear how far it will go to addressing some of the challenges in managing teacher transfers and postings which are often subject to political interference. It would be helpful from a broader perspective to understand the political economy of these issues as well.

Lastly, with the conduct of the elections of local bodies in Punjab in 2015, the establishment of District Education Authorities (DEAs) is expected soon. The establishment of DEAs is both an opportunity and a challenge and there is a need to actively engage the government on the transition planning as DEAs roll-out would significantly impact the delivery of education in the whole sector. It is also understood that DFID’s Sub-National Governance (SNG) programme and TAMO have worked together to put up draft DEA rules and this collaborative working needs to be continued in future. Both DFID and TAMO should now carefully look at the roll-out of DEAs and support SED in the process, in collaboration with the technical assistance team supporting the Roadmap stocktakes and the Chief Minister’s Special Monitoring Unit.

Output Indicator 1.2
This output milestone has been met. This indicator assesses the frequency of school visits by Monitoring and Evaluation Assistants (MEAs) and reliability of the data collected. Recent data shows that on average 96% of schools are covered by monthly MEA visits exceeding the 90% target. Furthermore, MEAs now use a tablet-based data system to collect monthly data from schools. This system was rolled out in all 36 districts in July 2015.

In 2013, the monthly data was subject to TPV and since then the TAMO team, through its DFCs, has carried out annual spot-checks of four indicators (student attendance, teacher attendance, functioning facilities and administrator visits). The logframe milestone set a +/-10% threshold for the margin of error (between the original MEA data and the DFC spot-check) as a proxy for quality.

In 2015, this margin of error threshold was exceeded by student attendance (16.7% in November) and functioning facilities (13.4% in October). Combining the three months’ data, only student attendance was higher (10.7%), driven by higher margins of error in five of the nine sampled districts: DG Khan (20.6%), Toba Tek Singh (19.4%), Multan (13.7%), Bahawalpur (12.2%) and Gujrat (10.0%). Interestingly, of the nine districts sampled, the MEA data on student attendance was higher than the DFC spot-check in all but one district. There was a similar pattern for the other three indicators. TAMO explained that the MEA data may be higher due to the possibility of word spreading about imminent visits in the area, although, as discussed below, this issue is in the process of being addressed. No data was available to assess how the margin of error may have varied since the 2013 exercise.

The TAMO DFC spot-checks are carried out in addition to their normal duties which can limit or vary the number of districts they are able to cover. Other quality checks are starting to take place. The PMIU highlighted that they began monthly spot-checks in ten districts in December 2015, although no data has been made available yet. PMIU is also working to refine the tablet monitoring application to increase the randomisation of MEA visits. This should reduce the risk of collusion between MEAs and teachers caused by advance warning of visits. MEAs already rotate across school clusters to avoid repeat visits to the same schools.

Output Indicator 1.3
This output milestone has been met. This indicator assesses the effectiveness of school councils by measuring the frequency and regularity of meetings and the utilisation of funds. To meet the criteria, school councils are required to hold meetings at least twice a quarter. The PMIU provided data for the financial year 2014/15 on school council meetings in 18 non-NSB districts. The PMIU did not collect school council meeting data for the 18 NSB districts. During the transition of data collection by MEAs from paper-based records to tablet-based data collection, the recording of the frequency of school council meetings was inadvertently dropped from the application. This has now been addressed. The indicator was reintroduced to the tablet-based application, and data collection started again in January 2015. During the review team visits, school councils appeared to be meeting regularly in the few schools visited by the team.

Utilisation of funds refers to the actual spending of funds received by school councils and data on this indicator is available as of the end of the last GoPb financial year (2014/15). The Non-Salary Budget (NSB) initiative started as a pilot in 2013-14 in nine districts, commonly referred to as ‘NSB districts’. In 2014/15, the pilot was expanded to include 18 NSB districts and from the start of the 2015/16 financial year all 36 districts of Punjab have been included. Under the initiative, school councils receive a dedicated amount, broadly based on school needs, to cover non-salary expenses. PMIU’s data reveals a budget utilisation of over 80% in the 18 NSB districts and over 50% in the 18 non-NSB districts for the year 2014/15. The reasonable level of budget releases and utilisation can be attributed in part to follow-up through pre-DRC meetings, during which AEOs are held responsible for timely and efficient budget utilisation by the school councils in their areas. TAMO, however, currently supports PMIU to collate this data and present it for analysis at provincial level.

During the review team visit to schools in Sheikhupura and Kasur districts, it was encouraging to hear that the provision of NSB was helping to re-engage school councils to take decisions on school improvement plans. Schools are reportedly using the grant to meet a range of expenses including repairs, utilities and classroom consumables.

Overall, budget utilisation in the 18 NSB districts looks promising. Similarly the frequency of meetings as well as budget utilisation in non-NSB districts, has improved over the past year. From 2016 onwards, more comparable data should be available across districts following the inclusion of all 36 districts in the NSB grant scheme.

Summary of responses to issues raised in previous Annual Reviews (where relevant)

Recommendation 2014/15 Annual Review	Response
Short-term: TAMO should set out a clear plan for refining the current key performance indicators (KPIs) being trialled in a small set of districts to achieve a fully functioning system of accountability; and build capability to run this in a decentralised manner. This needs to be integrated with existing mechanisms such as district and school report cards.	KPIs and performance tracking metrics have been developed for each of the GoPb’s 2018 goals for education and district data packs prepared to provide district officials with monthly updates on their performance. / 19 TAMO DFCs are facilitating EDOs and DCOs to review progress each month and develop detailed action plans to drive continuous improvement.
Short-medium term: As part of its forward work plan on school councils, TAMO should consider providing assistance on the guidance and support to school councils on school development plans and effective budgeting and spending.	TAMO has drafted a strategy for PESP II support to school councils focusing on enabling school councils to conduct monthly meetings with participation of all core members, preparation of meaningful school-based action plans and using NSB more effectively and transparently to meet school needs. / TAMO is planning a number of activities to implement the strategy. These will need to avoid duplication of similar and previously tested activities. TAMO will need to work closely with PMIU for early implementation of the strategy.

Recommendations
1. TAMO should assess the benefits of the pre-DRC meetings preferably through a third party. The impact of the re-engineered business processes needs to be properly analysed, along with the political economy of teacher transfers and postings before the system is rolled out to other districts.
2. The quality of PMIU data should continue to be monitored closely and spot-check findings used to continuously improve data quality.
3. TAMO and DFID to ensure dedicated technical assistance resources to support the roll-out of DEAs following the elections of local bodies besides ensuring clarity on roles and responsibilities among SMU, Roadmap teams, TAMO and SED, through clear transition planning.

Output Title	Better teacher performance and better teaching
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 New teaching and learning materials developed in line with new curriculum.	TAMO supports PCTB in the development of grade 2 and 3 Urdu, English, Maths, textbooks (for 2016-17) / Printing of textbooks by PCTB (November 2015) and distribution of textbooks by PMIU (March 2016)	Moderately did not meet expectation / New Urdu, English and Maths textbooks for grades 2 and 3 have been developed with the help of TAMO support, British Council and other experts and sent for printing by PCTB[7]. / Target was not met due to the wrong version of Urdu grade 1 textbook sent for printing.
2.2 Six-monthly learning assessment system in place.	Independent student assessment successfully conducted to acceptable standard twice during year (grade 3) / Assessment expanded to cover PEF schools, Daanish Schools[8] and other private schools in September 2015	Met expectation / Assessments carried out in February (10,944 students) and September (16,742 students) to an acceptable standard. / Assessment expanded to cover PEF schools in February; then TCF and CARE schools in September.
2.3 Improved integrity of PEC exams with reduced cheating and leakage, and improved test design and content quality.	Strengthened PEC exam development process - PEC exams administered under new, robust invigilation system and with improved quality of marking	Met expectation / PEC has a strengthened exam development process. It has developed a list of prioritised student learning outcomes, piloted a marking scheme and has a revised process for conduct of exams.
2.4 Quality and delivery of teacher training and mentoring.	DTE attendance at 90% / Year 1 quality drive launched	Met expectation / 92.5% of all schools were visited. / Quality drive initiated by Secretary SED and a number of other initiatives introduced by TAMO.
2.5 Teacher attendance rates in government schools	90% (12 month rolling average)	Met expectation / 92.7% average teacher attendance.
[7] There has been a delay in the printing of the textbooks due to a court case which has now been resolved. There has also been an issue with printing of grade 1 Urdu textbook as the wrong version was sent to the printers but this does not affect the scoring of the output.
[8] Daanish Schools are residential schools started in 2009, as an initiative of the Chief Minister Punjab Shahbaz Sharif. Their objective is to provide high quality education to children belonging to low-income segments of society especially in the less-developed areas of Punjab. Presently 5,216 students are studying in 14 Daanish schools.

Key Points
Learning levels in Punjab are low and this is a priority area for development. Output 2 aims to improve the overall quality of education that children receive through better teaching. The integrated quality plan developed by TAMO covers broader issues like improving teacher training, support for teachers in their classrooms, development and printing of better quality textbooks, and integrated teacher guides for English, Maths and Urdu; as well as special training sessions to ensure teachers know how to use the new textbooks. Its focus on strengthening the existing examination systems and introducing a new assessment system[9] has laid the foundations for a good system. Early results from learning assessments suggest the quality of education is clearly moving in the right direction.
[9] Currently there are five assessments being carried out in Punjab: PEC annual examination (grades 5 and 8); DTE monthly assessments managed by DSD (grades 1,2, and 3); the LND drive conducted by MEAs and measured by the PMIU on a monthly basis (grade 3); Quality Assurance Tests (QATs) by PEF; and, six-monthly assessments measured through TAMO (grade 3).

Sample-based assessments are undertaken every six months. The results indicate where children are finding it difficult to grasp concepts. Feeding back these results into teacher training and learning materials should ultimately lead to strengthened understanding of those concepts. Teachers are also being given the opportunity to meet in peer groups through professional development days (sessions were held in summer and September/October 2015[10]) to discuss their problems. What they identify in these sessions will also be fed back into training and the support provided by the District Teacher Educators (DTEs). This is a unique activity not being undertaken at this scale anywhere else in the world. A large-scale reform of the PEC examination system is also underway.
[10] Roadmap Stocktake December 2015

Addressing the quality of education is a priority for the Secretary SED, who launched a quality drive[11] in April 2015. DTEs provide mentoring and coaching support to teachers and EDOs are responsible for the management of the education system at the district level, including performance management of teachers. Under the quality drive, EDOs and DTEs adopt government schools with the aim that in a year’s time, the 5,000-strong DTE force will have covered all schools. The impact on the quality of education has been limited to date. The integrated support on quality led by TAMO includes broader issues like teacher training, development of quality teacher guides and learning material. Its focus on strengthening the existing examination systems and introducing a new assessment system has laid the foundations for a good system and is already improving the quality of education and student learning outcomes.
[11] The Quality Drive (launched by the Secretary SED) is separate from the Literacy and Numeracy Drive (conducted by MEAs).

Output Indicator 2.1
This indicator assesses the quality of education by measuring the development of new teaching and learning materials in line with new curriculum, and printing of the new material.

This target has been partially met: the textbooks for grades 2 and 3 and their corresponding teacher guides have been developed. The main improvements to the teaching and learning materials relate to revisions to the content to make it clearer and based on prioritised SLOs. The quality of content is reviewed by experts in pedagogy and field-tested in schools. Focus group discussions organised by TAMO with teachers and children found that the quality of the new books is better. Teacher training on using the new textbooks is scheduled for March 2016 before the new school year.

PCTB, with technical assistance from TAMO, has reduced and simplified a list of key SLOs that all primary school children need to meet in English, Urdu and Maths. TAMO has embedded writers within PCTB to develop an integrated package of textbooks and teacher guides with PCTB writers. This should help build capacity within PCTB. Grade 1 material was developed in 2014-15 and textbooks for grades 2 and 3 were developed and field-tested during the review period.

The new textbooks were field-tested in 29 districts by TAMO DFCs. The content of the textbooks is SLO-specific, focusing on core literacy and numeracy skills and the basics of English language, Maths, and Urdu. Supplementary reading material on topics such as road safety, peace-building and tolerance has been developed for the lower grades and has been included in the textbooks for higher grades. Gender has been considered in the development of textbooks. Some material was, however, taken out from textbooks indicating a need for gender training of key stakeholders. UNICEF is supporting PCTB on social cohesion and resilience.

Forty percent of textbooks have so far been printed for all grades; textbooks for grades 2 to 5 have not been printed. There was a long delay in the printing of these textbooks due to a court case which was resolved in PCTB’s favour in January 2016[12]. The remaining books have now been sent for printing and will be in schools by 1 April 2016, in time for the start of the academic year. There is an ongoing issue with the printing of the grade 1 Urdu textbook as the old version of the textbook was sent for printing and will be used for the coming year. This has happened for the second consecutive year and has a particularly large impact as grade 1 books are used for Kachi (pre-primary) grades as well. As per the current arrangement, PCTB develops the textbooks and PMIU distributes them. The arrangement is now being reviewed to shift the responsibility for distribution to PCTB.
[12] Private publishers claimed that PCTB does not have the mandate to develop its own textbooks. They also raised concerns that even with the mandate, the quality of the content in these textbooks will be very poor.

Output Indicator 2.2
This indicator measures the frequency and independence of learning assessments (grade 3) taking place as well as increase in its coverage to private schools (previous it was only government schools).

The target for this indicator has been met. Grade 3 student assessments were expanded to include PEF schools from February 2015 and The Citizens Foundation (TCF) and CARE Foundation Pakistan schools from September 2015. A total of 592 schools and 16,742 students were covered by the September assessments. Both the government sample (5,824 students) and PEF sample (5,692) were statistically representative thereby providing robust data which allows comparisons to be made.

The assessment tested grade 2 SLOs in English, Maths and Urdu. The results are discussed under Outcome indicator 3. In February 2015, the content of the assessment was expanded slightly to cover additional learning outcomes such as punctuation (English), one-digit division (Maths) and singular-plural words (Urdu). Multiple versions of the assessment paper were developed, covering the same SLOs but with different questions to minimise cheating or leaking of questions. Other measures taken to ensure reliable testing included:
- Before test: sealed test papers, dispatched one day in advance and delivered by MEAs.
- During test: 25% of assessments audited. Teachers asked to leave the classrooms while the test is being conducted. MEAs present.
- After test: paper sealed and taken by MEAs to district office and dispatched same day.

In addition, TAMO have highlighted that regular communication from SED to EDOs is helping to ensure the smooth conduct of the assessment (for example, encouraging invigilators to attend training) and has created a sense of accountability. TAMO also view the marking and compilation of results to be a transparent process as external parties do not have any incentive to cheat or misreport results.

The assessment process was audited by Pricewaterhouse Coopers (PWC) (contracted by TAMO) and DFCs (hired by TAMO) who conducted field visits and collected data on the conduct of the assessment. These audits highlighted some minor issues (such as fake students and invigilator error) but none at the scale to affect the results of the test.

Output Indicator 2.3
This indicator measures the reliability of the PEC exams and improvements in the test design and content quality by looking at the exam development process and how the exams are being administered and marked.

The target for this indicator has been met. Two basic areas for improvement were identified in the PEC exams: the quality of the content of PEC exams and the actual conduct of the exam and marking processes. PEC has made several improvements to the design, conduct, marking and reporting of exams. These include: robust test development; a strict item review process; better administration and strong invigilation; standardised marking; and, analysis and reporting of key trends in student performance.

The question bank for PEC exams is being aligned with prioritised SLOs from the curriculum through multiple iterations and field testing before the actual exam. TAMO is providing technical support for the development of an item bank. This is a database of possible test items (questions) used in exams. The questions are categorised according to their relevant student learning outcome and cognitive area, as well as the level of difficulty. TAMO is also supporting the development of a standardised marking scheme and an analysis framework. The technical expert shared that while there are now a large number of items, these are not enough to constitute a formal ‘item bank’, which would eliminate the need to write new exams and items each year. The review team heard that some of the recommendations of the expert are not being used by PEC for the item banks. This is an issue which TAMO needs to address if the expert’s recommendations are not being considered. PEC is now working in collaboration with the PITB for the development of item bank software[13].
[13] This is in line with the curriculum and PITB is providing IT support. Education expertise comes from PEC.

The conduct of the exam is being revamped to ensure integrity and reduce instances of cheating. Learning from exam design and conduct in 2015 will serve as a guideline for the second iteration in 2016. The number of examination centres has been increased and four to six different versions of the papers were used to reduce chances of cheating. The papers also included topic and difficulty level SLOs. The revised papers were piloted in January 2015 and finalised and in use by the end of February. Improved and strengthened invigilation guidelines have resulted in a reduction in misconduct; the 2015 exams reported misconduct in 5% of the exam centres. Early reports of 2016 exams include less than 1% instances of misconduct.	PEC has also improved the registration process by introducing an online system.

On institutional strengthening the review team thought that, based on discussions with the Managing Director PEC, the psychometrician and the technical assistance expert, PEC now has sufficient expertise on the technical side. PEC has been supported to revise its rules of business and human resource management but the CEO feels that his ambitious reform agenda needs further technical assistance. The review team was also informed that teachers were not comfortable with the new examination process as it represents a shift from rote learning to actual assessment of student learning against the curriculum. This requires teachers to adapt their teaching to teach to SLOs rather than textbooks.

Output Indicator 2.4
This indicator assesses the quality and delivery of teacher training and mentoring by measuring DTE attendance and launch of the Quality Drive by SED. The indicator has been met as 92.5% of schools were visited by a DTE, against a target of 90% (January – December average). Three districts, however, have much lower DTE visit rates (Rahimyar Khan, Mandi Baha-ud-Din and Gujrat) of 70% or less because a large number of their DTEs were dismissed for underperformance. Replacements are currently being recruited under the SED's standard recruitment procedures for DTEs. DTEs are required to make a minimum of two visits a month to a school to provide teacher coaching and mentoring. The visits focus on improving teaching, learning, classroom management and formative student assessment. The quality of teacher training and mentoring is assessed by TAMO DFCs who provide oversight and report back on DTE performance. A combination of initiatives listed under key points above are beginning to show improvements in learning outcomes of children[14] [15].
[14] DFC lesson observations as presented in the Roadmap Stocktake December 2015.
[15] LND, Sept-Nov 2015 – 230,000+ grade 3 students tested each month (random set of 6 students in each school visited by MEAs)

The DTEs are now engaged in SED’s quality drive. This means they will have to spend two consecutive days at two schools to provide intensive mentoring and training to teachers. This is in addition to their routine visits to schools. The drive was in response to evidence suggesting the previous schedule of DTE visits had limited impact. The Secretary SED leads the quality drive personally along with regional coordinators; progress is reviewed on a weekly basis. DTEs have a packed workplan under which they visit each school at least once a month for conducting monthly assessments which are now part of the system and have become an accepted norm for teachers. DSD provides teachers with support and teachers themselves mark the assessment papers. This is commendable as it will lead to improved student learning outcomes if this work is sustained. DTEs also conduct mentoring and class observations on assessments and hold sessions with teachers, including professional development days for primary school teachers. DTEs also report on non-performing teachers during their classroom visits. The mentoring visit forms shared with the review team comprised nine indicators. DTEs conduct monthly visits to follow up on advice and check on the progress. Results are also shared with the head teacher. With the increased support to DSD through additional time of DTEs and revised role of AEOs in the classroom, and with teachers actively learning from each other, there is likely to be a significant impact on the system, albeit it is currently slow in responding.

TAMO have advised and the review team endorsed the fact that this indicator needs revision given the involvement of DTEs in the quality drive and difficulty to meet original expectations on visits. TAMO suggests it may be more relevant to consider DSD indicators, given the broader work to support DSD to improve its measurement of student learning outcomes through assessments.

The integrated support on quality has started to impact upon improved SLOs. The Annual Review team were impressed by the levels of learning demonstrated by (randomly selected) students in the five government schools visited.

Given the recent change in DSD leadership, clear communication and recognition of expertise within the organisation will help ensure the quality drive gains momentum. The research wing is being strengthened including hiring of personnel and renovation of facilities. DSD is developing approximately 50 new teacher training modules in consultation with TAMO covering content and pedagogy. These modules will also help cater to the problem of multigrade teaching and will be used at monthly professional development days and at summer refresher trainings.

DSD expressed the view that outsourcing teacher training to the private sector, as advocated during a recent education Roadmap stocktake and pushed by the SMU, is simply not possible at this stage. Very few CSOs are willing to carry out the training of public sector teachers at the district level. One suggestion that DSD made was that the private sector could assist in teacher evaluation and assessments for promotion. DFID should consider this recommendation in consultation with TAMO and DSD.

Output Indicator 2.5
This indicator measures teacher attendance rates in government schools and has been met. The average teacher attendance rate of 92.7% exceeds the target of 90% (based on the Jan-Dec rolling average). District attendance rates are also greater than 90%. TAMO have advised that additional teacher duties (elections, polio) contribute less than 2% of absenteeism.

Summary of responses to issues raised in previous Annual Reviews (where relevant)

Recommendation 2014/15 Annual Review	Response
Short-medium term: Focus on continuous professional development support that robustly demonstrates impact. This should include support for better teaching and more effective leadership of schools and sub-provincial units. The current approach could be simplified and strengthened with better evidence of what works. A focus on teaching essentials might help, together with efforts to encourage students’ critical thinking and problem-solving skills.	Action has been taken on some elements of the recommendation for example development of good quality textbooks, increasing teacher attendance and testing of learning outcomes. This is a longer-term target if all the elements of CPD and teaching essentials are to be considered.
Ongoing: Draw on additional external expertise to peer review and quality assure the new textbook development plans, including cost and budget considerations, as well as the potential role of the private sector.	A robust process is in place to develop, review and quality assure textbooks with TAMO support. There is limited scope of engagement for the private sector as this is PCTB’s sole discretion and depends on their rules and regulations.
Short-medium term: Map out a long-term strategy for the development of a robust assessment system in Punjab that links all assessment and examination efforts (including the Grade 3 assessment, QAT and PEC). This should be led by PEC, but link across all the relevant education departments and relate to an understanding of students’ expected progression in core subject areas. There are opportunities to draw on the Systems Approach for Better Education Results (SABER) assessment diagnostic carried out in Punjab in 2012, to learn from current efforts to develop a global common metric for reading and Maths as well as bringing in additional external expertise such as the Australian Council for Education Research.	One credible item bank of questions is being developed to be used by PEC for its exams, DSD for its assessments, PMIU for the LND and for the six monthly assessment. A challenge going forward will be developing the linkages between the different organisations involved, having a coherent sense about the results and feeding it back into the teacher training system.
Short-medium term: Given the priority placed on credibility of exams by PEC, and the high risks around examination reform, TAMO needs to define how credibility will be assessed for PEC in relation to the points made above on both content and conduct.	TAMO is supporting a medium-term reform programme for PEC exams centered on strengthening the exams by improving the quality of exam content and design, enhancing reliability of exam conduct, developing an improved marking scheme and analysis of results.

Recommendations
1. Teaching and learning: TAMO should review its technical expertise to DSD to strengthen the current teaching and learning model/approach and rebalance emphasis from monitoring to actual coaching and/mentoring.
2. Assessment: TAMO should continue to develop linkages between the different assessments conducted at various intervals and strengthen the feedback system, particularly with DSD, so that results are incorporated into teacher training and CPD.
3. PEC should complete an institutional development plan or a needs analysis with the support of international expertise (discussions have started with Cambridge Examination and Assessment Board) provided through TAMO.

Output Title	Better Learning Environment
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Improved availability and functioning of basic school facilities	All districts with functioning of facilities > 90%	Moderately did not meet expectation / Average for all districts is 95.5% (January – December average, but two districts scored below 90% (84.4% and 89.1%)
3.2 Aggregate number of classrooms rehabilitated to international standards	10 Dangerous School Buildings: / 8 dangerous school buildings reached milestone 5 level; / 2 dangerous schools reached milestone 4 level / 367 primary, elementary and high schools: / 217 schools: milestone 1 level completed; / 150 schools: reached milestone 2 level	Moderately did not meet expectation / In dangerous school buildings, 2 have reached milestone 5 and 8 have reached milestone 4. / In primary, elementary and high schools: / contracts have been signed for 205 sites which have not yet reached milestone 1; / 136 have reached milestone 1; and / none has reached milestone 2.
3.3 Classrooms with multigrade teaching	Number of primary teachers to be hired to help address multigrade due to insufficient teachers = 13,000 / Number of additional classrooms required to help address multigrade due to insufficient classrooms = 20,000	Substantially did not meet expectation / 7,200 part-time coaches have been hired by SED. / Budget allocated for classroom construction, but none is complete.

Key Points
This output aims to contribute to increased enrolment, retention and learning outcomes through improvements to school infrastructure. Activities include: the construction of additional classrooms, staff rooms and toilet blocks through the Humqadam project; monitoring the availability of basic school facilities through the roadmap process; recruitment of additional primary school teachers; and GoPb construction of classrooms. School infrastructure is a high priority for SED and DFID given severe overcrowding, which goes well over the recommended 40 students per classroom in many schools. We are committed to ensuring a high quality learning environment in new infrastructure. Achievement of this component’s targets is supported by a quarter of PESP II’s total financial resources.

None of the milestones in the three indicators has been met for this year, although in the case of 3.1, the milestone was only narrowly missed. This is predominantly due to the lack of electricity in two districts which has hindered progress. In the case of 3.3, where two drivers of multigrade teaching (insufficient teachers and/or insufficient classrooms) are tracked, progress is behind schedule on both.

In the case of 3.2, which DFID is directly implementing through IMC, the Humqadam project to construct additional classrooms has experienced further delays over the past 12 months. Progress only really started in September 2015 when formal contract negotiations to build classrooms began. The speed of work since then has improved, but Humqadam has still not met the 2016 milestone set only two months ago based on their plans at the time.

The milestones for 3.2 were revised in November and progress in this review is being assessed against those new milestones. As such, progress is recorded as a B for the component and for the output as a whole. Were progress being assessed against the milestones for 3.2 as they stood at the time of the previous Annual Review, this component would have scored lower.

Output Indicator 3.1
The four basic school facilities covered by this indicator are: a boundary wall; toilets; drinking water; and electricity. DFID is monitoring progress by the GoPb through the Roadmap stocktake process.

Progress over the past 12 months is summarised in the table below. This shows that the average percentage of functioning facilities across Punjab has risen slightly and is above the milestone. However, two districts remain below the line, despite progress in both during the last year. For these two districts to continue to improve their provision of facilities, the challenge of electrification needs to be overcome. There are indications that work may be taking place to address this: the CM has tasked the Chief Secretary to ensure solar panels are installed. As recommended below, the PESP II team should consider whether the lagging behind of these districts should be addressed by further supportive action either through the Roadmap process or another intervention, or whether current GoPb plans will suffice.

	Jan - Dec 2014 average	Jan - Dec 2015 average
All 36 districts	93.7%	95.5%
Number with >90% facilities	33	34
DG Khan	76.4%	84.4%
Rajanpur	83.3%	89.1%

Output Indicator 3.2
Combined with activities in Khyber Pakhtunkhwa (KP) under the same contract, Humqadam is DFID’s largest infrastructure contract. The total contract value is £184 million: £104 million is earmarked for Punjab (all funding from DFID) and £80 million for KP (£71 million from DFID and £9 million from the Australian Department of Foreign Affairs and Trade). As per the contract with IMC Worldwide, the implementing partner, 23,000 classrooms were to be built across Punjab with the resources available. This would go some way to bridging the large gap, estimated by GoPb at 60,000 classrooms across the province. DFID’s support is in addition to the construction of 1,000 classrooms and rehabilitation of 8,000 classrooms scheduled to be carried out by the GoPb through its Communication and Works department.

Humqadam’s performance over this Annual Review period has fallen short of expectations. In June 2015, 1,130 classrooms were anticipated to have been completed by the time of the Annual Review. Not one of the classrooms had been completed. Milestones were revised in November 2015 to reflect slower progress but these were not met.

The implementation contract with IMC Worldwide was signed on 16 April 2015 shortly after receipt of Board of Investment registration. The time taken over registration had already resulted in significant delays in getting work started. IMC then began to hire staff and start the process of the pre-qualification of construction contractors. Some further delays occurred in the allocation of schools to be worked on which affected Humqadam’s planning processes. The original concept of using community contractors was dropped due to concerns about capacity and speed of delivery. The revised model uses conventional contractors with capacity building provided by Humqadam to members of the local community who then supervise the works under the auspices of Community Committees for School Infrastructure (CCSI). Since the last review, GoPb requested, and DFID and Humqadam agreed, to use some of the project funds to construct a total of 439 additional classrooms in two schools in each of 16 districts across Punjab and front-load this work. This work was prioritised due to the severe overcrowding in each of these schools caused by buildings being declared unfit for use.

At the early stages of going out to market, Humqadam discovered a significant discrepancy between their planning figures and what was practical for construction of a classroom of the quality being sought through this intervention. Research and analysis done during the planning and inception phases by Humqadam had resulted in an estimated cost of PKR 350,000-450,000 per classroom (up to around £3,000).The response from the market of conventional contractors, following negotiation from Humqadam in the second half of 2015, resulted in a first batch of contracts that fall between PKR 850,000 and PKR 1.1 million, averaging around PKR 950,000 per classroom (£6,000), although individual contract values are not final until all construction is complete in a site.

Because of the higher than planned for unit costs, the number of classrooms that can be built within the programme budget has dropped. Rather than build 23,000 classrooms, in addition to the 439 classrooms in 32 schools with dangerous buildings, it will only be possible to construct around 11,000 classrooms, assuming there are no further escalations in cost. This assumes around 6% of the available budget will be used for providing or improving missing facilities, the figure provided by GoPb. This is still a risk.

The DFID programme team went through a thorough process with Humqadam to test their revised costings to ensure that there was as little risk as possible of further escalation and to verify that they were commercially competitive. These discussions and a comparison with the cost of classroom construction by suppliers for the public sector suggest that the earlier estimates were not feasible. The reasons for this were the change in delivery model and some price increases in the time between estimates being drawn up and contracting starting. The changes in costs represent a weakening of the VfM expressed in IMC’s bid, but given the same market forces would apply to any alternative service provider, DFID did not consider at that stage reviewing IMC’s status as the supplier for this contract. IMC have assured DFID that they are fully confident in these new figures.

A process of enhanced monitoring by DFID has been in place since September 2015, with a view to addressing performance and restoring DFID and GoPb confidence. This has included increased staffing from the DFID side, more frequent meetings to discuss progress, five field visits, and the development and implementation of a broader monitoring strategy. All the sites visited were among the higher secondary schools where work is underway to build additional classrooms in schools with dangerous buildings. Work in the other schools has only recently begun. Overall, following discussions with the school councils, CCSI members present, contractors and Humqadam staff, the quality of building ongoing and the engagement of local communities were good. Construction in sites visited was progressing to schedule.

DFID began discussions with GoPb counterparts in December with a view to explaining the reductions in numbers of classrooms that can be built through this support. By mid-February, DFID aims to have finalised the numbers for the remainder of the contract’s duration, and reconfirmed the prioritisation of districts and schools within those districts. Considerations of need including overcrowding, multigrade teaching, poverty levels and equity must be taken into account, as agreed in the original analysis.

As detailed further in Section D, despite the changes the review still considers that this intervention represents Value for Money (VfM). The previous assumption that Humqadam could deliver higher quality classrooms for around half the cost of GoPb classrooms has proven to be based on incorrect information and calculations. However, following surveys and market testing it looks likely that Humqadam will deliver higher quality classrooms at lower costs than could be achieved through GoPb systems. Anecdotal evidence from Humqadam and contractors suggests that negotiations have resulted in contracts that are competitive given the requirements, with low profit margins for the sector. Improvements in quality, some of which are being introduced to Pakistan for the first time, include air wells to ensure air circulation and flexible gypsum walls to increase construction spend and reduce the environmental impact from brick use.

Humqadam is in the process of establishing CCSIs for each site where construction is taking place. 139 CCSIs had been formed in Punjab as of the end of December 2015, comprising 623 members. The gender balance is poor, with 595 male and only 28 female. 723 CCSI and school council members joined review meetings and 2,417 attended follow-up meetings over the past three months. Training is being provided to school council and CCSI members on the principles of construction supervision. Humqadam has developed a community development toolkit which is guiding community engagement. This and the capacity building of some of the construction companies provide additional added value beyond the actual infrastructure.

Humqadam launched a website, www.humqadam.pk, in September 2015. They have active Facebook and Twitter accounts to spread awareness of their work. Humqadam have also launched a design competition which seeks proposals for designs from students: 11 architecture schools were visited to launch the competition. It is hoped that this will have a positive effect on the buy-in of local communities and should be a positive step in spreading awareness of the work. Outreach of all forms will increase once construction is complete in the first schools from March 2016.

The process of rebuilding confidence that Humqadam will deliver on the revised figures is taking place, with finalisation of the first schools due in March. Milestones and targets will need to be revised again once discussions with GoPb have been completed. From this point, they should not need to be revisited.

Third Party Validation (TPV) had initially been planned by DFID as part of this component, to be managed by TAMO but was removed at a later stage. However, following industry good practice combined with concerns about performance, DFID decided to reinstate TPV and contracted Halcrow Group for this purpose. Halcrow will conduct two phases of TPV in Punjab, one in January and another in the summer of 2016. Findings will inform the case for continued TPV over the remainder of the period of construction. Their initial report from the first round of inspection at 13 sites across Punjab is broadly positive but expresses general concerns about delays of several weeks in some sites, a need to improve monitoring by Humqadam’s technical teams, and specific construction issues at some sites. DFID will share these concerns with Humqadam for corrective action.

Output Indicator 3.3
There were two milestones for this output indicator. Neither of these has been met.

As a result of not receiving funds from the GoPb Finance Department, and struggling to find sufficient numbers of qualified teachers, SED has hired 7,200 part-time coaches, falling far below the milestone both in number and nature of recruitment. Plans expressed by GoPb in December 2015 are for 18,000 primary school teachers to be hired in 2016, but TAMO is working with them to increase this to 60,000 to ensure that, combined with natural attrition, the net increase in teachers is achieved.

In terms of the second milestone, the GoPb has allocated resources and plans to construct 1,000 new classrooms and to repair or rebuild 2,500 dangerous buildings covering some 8,000 this financial year, Progress is however behind schedule due to the previous non-release of funds. To the review team’s knowledge, funds are now being allocated and some construction work has begun, though none has been completed.

Given that progress has been weak on this indicator, DFID should continue to influence GoPb to realise its commitments in this area through the Roadmap stocktake (where this is already an indicator).

Summary of responses to issues raised in previous Annual Reviews (where relevant)

Recommendation 2014/15 Annual Review	Response
Short-medium term: GoPb to ensure that the Communication and Works Department (responsible for infrastructure) and SED effectively share data on school construction to enable informed planning and avoid duplication of effort.	To the best of the review team’s knowledge, this has been taking place: Humqadam explained that due to construction work begun by the GoPb, they have pulled out of work in 22 of the 367 primary, middle and high schools they were planning to be working in at this stage. In some cases this would appear to have happened late into the planning phase, delaying the Humqadam planning process.
The ‘key points’ section of last year’s review also suggested raising this output’s risk rating from ‘medium’ to ‘high’ on the basis of delays in contracting Humqadam classroom construction.	This was not done, and a year later the output has failed to meet milestones across all three indicators. Progress is particularly behind original plans for indicator 3.2. A recommendation is made to adjust the risk rating.

Recommendations
1. Given the challenges around achieving milestones in all three indicators, DFID should raise the risk rating and take/continue corrective action relating to delivery of the Humqadam component, as well as the potential reputational risk of being perceived to under-deliver for GoPb, and the implied weakened (though continuing) case for the VfM of this intervention.
2. Consider further action to address missing facilities in DG Khan and Rajanpur or revise milestones to reflect that significant improvements from this point are unlikely.
3. Continue enhanced DFID monitoring of Humqadam until such time as performance begins to match expectations.
4. DFID to provide ongoing liaison and coordination support between Humqadam and TAMO/GoPb to avoid further delays due to duplication of planned works.

Output Title	Improved access to schools, especially in priority districts
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Additional children enrolled in priority districts as part of CSO-led supply side interventions	32,000 out-of-school children enrolled in new schools in 2 priority districts (Rahimyar Khan and Muzaffargarh)	Met expectation / 31,772 out-of-school children enrolled into new schools in Rahimyar Khan and Muzaffargarh
4.2 Number of children in school supported through the Punjab Education Foundation (cumulative) / i) Education Voucher Scheme (EVS) / ii) New School Programme (NSP) / iii) Foundation Assisted Schools (FAS)	i) 350,000 / ii) 115,000 / iii) 1.3 million / Boys: (i) 192,500 (ii) 63,250 (iii) 715,000 / Girls: (i) 157,500 (ii) 51,750 (iii) 585,000	Moderately did not meet expectation / 302,516 / 112,770 / 1,442,361 / Boys: (i) 165,229 (ii) 58,640 (iii) 791,098 / Girls: (i) 137,287 (ii) 54,130 (iii) 651,263
4.3 Number of children supported through the Punjab Inclusive Education Programme (cumulative)	PIEP Project Implementation Unit (PIU) established and fully functional	Met expectation / The PIEP’s PIU is functional, with a project director, senior management and monitoring teams recruited. Partnerships have been initiated with government schools in Bahawalpur and Muzaffargarh, and with PEF for inclusive education in LCPS in seven districts.

Key Points
This output aims to support the GoPb to maintain progress on improved access to schools, particularly for marginalised groups, including students with special schooling needs. The GoPb plans for any new schools built in the province to be achieved through PEF’s expansion. While this is a clear political endorsement of PEF, it will be important to ensure equitable financing for the most marginalised and poorest communities. Output 4 is being delivered through sector budget support, PEF, CSOs and technical assistance provided by TAMO and the Roadmap team.

Output indicator 4.1
This indicator measures the number of previously out-of-school children in priority districts enrolled through CSO-led supply side interventions. The milestone has been met, with total enrolment falling just 228 short of the 32,000 target. As detailed in the table below, BRAC in Rahimyar Khan and Ghazali Education Trust (GET) in Muzaffargarh, have set up 700 and 192 schools respectively in collaboration with PEF and have enrolled a total of 31,772 children.

Partner	District	No. of schools	Children	Teachers
BRAC	Rahimyar Khan	700	21,000 / (13,440 girls, 7,560 boys)	700 / (686 female, 14 male)
Ghazali Education Trust (GET)	Muzaffargarh	192	10,772 / (5,284 girls, 5,438 boys)	407 / (163 female, 244 male)
Total		892	31,772	1,107

From an equity perspective, these pilots are designed to target the most marginalised and hard-to-reach children, mindful of social class, religion, ethnicity and disability. This dimension is not fully reflected in the quantitative target in the output. GET enrolled 419 out-of-school children with disabilities, but data was not disaggregated by gender, ethnic or religious backgrounds. BRAC did not provide data on the number of children from minority backgrounds.

Both organisations are responsible for providing end-to-end solutions for enrolment and retention of out-of-school children. This includes identification and targeting, establishment of schools (in partnership with PEF), recruitment of teachers, outreach and mobilisation of communities to enrol children into school, and effective management of schools to ensure that children attend regularly, stay in school, and learn more.

BRAC enrolled 21,000 out-of-school children through a survey of 800 households in Rahimyar Khan and established 700 single-teacher schools. 686 of the teachers are female. BRAC’s approach included meetings with the community, information from nearby government schools, affidavits from guardians, and regular project monitoring to identify out-of-school children. Pupil retention is encouraged through child-friendly schools, recruiting female teachers, engaging parents and functional school management committees, and an improved quality of education through teacher training.

GET enrolled 10,772 out-of-school children by establishing 192 new schools in Muzaffargarh, missing their target of 12,000 in 240 schools by November 2015. This contributed to falling just short of the milestone for output 4.1 by 228 children. Similar to BRAC, out-of-school children were reached through community mobilisation and an enrolment campaign. Student retention is targeted through child friendly schools and provision of quality education. GET used Benazir Income Support Programme (BISP) data, detailed household survey and informal survey data through community meetings, together with verification by PEF and TAMO, to target the best areas for establishing schools. GET’s approach to local hiring of field staff and 407 teachers and encouraging parents to send their children to school, coupled with mobilised local school committees, all helped contribute to the target.

Both partners have faced some initial challenges including delays by PEF in verifying sites for school establishment, delays in the delivery of textbooks for BRAC schools, and the lack of female teachers and suitable sites in GET communities. These challenges have broadly been overcome to meet the milestone, but may need to be revisited as part of any scale-up plans. A TPV is currently underway to assess the success of the pilot interventions. Findings are expected in March and should also include data on the retention of students which will help in judging whether the interventions have been successful beyond enabling access.

Output indicator 4.2
This indicator measures progress on increasing enrolment in PEF schools. The government’s goals to improve access, particularly for some of the most marginalised children in Southern Punjab, rely heavily on the ambitious expansion plans of PEF. PEF aims to deliver quality education to some of the poorest children through LCPS. With DFID support, PEF plans to enrol 2.8 million children by 2019. It supports children at a lower cost than the government, and whilst facilities are basic, recent analysis suggests that 75% of grade 3 PEF children are meeting basic Urdu, Maths and English standards, compared with 61% of children in government schools.

In the last year, PEF has increased total enrolment across its programmes by over 100,000 children. Whilst this increase in enrolment is impressive, the rate of expansion risks falling short of PEF’s own targets for the academic year. This is a particular concern given the growing ambitions for PEF outlined below. PEF has exceeded the logframe enrolment target for the Foundation Assisted School (FAS) programme which converts existing fee paying LCPS into no-fee PEF-supported schools[16]. It has not however met the targets for its Education Voucher Scheme (EVS) and New Schools Programme (NSP) which are specifically targeted at out-of-school children.
[16] The 2014-15 Nielsen household survey included analysis of FAS schools and found that the majority of students attending FAS schools belong to low-income groups and that enrolment has expanded in FAS schools after partnering with PEF. However it remains unclear whether the new enrolment is truly additional as a result of PEF support or whether these children would have enrolled regardless. The analysis also estimated that 14% of students would be able to afford fees in the absence of PEF support.

PEF emphasises that the supply of private entrepreneurs responding to its incentives is central to the growth in the PEF model. However as the organisation expands further, it is increasingly important to ensure PEF’s management and governance systems are strong enough to maintain minimum quality standards at scale, whilst effectively serving the most marginalised. Efforts to strengthen capacity in PEF over the last year have been hampered by three changes in the Managing Director. A number of management positions remain vacant, including the Finance Director post. DFID has made clear that any further releases of its funding to PEF are contingent on these positions being filled. Through TAMO, DFID aims to support PEF’s expansion with technical assistance focused on organisational capacity, effective targeting and improvements to quality. Delivery of technical assistance has faltered, partly as a result of the changes in Managing Director. TAMO is currently providing assistance on the FAS Quality Assurance Test and improving feedback to schools on test outcomes.

Beneficiary identification, verifications for per-child payments and monitoring mechanisms are areas of potential weakness that may impede PEF’s ability to target effectively and mitigate risk of fraud if not checked during expansion. Schools currently self-report enrolment which is then verified at several points in the year by monitors. PEF is recruiting over 100 MEAs to increase coverage and has plans to automate its monitoring processes and fill its vacancies, but it is not clear whether these plans are sufficient to match the scale and pace of its expansion. This expansion risk was also captured in the latest DFID Portfolio Risk Assessment Programme (PRAP) progress review of PEF (2014). The review highlighted a few key risks, including: the capacity of governance, management and accountability mechanisms to be appropriately sighted on the enlarged scale of activities; the need to ensure that the quality of the control environment is not affected by the scale-up; and the ability to track and review progress against expansion plans.

The last Annual Review highlighted the need for a long-term strategy that consolidates PEF’s expansion plans and develops its future vision for partnership with the private sector. Whilst PEF continues to operate in the absence of a comprehensive strategy, it has nevertheless embarked on a number of new initiatives over the last year, taking it beyond the scope of its original expansion plans. This includes its partnership with SED under the DFID-supported Punjab Inclusive Education Programme (PIEP) and its partnerships with BRAC and GET. Together, these initiatives help to strengthen PEF’s own focus on equity, improving enrolment in hard to reach areas and across marginalised groups. PEF has also started a programme to enrol the children of brick kiln workers, who are among the most marginalised and excluded groups of children due to the bonded nature of their parents’ and indeed their own status.

These activities are however small-scale when compared with the introduction of a new scheme, driven by the CM’s Roadmap and managed by PEF, to outsource the management of 5,000 low-performing government schools to the private sector. Whilst this initiative has the potential to drive up the quality of education, taking on these schools will almost double the number that PEF currently oversees. This has inherent risks.

The review team has strong reservations about the pace of this latest reform and the capacity of both PEF as well as the organisations that take on these schools to manage and deliver this scheme effectively, especially given the additional work likely to be needed as these are already low-performing schools. There are also risks that the roll-out of the scheme will come at the expense of any efforts in PEF to strengthen its capacity to manage the scale-up in its core programmes. The DFID programme team are alert to these concerns and will take up these issues with PEF in its meetings in February. Having a long-term strategy in place could help PEF to take stock of ongoing and new expansion initiatives and encourage alignment of plans with its capacity and vision.

Output indicator 4.3
This indicator measures progress under the new Punjab Inclusive Education Programme (PIEP) to support children with mild disabilities in school. The indicator milestone has been met. PIEP’s Project Implementation Unit (PIU) is established and functional with all key posts filled, including the project director, senior management and monitoring staff. Partnerships have been established with government schools in Bahawalpur and Muzaffargarh, and with PEF for inclusive education in LCPS.

The aim of the inclusive education work stream is to cater to children with mild disabilities and enrol them in mainstream schools. Previously, children with mild disabilities were typically expected to enrol in a special education school. These schools are less widely available and more expensive to run as they cater to a full range of disability. The objective of PIEP is to be achieved by identifying and enrolling out-of-school children with mild disabilities in government and PEF schools, promoting a disability-friendly environment in the schools, training teachers, enhancing school infrastructure to make it accessible, and providing assistive devices to children and teachers as needed. Integrating children with mild disabilities into mainstream schools is a positive development, as currently most children with disabilities are either being educated in separate schools or are simply not in school. There are likely to be strong societal benefits in terms of promoting the acceptance and inclusion of children with disabilities by fellow students, parents and teachers.

The pilot with government schools focuses on Punjab’s low performing districts of Muzaffargarh and Bahawalpur and the upcoming pilot will be in PEF partner schools in districts Jhelum, Rawalpindi, Chakwal, Attock, Lahore, Multan and Vehari. The district screening teams have already identified 1,122 children (including 472 females) with mild disabilities. These disabilities include visual and hearing impairments, physical disabilities, and learning disabilities. A total of 1,282 educators have been trained to understand the special needs of children with disabilities. The training was held in collaboration with DSD and 22 master trainers, 279 district teacher educators, 552 primary school teachers and 429 education managers received the training. A range of screening and monitoring tools have been deployed for identification, data collection, enrolment, and tracking of these children.

Two thirds of the budget allocation for this programme remains unprogrammed. TAMO is supporting PIEP to develop options for further scale-up. As this is a brand new approach to delivering education to children with mild disabilities, it will be important that lessons and evidence from the pilots are used to inform any future plans. Any emerging challenges around the integration of children in schools will need to be addressed quickly to reduce the risk of dropouts early on in the pilots.

Summary of responses to issues raised in previous Annual Reviews (where relevant)

Recommendation 2014/15 Annual Review	Response
DFID to clarify the main purpose of the Access to Finance component and, based on this analysis, determine if there is a strong enough case to proceed.	Following the review, a dedicated DFID team was set up to undertake further analysis and explore potential models for access to finance. The analysis concluded that there was still a rationale for the component but needs have also been addressed through other programme components including PEF (quality) and the infrastructure component (access). The analysis also questioned DFID capacity to develop and implement a new finance model within an already complex programme. There were also concerns about the timeframe needed to develop the model within PESP II. The component has remained on hold.
DFID to task TAMO to analyse teacher pay/profit margins/negotiability/affordability and use this analysis to take a final view on implementation of minimum wages in LCPS. The analysis should also highlight risks and mitigating factors in the context of longer-term PEF thinking.	TAMO completed an initial analysis of the affordability of teachers if PEF schools were to pay the minimum wage equivalent to all teachers and supporting staff. The analysis estimated that per child payments under the current PEF funding model would need to increase by 50% to 100% to meet minimum wage levels depending on the number of hours worked. / The review team recognise that this is an area of ongoing concern and policy work for DFID that needs continued attention. DFID has previously had discussions with the GoPb and PEF to explore how LCPS employers could raise their wage structure for teachers in their schools. Securing any significant changes to PEF’s policy on teacher pay will require further work with PEF and other GoPb stakeholders to ensure their buy-in, as well as a better understanding of the potential impacts on the LCPS sector as a whole. / Teaching nevertheless represents one of the few professions that are currently available to women in Pakistan and the majority of PEF teachers employed are women. Whilst these teachers may be willing to work for low wages, there is a strong case for PEF to revisit its policy and progress improvements to ensure the wages in its partner schools are fair given prevailing labour market conditions and legal obligations. In addition to the general principle of paying an acceptable wage, low salaries are likely to affect turnover of staff in LCPS and potentially affect teacher motivation and performance.

Recommendations
1. CSO partners (BRAC and GET) should disaggregate target by gender and partners to reach, track and provide disaggregated data on children with disabilities, children from minority backgrounds and teachers.
2. Partners should define child friendly schools, such as disability friendly, the location of toilets and safety issues faced by girls and agree a standardised package/checklist.
3. DFID should step up its engagement with PEF commensurate with emerging risks around capacity and scale-up and work closely with TAMO to re-energise its technical assistance to PEF.
4. PEF should build on work already started to finalise an institutional strengthening plan which reflects the additional risks and demands anticipated from expansion. This should include clear plans to strengthen its identification, payment and monitoring processes.
5. PEF should consider consolidating its plans into a clear strategy that sets outs its longer-term vision for delivering quality education through the LCPS sector that determines the population segments it aims to target.
6. DFID should continue discussions with PEF and other GoPb stakeholders on teacher pay in PEF schools and advocate for progressing improvements in PEF’s policy and practices to support the payment of fair wages. To inform these policy discussions, DFID might need to support further work in the sector to improve understanding of the possible impact of paying higher wages on labour market dynamics and the LCPS sector.

Output Title	Enhanced demand for education
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones ( Nov 2015)	Progress (Dec 2015)
5.1 Number of: / (i) tertiary level scholarships for poor and able student (boys: girls) / (ii) higher secondary scholarships for poor and able girls per year.	(i) 310 tertiary scholarships[17] / (ii) 6,500 higher secondary girls scholarships	Met expectation / (i) 210 tertiary scholarships / LUMS: 149 (against its target of 210) / PEEF: 61 (at the time of review against an academic year target of 110). / (ii) 8,500 new higher secondary girls’ scholarships
5.2 Additional children (ages 6 - 11) enrolled in priority districts as part of CSO-led demand side interventions	30,000 additional out-of-school children enrolled in 2 priority districts / (Bahawalpur and Bahawalnagar)	Met expectation / 30,398 additional out-of-school children enrolled in Bahawalpur and Bahawalnagar
5.3 Communication events held, materials distributed, disaggregated by type of audience	Develop communications materials for SED to distribute amongst teachers and field staff regarding the overall reform process and objectives / Conduct a baseline perception survey to measure current attitudes of public towards the reform process	Met expectation / Key material developed and distributed. / Baseline perception survey conducted in December 2015 (results awaited).
[17] The higher secondary girls’ scholarships are only for women. The tertiary scholarships are based on merit and need only. We know how many of these went to girls and the same has been reflected in the narrative.

Key Points
This output seeks to stimulate demand for and increase access to equitable education by supporting boys and girls to progress through the system to higher education. DFID funding to PEEF and LUMS contributes to this output, as well as funding to CSOs through the programme’s priority districts component. This output targets some of the poorest and most disadvantaged girls and boys in Punjab to get a quality education and improve their livelihoods. The programme is also working to hold up the beneficiaries of this output as examples of the success that is possible within their communities and increase demand for quality education.

Output Indicator 5.1
DFID is funding graduate-level scholarships through PEEF at the seven best universities in Pakistan. 500 scholars are due to be reached over the course of the programme, with 110 scholarships planned to be provided in the current year. These scholarships are awarded on the basis of merit and need, but without quotas on gender or any other criterion. Though PEEF had awarded 61 scholarships against the target of 110 at the time of the review, they are on track to meet their own target for the year as the process of awarding the scholarships for the academic year is still running.

PEEF also provides higher secondary scholarships to girls from the 11 priority districts in Punjab, again on the basis of merit and need. In the first two years, DFID provided direct support to around 17,000 girls from one of the most under-developed areas of Punjab. This year PEEF exceeded its target of 6,500 scholarships, using savings generated by assigning fewer residential scholarships to award a total of 8,500 scholarships.

PEEF has a robust management system in place with regular external audits and quarterly progress reporting to DFID. The organisation celebrated the award of 100,000 scholarships at an event in October 2015, attended both by the Chief Minister and DFID. Lastly, to promote a sense of contribution back to their communities, PEEF has been working with scholars to gather information on out-of-school children in their local communities which shall be shared with the Education Department to support their enrolment.

LUMS provided fewer scholarships than planned; 149 against the logframe milestone of 210. Around 24% of the 450 scholars currently being supported by DFID are female (i.e. 108 out of 450) and scholars come from across Pakistan including Baluchistan and FATA. At an equity level, LUMS should consider how to encourage more applications from women and from under-represented areas of Pakistan, although their activities this year in conducting outreach to 67 cities and towns across Pakistan is a positive move. Currently around half of those receiving DFID scholarships are receiving 100% funding based on their need, and half are receiving 80-99% funding. Given the ambition of this output to reach the neediest students, DFID should review the partial funding component.

LUMS launched its ‘LUMS Ambassador Program’ last year, aiming to use NOP scholars as social leaders to increase awareness of and demand for the benefits of higher education. This year, 150 students were trained and 102 conducted structured workshops in their communities. LUMS plans to expand this programme to non-NOP students.

LUMS has also launched a residential summer coaching scheme, seeking to broaden the application base for places at LUMS. Links have already been forged with PEEF, meaning that all PEEF intermediate scholars funded by DFID are now being invited to apply for the LUMS summer coaching scheme.

In conclusion, PEEF significantly exceeded the target on higher secondary girls’ scholarships, and remains on track to meet its graduate scholarships target by the end of the academic year. LUMS fell short of meeting its assigned target due to both the limited availability of candidates meeting both the merit and need-based criteria, as well as the limited outreach of the university to such students. LUMS should be focusing on how to increase its outreach to deserving students by strengthening the summer coaching program and targeting it towards more deserving scholars, especially girls.

Output Indicator 5.2
Through DFID support, Strengthening Participatory Organisation (SPO) is working in Bahawalpur and Bahawalnagar districts. It is responsible for identifying and enrolling out-of-school children, conducting outreach and community mobilisation, and establishing partnerships with different school systems (government, low-cost-private, community and non-formal). SPO is monitoring partner schools to ensure that children attend regularly, stay in school and learn more. SPO faced some challenges around securing the cooperation of education officials, poor school infrastructure and accessibility to school sites.

SPO achieved the milestone of 30,000 out-of-school children enrolled. To date, it has enrolled 30,132 (16,124 girls and 14,008 boys), with an estimated 50 children dropping out. Around 850 teachers were trained on creating more child-friendly classroom spaces. Work has been done to reactivate 156 school councils that were not functioning across the two districts. 30 new locations were identified for the National Commission on Human Development (NCHD) feeder schools in Bahawalpur, 11 of which were established. SPO conducted social mobilisation through community meetings, meetings with mothers, meetings with local leaders and using information from DFID-supported AAWAZ[18] programme centres[19]. SPO have taken a variety of approaches in incentivising out-of-school children to enrol, including providing assistance for some on transport costs, sourcing furniture in schools where a need was identified, and providing school materials to all (bags, stationery). The British Council is also implementing a programme in partnership with Educate a Child (EAC) to expand its Ilm-Possible programme. The programme is focusing on mobilising communities and enrolling out-of-school children through trained community volunteers.
[18] AAWAZ – Voice and Accountability Programme is a community development programme that contributes to the empowerment of poor women, minorities and excluded groups by increasing their participation in decision making and politics at the local, provincial and national levels. It supports communities help themselves, and helps them to connect to, and work with, government and the state for improved services and legal frameworks.
[19] AAWAZ Agahi Centres are information centres in the DFID supported AAWAZ programme at the Union Council level; these centres provide information to communities on women related issues and support is available for them on their issues.

The review team was concerned at the monitoring capacity of SPO. While their intervention has allowed them to reach their milestone, the approach taken appeared to lack strategy, with SPO providing against the incentives identified by families or schools. SPO were also unable to explain which of their selective interventions were having the least or the most impact on enrolment because they are not currently tracking this information. Because school materials are being provided to all beneficiaries, it will also not be possible to assess the relative impact that this intervention has had on enrolment. Unless this data is collected, this activity risks failing to achieve the objective of the pilot in identifying which approaches hold the most promise for maximising enrolment.

SPO also raised a concern in terms of communications. In the initial period of their operation, SPO expressed challenges with TAMO, though those had since been resolved. SPO mentioned that they would appreciate a closer direct working relationship with DFID.

Output Indicator 5.3
Communication material was developed for SED and distributed amongst teachers and field staff regarding the overall reform process. Parho Punjab Barho Punjab (Learn Punjab, Prosper Punjab) posters were developed and disseminated to all districts and district-level launch events were held across Punjab. SLO posters are being printed for distribution to all primary schools. A large event celebrating the 2018 education goals was held in Lahore under the banner of ‘Parho Punjab, Barho Punjab’ and a major initiative was launched to increase enrolment of children in schools along with a focus on quality education. The TAMO DFCs attended these events and reported that it was well organised and received by participants. PEEF also held a well-publicised 100,000 scholarships event in October 2015 and has received support from TAMO on the development of communications materials. The quality of TAMO’s support in this area appears to have been highly regarded by partners.

The baseline perception survey to measure current attitudes of the public towards the reform process was conducted in December 2015 as part of the Nielsen household survey. The results of this are yet to be shared by Nielsen as they experienced some delays. The perception survey on education reform has two main components: to gauge respondents’ views and opinions, and understanding and awareness of the current education reform. The two components can be combined to produce a variety of indices that will allow cross-sectional and time-series comparisons of perception across different indicators such as gender, age, demographic indicators and occupation.

Summary of responses to issues raised in previous Annual Reviews (where relevant)
Recommendation 2014/15 Annual Review	Response
Short-term: DFID to ensure both LUMS and PEEF have clear plans in place for outreach activities to be initiated in the coming months. In particular, LUMS should strengthen its Ambassador scheme, learning from good examples internationally. One suggestion is to look at models where students conduct outreach activities as a form of paid work experience following their final exams. Links to Alif Ailaan, a DFID-funded education advocacy programme, are also recommended to complement the outreach and publicity work conducted at local level.	TAMO has supported PEEF to develop and implement several outreach activities, described above. / 150 scholars were trained under the LUMS Ambassador programme and 102 have conducted workshops in their communities. / TAMO has reached out to Alif Ailaan to collaborate on the Education Ambassador programme for 2016; Alif Ailaan is interested to support the NOP programme reach out to underprivileged children and plans for this are in place.
Short-term: TAMO should work with LUMS to establish more robust management information systems to enable better reporting and tracking of students, alumni and scholarships. The DFID team should also investigate the trends in the number and costs of LUMS scholars, the proportion of the scheme DFID funds and the administration costs to ensure that confidence in the targeting and value of the scheme remains.	TAMO has developed and shared recommendations with LUMS for the management information system (MIS), and work on producing the MIS will start in Spring 2016.

Recommendations
1. Scale up the LUMS summer coaching session and explore the possibility of a special summer coaching session specifically for DFID-funded higher secondary girls (PEEF) programme.
2. Consider whether DFID funds should only be used for those who need 100% LUMS scholarships, or whether to continue fund partial scholarships. Activities to encourage more applications from the neediest should be considered, perhaps through a reallocation of funds and a greater emphasis on outreach. These could include a foundation course to bring students up to standard, focusing on the neediest and on girls.
3. Conduct a study on the economic and social returns of the LUMS and PEEF scholarships, capturing the income and non-income benefits including reasons for beneficiaries of the intermediate scholarships (PEEF) not progressing to higher education.
4. DFID, TAMO and SPO should assess the various demand-side interventions together with the findings from the TPV and determine what learning and evidence can be obtained from the pilot to inform any future extensions of the model.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Sector budget support is the largest budget component under PESP II comprising 40% of the total programme value and 66% of spend to date. It provides financial support to the GoPb’s budget for delivery of primary and secondary education services. District government expenditure on salaries, the vast majority of which is on teachers, formed 79% of total spend in the sector in 2014/15. Allocations in 2015/16 are similar at 77% suggesting no major changes in the last year. Spend on non-salary budget has often been squeezed as a result of real increases in teacher salaries. Final spend on non-salary items in 2014/15 was equivalent to 6.8% of the total current budget spend, down from 10.1% allocation. The non-salary allocation share for 2015/16 is 8.4% which is a positive increase on the spend share for the previous year.

PEF makes payments to schools on a per student basis. Total spend is therefore influenced by the numbers of children enrolled. The underlying cost driver for these payments is school operating costs. In the last year, PEF raised its per student payment for primary from PKR 450 to PKR 550 (£3.50). This was the first change in at least two years and reflected existing plans to increase rates in line with increasing school costs. PEF has also stipulated that schools pass on 50% of the increase to teachers in the form of increased salary.

Of all the PESP II components, the school infrastructure component has suffered the largest changes in costs over the last year. As detailed under output 3, average unit cost estimates to build a classroom have almost doubled in the last year. Humqadam are of the view that costs have now stabilised and any further changes in costs are unlikely to have any significant impact on outputs. Inflation does however remain a concern. Prices of raw materials rose approximately 12% in the last year and, together with labour costs, may rise further. Costing projections will need to build in inflation as well as potential exchange rate risk to manage any further upward pressure on costs.

DFID operates output-based contracts with TAMO, the Roadmap Team and also with the CSOs, through TAMO. It does not track actual delivery costs in-year. Staff fees constitute the largest cost item in the TAMO and Roadmap budgets constituting approximately 69% and 90% respectively. This reflects the fact that delivery of technical assistance is human resource intensive. These costs are driven by the hourly rates, the number of hours charged, and the composition of senior and more junior staff engaged on the programme. Savings were made in the last contract amendment by identifying synergies in staffing across the TAMO and Roadmap teams. TAMO estimates these staffing savings at around £1.3 million. Per child costs for the CSO component may need to be reviewed following a decision about scale-up. Both BRAC and GET highlighted higher than anticipated costs in Punjab’s priority districts due to remoteness and availability of suitable school sites and qualified teachers.

Scholarship costs have changed little since the start of the programme and are driven by course fees and student living costs. PEEF has managed to award 2,000 more scholarships than planned in 2015 due to savings from fewer than anticipated boarders. The largest planned spend item in the PIEP is the top-up voucher for children with mild disabilities. This is not expected to change unless initial findings in the pilot determine that the voucher is not set at the right level to incentivise enrolment.

VfM performance compared to the original VfM proposition in the business case
The original business case assessed VfM on the basis of the impact of additional enrolment and improved quality of education on future expected wage earnings, and undertook a qualitative assessment of wider societal benefits. It estimated a benefit cost ratio for the programme of 1.5. Since then, the scope of the programme has changed and the estimates in the appraisal are no longer comparable. There is however an increasing range of data available to assess VfM within the programme. In this vein, a new monitoring and VfM framework was developed over the last year to improve analysis of progress and VfM over the course of the programme. The following assessment draws on data collected for the framework.

Sector budget support, influence and technical assistance
Since the start of PESP II, DFID’s funding to the Punjab education sector has directly funded the equivalent of approximately 830,000 primary and secondary children through three years of schooling. By linking disbursements to progress on reform activities, sector budget support is also delivering value by incentivising changes that impact on the system as a whole. Early successes are visible from the Disbursement Linked Indicators (DLIs) that DFID attached its sector budget support to up until 2015, and which were aligned with the World Bank’s Punjab Education Sector Project. The first phase of teacher rationalisation was implemented despite resistance and merit-based teacher recruitment was introduced, opening the door to better teachers. The government has adopted the free textbook initiative as well as the provision of non-salary budget to schools which was extended in July to all 36 districts in the province. The non-salary budget provision has seen some large schools receive over PKR 800,000 (£5,160) a year for the first time to cover basic needs and fund small-scale improvements and short-term staffing gaps. Previously, schools were receiving a maximum of PKR 20,000 (£130) a year which was far below the needs of the school. These reforms appear to be taking root but will need further monitoring over the coming years to better assess their impact on education outcomes.

It is too early to assess the impact of DFID’s extended sector budget support on institutional strengthening under the new results framework. If successful, the value of this support should be reflected in better management across the core functions of the sector with a strong focus on learning. Progress against results at the end of this financial year will be a good indicator of whether the sector budget support is working to this effect. As recommended elsewhere in the review, the prospects for delivering good VfM for this component will depend on the extent to which the RAF is at the centre of DFID’s engagement. This will also require clear alignment of the technical assistance to the Framework and strong buy-in from the government if it is to be a success.

Sector budget support is designed to afford DFID access and influence with the GoPb. For support that this year represents less than 1% of the education budget, the access is substantial. It is difficult however to discern the extent to which the Roadmap stocktakes and DFID’s roadmap assistance are in fact the main influence enabler and driver of DFID’s current relationship with the education sector. The fact that technical assistance dominated conversations with government officials during the review is a positive sign that DFID’s relationship might be maturing towards one focused primarily on technical support.

The CM’s commitment to education has helped to raise the profile of education on the government’s agenda. Budget allocations have also increased net of DFID’s support, but there is scope to put additional pressure on increasing resourcing for the sector, given the ambitious reform plans. The budget allocation for basic education[20] constitutes close to 20% of the overall Punjab budget for 2015/16. It represents an estimated 14% nominal increase on actual spend in 2014/15 and a 3% increase on the final 2014/15 budget allocation[21]. Performance on budget utilisation in 2014/15 is satisfactory but with some room for improvement. The government spent 84% of its final development budget for basic education and 75% of its non-salary current budget[22]. Despite being a small share of the overall GoPb education budget, DFID’s sector budget support can and should be used as a lever to push for more and better spend. In the last year, lobbying efforts on the budget concentrated on securing additional commitments to the non-salary budget in support of the 2018 goals and increasing the GoPb’s own commitments to PEF. Allocations to PEF have subsequently increased in line with DFID’s own financial contribution and demands. Due to the way in which the budget is classified, it has been more difficult to determine additionality commitment in the non-salary budget, but overall non-salary budget allocation has increased.
[20] Excludes allocations for tertiary education
[21] Final budget refers to the budget after re-appropriations and supplementary grants. Source: Budget execution reports based produced by TAMO and presented to SED.
[22] Execution as a percentage of original budget allocations was 58% for non-salary current budget and 80% for development budget. Original budget numbers are however subject to change in-year due to block transfers to districts. Percentage spend of final budget is used in this review.

The value of the Roadmap is largely manifested in the efficiency gains in delivery that the monitoring routines and stocktakes have helped to drive. The most cited example is teacher attendance which has risen from a 2010 baseline of 81% to over 90% in 2015. The change translates into a rough estimate of almost 29,000 additional teachers present in school with clear benefits for child learning. Notable changes have also been seen in the percentage of functioning facilities, as demonstrated in the chart below. Student attendance, which is less in the direct control of the school but likely to be responsive to school conditions, has seen less marked change to date.

Attribution to the Roadmap is not direct but it was clear from the review team’s district visits that it is a strong driving force. The sustainability of the approach or the ability for it to drive longer-term reforms in quality that yield slower results remains to be seen. There are some potential negative benefits to watch for. Monitoring has a transaction cost and too much can distract from quality delivery. There is also a risk that targets create perverse incentives to focus on a subset of priorities at the cost of others and that better performance is incentivised in an unsustainable manner through fear of penalty as opposed to real buy-in to the reform process. The impact of these negative impacts is not known but should be closely monitored.

Core Roadmap Indicators (Baseline - Dec 2015)

The VfM of technical assistance depends on its success in supporting sustained changes in capacity and the delivery of well-managed reforms, whilst recognising that the technical assistance should not be in complete control of the process. It is evident that TAMO are thinking more about effective capacity building and are right to avoid building models of dependence in departments. TAMO’s work with PCTB on textbook development is a good example of successful working with different layers of the organisation to deliver higher quality books. TAMO estimates that its value addition to the textbooks translates into a one-off cost valued at approximately 20% of the annual cost to the government to deliver a textbook. The value of TAMO’s efforts can be quickly eroded however if institutions are not on board. The review has highlighted reservations voiced by some departments about TAMO’s style and type of expertise provided. As recommended in this review, reviewing the balance in approach and composition of support to the institutions TAMO works with and ensuring that capacity is strengthened at several layers of management should help to mitigate this risk to delivering good VfM. Technical assistance needs to work on the basis of partnership with the government, driven by demand and aligned with GoPb priorities.

PEF
DFID’s funding is contributing to a government-supported expansion in PEF enrolment from 1.6 million children in 2013/14 to 2.8 million in 2019. To ensure funding is additional, DFID’s support is conditional on the GoPb increasing its own contributions. The government increased the PEF budget from PKR 8 billion (£51.6 million) in 2014/15 to PKR 10 billion (£64.5 million) in 2015/16, in line with an approximate PKR 2 billion (£12.9 million) allocation from DFID.

PEF delivers education of a quality at least comparable with government schools at lower cost and, increasingly, is expanding access in areas where government schools are less present. In 2013/14, it cost PEF an average of £40 a year to support a child in a PEF school. The cost will have risen slightly in 2015 to reflect the increase in per child monthly payments but remains low. By comparison, the average spend per child in a government school in 2014/15 was approximately £100, whilst in the UK the average annual spend on a child in primary school is upward of £3,000 a year[23].
[23] Rough estimate based on IFS 2015 Schools Spending Briefing note and previous right to information responses. Actual spend likely to be higher once all spend be relevant authorities is included. Costs do not take into account differences in purchasing power parity.

PEF schools are publicly funded but privately managed. The partnership with PEF gives the school owner freedom to manage their business providing they meet a set of quality criteria. Whilst facilities are pretty basic, initial evidence suggests that learning is generally better than in government schools. The most recent six monthly learning assessment (September 2015) included PEF schools. The report found that whilst only 75% of children were able to demonstrate all basic learning outcomes, this was better than performance in government schools where 61% of children met the basic learning standards.

Performance and quality do however need to be improved further. PEF currently pays PKR 550 (£3.50) per child per month in primary school[24]. This amount covers basic costs and is enough to incentivise enrollment and supply of schooling but it provides limited scope for schools to invest substantially in quality improvements or increase teacher pay. The review already advocates for PEF to progress improvements to its policy and practice to enable the payment of higher wages. Whilst not yet tested, VfM might also be enhanced by increasing support on quality and teaching, or introducing initiatives to extend credit to schools looking to invest in quality improvements. Evidence could then be used to inform any scale-up.
[24] The amount is increased for children in middle and higher grades.

Infrastructure
The original VfM proposition for this component was that classrooms could be built of higher quality and at lower cost than classrooms contracted through the Government’s own Communication and Works Department. Fiduciary risk would also be lower.

The current unit cost following the first round of contracting has risen to an average of PKR 950,000 (approx. £6,000) per classroom from an original estimate of PKR 350,000 to PKR 450,000 (approx. £3,000). The average for a classroom contracted through the Communication and Works Department is estimated at between PKR 1.1 million and PKR 1.2 million (approx. £7,400). Whilst the cost increase has eroded the strong economy case for the intervention, there is still potential to deliver VfM. The quality innovations listed under output 3 should generate efficiency gains by delivering classrooms of higher quality as well as building a skill base of new techniques that can be replicated elsewhere. These quality enhancements are currently being validated as part of the TPV. Humqadam’s community engagement model also has the potential to improve the VfM of the intervention by building communities that are incentivised to maintain and thereby extend the lifetime of the classrooms. The capacity building of contractors learning the new techniques should also mean that they will replicate these in future contracts, especially the improvements that are cost-saving or cost-neutral.

Assuming no further cost increases, the new classrooms are expected to improve the learning environment for an estimated 440,000 children[25] by reducing over-crowding, and, with the quality innovations, creating more comfortable classrooms. Potential impacts may include increases in learning outcomes, enrolment and retention of children in the beneficiary schools. The extent of these impacts depends however on how the new construction is linked with other resourcing decisions, including the supply of teachers who can teach well, provision of missing facilities and sufficient non-salary budget to maintain the new classrooms in a good condition. There may be scope within the PESP II programme to strengthen these links by engaging PMIU and district education officers. It is recommended that as part of Humqadam’s monitoring and evaluation strategy, education outcomes are clearly tracked pre- and post-construction to improve understanding of the impact.
[25] Based on an estimated 40 children per classroom.

Scholarships
Expected wage earnings in Pakistan tend to increase disproportionately for those with a higher or tertiary education. A graduate from the LUMS scholarship programme receives an average starting salary of PKR 71,235 (£460), compared with the average household income of a scholar, estimated at PKR 46,089. Similarly, although data on the salaries of PEEF graduates was not available, the maximum annual household income of a PEEF scholar does not exceed PKR 25,000 (£160), suggesting that the relative earnings for the individual graduate are likely to be high. Per student costs are however also higher, ranging from an estimated annual cost of PKR 9,600 (£60) for a high secondary PEEF scholar to PKR 36,000 (£230) for an undergraduate PEEF scholar, and up to PKR 664,800 (£4,300) for a scholar at LUMS. The trade-off is potentially more children supported at lower levels of education where individual private returns may be lower but where the overall balance of economic costs and benefits to society may be more favourable. Capturing the full range of benefits from an education in quantitative terms can be difficult to do. The review has recommended further analysis of the socio-economic returns of the scholarship programme to judge the extent of this trade-off.

PEEF has been successful at targeting low-income households and, with DFID support, has expanded its scholarships for girls in priority districts. This is important from an equity perspective as the 68% participation rate for girls of secondary school age in priority districts is almost 10 percentage points lower than for boys.

LUMS has a sophisticated process to validate the eligibility of scholars; however it has struggled through its outreach activities to locate sufficient candidates that meet both the poverty and merit criteria. As a result, over 50% of the DFID-funded scholarships extended provide less than 100% financial support to scholars. The difference – which can be up to PKR 10,000 (£65) a month - is covered by the scholars themselves. This arrangement potentially erodes the VfM of DFID’s support if LUMS is unable to serve the poorest. Whilst LUMS operates a gender neutral selection process, the share of girls attending its outreach events is also low. As recommended under output 5, this needs addressing if LUMS is to meet DFID’s equity concerns as part of its overall VfM assessment.

Last year’s review noted that efforts by the scholarship programmes to harness other potential spillover benefits, in particular demonstrating the value of an education to a wider audience, had been limited. LUMS has since established an Ambassador programme, which requires all scholars to complete some outreach activities. The impact has not been formally assessed, although anecdotally, the number of applications from a particular school tends to increase once one student has been successful in obtaining a scholarship.

Civil Society Organisations and Inclusive Education
BRAC receives approximately PKR 700 (£4.50) per month to enrol and support a child in school. GET receives the same amount but overall resource costs per child are likely to be higher as some costs are reportedly internalised by GET. The real value from these interventions comes from their demonstrable ability to enroll out-of-school children in some of the hardest to reach places where neither PEF nor Government schools have a presence. The standard PEF payment of PKR 550 (£3.50) is supplemented to reflect that these are new mobilisation efforts operating in difficult areas.

The numbers enrolled in the first nine months of operation are impressive. Retention figures for the first few months of enrolment are not yet available but should be reviewed as part of the TPV. If these numbers are sustainable and the models are able to deliver quality schooling cost effectively, then it is possible PEF will continue these partnerships. An original rationale for this intervention was the need to tackle obstinate access issues in new ways and learn from what works. Partnering with PEF should in theory help to internalise this learning, providing both partners use each other to this effect.

SPO has also been successful in enrolling large numbers of out-of-school children in a short timeframe, but opportunities in the pilot to assess the relative effectiveness of different interventions have not been properly exploited. This was an important part of the original rationale. Evidence of a clear and strategic approach is limited and there seems to have been little use of existing evidence to determine what incentives might work best. SPO has drawn on its expertise in community mobilisation, but it is less clear how these activities might translate into a scalable and demonstrable model for demand-initiated enrolment. As recommended under output 5, DFID, TAMO and SPO should assess the interventions and determine what learning and evidence can be obtained from the pilot to inform any future extensions of the model, recognising the specific role that these interventions are expected to play in improving equitable access to quality education.

The PIEP voucher scheme has only been in operation for a few months and has not started supporting enrolment. If successful, it has the potential to provide an education for children who would otherwise not be attending school at an estimated monthly average running cost of PKR 650 (£4) per child. There is also scope to generate savings if children can be successfully enrolled into mainstream schools rather than placed in special education schools which tend to cost more to run and are only available at Tehsil level, the administrative level below the district office.

Assessment of whether the programme continues to represent VfM
On balance, PESP has met expectations on delivery over the last year. In the last year[26], PESP has supported an estimated 230,000 children in government schools through its budget support and 8,759 new young people through scholarships. PESP II has also supported approximately 320,000 children in school through its support to PEF and enrolled over 60,000 out-of-school children through CSO-led initiatives. Providing these children receive a quality education, the returns to them are likely to be high. PESP II support for system reforms has made some progress, but these take time to take root and translate into improved outcomes across the sector, which is where VfM will ultimately be judged. Attribution will always be challenging, but sustained changes in learning outcomes and access across target areas and groups will help to determine if these reforms are taking effect.
[26] Results for sector budget support and support to PEF calculated using the DFID Results Framework methodology and reported as part of DFID results for the period 2014/15.

Direct attribution to PESP II is difficult but there are early signs of positive change. Progress against programme outcomes is generally on track. Participation rates, whilst still too low, have increased across all levels, gender and priority districts between 2011 and 2015. New data is beginning to provide an insight into progress on learning. The latest learning assessment showed a small improvement in the percentage of government school children meeting basic learning outcomes from 58% to 61%. Evidence of progress was also identified in a DFID-supported expenditure tracking survey by the World Bank (WB) in 2015[27]. The survey traced public expenditure down to the primary school level in Punjab for three spend areas and matched this against the quantity and quality of service delivery found within the school. The survey found positive improvements in the provision of missing facilities to schools and the share of girls enrolled, but noted that improved budgeting and planning processes that take account of schools’ needs would improve the effectiveness of education spend.
[27] Tracing the Flow of Public Money. Punjab: Expenditure and Quantity of Service Delivery (EQSDS) in the Primary School Sector (2015), The World Bank (awaiting publication)

The VfM analysis suggests most of the PESP II components are delivering value. It is harder to judge if the programme is working as effectively as a whole to maximise VfM. Opportunities to exploit synergies across the components should be clearly identified and pursued. The scholarships component would benefit from a review of its relative VfM in the programme. Learning should be central to the priority districts component to ensure the value of the interventions is extended beyond the direct beneficiaries. Finally, a tight focus on core reforms under the RAF would help ensure sector budget support is working as effectively as possible.

Quality of financial management

Complexity
PESP II is an extremely large programme with many different funding mechanisms and partners, both direct and indirect. These include sector budget support, direct contracting with for example with ASI, McKinsey, IMC Worldwide; and indirect grant funding via TAMO. These also cover the span of advance funding, funding in arrears and input and output-based financing. Partners range from government, to large multinational for-profit corporations with rigorous financial controls, to small national-level CSOs for whom their contract on PESP II represents a significant portion of their overall budget.

Each of these mechanisms has been selected for the individual intervention with a view to having the highest impact. Nevertheless, taken together, especially at the overall scale of £420.5 million, risks remain high. There are relatively small numbers of DFID staff attributed to this project to monitor finances and additional financial challenges for DFID in undertaking frequent travel to Lahore.

Our line of sight on funding to TAMO, the technical assistance for the Roadmap and IMC is good, and all three have robust financial procedures in place, which have for the large part mitigated against any financial management risks. Our line of sight for indirect partners and their financial management processes is weaker.

Partner Capacity
Challenges expressed in last year’s Annual Review over an absence of technical assistance to support sector budget support have to some extent been addressed now that TAMO is fully established. Nevertheless, influencing the timely release of financial aid down to the education sector, namely support destined for PEF and PEEF, remains a challenge. The review team heard anecdotally from departments that funds held by the Finance Department are not always transferred within expected timelines.

Capacity of some indirect partners is more challenging, and it is with these partners that DFID has less of a direct relationship (CSOs like GET and SPO). In addition, concerns over the financial management capacity of PEF given staffing issues contributed to the reduction of a disbursal of funding from £12 million to £6 million in December 2015.

The review team also encountered anecdotal evidence that some organisations are very reliant on TAMO support for planning, which affects their finances. The Special Education Department, for example, has been allocated around PKR 1.2 billion, but at this stage has only developed a PC-1 planning document which covers spend of around PKR 400 million and was drafted by TAMO. On questioning over their future plans, they referred us to TAMO.

Accuracy of forecasting / timing of disbursements
Over the FY 2015/16, programme spend has been broadly in line with forecasts, with discrepancies fairly small where they took place (see chart below). At this point of programme implementation, £164 million of the available £420.5 million has been spent, which is in line with plans.

At this stage, the school construction work under output 3.2 is severely delayed and consequently spending significantly under forecasted amounts. This is despite the news that higher unit costs will decrease the overall number of classrooms that can be built with the available funds. Evidence suggests that spending on this component will return to the higher forecast amounts from around April now that construction is under way. Payment by IMC Worldwide of construction firms is being done by milestones based on progress on sites. Completion of work on sites is due to begin from March.

Audit
Audit arrangements vary by programme component. For sector budget support, the latest report from the Auditor General of Pakistan covers the period 2013-14 and was issued on 19 March 2015. It covers both DFID and World Bank funds over the period. Although the opinion is that overall performance is good, the management letter highlights a series of issues relating to ineligible or unjustified expenditure, and finds that procurement and contract management needs to be improved.

PRAP has carried out an audit of TAMO and shared the draft report with DFID. As this has not been finalised, the findings cannot yet be shared. In addition PRAP annually reviews progress on PRAP Audit findings in PMIU, PCTB, PEF and DSD. A baseline report is currently being compiled on IMC-Humqadam.

The most recent audits received of LUMS and PEEF were carried out for financial years 2013/14 and 2014/15 respectively. Similarly, the audit report for PEF for 2014/15 is available and is unqualified in opinion.

IMC Worldwide have internal audit in place through KPMG, and an external audit is currently being carried out by Ernst & Young, which will be shared with DFID when completed.

Public financial management
Public financial management remains a crucial pillar of the sector budget support to the GoPb and features as one of the five main areas of the RAF. DFID conducts a six-monthly review of the progress against RAF with the SED alongwith all associated departments. TAMO facilitates this discussion. There has been some positive progress in this area including, for the first time, conduct of a payroll audit of SED as well as the introduction of discussions of budget performance of the previous financial year led by the Secretary. The active involvement of the PESP II team helped put pressure on development budget releases in-year. Overall budget utilisation for the financial year 2014/15 reached 89%.

A lot needs to be done however in terms of follow-up of the pay roll audit recommendations as well as making budget utilisation discussions a quarterly routine. The government also raised with the Annual Review team the need to build capacity of financial management both at the provincial and district levels. DFID’s Sub National Governance (SNG) programme is working with the technical assistance under PESP II to strengthen financial management systems in education as well as providing support in drafting District Education Authorities’ establishment and financial rules. This collaboration aligns with SNG’s own objectives to strengthen service delivery and becomes even more important in view of the upcoming roll out of DEAs in all 36 districts of Punjab.

DFID’s SNG programme is providing additional support to the education sector by developing a Medium Term Budgetary Framework (MTBF) in SED. DFID also convenes a quarterly public financial management coordination meeting to minimise duplication of assistance across DFID programmes.

Recommendation
The PESP programme team should seek urgent assurances over the discrepancies described in the Auditor General’s 2013-14 report, insofar as they relate to DFID funds or represent the potential for mismanagement of DFID funds.

Date of last narrative and financial report	Each intervention receives narrative and financial reports in line with distinct requirements based on the nature of the relationship. The internal PESP II delivery plan contains links to the latest reports.
Date of last audited annual statement	Each intervention receives audits in line with distinct requirements based on the nature of the relationship. The internal PESP II delivery plan contains links to the latest audits.

E: RISK

Overall risk rating: Low/Medium/High
Medium

Overview of programme risk
The Annual Review team assessed the PESP II risk matrix. Most of the risks are still valid and the overall assessment of risk is unchanged from medium, but is variable across the different outputs. More detail is given in the risk matrix (Annex I), which also forms part of the internal PESP II delivery plan.

The review team has some general observations on the structure of the risk matrix:
- It would be helpful if the risks are loosely grouped under different risk headings such as political, delivery, institutional capacity, fiduciary and reputational.
- Risk one and three can be merged and possibly reworded as: ‘Lack of political will and resistance to reform and mitigation strategies can be developed for three levels: political, management/bureaucracy and teachers.
- Mitigation strategies should be time-bound to enable follow-up by the team.
- Risk six could be made more explicit keeping in view the recent decentralisation taking place, setting up of DEAs, and the possible impact on delivery.

The PESP II team should consider incorporating a few additional risks into their risk matrix:
1. School reconstruction/IMC component: Market or other forces result in cost increases which in turn reduce the total number of classrooms that can be constructed.
2. School reconstruction/IMC component: Conventional contractors are unable to deliver quality, scale, cost and/or speed of construction required.
3. DFID staffing: High turnover of staff over the next six months could weaken relationships with partners and affect the momentum of the programme.
4. Capacity of government officials: High turnover of heads of key organisations such as PEF, DSD and PMIU can affect the implementation of the programme.
5. Roadmap: The Roadmap process has the potential to distract from the key reforms focusing on quality which requires a longer time period to show impact.
6. Sustainability: Technical assistance fails to build the capacity and ownership needed to support sustainable reforms.
7. Capacity of PEF: PEF lacks the capacity to expand effectively in line with targets whilst ensuring minimum quality standard. PEF’s capacity to deliver core programmes is weakened by the implementation of the expansion plan and the new initiative of outsourcing low-performing government schools to the private sector.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Progress is on track against the targets except for output three (reasons already mentioned under output 3).

Performance of partnerships
PESP II is a large and complex programme with many stakeholders. It can be challenging in such a programme to ensure sufficient focus on all stakeholders, and intensity of scrutiny adjusted to reflect differing and evolving levels of need of the different partners.

TAMO – ASI/McKinsey
Following on from a Key Supplier Management (KSM) visit by ASI Senior Management in April which resulted in a change of senior personnel, including the establishment of a new ASI Country Director position, ASI and DFID relations have become more open and candid with an emphasis on tackling and overcoming the challenges to progress and solutions. The ASI Chief Operating Officer assumed the Director position for the TAMO contract on a temporary basis. There have been notable improvements in consortium relations and improvement in programme management, supported by stronger senior oversight. Senior-level monthly calls with DFID have been used constructively to monitor progress. The process of agreeing the Year 2 workplan and budget was notably more effective and efficient than previously; and there was rationalisation of positions at the Director level. However, DFID remains concerned that two years into a five-year contract, 60% of the budget for TAMO has been spent. This has already been taken up in discussions with TAMO. This is only in part due to an increase in scope from the original TORs. The KSM process continues to be an important part of managing this contract and relationship.

There appeared to be concerns among departments consulted that they are not getting the technical assistance they need, and that the balance between a ‘facilitative’ and a ‘directive’ approach to technical assistance was not right for them. However, departments were also not always clear on how the technical assistance should best be delivered, making any resolution to this dissatisfaction challenging.

TAMO depends a lot on their management expertise rather than technical knowledge. Feedback from several stakeholders consulted suggests that this balance should be reviewed. The reporting and monitoring mechanisms for TAMO needs to be firmed up and all important programme decisions should be taken after consultation with the DFID team, including relevant workstream leads. This has been impeded by the lack of relevant staff (Social Development Adviser for over a year). TAMO’s upcoming contract renewal should be a good time to re-evaluate outputs, work plans and deliverables to ensure good VfM.

Punjab Education Roadmap - McKinsey
The contract with McKinsey to provide technical assistance to the Punjab Education Roadmap expired in May 2015. An OJEU process was launched to appoint a successor supplier. Two bids were received and the incumbent supplier McKinsey won the contract to provide technical assistance to the Roadmap to March 2019 in line with the end of PESP II. This is currently in its inception phase and the focus will be on building the sustainability of the Roadmap process within government, together with an exit strategy.

Government of Punjab departments
The partnership with the GoPb is through sector budget support and technical assistance. In the summer of 2015 a new RAF was negotiated with the GoPb to govern the release of sector budget support. This delinked DFID sector budget support from the previous arrangement whereby disbursements were made in line with WB DLIs under their own PESP II agreement (see other donors section). Funds were withheld due to partial achievement of RAF Year 1 targets including the drafting of institutional development plans.

SED and its allied departments (PMIU, PEF, DSD, PEC) respect the partnership with DFID and are appreciative of DFID’s substantial assistance to the GoPb’s education agenda. They have however requested more direct contact with DFID personnel, which the PESP team should consider addressing according to the relative needs for support of different organisations.

Secondly, SED and its allied departments stressed the desire for a more collaborative role between the technical assistance team and relevant agencies. The issue is of course complicated by less clarity on the part of government agencies on their exact needs and a strong preference for technical experts as opposed to generalist technical assistance to address any identified needs.

Priority districts and scholarships – BRAC, GET, SPO, PEEF, LUMS
The DFID PESP II team should consider providing additional support to the Special Education Department on inclusive education, as well as to the CSO partners BRAC, GET and SPO both from a quality and fiduciary perspective. LUMS management should be encouraged to be more proactive in finding solutions to continuing gender inequality in their scholarship recipients. PEF is also a strong candidate for quality technical assistance support especially with respect to their monitoring framework besides a review of anti-corruption measures in place. PEEF have performed well over the review period, and are led by a strong senior team with a clear vision.
School construction – IMC Worldwide
The partnership with IMC Worldwide, acting as Humqadam in Pakistan for the school infrastructure component, has been through a challenging year. Progress has been slower than anticipated by IMC and the large increase in unit costs was identified late, despite assurances to DFID in the months and weeks prior to the announcement that costings were still on-track. This has also affected levels of confidence in this component, which is politically high-profile, within both provincial governments.

DFID has responded by enhancing its own staffing on the contract including appointing a ‘virtual’ Senior Responsible Owner (SRO), as well as initiating regular conversations between the DFID Head of Basic Services Group and IMC Worldwide’s Managing Director. Better progress is being made, as Humqadam staffing increases in strength and numbers, and more school construction contracts are awarded. DFID must maintain close monitoring until such a time as full confidence in delivery returns and most likely beyond that time, given the delivery and reputational risks for DFID of any future slippage in costs, pace or quality. As of yet, DFID HQ does not have a formal KSM management process with IMC Worldwide but an informal arrangement by DFID Pakistan using the KSM template could be used for this contract.

Other donors
The World Bank and DFID continue to have strong partnership in education in Punjab. The World Bank PESP II programme ended in July 2015. Initially DFID sector budget support disbursements to the GoPb were linked to World Bank DLIs. However, the delay in design for the World Bank’s successor programme PESP III has meant a gap in World Bank funding. The World Bank’s PESP III programme has an indicative value of US$ 300 million (£200 million) over five years and is scheduled to go to their Board in March.

Recommendations
Begin a formal KSM process with IMC Worldwide in Pakistan.

Asset monitoring and control
Asset registers are held for the TAMO and Humqadam contracts as well as for the scholarships programmes.

Robust asset registers are shared with DFID regularly and the DFID team carries out spot-checks of these assets annually. DFID is not creating assets under the sector budget support component as all assets are owned by the GoPb.

G: CONDITIONALITY

Update on partnership principles
The published business case states that funding is based on the Government of Pakistan’s commitment to poverty reduction, protection of human rights and strengthening public financial management and accountability, as set out in the UK’s Development Partnership Arrangement (DPA) with Pakistan.

The new Partnership Principles Assessment (PPA) is regularly discussed with the Government of Pakistan and the text shared every quarter. The PPA was discussed most recently at the annual bilateral assistance talks on 15 October 2015. The PPA sets out the Government of Pakistan’s commitment to the four partnership principles as demonstrated through its policies and actions: reducing poverty and achieving the Millennium Development Goals (MDGs) and Sustainable Development Goals; respecting human rights and other international obligations; strengthening financial management and reducing the risk of funds being misused through weak administration or corruption; and, a commitment to strengthening domestic accountability.

DFID Pakistan’s assessment is that the government is demonstrating a credible commitment to the four principles. DFID can therefore continue to deliver sizeable programming on budget. Progress towards the MDGs and poverty reduction is proceeding, albeit slowly given the challenges. Progress on human rights is mixed. On public financial management and anti-corruption the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels. Elite capture and its influence is often cited as a concern. Recent pressures on international non-governmental organisations have led to a downturn on domestic accountability; but there is cautious optimism about a new registration process.

The majority of the UK’s investment in PESP II is in sector budget support financial aid and technical assistance to GoPb. The political will to reform, combined with ownership from SED and the improved capacity of various departments, has significantly aided progress. There has also been strong commitment on the part of the Finance Department, as evidenced by its work with DFID’s SNG programme; however the public financial management component under PESP II needs to be further strengthened.

The GoPb is working on a Medium Term Budgetary Framework (MTBF) and a formal fiscal monitoring framework has been put in place. DFID’s work on the Public Expenditure Review has also led to a focus within the overall budgeting process on primary education as well as on non-salary and development budget expenditure. Under PESP II, the SED is establishing a financial management cell besides working on budget planning and expenditures.

Lastly, the GoPb has made some good strides on accountability both through enacting the Rights to Information Act as well as establishing a Citizens’ Feedback Initiative to inform the government about service delivery issues. In the education sector specifically, the government is now using a tablet-based monitoring system to hold education managers and teachers to account.

H: MONITORING & EVALUATION

Evidence and evaluation
The contract for the formal evaluation (covering both Punjab and Khyber Pakhtunkhwa education sector programmes) was awarded in early 2013 to OPM. The inception phase was subject to a series of delays, including necessary alterations to the sub-evaluations set out in the terms of reference (TORs). The contract was terminated in January 2016 by mutual agreement and other options are being explored, including utilising the Pakistan data from the forthcoming centrally managed Research on Improving Systems of Education (RISE) evaluation and/or commissioning specific research on narrower research questions.

Monitoring progress throughout the review period
A broad range of monitoring information and evidence is regularly reported on across this project. Different reporting mechanisms exist for different aspects, sometimes by component and sub-component but also by stakeholder (for example, quarterly reports from LUMS and PEEF). A variety of monthly and quarterly reports are received from stakeholders (for example PEEF/LUMS) and regular meetings have been established to discuss progress (for example the DFID team monthly monitoring meetings with TAMO). More formally, the bi-monthly stocktake of the Roadmap provides a high-level forum to discuss a range of key education indicators (such as student attendance and missing facilities) with the CM, Secretary Education and Sir Michael Barber, as the UK Special Representative for Education in Pakistan.

In response to the previous Annual Review recommendation, attempts have been made to bring together the evidence and monitoring information, through the development of a monitoring and VfM framework. This is still in progress, but it is hoped that this can inform the future quarterly review meetings and embed the use of evidence into the regular project management cycle. Given the range of data now available on the sector, DFID should ensure TAMO follows through with plans to establish a data monitoring group to build consensus and confidence in education data. The data group would also benefit from participation of government officials.

Overall the Annual Review team felt that greater use and ownership of the logframe is required. In some cases, data was not available (for example a gender breakdown for school attendance or complete data on school council meetings) making assessment of logframe progress difficult. Similar issues were highlighted in the last Annual Review and whilst some improvements have been made, regular monitoring and increased ownership of the logframe is required, in line with good programme management practice.

The DFID team assigned to work on PESP II has been through several changes this year, some of which have tested DFID’s ability to maintain close oversight of all components. DFID’s capacity to monitor has been constrained in recent months by the temporary secondment of the education adviser based in Lahore to another post, as well as simultaneous constraints in DFID’s administration budget which have resulted in field visits to Lahore only possible for the Roadmap stocktake meetings. There has also been a significant turnover of DFID programme staff, notably the change in Senior Responsible Owner in January this year following the departure of the PESP II Programme Manager. This has notably reduced DFID’s ability to maintain and foster relationships with key stakeholders. As mentioned earlier, DFID relies heavily on TAMO for information on many aspects of the implementation of PESP II, which represents a risk, especially in cases where TAMO sub-contracts partners. In contrast, there has been progress on DFID staffing to manage the school infrastructure component, which was increased to allow for closer performance management of IMC.

Assignment of responsibility for different aspects of PESP II among DFID staff could be further clarified. The complex arrangements in a programme like this require especially clear reporting lines and responsibilities. A matrix management approach might be appropriate and worth piloting.

Recommendations
1. DFID and TAMO need to work together over the coming months to ensure the monitoring and VfM framework is fully operationalised and integrated into regular monitoring, and adapted as necessary so that it meets the needs of the programme. Consistency in updates and scrutiny of data will need ongoing attention.
2. Ensure TAMO follows through with plans to establish a data monitoring group to build sector consensus and confidence in education data. The data group should include participation from government officials to ensure the work is also taken forward within government.
3. Although the logframe was revised in response to the previous Annual Review recommendations, greater ownership and use (by both DFID and TAMO), is now required to ensure that progress is regularly monitored and means of verification targets and methodologies are clear to all involved. The Review team have proposed some recommendations regarding revision of some of the indicators (Annex II).