Annual Review - Summary Sheet

Title: AAWAZ Voice And Accountability Programme, Pakistan
Programme Value: £34.5 million		Review Date: May 2016
Programme Code: 114433	Start Date: May 2012	End Date: May 2017

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	B	A	A	A+
Risk Rating	Moderate	Minor	Moderate	Moderate

Summary of progress and lessons learnt since last review
Senior Responsible Owner (SRO) with DFID AAWAZ Programme Manager conducted the annual review (AR) through field visits, meetings with partners and using M&E reports. All AR 2015 recommendations were compiled into an action plan and completed before 30 April 2016.

AAWAZ is DFID Pakistan’s largest demand side voice and accountability programme. It aims to ensure that democratic processes are more open, inclusive and accountable to citizens in Pakistan. It focuses on: women’s and minority rights, their political participation and decision making; tolerance and prevention of violence; and increasing the accountability and responsiveness of the state to citizens’ demands for improved service delivery.

AAWAZ had its best year to date. It met 90% of its indicator milestones, exceeded half of them by at least 20% and some by 50% with an increase in the pace and the quality of programming that achieved the following results:

- 5,125 active AAWAZ groups / networks with 176,955 members (90,430 women, 86,408 men and 117 transgender people);
- AAWAZ has now reached over 3 million poor people directly and over 6 million indirectly;
- 1,342 women (370 KP, 972 Punjab) stood as candidates for local government elections and about 280 (203 KP to reserved seats and 77 Punjab to general seats) were elected;
- Every quarter, over 74,000 women accessed the AAWAZ Aagahi Centres (citizen advice bureaus) for support and advice and information about public services;
- 7,000 engagements through khuli kachehries (citizen townhall meetings) and one-on-one sessions with government decision-makers across two provinces to raise demands for better services in health, education and water/sanitation; benefited over 3 million people;
- Early Response Mechanisms in place in all (4,500) AAWAZ village fora (AVF) preventing conflict that benefited almost 3 million people;
- AAWAZ campaigns against hate speech and violence against women and girls (VAWG) and for improved local government reached 2.65 million people; and
- Domestic Violence Act, 2016 in Punjab passed with the direct input of AAWAZ partners and their behind the scenes lobbying.

The knowledge, attitude and practices (KAPs) survey provides a mass of examples of transformations in individuals and groups. 50% of men and women reported change in their knowledge, attitude and practices regarding participation of women in political and public spheres and violence against women and girls (VAWG) as compared to 25% indicated in the M&E assessment conducted in March 2015. Over 90% of the survey respondents were aware of VAWG and pro-women legislation as compared to 56% indicated in the baseline 2014/15.

AAWAZ Aagahi Centres (citizen advice bureaus and community meeting places) and their female Resource Persons are becoming key places for ordinary poor people to connect to state services.[1] They also continue to be as a safe meeting place for women outside of the family to network, learn and study. Local government line agencies continue to publicise their special events (polio vaccination, health camps, etc.) and programmes displaying their materials and posters, bringing government services closer to communities.
[1] In this context, state citizen engagement enables poor women, men and the excluded to speak for themselves about their needs and priorities for services directly to government. In addition, it enables government to understand, budget and plan for the needs of all their citizens to provide inclusive, effective and efficient services.

The re-focusing of AAWAZ work away from conflict resolution to the prevention of conflict has allowed village community groups and structures to identify the triggers for violent conflict and empowered them with options for pre-emption. For example, in Nankana Saib the AAWAZ district forum (ADF) brought together Sikh and Muslim religious leaders to quickly de-escalate a conflict that had arisen after young people had thrown stones at a Sikh religious procession. The dialogue prevented an inter-faith conflict and increased community cohesion.

The intended result of all AAWAZ interventions is to build social capital[2] - alliances and networks to build common ground, solidarity, mutual understanding and support for collective action and positive change. It also builds an alternative to patron-client relationships, acts as a social safety net and can resist the trend towards an ever more unequal, divided and intolerant society.
[2] OECD defines social capital as “networks together with shared norms, values and understandings that facilitate co-operation among groups”.

Key lessons learnt:
Investing in targeted, good quality capacity building can result in real changes and pay huge dividends.
The changes seen are particularly remarkable at village level and in the personal transformations that have taken place for so many women at all levels. Having first class specialists and a strong leadership team in the Management Organisation (MO) to provide quality technical support and guidance makes a big difference to the quality, scope and impact of the programme.

Where changing social norms is a necessary precursor to overcoming obstacles to genuine, inclusive development and democracy, it is unrealistic to expect quick fixes. The time taken for AAWAZ to reach its current high level of engagement and results, illustrates the need for patience when embedding this type of large, complex programme that must strengthen its own internal capacity and social capital to develop social capital externally.

The benefits of successful influencing on service delivery go beyond improving local governance and impact of having better services. This work also increases the community’s confidence in the AAWAZ programme and it gives credibility to the involvement of women and minorities.

Summary of Main Recommendations:

Strengthen state citizen engagement by
(a) deepening the linkages between local government and AAWAZ community structures to build trust and to ensure that women, minorities and the poor people are not excluded; and
(b) investing in all 450 Aagahi Centres through further capacity building of female Resource Persons to reinforce their learning, explore innovative ways of outreach and avenues for sustainability.

Consolidate existing achievements and further develop the participation and leadership of women, minorities, and young people through staying engaged at all levels.

Systematically share and apply lessons
(a) across all implementing partners to spark innovative improvements and bring all districts up to the same quality of programming; and
(b) across other DFID programmes like sub national governance (SNG) and other demand side programmes in health and education to maximise the benefits.

Empower the steering committee (ASC) to set the strategic direction and oversight through use of synthesised programme and financial management information.

Continue to strengthen VfM and financial compliance
(a) strengthen collection of disaggregated data/information on beneficiary streams directly attributable to programme interventions for VfM; and
(b) ensure all audit recommendations are implemented to continue to strengthen financial systems and move the programme from medium to low risk.

Safeguard DFID’s investment to date
AAWAZ should be given a time and cost-limited extension to build avenues for sustainability, identify areas for a new programme and to ensure continuity until a new voice and accountability programme is up and running in 2019. Otherwise, we risk losing the investment to date if the programme ends 21 May 2017 as planned. This is all the more important in an environment where space for civil society and demand side action is continuously being eroded.

An annual review action plan will be used to monitor progress against recommendations.

Acronyms
ADF	AAWAZ District Forum
AF	Aurat Foundation
APF	AAWAZ Provincial Forum
AR	Annual Review
ASC	AAWAZ Steering Committee
AUF	AAWAZ Union Council Forum
AVF	AAWAZ Village Forum
CBO	Community Based Organisation
CNIC	Computerised National Identity Card
COP	Communities of Practice
CPO	Community Partner Organisation
CSO	Civil Society Organisation
DAI	Development Alternatives Inc.
DCC	District Coordination Committee
DCO	District Coordination Officer
ED	Executive Director
ERM	Early Response Mechanism
EWS	Early Warning System
FDI	Foreign Direct Investment
GBV	Gender Based Violence
IRR	Internal Rate of Return
JASAT	Jamhuriat Angan se Aiwan Tak (training)
KP	Khyber Pakhtunkhwa
MIS	Management Information System
MO	Management Organisation
MOU	Memorandum of Understanding
MPA	Member Provincial Assembly
NGO	Non-Government Organisation
PARR	Programme Analysis, Research and Results
PMC	Programme Management Committee
RAG	Research Advisory Group
RTI	Right to Information
SAARC	South Asian Association for Regional Cooperation
SAP-PK	South Asia Partnership-Pakistan
SDC	Sustainable Development Conference
SDGs	Sustainable Development Goals
SLU	Strategic Learning Unit
SMT	Senior Management Team
SPO	Strengthening Participatory Organisation
UC	Union Council
UN	United Nations
UNDP	United Nations Development Programme
USAID	United States Aid
VfM	Value for Money
VAWG	Violence Against Women and Girls

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-114433/documents
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-114433/documents

Project Outline
The AAWAZ Voice and Accountability Programme is a five year £34.5 million programme (May 2012 - May 2017). It operates at local, provincial and national levels, directly reaching over 3 million and indirectly reaching over 6 million poor and marginalised people - women, men, minorities and transgendered. It operates across 4,500 villages in 45 districts in (26) Punjab and (19) Khyber Pakhtunkhwa. AAWAZ is implemented through Development Alternative Inc. (DAI) with leading Pakistani civil society organisations: South Asia Partnership (SAP PK); the Aurat Foundation (AF); Strengthening Participatory Organisation (SPO); and Sungi Development Foundation. It is DFID Pakistan’s largest demand side programme.

Impact: Stable, inclusive and tolerant democracy in Pakistan
Outcome: Democratic processes in Pakistan are more open, inclusive and accountable to citizens.
Outputs:
- Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa (KP) and Punjab.
- Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa (KP) and Punjab.
- Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa (KP) and Punjab.
- Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa (KP) and Punjab.

##### Context
##### Pakistan is increasingly characterised by high levels of violence and insecurity, poverty, inequality, deteriorating human rights and increasing religious intolerance. Women in Pakistan face extreme gender inequality. The World Economic Forum Global Gender Gap Index now ranks Pakistan144 out of 145 countries.[3] 7.1 million girls are out of school and half of all women are illiterate, rising to 70% in rural areas. Violence against women and girls (VAWG) in Pakistan is commonplace. The situation for religious and other minority groups is also precarious. Pakistan remains one of the least peaceful countries in the world: it lies 154th out of 162 on the Global Peace Index[4] and 4th out of 162 countries most affected by terrorism. [5]
[3] This places Pakistan between Yemen at 145 and war torn Syria at 143. Scandinavian countries are at the top, with UK ranking 18th, USA 28th, Bangladesh at 74th, India at 108th, Saudi Arabia at 134th sitting above the bottom 10 countries all of which have predominantly Muslim populations.
[4] Institute for Economics and Peace, index 2015 see: http://www.visionofhumanity.org/#/page/indexes/global-peace-index Syria ranks 162, Iraq 161, Afghanistan 160, South Sudan 159, Central African Republic 158, Somalia 157, Sudan 156, DRC 155.
[5] Only Iraq, Afghanistan and Nigeria have higher scores. Figures from the Institute for Economics and Peace, index 2015 see: http://www.visionofhumanity.org/#page/indexes/terrorism-index/2013/PAK,AFG,IRQ/OVER

Pakistan faces other significant economic and social challenges. The economic cost of militarisation, lack of security and involvement in domestic and international conflicts is believed to be some US$40 billion a year.[6] Corruption has undermined public confidence in the state and the rule of law. Poor governance and the dominance of military, bureaucratic and political elites has distorted resource distribution. Pakistan has over 66 million people living in poverty whilst the gap between rich and the poor is widening. Provision of basic services falls far short of international norms and many groups, including women, are excluded from access to services. As a result, over a third of Pakistanis remain poor, and under-educated. Weak implementation, enforcement, and under resourcing of laws and policies designed to protect and enhance the rights of women, children and minorities compounds their disadvantages and perpetuates their inequality.
[6] ibid

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The outcome: Democratic processes in Pakistan are more open, inclusive and accountable to citizens.

AAWAZ contributed towards good governance by protecting and expanding existing public spaces for poor and excluded people especially women, minorities, and transgendered. They are able to express their views, needs and priorities without discrimination or retribution. In addition, they are empowered to take action to improve their lives and to engage with government for better services.

AAWAZ (45) districts have seen an increase in the accountability and responsiveness of local line agency officials and politicians in response to AAWAZ forum activities. Aagahi Centres at union council level are being used by line departments to publicise their programmes and activities. In Okara district of Punjab 102 disabled persons, 19 of whom were women, were registered with the social welfare department with the support of AAWAZ to access services. Influencing by AAWAZ fora at village, union council and district levels has resulted in service delivery improvements in health, education and water that benefitted more than 476,000 thousand households (equivalent to approximately 3.332 million individuals). In Haripur district of KP, as a result of strong lobbying and advocacy, funds were allocated to upgrade a school to higher secondary level benefiting children from a community of 70,000 people in the surrounding area.

When AAWAZ began work, a key challenge was that many women were confined to their houses, and had almost no contact with the outside world. During the course of the project, dramatic transformations in attitudes and behaviours meant that in the past year 82,000 women have actively participated in AAWAZ community meetings and in 43,000 in khuli kachehries - citizen townhall meetings. In AAWAZ areas, more than 2.48 million women have registered for computerised national identity cards (CNICs) giving them access to state services, eg 75% are now registered to vote. In the recent local government elections, 1,342 women stood as candidates and some 280 were elected. A further 325 of them are expected to become councillors in Punjab through the nomination system - see output one. However, inclusion in democratic processes goes beyond the formal political sphere. Nearly 229,000 AAWAZ women hold leadership positions – in AAWAZ groups and networks, as members of local Women’s Assemblies, AAWAZ Change Makers and Aagahi Centre female Resource Persons. They are actively involved in decision-making, giving them increased voice, choice and control over their lives. AAWAZ is working at scale and having impact.

The organized targeting that includes minority and socially excluded groups has created more inclusive and representative groups and networks. AAWAZ fora have held peace melas (festivals), supported the anti-hate speech campaign, and developed early response mechanisms to pre-empt violent conflict that have benefitted some 2.759 million people (as of February 2016). The campaigns on violence against women and girls (VAWG) and anti-hate speech have prompted national debates and district governments are engaging closely with AAWAZ fora to map and pre-empt inter/intra faith conflicts.

Overall output score and description
The project has exceeded expectations this year and is marked A+. This mark is supported by the very good achievements against milestones, but it also recognises the real improvements in programme quality across all outputs, in strategic influencing, in financial compliance and in M&E.

Key lessons
AAWAZ is filling a major governance gap by overcoming the disconnect between government, state and citizen. This critical engagement between people and state gives government a better understanding of community needs whilst citizens are holding them accountable to improve their performance. This in turn helps reduce service gaps, empowers women and men to play an active role in their own development and contributes towards the achievement of results. It amplifies and multiplies the impact of AAWAZ against all of the programme outputs.

Peace mapping and power analysis exercises are proving extremely helpful in enabling forum members and the community to identify the types and triggers of conflict, and explore ways to pre-empt those conflicts. The consultative way in which the exercise is being done brings communities together and moves them away from being helpless bystanders to active agents for concrete action to preserve peace and harmony in their communities. Communities are now actively using these tools.

The innovative and comprehensive Jamhoryiat Angan Se Aiwan Tak’ (JASAT) training programme (Democracy: from Home to Parliament) focused on citizens at district level and below. Through it, local communities and individuals have increased their understanding of the key areas: gender, women’s rights and masculinity[7]; prevention of violent conflict; and influencing to improve government services including government accountability. The benefits of this training approach is elucidated well in the KAPs, where three-quarters of men and boys (76%) possessed knowledge of basic human and women rights, on how to participate inclusively with women in public events and how to provide a safe environment for women to make their views known through using an inclusive listening style. This is helping to make men active gender champions supporting positive change for women at the local level.
[7] Looking at men’s gendered roles in society and expectations including men’s behaviours and the impact on gender equality and women’s empowerment.

The reaching out of AAWAZ to external development partners and to government through evidence-based advocacy has not only raised the profile of transgendered, women in politics and the role of minorities but also ensured that the wealth and depth of AAWAZ research is disseminated and used widely. This is highlighted well through AAWAZ reaching out to UN and development partners to support the development of a voice and accountability index, building on AAWAZ data sets.

The importance of walking with civil society implementing partners by the management organisation (MO) cannot be underestimated. The strengthening of the MO technical capacity in parallel with supporting implementing partners to improve their compliance frameworks has not only contributed to the deepening of the quality and the quickening of the pace of delivery, but has also improved its efficiency, transparency and value for money. It helped to provide a clear vision and much better understanding of what success looks like with renewed energy, vision, tools and systems to implement.

Key actions
AAWAZ should continue to link state and citizen through actively engaging with local government from village, union council to district levels. This will build shared skills, lead to increased understanding and respect between all parties, and could result in regular cooperation with communities in the planning, delivery and monitoring of government services.

AAWAZ work is time and labour intensive and the challenges faced to implementation vary across both provinces and all 45 districts. It is not surprising that not all districts are at the same level. In the most difficult and conservative districts, special efforts to ensure inclusion should be enhanced. The most effective methods being practiced in these districts should be documented, shared and implemented across the programme to systematise learning.

AAWAZ provincial fora (APF) in KP and Punjab continue to be important mechanisms to trigger change at the macro level, and forge strategic partnerships with provincial ministries and key decision makers. Parliamentarians in these fora will continue to need support to enhance APF performance and tangibly influence legislative development.

Has the logframe been updated since the last review?
Yes. Based on recommendations in the 2015 annual review qualitative indicators and milestones were included. In addition, changes were made to reflect the new approach to output 2 from conflict resolution to conflict prevention. Revisions to the logframe were proposed in discussion with DFID and formally approved in September 2015.

## C: DETAILED OUTPUT SCORING

Output Title	Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa (KP) and Punjab
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Under this output, the programme is expected to increase the participation of women and excluded groups in community and other decision making processes at local, provincial and national levels. It is also expected to decrease the number of men and women reporting acceptance of violence against women. AAWAZ exceeded expectations in the implementation of this output achieving an A+ score overall whilst deepening the quality of programme through the rollout of the Jamhoryiat Angan Se Aiwan Tak’ (JASAT) (Democracy: from Home to Parliament) training package.
OUTPUT 1 Scoring Against Logframe
Indicator(s)	Milestones	Progress	G
1.0 Number of women and girls participating in awareness raising sessions and change agent training on participation in public spaces and political processes and women's right to freedom from violence and receiving change-agent training	55 women master trainers trained on additional modules / 35,000 women & girls (50% of total women forum members) made aware of pro-women laws, early marriages, customary practices & women rights of political participation / 50% women in AAWAZ fora demonstrate positive change in knowledge (pre/post evaluation) / 4,500 women trained as change makers & at least 50% able to establish circle of influence in AAWAZ fora where 2 out of 4 issues (gender, discriminatory practices, exclusion & right to information) are discussed & regular follow-up is maintained	60 women lead trainers (24 in KP) trained across four partners.44 women trained (20 in KP) on JASAT II. / 77,051 women and girls (33,989 KP, 43,062 Punjab) made aware by Feb’2016. / 83% women in AAWAZ fora demonstrate positive change in knowledge. / 6,807 women (2,583 KP, 4,224 Punjab) trained as change makers. More than 70% established circle of influence and sharing information with an estimated 20-30 women in a village on all four themes.	A++
1.1 (Qualitative ) Cadre of women in AAWAZ Forums demonstrating: / a. Knowledge on basic human and women rights / b. Confidence of participation in public forums and AAWAZ initiatives / c. Communication skills-listen and value women with attention and compassion and without judgment, advice or interruptions / d. Confidence in decision making and their follow-up / e. Negotiating, influencing and relationship skills	50% sample size with at least 3/5 skills / Knowledge on basic human and women rights / Confidence of participation in public fora and AAWAZ initiatives / Communication skills-listen and value women with attention and compassion and without judgment, advice or interruptions. / Confidence in decision making &their follow-ups. / Negotiating, influencing and relationship skills	76% of respondents had least 3/5 skills with one-third of women respondents possessing all five skills.	A+
1.2 Number of men & boys participating in awareness raising sessions & change agent training on role of male socialization as root causes of gender inequality, women's right to freedom from violence and participation in public spaces and political processes and receiving change-agent training	55 men master trainers trained on additional modules / 35,000 men and boys made aware on pro-women laws, early marriages, customary practices and women rights of political participation / 50% men in AAWAZ fora demonstrate positive change in knowledge (pre/post evaluation) / 4,500 men trained as change makers &at least 50% of them able to establish circle of influence in AAWAZ fora where 2 out of 4 issues are discussed and regular follow-up is maintained	50 men lead trainers (22 KP, 28 Punjab) trained across four partners. 47 men trained (25 KP, 22 Punjab) on JASAT II. / 70,381 men and boys (33,808 KP, 36,573 Punjab) made aware by Feb’16. / 77% men in AAWAZ fora demonstrate positive change in knowledge on women’s rights. / 7,161 men (3,029 KP, 4,132 Punjab) trained as change makers with over 70% of them having established circle of influence and sharing information with around 20 men per village on all four themes.	A+
1.2 (Qualitative) Number of men & boys in fora demonstrating: / a. Knowledge of the role of male socialisation masculinity, power, privilege & control as root causes of gender inequality b. Communication skills – to listen to girls & women with attention & compassion, & without judgment, advice or interruptions / c. Improved relationship skills - involving girls and women in decision making	50% sample size with at least 1 of 3 skills / Knowledge on the role of male socialization, masculinity, power, privilege and control as root causes of gender inequality / Communication skills – to listen to girls and women with attention and compassion, and without judgment, advice or interruptions / Improved relationship skills - involving girls and women in decision making	85% men improved their communication skills-to listen with attention and to value the inputs of women.	A++
1.3 Number of women actively participating in AAWAZ fora and public events and in leadership positions	65,000 women actively participating in forum meetings / 13,000 actively participating in women assemblies/khuli kachehries / 13,500 women in leadership positions and 30% of them demonstrating at least 2/5 skills: / Knowledge of women rights &legislative agenda / Communication, influencing & relationship skills / Play effective role in campaigning/contesting for LG bodies election and/or women assemblies / Possess budget literacy & carrying out local level advocacy / Take initiatives to voice and address VAWG in their community	82,701 women actively participated in fora. / 43,978 women actively participated in women assemblies/ Khulli kachehries and Youth conventions / 19,763 women in leadership positions[8] / Over 51% of them demonstrating 3 out of 5 skills / 80% know women's’ rights & legislative agenda / 85% of women leaders are confident to contest elections. Almost all have supported local community women re CNIC and voter registration. / 76% have actively participated in developing local action plans & advocacy initiatives	A+
1.4 Number of women receiving CNICs, registered as voters & supported by AAWAZ to file nomination papers in the local government elections	85% women receive CNIC / 75% women voters registered / 500 women and 100 excluded group members emerged as candidates for local government elections	82% women receive CNIC 145,967 in total[9] / 73% women registered to vote; 99,680 in total[10] / 1,342 women (370 KP, 972 Punjab) as candidates for local government elections. Around 280 candidates won these elections.	A
[8] This includes 8,948 office bearers, 414 Aagahi resource persons, 1,481 women assembly members, 6,877 change makers and 2,043 women in sub-committees.
[9] The lower than expected figures for Computerised National Identity Card (CNIC) and voter registration by February 2016 are due to the government halting CNIC registration between September - November 2015. As CNIC registration is a prerequisite for electoral registration, this also affected the number of new women voters registered. Registration re-opened in January 2016 and the final percentage of women voters registered is confidently expected to exceed the milestone target by a large margin.
[10] See 12 above

Key Points
AAWAZ continued to raise the bar on women’s leadership last year. Not only through the provincial forum’s successful lobbying for the enactment of the Punjab Domestic Violence Bill, 2016, but also through the rollout of JASAT trainings. The JASAT trainings, conducted twice in the reporting period, on gender, masculinity, leadership, prevention of violence and inclusion reached about 147,432 women, men and excluded groups’ in all 45 districts.

AAWAZ capitalised on this training to empower women to participate as candidates and voters in Punjab and KP local government elections. In some areas of KP, women cast their votes for the first time in the history of the region. In that context, it was remarkable that 370 women in KP stood as candidates, and 280 of them were elected to office. In Punjab, 972 women filed their nomination papers for local election, but the government decided that women should be appointed and not elected to reserved seats. It is expected that 325 women from AAWAZ will become councillors under this process.

AAWAZ created, trained and mentored a cadre of women and men change makers, through JASAT, to become role models in their communities. Their role is to reach out beyond the AAWAZ forum membership and create circles of influence on women's rights, gender-based violence, inclusion and conflict prevention. The further capacity building of Aagahi Centres female resource persons in the past year strengthened their knowledge to support women enquiring about CNIC (national identity card), voter registration, income support and other government services with 74,000 women per quarter now using centres. It also strengthened the linkages between all community actors including change makers and community women leaders giving them a safe space to plan, network and engage with their communities.

In addition, JASAT training supported women community leaders from village and union council to be elected to District Women's Leader Assemblies. Through the assemblies, women gain experience of stepping into the public sphere and what it means to have to articulate their views as an elected leader.

Building on this, AAWAZ took their focus on women’s community leadership development to the regional level this year. AAWAZ organised a regional conference in January 2016 bringing together women community leaders, supported by civil society, from 5 of the 8 South Asian Association for Regional Cooperation (SAARC) countries.[11] This high profile conference offered an opportunity for the newly trained AAWAZ women leaders to practice their skills at a regional level to make recommendations to the SAARC Secretariat. For example, they recommended that SAARC establish a Strategic Development Goal 5 (SDG)[12] (women’s empowerment) desk in their office to monitor, track and support the realisation of this global goal. The Secretariat will take forward all their recommendations for discussion at the inter-governmental meeting in Pakistan in October 2016.
[11] Afghanistan, Bangladesh, Bhutan, India, Maldives, Nepal, Pakistan, and Sri Lanka
[12] At the United Nations Sustainable Development Summit on 25 September 2015, world leaders adopted the 2030 Agenda for Sustainable Development, which includes a set of 17 Sustainable Development Goals (SDGs) to end poverty, fight inequality and injustice, and tackle climate change by 2030.

Recommendations
Aagahi Centre female resource persons, change makers and women’s community leader assemblies need combined support to reinforce their leadership skills, networks and social capital to consolidate and reinforce their comprehension of AAWAZ key themes.

AAWAZ should continue to strengthen the APFs to use evidence-based research to advocate for progressive legislative / policy development and monitor the implementation of key legislation like the Domestic Violence Act, 2016

AAWAZ should continue to explore options for sustainability and more effective outreach: from mobile Aagahi Centres to innovative ways of increasing CNIC and voter registration, to women in non-AAWAZ rural areas (radio, theatre or other media). The lessons learned should be implemented where possible and well documented for a successor programme.

Output Title	Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa (KP) and Punjab
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output 2 seeks to promote greater community cohesion and tolerance to create an environment in which women and other excluded groups can participate more fully in political and public life. The output design emphasises developing the capacity of citizens to be able to work together to identify and prevent disputes peacefully without recourse to violence. Previously the output included conflict resolution, but this was removed after the 2015 annual review and focus is now solely on conflict prevention. The scoring of A+ reflects the attainment of the miletstones, but also the successful embedding of the new prevention approach that is now yeilding dividends as evidenced below.

OUTPUT 2 Scoring Against Logframe
Indicator(s)	Milestones	Progress	G
2.1 Number of women and men informed about support mechanisms and provided with awareness on non-violent communication and valuing diversity	5 key messages developed and disseminated on non-violence and tolerance (continually reinforced) / 70,000 citizens including 50% women made aware on non-violent communication and valuing diversity / 50% men and women in AAWAZ fora demonstrate positive change in knowledge (pre/post evaluation)	5 key messages developed and disseminated. / 76,660 citizens (31,440 KP, 45,220 Punjab) made aware through awareness raising sessions. Carried on TV cable networks, AAWAZ messaging had the potential to reach more than 1.3 million people in Punjab and KP. / 58% demonstrated positive change in knowledge.	A+
2.2 Number of women, men and socially excluded citizens positively impacted by AAWAZ forum interventions/ members' actions to protect them from discrimination, harmful cultural practices & violence (sectarian, inter-faith, gender based, etc.)	4 million people in 45 districts / Early response mechanisms (ERMs) for dispute pre-emption in place in at least 50% of village fora / Early warning system (EWS) in place for at least 10 of 22 districts identified as very conflict prone	2.759 million (1.21 KP, 1.549 Punjab) people positively impacted as of February 2016. / ERMs in place in 100% village fora. / EWS initiated in 19 districts (4 KP, 15 Punjab). All 45 AAWAZ District Fora have developed peace maps.	A
2.2 Qualitative / Percentage of people in programme districts who consider community pre-emption and cohesion mechanisms to be credible and effective	15%	89.6% of the village respondents are aware of the conflict pre-emption mechanisms and considered them credible and effective. (Source: Annual Follow-on Survey 2016)	A++
2.3 Number of women and excluded group members participating in AAWAZ Fora' local level peace building initiatives (data disaggregated by gender and religion)	20,000 women and excluded groups participating in events and 20% reporting (post event feedback) significant improvement in social cohesion knowledge and attitude	76,660 (59,044 women, 17,616 men from minority groups, 20 transgender people, 240 persons with disability and 2000 non-AAWAZ Forum members) (32,490 KP, 44,170 Punjab) participated in peace events.	A++

Key Points
Since the programme’s inception, 2,759,521 citizens have benefitted through the prevention of 2,300 conflicts including 1,160 domestic violence and 135 interfaith/sectarian conflicts. Over the past 12-months AAWAZ successfully adopted a new approach to output 2, focusing on the prevention rather than the resolution of inter-faith / sectarian conflict and gender-based violence (GBV). See Annex for specific results against output 2 by indicator, millstone and achievement.

Communities used various participatory tools to carry out dispute trend analyses and analyses of GBV, its causes and consequences. They used the conflict tree tool to understand the root causes and triggers for domestic, sectarian and interfaith conflicts. Each village forum prepared its own strategy for preventing violence, which was captured in its Early Response Mechanism (ERM). Change makers with women leaders were deeply involved in this process and play a key role in prevention.

Violence against women and girls (VAWG) was found to exist in 90% of villages, and sectarian and inter-faith conflicts in one third of those villages surveyed. Participants identified the determining factor of domestic violence to be women’s lack of power and control in the household. Women and minorities demonstrated a keen interest in these activities and their participation remains high. Those trained report feeling empowered to address conflict and work together for common solutions in situations that previously had left them as powerless bystanders.

In addition, AAWAZ identified the 22 most conflict prone districts for special attention. Of these, 19 districts developed Early Warning Systems (EWS) by bringing together multi-stakeholder groups to create peace maps. Typically, these groups include district government officials, the police, influential religious scholars, the media, local VIPs, members of official peace committees, ADF members and other CSOs, with the addition of trade unions and religious police in some districts. The EWS involves an iterative monitoring of the triggers of violent conflict and a commitment to collaborative responses from all those party to the development of the system, working through individuals (peace supporters/connectors) identified through the peace mapping exercise that have influence in the community.

The impact of the new approach is evidenced across the board. For example, in Faisalabad city where an inter-faith conflict arose between Muslim and Christian communities over religious processions, the AAWAZ peace committee initiated a dialogue. This resulted in a peaceful agreement between both communities to limit their processions to their own areas. Consequently, conflict during Rabi-ul-awal (Muslim religious festival) and Palm Sunday (Christian religious festival) was avoided in Punjab’s second largest city.

 Recommendations
AAWAZ should deepen the community’s understanding of the difference between conflict prevention and conflict resolution especially in the area of gender based violence (GBV). It is important that communities understand that their role is to create a less accepting environment for domestic violence and to disrupt domestic violence rather than mediating between parties.

AAWAZ needs to seize the opportunity at the district forum level to strengthen the knowledge of its leadership and enhance their strategic role in conflict prevention in order to tackle deep-seated societal barriers to peace, inclusion and social cohesion.

Output Title	Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa (KP) and Punjab
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

This output equips forum members especially women and their communities with skills and tools to connect constructively with government to improve their daily lives and strengthen mutual accountability. This breaks the traditional patron-client relationships through which deals are done and services delivered that exclude the majority. This state citizen engagement enables poor women, men and the excluded to speak out about their needs and priorities for services and to hold government to account. In addition, it enables government to understand, budget and plan for the needs of all citizens for effective and efficient services. Progress exceeded expectations across this output scoring an A+ overall.

OUTPUT 3 Scoring Against Logframe
Indicator(s)	Milestones	Progress	G
3.1 Number of women and socially excluded citizens informed of rights, procedures and hotlines for accessing and demanding improved delivery of services from public officials	450 resource persons of AAWAZ Aagahi Centers equipped with resource material / 450 AAWAZ Aagahi Centers actively used to connect citizens to state services and information / 15,000 females accessing AAWAZ Aagahi Centers / 1 million citizens informed through electronic media	450 resource persons (190 KP, 260 Punjab) of AAWAZ Aagahi Centres trained and equipped with material / 450 AAWAZ Aagahi Centers actively used to connect citizens to services and information. / Over 74,548 women and girls accessed AAWAZ Aagahi Centers / AAWAZ reached an estimated two million people through print and electronic media, telephone and face-to-face interactions.	A+
3.2 Number and types of demands raised with public officials and political representatives in education, health and other priority areas benefiting women, girls and other excluded groups	4,750 demands raised / 5,000 engagements with district and provincial government duty-bearers on policy or implementation issues impacting improved service delivery	16,494 demands (6,720 KP, 9,774 Punjab) raised / Over 7,000 engagements made in khuli kachehries/one-on-one meetings between citizens including women with district and provincial government officials on policy or implementation issues. / The District Coordination Committees (DCCs) established in 16 districts of KP would further enhance state-citizen engagement.	A+
3.3 Number of households impacted by improved service delivery (data disaggregated)	120,000 households benefitted	476,060 households (195,188 KP, 280,872 Punjab) benefitted equivalent to 3.332 million (1.366 KP, 1.966 Punjab) people. / 2,822 demands met: 1,167 education; 790 health; 865 others) / In KP, 1217 demands (528 education, 360 health, 329 others). / In Punjab, 1605 demands (632 education, 392 health and 581 others).	A+
3.4 Qualitative / Cumulative number of demonstrable changes in policy and implementation by local/provincial government in response to public demands where there is attribution to AAWAZ, a proportion of which reflect the voice of women and other socially excluded groups	At least 10 examples from across the programme	15 examples from across the programme exhibiting demonstrable change: / Punjab Government issued a notification protecting the 5% job quota for religious minorities across the province. / Election Commission of Pakistan annulled parliamentary by-election in constituency PK-95, Lower Dir-II, KP for barring female voters. / Further examples can be seen in the output 3 narrative below.	A+

Key Points
The results achieved to date are significant with 16,500 separate service problems identified and 2,800 improvements made in services of which 1,167 related to education and 790 to health. With an average of around 168 households with an average size of just under 7 members positively affected from each improvement, the number benefitting was some 3.33 million people.[13]
[13] The direct results for children were that 200,000 pupils (82,869 girls, 120,496 boys) were prevented from dropping out and around 50,000 (22,000 girls, 28,000 boys) were newly enrolled.

7,000 khuli kachehries - citizen town hall meetings were held to date between citizens, including women members, with district and provincial government officials on service delivery issues for water, health and education. AAWAZ khuli kachehries are planned at union council level but take place in one of its constituent villages once a year. They provide a robust citizen-state interface where government officials and elected representatives are accountable to women and socially excluded. As a result, the khuli katcheri has become an important place in which women and minorities can make their views known.[14]
[14] In very conservative districts, where speaking in mixed fora not yet possible, separate women only khuli katcheries are held

To ensure the sustainability of whatever dialogue AAWAZ has established with government to date, partners’ advocacy should aim to get governments to institutionalise meetings in which citizens and the state can regularly discuss issues of concern and seek mutually agreed solutions. The creation of district coordination committees (DCC) across KP and Punjab has helped institutionalise relationships between AAWAZ and district government. Challenges remain in Punjab in getting all districts to establish a DCC and the signing of a MOU between AAWAZ partners and the government of Punjab could help in this regard.

AAWAZ district groups had great success in the last 12 months lobbying for policy and service implementation changes that benefited women and the socially excluded to protect and enhance their rights. Due to AAWAZ advocacy the Punjab Government issued a notification protecting the 5% job quota for religious minorities across the province. In KP, the Election Commission of Pakistan annulled the parliamentary by-election in constituency No PK-95, Lower Dir-II for barring female voters.
Further results linked to AAWAZ advocacy included:

Punjab
- Anti-hate speech prevented in Toba Tek Singh by reporting incorrect mosque louder speaker use.
- Khushab District Development Plan 2014-15 influenced to include 25 schemes for better service delivery worth £1.66 million (Rp266 million).
- Partnership agreed between AAWAZ and district Ombudsperson Toba Tek Singh to monitor government’s response to community demands raised for better services.
- Working hours, wages and tenure of over 3,000 sanitary workers (15% female) improved in Faisalabad.
- 312 houses (2,184 people) in Toba Tek Singh Christian sector protected from demolition, in spite of pressure from developers.
- 800 people supported to get disability certificates to access services in Lahore.
- Helpline for transgendered people established to provide information, advice and support in Lahore.
- 80 members of the minority (non-Muslim) community accessed vocational skills programme funded by provincial ‘zakat’ fund, previously reserved for Muslims only in Nankana Sahib.

Khyber Pakhtunkhwa (KP):
- More than 300,000 labourers (12% women) benefited from the enforcement of Labour Laws in Industrial Estate Hattar, the province’s biggest industrial estate, in Haripur.
- District Gender Committee (DGC) under the Social Welfare Department established in Swabi.
- More than 200 community midwives reinstated in Pakpattan district for better service delivery.
- Supported the safer participation of 125 women in Lakki Marwat district, local government elections, where women voted for the first time.
- 2 women selected as jury members in Dispute Pre-emption Council of Haripur district.

The focus on strengthening Aagahi Centres continued in the past year leading to their female resource persons being better equipped to advise and guide visitors. Key materials regarding a range of services and programmes are now available in the centres. They have played an important role in enhancing citizens’ awareness of their entitlements and how to access them. We now need to explore avenues for their sustainability in a tripartite partnership between the community, local government and civil society.

Recommendations
Strengthen state citizen engagement and explore avenues for sustainability aspects of the programme through institutionalising links of AAWAZ fora at village, union council and district levels with government.

Make local government work for women, minorities and the poor by ensuring that their voice influences plans and budgets for social services and such plans are cognisant of their needs.

Strengthen AAWAZ district coordination committees through deepening the knowledge of district forum members levels in health, education and water to enable them to better leverage positive outcomes for their communities.

Support better AAWAZ government cooperation by getting an MOU signed between partners and the Government of Punjab.

Output Title	Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa (KP) and Punjab
Output number per LF		4	Output Score	A+
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output 4 comprises programme analysis, research and results commonly referred to by its acronym as PARR. PARR is designed to be AAWAZ’s engine room for knowledge and research to leverage reforms in practice and policy through the development and use of credible evidence.
Its work involves:
analysis and synthesis of monitoring information collected by the consortium partners responsible for outputs 1, 2 & 3;
- follow-up activities to confirm, deepen and add value to partners’ monitoring information, including the identification of lessons and best practice;
- research to strengthen contextual information and/or fill out gaps;
- research and policy briefs that can be used to influence decision-makers ; and
- activities to generate local, national and global debate on empowerment and accountability.
AAWAZ met or exceeded expectations across the implementation of this output and scored an A+.
OUTPUT 1 Scoring Against Logframe
Indicator(s)	Milestones	Progress	G
4.1 Effective evidence-based, qualitative and quantitative M&E systems established	M&E plan implemented across MO and partner organizations / MIS system used to produce better analyses of results	M&E plan developed, approved and being implemented. / 9 quantitative and qualitative assessments completed. / MIS system developed and used by all programme staff and 80% district staff across all 45 districts. Levels of date available and standard of analysis improved significantly	A+
4.2 Number of quality evidence-based research commissioned on select thematic issues and disseminated for policy and practice	10 commissioned studies on selected themes conducted and disseminated / 4 evidence-informed policy briefs for AAWAZ initiatives produced and used by CSO network and research organizations. / 12 Response Fund innovative projects launched / Knowledge base established and functional with effective information sharing between partners	12 studies (migration of minorities, transgender issues, Christian women’s political participation, tracking legislation, best practices in implementation, Swat women's Jirga, Shia-Sunni conflict, voice and accountability index, bazaar-mosque relationship in Punjab, laws of honor killing and rape in Pakistan, Disenfranchisement of Women in Lower Dir, Making Voice and Accountability work for the SDGs,) completed. / 4 position papers/policy briefs (on strengthening local governments, citizenship and exclusion; district health and education issues; and discrimination in the legal profession) completed. / 13 projects valuing at 0.87 million GBP implemented under Response Fund. Among these, 8 projects completed / Knowledge management strategy in place. Plan developed to leverage knowledge products through seminars, lobbying meetings and media interventions for advocacy	A
4.3 Cumulative number and types of quality advocacy campaigns initiated by AAWAZ, consolidated, synthesized and analysed by Programme Analysis, Results and Research (PARR)	3 Campaigns launched / 1 million people reached on key issues such as violence against women (VAWG), hate speech and improved local governance	Policy Advocacy Action Plan prepared and monitored / 3 Campaigns (end violence against women & girls; anti-hate speech and local government) underway. / 2,65 million people reached on women rights through Pakistan Television (PTV), radio and social media.	A+
4.3b Number of women and men who are in AAWAZ fora demonstrating knowledge on the AAWAZ’ s research and communication products and number of adaptations in implementation and policy attributable to AAWAZ products	50% sample size aware of at least 4/10 studies on select themes / At least 7 examples from across the programme on implementation and policy reforms and demonstration of good practice attributable to AAWAZ products	Data assessment tools developed and assessment will be rolled out for 4/10 studies in the next quarter. Field studies endorse that the material is being used. / 7 response fund field-based projects contributed to change in implementation and policy. / - Youth Development Foundation through its ‘Partnership for Peace’ initiative identified 496 young peace activists (177 female, 319 males – 40% from minorities) from four districts (Lahore, Peshawar, Khanewal & Bahawalpur) to promote inter-faith harmony and pluralism. / - Farmers Development Organisation through its ‘Voices of Minorities in Motherland’ initiative established a baseline of land and property rights of the minority communities. It also established five district level (Multan, Muzaffargarh, Khanewal, Lodhran & Bahawalpur) fora. These fora engaged with multiple stakeholders to protect rights of the minority groups. / - Centre for Governance and Public Accountability’ through its ‘Strengthening voices of women and excluded groups for transparent and accountable public service delivery’ initiative, launched a help-desk in RTI Commission. It conducted 73 Awareness sessions in five districts (Swabi, Mardan, Nowshera, Charsadda & Peshawar districts). This led to an increase in RTI requests.	A

Key Points
AAWAZ’ s Strategic Learning Unit (SLU) is producing cutting-edge, innovative and revolutionary research capturing voices of marginalised and excluded groups and providing critical evidence for more inclusive and gender sensitive policies. Last year, it produced 6 research papers, 7 policy briefs/case studies and a report on the latest perception survey covering a range of sensitive topics relating to minorities, conflicts, honour killing & rape legislations, disenfranchisement of women, state accountability and public policy.

The AAWAZ research papers on ‘Qualified Equality: Minorities in the Constitution of Pakistan;’ ‘Minorities in the Judicial System;’ and ‘The Laws of Honour Killing and Rape in Pakistan’ highlight how AAWAZ continued to bring sensitive issues to the public domain and leverage policy makers for action. For example; the paper on honour killing supported the APF Punjab to work with lawmakers interested in drafting amendments to strengthen protection for women and girls. In addition, specific reports on health and education were shared with recently elected district governments to highlight issues in service delivery. Studies on ‘Untouchability (A Study of Social Exclusion)’ and ‘Radicalization and Women’s Space’ are highly anticipated in the coming months.

A voice and accountability index was developed that sparked interest at the government’s Planning Commission when presented at an international conference in Islamabad. Unit staff are discussing how to use this methodology to track progress on SDGs by integrating voice and accountability indicators into the expected data collection work. Unit staff are also in close consultation with UNDP who are working with parliament on tracking the SDGs.

Through the Response Fund, 13 innovative projects launched through community-based organisations covering a number of non-traditional themes using a variety of vehicles including documentaries, mapping, songs and training packages. These initiatives exposed these smaller scale CBOs to the national development agenda whilst linking their localised interventions to the higher-level norm-breaking agenda.

The team also developed inclusive materials in the form of short videos and posters for village fora and Aagahi Centres to convey key messages on research findings, recognising that many people are illiterate. They also initiated face-to-face Communities of Practice (COP) meetings with the field staff focusing on the implementation experiences of the campaigns. AAWAZ intranet used as a vehicle to share ideas and generate discussion, although it has connectivity issues in the field.

AAWAZ estimates that more than 2.6 million people were reached through campaigns on anti-hate speech and local government issues using press, television, radio and social media. COP sessions used to capture learning on their impact in the field and will inform future campaign designs.

Recommendations
AAWAZ should continue to link with provincial and district forum members to determine their research needs in relation their legislative and other advocacy agendas.

It would be advisable to change the name of AAWAZ District Human Development reports, as this title is normally associated with UNDP’s flagship publication and could cause confusion.

AAWAZ should continue to use the research generated to become a knowledge partner of government at federal and provincial levels to advocate for progressive policies and legalisation to enhance the wellbeing of women, minorities and the excluded.

AAWAZ should also continue to build synergies and linkages with other DFID programmes like Sub-national Governance (SNG) and other voice and accountability (demand side) programmes in health and education sectors to maximise the benefits. One possible area can be accessing and utilising the data collected through other programmes e.g. geographical information system (GIS) data under SNG programme.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The programme spend remained on track (94%) this year in line with the forecasts. This is a massive improvement compared to previous years indicating the enhanced capacity of the MO / implementing partners and strengthened systems. AAWAZ spent £8.241 m against a budget of £8.825m.

The AAWAZ implementation budget is divided into three main categories for the MO and each consortium partner: fees (core staff costs including overheads), operations (travel, rent, accommodation, utilities, etc.) and programme activities (activities at the field level).

Of the funds spent in the current year, 51% was on fees, 14% on operations and 35% on the programme. The major cost driver is staff salaries as the programme has 461 staff at various programming and technical levels. This is normal for a complex programme of this type that involves direct social mobilisation in 4500 communities as well as research, advocacy and influencing at higher levels. All field and advocacy staff costs are included in the fee element of the budget in contrast to the common practice of including them under the programme budget.

The ‘Social Mobilisation’ stream through the JASAT training package consumed a major (36%) share of the programme expenditure this year as the training was rolled out in 4500 communities. This enabled these communities, particularly women, to work on key areas like women’s rights, conflict prevention, masculinity, gender based violence (GBV), and influencing to improve government services including government accountability.

Programme total spend to date is £26.6m (77%) against a total budget of £34.5m. After a low spending trajectory in the initial years, this programme is now performing at full scale and remains on track for its final implementation year with £7.75m budget focusing more on sustainability and strategic level interventions. As part of the exit strategy, the MO has already started reducing its staffing levels as well as the levels of short-term technical assistance from DAI London.

VfM performance compared to the original VfM proposition in the business case
AAWAZ partners developed a VfM framework and have begun to replace the assumptions in the framework with primary data, which is currently being collected. The set of indicators included in this framework are much more comprehensive and link directly to the implemented interventions, compared to the indicators proposed at the business case stage. This will enable AAWAZ to demonstrate evidentially accurate returns by the end of 2016.

A unit cost analysis to date suggests that for every £10 the project spends, more than 6 citizens are safer; 7 citizens have better access to public services; 5 citizens are more satisfied with public services and at least 1 citizen has choice and control over her/his development and is able to hold decision-makers to account[15].
[15] Beneficiary numbers were collected through regular M&E reporting. These numbers will be tested through impact assessment planned for the programme.

A sensitivity analysis for AAWAZ shows that the programme is most sensitive to delay in implementation. It is more sensitive to reduction in benefits compared with increase in cost. However, the cessation of benefits at the end of project completion will still yield a high IRR and Net Present Value (NPV). In addition, investments made in capacity building and skills development of people through AAWAZ fora, from village to district level, will make programme results more sustainable.

Assessment of whether the programme continues to represent value for money
The programme continues to represent significant value for money. This is evident from the findings of field visits, meetings with forum members and the wealth of anecdotal information emerging from case studies and updated cost benefit estimates.

AAWAZ has directly engaged with 176,955 citizens (50% women) across 45 districts through its community fora at a cost of £15[16] per citizen per year. Its indirect outreach is to 7.4m people at a cost of £1 per citizen per year. This programme deliberately targets marginalised groups that can reduce the efficiency and economy due to higher costs of reaching the hardest to reach, but AAWAZ is reaching them at £15. Many of the transformational attitudinal changes are difficult to measure so the qualitative benefits are likely to be higher still.
[16] The cost of mobilisation and capacity building elements per forum member per year, which is 36% of the programme budget. Relevant percentages of Fee and Operations elements have also been included in calculating the unit cost.

Aagahi Centres (450) have also been upgraded and converted into advisory bureaus and safe spaces at a cost of £99 per centre to generate constructive dialogue among communities on issues related to inclusion, gender, gender based violence (GBV), conflicts and accountability. Through women assemblies, 1,481 women were engaged at a cost of £7 per woman across 45 districts and were equipped with necessary leadership skills to act as mentors and role models to guide their respective communities.

As its intended impact, AAWAZ is aiming to increase the percentage of Pakistanis feeling safer from 38% to 50% with an overall implementation cost of £34m. It would cost the programme £2.83m per percentage point of population or £1.55 to make each additional citizen safer considering an overall population of 182 million. An analysis of activity based programme costs shows that robust, competitive and rigorous policies on operational, procurement and financial management ensure that it operates with a high level of economy and that the inputs are procured at the right prices. In the future though, it will be important to find benchmarks from other similar projects for purposes of comparison.

Quality of financial management
The quality of financial management by the MO remained very robust across the financial supply chain. A multi-level control system including due diligence, external audits, compliance and spot checks is in place to identify any deviations from contractual agreements, other irregularities and to suggest measures to reduce financial risk. CBOs remained a challenging link in the chain so a performance assessment was carried out against robust criteria, which brought the total number down to 127 from 174, filtering out less efficient and comparatively ineffective partners and strengthening the quality of programme delivery. AAWAZ was also able to produce a wide range of detailed financial data and analysis that meant the Senior Management Team (SMT), Programme Management Committee (PMC) and AAWAZ Steering Committee (ASC) were able to relate finances to the programme results in order to improve programme delivery and value for money (VfM).

To improve cost efficiencies and safeguard DFID funds, capacity of the MO and all downstream partners was strengthened to identify, tackle and report fraud. We worked with all partners to revise their whistle-blower policies and improve their reporting / response to fraud issues. Furthermore, we ensured that personal bank accounts in field offices were no longer used for programme activities in line with audit recommendations. Working with the MO and the implementing partners, we developed an action plan combining the Annual Review 2015 recommendations with the external audit and internal compliance audit observations. We ensured that this action plan was followed and implemented through our monthly consultations with the MO.

The quality and performance of financial management was strengthened using the annual review recommendations, external audit observations and internal compliance audit findings over the last two years. Sufficiently qualified, full time financial managers for the AAWAZ programme were appointed in all implementing partners to improve accountability. Financial managers at DAI were empowered to continue their rigour on compliance and financial management. Partners’ risk rating in the recent external audit improved from high/medium to medium/low.

Going forward, the flexible approach of the costed work plan should be enriched further to encourage innovation and to respond to localised challenges. This would reflect that some districts are more remote and difficult to access and unit costs can differ across activities and partners because of this.

Date of last narrative financial report	29th Mar 2016
Date of last audited annual statement	17th Mar 2016

Recommendation: As identified in the recently completed desk based VfM review, programme now needs to strengthen collection of data/information on beneficiary streams directly attributable to programme interventions.

E: RISK
Overall risk rating: Moderate

Risk to programme being disrupted/delayed by Output
Output 1 = Moderate	Output 2 = Minor	Output 3 = Minor	Output 4 = Moderate

AAWAZ divides risks into four categories:
(i) External risks beyond the direct control of the programme team, (ii) Financial risks, (iii) Activity risks, and (iv) Human resources risks.
The programme’s risk register was reviewed since the last annual review and is reviewed quarterly. A culture of risk-awareness, zero tolerance to corruption and strengthened financial compliance are now embedded across the programme.

External Risks: AAWAZ mitigates the main risk - the level of mistrust by Federal and Provincial government of international aid organisations and national NGOs – by the continued positive relationships between consortium personnel and the governments. Religious extremism and sporadic yet persistent acts of violent terrorism are constant risks in both Punjab and KP, while very conservative social context and strict patriarchal attitudes threaten to frustrate work to realise the rights of women and minorities. Natural disasters also temporarily held back programming.

Financial Risks: AAWAZ has good financial systems, procurement protocols, internal and external controls and auditing procedures. Effective M&E and financial management systems complement these controls to minimise fiduciary risk. In addition, field visits, spot checks and regular coordination meetings with the supplier and the implementers are used to maintain vigilance and to improve fiduciary risks. A concerted effort by the MO to improve financial compliance improved the performance of all consortium partners leading to a medium / low risk rating in the recent external audit down from a medium / high rating.

Activity Risks: There are no present activity risks to the programme. The team continues to compensate for any loss of momentum due to temporary gaps in available funds.

Human Resource Risks: The programme team is stable. Security threats are mitigated by the MO’s strong security systems and personnel.

Outstanding actions from risk assessment: None beyond current practice within AAWAZ.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The project is expected to deliver on its milestone targets before the date when it is due to finish. It had spent 94% of its annual budget by 21 May 2016. It is expected that all funds will be spent by the end of the project's planned duration. Milestone targets are able to move ahead of spending because they are not cost intensive, with many of them depending on the work done voluntarily by AAWAZ forum members.

Performance of partnership (s)
In the past, the ability of the consortium partners to function as a unified group has been a cause for concern. A recommendation in the AR 2015, that the AAWAZ Steering Committee (ASC) should be revitalised and receive synthesised programme and financial management information from the MO, was actioned and now they play a more strategic oversight role. The ASC meets less frequently but each meeting is longer, which enables the MO to host informal supper meetings between the Executive Directors (EDs), as well as sessions without DFID staff present. This has helped EDs get to know one another better without always feeling the need to compete. The result is that their teamwork has improved.

As noted elsewhere, as the project progresses the uneven performance of consortium partners becomes more noticeable. It is important that the MO does not ignore this situation but discusses the issue with partners whose performance is weaker than others to determine remedial action and ensure lesson learning. The performance of the MO itself gets better and better. Leadership has improved significantly and the recruitment of high quality specialists means it has the respect of consortium partners. Improvements in the way CBOs/CPOs are supported and recognised within the project are still required.

Asset monitoring and control
The MO conducts an annual compliance review as well as spot check verifications at regional and district offices of all the consortium partners and selected CPOs (community partner organisations). The scope of the review includes inventory management and procurement. The MO also maintains an asset register and logs for vehicle use. The annual review team conducted an asset check during their field visits and every quarter DFID staff review the asset register submitted by the MO.

G: CONDITIONALITY

AAWAZ is a demand side, voice and accountability programme and all funding is going to civil society organisations through a management firm. It does not contain any elements of budget support or financial aid. It is part of the wider aid relationship between the UK and Pakistan, which is based on an assessment of Government’s commitment to our Partnership Principles. DFID Pakistan’s assessment is that the government is demonstrating a credible commitment to the Partnership Principles. DFID can therefore continue to deliver on AAWAZ programme activities.

H: MONITORING & EVALUATION

Evidence and evaluation
AAWAZ is now benefitting from very high quality monitoring and evaluation founded on a solid baseline. Due to the considerable effort the MO's M&E specialists have put into the effective working of the cross organisation M&E Working Group, new levels of analytical and critical thinking are evident across the consortium partners M&E specialists. The latter freely acknowledge that the improvement is the result of guidance and inputs from the head and team of the MO's M&E unit.

An M&E plan has been developed and is now being implemented. The M&E team made 79 monitoring visits with a special emphasis on qualitative issues and 41 support visits assisting partners with M&E issues. All visits included a debrief to the AAWAZ district team including suggestions for solving problems. Reports on visits are sent to the appropriate member of the M&E working group, district coordinators, national programme managers and sometimes programme directors. The consolidated findings from visits and lessons learned are shared in the quarterly review meetings.

To triangulate results and better verify progress, 9 quantitative and qualitative assessments of specific aspects of the programme have been completed. SLU has been providing support to M&E around data analysis, report writing and refining methodologies. The programme continues to represent significant value for money.

A management information system (MIS) also has been developed and, following orientation sessions for 215 staff, is currently being used by all programme staff and 80% of district staff. This involved a large amount of work and is no small achievement. District staff need more capacity building as well as encouragement to dedicate the extra time needed to complete all the data forms.
Presentations on the MIS system were also made to provincial governments in a move to ensure complete transparency regarding AAWAZ operations and to build and maintain good institutional relations. Going forward, M&E working group will continue to review the MIS forms to ensure that only necessary information is being collected.