## Template
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Iraq has increased stability and security with a government that is more responsive to the needs of all Iraqi people | Number of IDP returns | Planned | 0 | 300,000 by November 2015 |  | 600,000 by August 2016
Achieved
Source
OCHA/GoI reports
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Amount disbursed by the Government of Iraq (GoI) in the form of cash transfers to IDPs and households under poverty line | Planned | 0
Achieved
Source
JCC/JCMC reporting
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Humanitarian aid and protection is delivered to the most vulnerable in Iraq, and the Government of Iraq is supported to respond to the ongoing crisis | Number of attributable DFID beneficiaries (against the total in the Humanitarian Response Plan (HRP)) | Planned |  |  |  | 200000 | Continued GoI and international humanitarian financing; GoI willingness to work with UN and use crisis management mechhanisms
Achieved
Source
HRP total is 5.6m beneficiaries. Sourced from HRP/OCHA and DFID funded project reports eg IHPF (attribution), ICRC (attribution) and UNHCR (direct)
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| The time required after the trigger event for the Joint Coordination & Monitoring Centre (JCMC), Joint Crisis Centre (JCC) and the governorate to produce near real-time information [with the displaced population and their needs after the trigger event of a crisis]. | Planned | JCMC and JCC have limited institutional capacity for information management, joint planning and response coordination within the GoI and with the international humanitarian actors | JCMC, JCC and Governorate Emergency Cells established a mechanism for joint collection of information on planning, response and experiences (by Dec 2015) | JCMC and JCC produce quality and accurate data on crisis situations and people's needs regularly in coordination and information gathering with GoI/KRG Ministries and Governorate (by March 2016) | Within one week after the trigger event of a crisis, real-time information on crisis situations produced (by June 2016)
Achieved
Source
JCMC, JCC and UNDP reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (December 2015) | Assumptions
Humanitarian and protection assistance delivered | Number of identified Persons of Concern receiving cash grants (UNHCR) | Planned | 0 | 30,000 (30.9.15) |  | 52800 | Security situation/access doesn't deteriorate; sufficient capacity of implementing partners
Achieved
Source
UNHCR reports to DFID on direct beneficiaries
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (December 2015)
| Number of indirect beneficiaries receiving water and habitat activities (ICRC) | Planned | 0 |  |  | 41,080 (or 4%)
Achieved
Source
ICRC reports. UK attribution
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
40 |  | Planned | 0
Achieved
|  | Source |  |  |  |  | RISK RATING
High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Most vulnerable people are identified and targetted | % of the pooled fund’s disbursements to priorities outlined in country specific allocation strategy (IHPF) | Planned | 0 | First allocation of the IHPF agreed in Advisory Board (July 2015) and disbursed (Aug 2015) |  | 100% | Cluster Priorities/areas are: Food Security, Emergency Shelter and Non-Food Items, Camp Coordination and Camp Management, Emergency Livelihoods and Social Cohesion, Health, Education and Food Security
Achieved
Source
OCHA IHPF reporting to donors
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| The IHPF results framework includes key indicators and achievements by cluster (IHPF) | Planned | 0 | IHPF results framework implemented by October 2015
Achieved
Source
IHPF reports
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
40 |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Capacity for crisis response and stabilisation increased | Number of crisis and daily situation reports, and directives produced by JCC/JCMC | Planned | 0 |  |  | 365
Achieved
Source
UNDP, JCC/JCMC reports
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Minimum of 52 Weekly Incident lists issued by INSO | Planned | 0 | 11 (1.9.15) | 28 (1.2.16) | 52 (31.5.16)
Achieved
Source
INSO progress reports
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20 |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.