## Logical Framework
PROJECT NAME | URBAN PARTNERSHIPS FOR POVERTY REDUCTION (UPPR)
IMPACT | Impact Indicator 1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | December-14 * | 2015-03-01 | 2015-12-01
Urban poverty in Bangladesh reduced | Proportion of population below the national poverty line* | Planned | 21.3% | 19.9% | 18.5% | 17.1% | 16.4% | N/A | N/A
|  | Achieved | 21.3% | No HIES | No HIES | No HIES | No HIES | N/A | N/A
Source
Bangladesh Bureau of Statistics (BBS) - Household Income and Expenditure Survey (HIES) *This indicator considers urban population only
| Impact Indicator 2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| Achievement in reaching MDG Indicator 7.10 Proportion of urban population living in slums | Planned | 61.6% (2009) | 59.8 | 58 | 56.2 | 54.4 | N/A | N/A
|  | Achieved | 61.6% | No Data | No Data | No Data | No Data | N/A | N/A
Source
United Nations Statistics Division (UNSD) - Millennium Development Goals (MDGs) Global Monitoring Database
*All Dec 2014 targets to be achieved by Aug 2014, except for the six cost extension phase targets set for Mar 2015. Indicator 3.4 nutrition targets are to be achieved Dec 13, 14 & 15
OUTCOME | Outcome Indicator 1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01 | Assumptions
Livelihoods and living conditions of 3 million poor and extreme poor people living in urban areas, especially women and children, sustainably improved | % of beneficiary households (HH) multi-dimensionally poor by Multi-Dimensional Poverty Index (MPI) Average % (intensity) of deprivations among beneficiary households multi-dimensionally poor by MPI | Planned - Multi-Dimensionally Poor |  |  |  | 38.8% | 38.1% | N/A | N/A | -National economic growth does not decline significantly. -Government of Bangladesh economic policies become progressively pro-poor. -Government and development partners prioritize urban poverty reduction policies and programmes. -Political instability does not disrupt the programme.
|  | Achieved - Multi-Dimensionally Poor | [5 empty] | N/A | N/A
|  | Planned - Intensity of Deprivation |  |  |  | 47.5% | 46.8% | N/A | N/A
|  | Achieved - Intensity of Deprivation | [5 empty] | N/A | N/A
Source
Multi-Dimensional Poverty Index study to be conducted in sample of towns in 2013 and 2014.
| Outcome Indicator 2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % poor settlements in Community Development Committees (CDCs) reporting at least 10% improvement in Water and Sanitation and Infrastructure conditions | Planned |  |  |  |  | 60% | N/A | N/A
|  | Achieved | [5 empty] | N/A | N/A
Source
This will be a sample study in 2014 of settlements within Community Development Committees using the Settlement Land Mapping study of 2010 as a baseline - using this baseline, poor settlements scored 31 (from 100) on the Water and Sanitation Index and 39.3 (from 100) on the Infrastructure Index.
| Outcome Indicator 3 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % empowered women by the UPPR participatory women’s empowerment scorecard | Planned |  |  |  | 55% | 60% | N/A | N/A
|  | Achieved | [5 empty] | N/A | N/A
Source
The Women's Empowerment Scorecard Sample Study will be conducted in 2013 and 2014. Empowerment indicators and threshold will be determined in a participatory manner The 2013 study will consider progress up to 2013, from start of UPPR while the 2014 study will explore progress in the last 12 months as UPPR looks to build sustainability at community level.
| Outcome Indicator 4 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| Key policy instruments influenced: - Two annual urban targets of Sixth Five Year Plan met - Formation of high level Ministerial Committee for Bangladesh Urban Forum - Establishment of permanent Secretariat for Bangladesh Urban Form - % of Pillar 6 targets of UNDAF achieved | Planned - Two Annual Targets met |  |  |  | Yes | Yes | N/A | N/A
|  | Achieved - Two Annual Targets met | [5 empty] | N/A | N/A
|  | Planned - High Level Committee |  |  |  | Yes | Yes | N/A | N/A
|  | Achieved - High Level Committee | [5 empty] | N/A | N/A
|  | Planned - Secretariat |  |  |  | Yes | Yes | N/A | N/A
|  | Achieved - Secretariat | [5 empty] | N/A | N/A
|  | Planned - Targets met |  |  |  | 30% | 40% | N/A | N/A
|  | Achieved - Targets met | [5 empty] | N/A | N/A
Source
* Sixth Five Year Plan Annual Report * Bangladesh Urban Forum Records * UNDAF Annual Report
INPUTS (£) | DFID (£m) |  | Govt (£m) | Other (£m) | Total (£m) |  | DFID SHARE (%)
0
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01 | Assumptions
Urban poor communities mobilized to form representative and inclusive groups and prepare community action plans | # of HH in supported low-income settlements socially mobilised into primary groups (PGs) | All Households | [7 empty] | Pourashavas and CCs willing and able to respond to the demands of organized poor communities. Political economy and socio-cultural factors do not adversely affect the effective operation of groups.
|  | Planned - # HH in CDCs | 420000 | 600000 | 700000 | 700000 | 700000 | N/A | N/A |  |  | 3010000
|  | Achieved - # HH in CDCs | 450937 | 685433 | 816242 |  |  | N/A | N/A
|  | Planned - # HH in PGs | 294000 | 420000 | 490000 | 518000 | 525000 | N/A | N/A
|  | Achieved - # HH in PGs | 263265 | 501838 | 623595 |  |  | N/A | N/A
|  | Planned - % HH in PGs | 70% | 70% | 70% | 74% | 75% | N/A | N/A
|  | Achieved - % HH in PGs | 58.38% | 73.21% | 76.4% |  |  | N/A | N/A
Source
* UPPR Form 1: Mobilisation data, including CDC and Primary Group membership demographics * UPPR use a factor of 4.3 to determine number of members per household * As the mobilisation target was exceeded by 2012, the focus will be placed upon strengthening mobilisation for the remainder of the project.
| Output Indicator 1.2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % decision making positions (DMP) in community structures (CDC, Cluster and Federation) held by extreme poor and poor females and females from vulnerable and socially excluded households | Planned: % DMP held by women from Extreme Poor and Poor households |  |  | 85% | 85% | 85% | N/A | N/A
|  | Achieved: % DMP held by women from Extreme Poor & Poor households |  |  | 88% |  |  | N/A | N/A
|  | Planned: % DMP held by females from vulnerable and socially excluded households |  |  | 10% | 10% | 10% | N/A | N/A
|  | Achieved: % DMP held by females from vulnerable and socially excluded households |  |  | 14% |  |  | N/A | N/A
Source
Participatory Identification of the Poor (PIP) database for CDCs only. The data above is based upon CDCs only. New data collection is required during 2013 for Clusters and Federations. Annual targets constant as no longer mobilising but focusing on sustainability.
| Output Indicator 1.3 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % of CDCs with a first Community Action Plan (CAP) and Repeat Community Action Plan (ReCAP) | Planned - First CAP |  |  | 80% | 85% | 90% | N/A | N/A
|  | Achieved - First CAP |  |  | 79% | 97% |  | N/A | N/A
|  | Planned - ReCAP |  |  | 50% | 55% | 60% | N/A | N/A
|  | Achieved - ReCAP |  |  | 45% | 66% |  | N/A | N/A
Source
UPPR Form 2 - Mobilisation events including number of meetings and CAPs. * ReCAP is a percentage of all CDCs formed up to December 2011 (2,221). * The above figures are subject to verification as initial inquiries suggest ReCAP is undercounted. We plan to collect hardcopies of all CAPs and ReCAPs at HQ over Quarter 2 of 2013 and will update accordingly.
| Output Indicator 1.4 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| Number of clusters participating in the ward-level planning pilot that are aligned to ward boundaries and registered with the appropriate authority | Planned | [5 empty] | 10 | N/A |  | new activity for cost extension
|  | Achieved | [6 empty] | N/A
Source
Documentation of redrawn clusters and of registration shared with DFID
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
20% | Number of towns participating in the ward-level planning pilot that have developed climate change resilience strategies | Planned | [5 empty] | 4 | N/A |  | new activity for cost extension
|  | Achieved | [6 empty] | N/A
|  |  | Source | [6 empty] | RISK RATING
|  |  | Documentation of the climate change resilience strategies shared with DFID | [6 empty] | Medium
INPUTS (£) | DFID (£m) |  | Govt (£m) | Other (£m) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01 | Assumptions
Poor urban communities have healthy and secure living environments | # of beneficiary households in supported low-income settlements to benefit from: - water facilities (tubewells and water reservoirs) - latrines - Drainage and footpath facilities | Planned - Water Supply | 149660 | 225160 | 162805 | 192087.1744 | 195433.3969 | N/A | N/A | City-wide infrastructure and services needed for community-based projects to be viable in place. Formal and informal tenure of poor households and communities respected. Health and other service providers are effective and protect the interests of the poor and very poor.
|  | Achieved - Water Supply | 100416 | 123316 | 166726 |  |  | N/A | N/A |  |  | 22900
|  | Planned - Latrine | 67350 | 99219 | 135708 | 169279.9108 | 173118.9671 | N/A | N/A
|  | Achieved - Latrine | 67760 | 89901 | 143163 |  |  | N/A | N/A |  |  | 22141
|  | Planned - Drain and Footpath | 86060 | 137860 | 306983 | 390701.8119 | 400224.7653 | N/A | N/A |  |  | 45041
|  | Achieved - Drain and Footpath | 151462 | 203094 | 324894 |  |  | N/A | N/A |  |  | 67182
Source
* UPPR Form 6: Settlement Improvement Fund (SIF) Activities (Quarterly) * UPPR SIF Database
| Output Indicator 2.2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % HH members in CDCs with access to improved water source | Planned |  |  |  | 70% | 70% | N/A | N/A
|  | Achieved | [5 empty] | N/A | N/A
Source
* UPPR - Settlement Improvement Fund (SIF) Short-Term Outcome Sample Survey in 2013 and 2014. * Measuring acccess to the improved water source will include distance, time, water quality, litres per household member per day and maintenance.
| Output Indicator 2.3 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % HH members in CDCs with access to improved latrines | Planned |  |  |  | 70% | 70% | N/A | N/A
|  | Achieved | [5 empty] | N/A | N/A
Source
* UPPR - Settlement Improvement Fund (SIF) Short-Term Outcome Sample Survey in 2013 and 2014. * Measuring acccess to the improved latrine will include distance, time, maintenance and safety.
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
30% | % of SIF community contracts completed during the calendar year which took less than 12 months to finish | Planned |  |  | 70% | 75% | 75% | N/A | N/A
|  | Achieved |  |  | Update Q4'13 |  |  | N/A | N/A
|  |  | Source | [6 empty] | RISK RATING
|  |  | UPPR SIF Database * 2012 data will be available in December 2013 following revisions to the database | [6 empty] | Medium
INPUTS (£) | DFID (£m) |  | Govt (£m) | Other (£m) | Total (£m) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01 | Assumptions
Urban poor and extremely poor people acquire the resources, knowledge and skills to increase their income and assets | # of beneficiaries receiving: -skills development training (apprenticeships) -small enterprise block grant | Planned - Skills Training | 24466 | 37800 | 46532.4636 | 63533.5818 | 64897.2182 | N/A | N/A | Employment and business opportunities are available at town level. Other support services (e.g., microfinance) willing and able to provide services to self-employed workers. |  | 279058.0382
|  | Achieved - Skills Training | 24791 | 38733 | 47313 |  |  | N/A | N/A
|  | Planned - Female Skills Training |  |  | 27919.4782 | 38120.1491 | 38938.3309 | N/A | N/A
|  | Achieved - Female Skills Training | 17661 | 28637 | 34783 |  |  | N/A | N/A
|  | Planned - Block Grant |  |  | 90992.6333 | 114206.919 | 115921.2048 | N/A | N/A |  |  | 498461.1805
|  | Achieved - Block Grant | 19591 | 55539 | 88384 |  |  | N/A | N/A
Source
UPPR Form 5: Socio-Economic Fund (SEF) Activities (Quarterly) UPPR SEF Database A target of 60% women for apprenticeships has been set by SEF Guidelines Block grants are for extreme poor women only
| Output Indicator 3.2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % of beneficiaries who found employment six months after receiving: -skills development training (apprenticeships) -small enterprise block grant | Planned - Skills Training |  |  |  | 60% | 60% | N/A | N/A
|  | Achieved - Skills Training |  |  |  | 63% |  | N/A | N/A
|  | Planned - Block Grant |  |  |  | 60% | 60% | N/A | N/A
|  | Achieved - Block Grant |  |  |  | 93% |  | N/A | N/A
Source
UPPR - Socio-Economic Fund (SEF) Short-Term Outcome Sample Surveys
| Output Indicator 3.3 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| # of children supported towards achieving their Primary School Certificate (PSC) and Secondary School Certificate (SSC) | Planned - Total | 22168 | 36350 | 61363.9167 | 92973.7348 | 95882.8258 | N/A | N/A |  |  | -25445
|  | Achieved - Total | 24153 | 47377 | 71161 |  |  | N/A | N/A
|  | Planned - Female | 15517.6 | 25445 | 42954.7417 | 65081.6144 | 67117.978 | N/A | N/A
|  | Achieved - Female | 16766 | 31629 | 46760 |  |  | N/A | N/A
|  | Achieved - Female PSC |  |  | 4810 |  |  | N/A | N/A
|  | Achieved - Male PSC |  |  | 2835 |  |  | N/A | N/A
|  | Achieved - Female SSC |  |  | 10321 |  |  | N/A | N/A
|  | Achieved - Male SSC |  |  | 5818 |  |  | N/A | N/A
Source
UPPR - Form 5: Socio-Economic Fund (SEF) Activities (Quarterly) UPPR - SEF Database A target of 70% girls has been set by SEF Guidelines. Targets added retrospectively for 2010-2011.
| Output Indicator 3.4 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % of beneficiaries in supported low-income settlements receiving: -Iron and folic acid (IFA) -Deworming tablet (DT) -Deworming Suspension (DS) | Planned - Pregnant women IFA |  |  |  | 85% | 85% | N/A | 85%
|  | Achieved - Pregnant women IFA | [5 empty] | N/A
|  | Planned - Pregnant women DT |  |  |  | 85% | 85% | N/A | 85%
|  | Achieved - Pregnant women DT | [5 empty] | N/A
|  | Planned - Adolescent girls IFA |  |  |  | 85% | 85% | N/A | 85%
|  | Achieved - Adolescent girls IFA | [5 empty] | N/A
|  | Planned - Adolescent girls DT |  |  |  | 85% | 85% | N/A | 85%
|  | Achieved - Adolescent girls DT | [5 empty] | N/A
|  | Planned - Children Under 5 DT |  |  |  | 85% | 85% | N/A | 85%
|  | Achieved - Children Under 5 DT | [5 empty] | N/A
|  | Planned - Children Under 2 DS |  |  |  | 85% | 85% | N/A | 85%
Achieved - Children Under 2 DS
Source
UPPR - Nutrition Intevention M&E System
| Output Indicator 3.5 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| # and % of primary group households saving and having access to credit through savings and credit groups | Achieved # of PGs | 263265 | 501838 | 623595 |  |  | N/A | N/A
|  | Planned - # HH in SCGs | 147000 | 210000 | 245000 | 259000 | 262500 | N/A | N/A
|  | Achieved - # HH in SCGs | 258000 | 317546 | 376777 |  |  | N/A | N/A
|  | Planned - % in SCGs | 50% | 50% | 50% | 50% | 50% | N/A | N/A
|  | Achieved - % in SCGs | 98% | 63.28% | 60.42% |  |  | N/A | N/A
Source
UPPR Form 3: Savings and Credit Group
| Output Indicator 3.6 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| % of SEF community contracts completed during the calendar year which took less than 12 months to finish | Planned |  |  | 80% | 80% | 80% | N/A | N/A
|  | Achieved |  |  | Update Q4'13 |  |  | N/A | N/A
Source
UPPR SEF Database * 2012 data will be available in December 2013 following revision to the database
IMPACT WEIGHTING (%) | Output Indicator 3.7 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
30% | Number of MOUs signed between the community and municipality with private sector entities to provide training and employment opportunities in poor urban settlements | Planned | [5 empty] | 8 | N/A |  | new activity for cost extension
|  | Achieved | [6 empty] | N/A
|  |  | Source | [6 empty] | RISK RATING
|  |  | Documentation of MOUs shared with DFID | [6 empty] | Medium
INPUTS (£) | DFID (£m) |  | Govt (£m) | Other (£m) | Total (£m) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01 | Assumptions
Pro-poor urban policies and partnerships supported at the national and local levels | # of programme towns where low-income settlements are officially recognised by Municipal and Pourashava Mayors through signing the Settlement Map | Planned |  |  |  | 15 | 22 | N/A | N/A
|  | Achieved |  |  | 2 |  |  | N/A | N/A
Source
Evidence of signed Settlement Land Maps
| Output Indicator 4.2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| # of press and television reports covering urban poverty issues in UPPR low-income settlements | Planned - UPPR |  |  | 80 | 175 | 240 | N/A | N/A
|  | Achieved - UPPR |  |  | 129 |  |  | N/A | N/A
Source
UPPR and United Nations Information Centre - Press Clippings
| Output Indicator 4.3 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| # of partnerships and linkages established through the project | Planned - Partnerhips | 20 | 30 | 110 | 130 | 135 | N/A | N/A
|  | Achieved - Partnerships | 27 | 92 | 107 |  |  | N/A | N/A
|  | Planned - Linkages | 40 | 60 | 500 | 635 | 670 | N/A | N/A
|  | Achieved - Linkages | 71 | 355 | 497 |  |  | N/A | N/A
Source
Partnerships and Linkages database, including both town and community led linkages. Linkages: collaborations with other organisatons to deliver services that involve no exchange of funds. Partnerships: collaboration with other organisations where UPPR pays for the services provided.
| Output Indicator 4.4 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
| New models of security of tenure are piloted and documented | Planned | [5 empty] | 3 | N/A |  | new activity for cost extension
|  | Achieved | [6 empty] | N/A
Source
Documentation of new models of land tenure security shared with DFID
IMPACT WEIGHTING (%) | Output Indicator 4.5 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-12-01
15% | Number of towns where the capacity of LGIs to support pro-poor policy development is deemed at least satisfactory on a capacity assessment scorecard | Planned | [5 empty] | 6 | N/A |  | new activity for cost extension
|  | Achieved | [6 empty] | N/A
|  |  | Source | [6 empty] | RISK RATING
|  |  | UPPR is developing a capacity assessment scorecard which it will complete with towns in 2013 and 2015 | [6 empty] | Medium
INPUTS (£) | DFID (£m) |  | Govt (£m) | Other (£m) | Total (£m) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-03-01 | Assumptions
Effective project management systems established and operational | Proportion of SIF budget delivered (in GBP and USD) | Planned - GBP |  |  | 6200000 | 6200000 | 667588.72 | N/A | N/A
|  | Achieved - GBP |  |  | 5900165.52 |  |  | N/A | N/A
|  | % in GBP |  |  | 95.16% |  |  | N/A | N/A
|  | Planned - USD |  |  | 10000000 | 10000000 | 1076756 | N/A | N/A
|  | Achieved - USD |  |  | 9516396 |  |  | N/A | N/A
|  | % in USD |  |  | 95.16% |  |  | N/A | N/A
Source
UPPR - ATLAS Financial System Report (Yearly) This is the annual figure to ensure consistency with exchange rates
| Output Indicator 5.2 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-03-01
| Proportion of SEF budget delivered (in GBP and USD) | Planned - GBP |  |  | 3782000 | 4030000 | 310000 | N/A | N/A
|  | Achieved - GBP |  |  | 3750101 |  |  | N/A | N/A
|  | % in GBP |  |  | 99.16% |  |  | N/A | N/A
|  | Planned - USD |  |  | 6100000 | 6500000 | 500000 | N/A | N/A
|  | Achieved - USD |  |  | 6048550 |  |  | N/A | N/A
|  | % in USD |  |  | 99.16% |  |  | N/A | N/A
Source
UPPR - ATLAS Financial System Report (Yearly) This is the annual figure to ensure consistency with exchange rates
| Output Indicator 5.3 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-03-01
| % of project human resource positions staffed at HQ and Town levels | Planned - HQ |  |  | 90% | 90% | 90% | N/A | N/A
|  | Achieved - HQ |  |  | 67.2% |  |  | N/A | N/A
|  | Planned - Town |  |  | 90% | 90% | 90% | N/A | N/A
|  | Achieved - Town |  |  | 88.6% |  |  | N/A | N/A
Source
UPPR - Human Resources Data (six monthly)
| Output Indicator 5.4 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-03-01
| % of female staff at HQ and Town levels | Planned - HQ |  |  | 20% | 25% | 25% | N/A | N/A
|  | Achieved - HQ |  |  | 9.8% |  |  | N/A | N/A
|  | Planned - Town |  |  | 20% | 25% | 25% | N/A | N/A
|  | Achieved - Town |  |  | 18.3% |  |  | N/A | N/A
Source
UPPR - Human Resources Data (six monthly)
IMPACT WEIGHTING (%) | Output Indicator 5.5 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-03-01 | 2015-03-01
5% | Number of short and long term outcome studies and research studies on UPPR best practices carried out | Planned | [5 empty] | 7 | N/A |  | new activity for cost extension
|  | Achieved | [6 empty] | N/A
|  |  | Source | [6 empty] | RISK RATING
|  |  | Completed reports shared with DFID | [6 empty] | Medium
INPUTS (£) | DFID (£m) |  | Govt (£m) | Other (£m) | Total (£m) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
INDICATORS TO BE REVIEWED BY THE MID-TERM REVIEW TEAM
Theme |  | Indicator |  |  | Related Logframe Outcome/Output
Ability of CDCs to plan yearly and timely through CAP and Re-CAP |  | #/% of Community Action Plans (CAPs) prepared and approved by community and endorsed by Project Town Board (PTB) |  |  | Output 1
|  | #/% of new CDC conducting CAPs |  |  | Output 1
|  | #/% of existing CDCs performing yearly Re-CAP timely |  |  | Output 1
CDC graduation |  | #/% of Community Development Committees (CDCs) which have presented concerns of beneficiary households to local authorities |  |  | Output 1
|  | % of PGs/CDCs reporting improved capacity to address crime, dowry, domestic violence, polygamy and drug abuse |  |  | Output 1
|  | # of mature Community Development Committees (CDCs) |  |  | Output 1
|  | # of programme towns where federations are established |  |  | Output 1
Tenure security |  | % of beneficiary household heads in supported low-income settlements who believe there's a strong likelihood of being evicted from their dwellings in the next five years (strong likelihood = more than 50% likelihood) |  |  | Outcome
|  | # of programme towns where Government authorities clarify the tenure security status of low-income settlement dwellers |  |  | Outcome
|  | # of programme towns where Government authorities clarify the tenure security status of low-income settlement dwellers of at least one settlement in local or central Government land |  |  | Outcome
GoB allocation of resources for the urban poor |  | % of Local Government Engineering Division resources allocated for urban pro-poor activities |  |  | Outcome

## Supporting Notes
Indicator | Comments
Proportion of population below the national poverty line* | The Household Income and Expenditure Survey (HIES) is conducted at five year intervals. It should be conducted again in 2015.
Achievement in reaching MDG goal 7 target 11, a significant improvement in the lives of at least 100 million slum dwellers by 2020 | The wording reflects the indicator although it should be noted that this target was surpassed by 2010.
Outcome Indicator 2: % poor settlements in Community Development Committees (CDCs) reporting at least 10% improvement in Settlement Living Conditions Index by 2014 | The SLM focused on settlements rather than CDCs using 16 indicators across 5 sectors. It is proposed to undertake a follow-up study in a sample of these settlements focusing on Water and Sanitation and Infrastructure to see how many achieved at least a 10% improvement on their 2010 score. On average Water and Sanitation scored 31 and Infrastructure scored 39.3 from a maximum score of 100. It would be possible to compare settlements outside of CDCs although it should be noted that they may be receiving similar interventions from other organisations.
Outcome Indicator 3: % empowered women by the UPPR participatory women’s empowerment scorecard | The target of 50% in 2013 and 60% in 2014 is based in part on the experiences of the Chars Livelihood Project when undertaking a similar study. However given that the emphasis on female mobilisation and the urban context it is difficult to estimate when no baseline has been taken. UPPR will develop a participatory measure of empowerment with the support of a qualitative consultant.
Outcome Indicator 4: Key policy instruments influenced: - Two annual urban targets of Sixth Five Year Plan met - Formation of high level Ministerial Committee for Bangladesh Urban Forum - Establishment of permanent Secretariat for Bangladesh Urban Form - % of Pillar 6 targets of UNDAF achieved | These indicators are as discussed with DFID although UPPR/UNDP would like to retain the UNDAF indicator. Firstly the UNDAF is a significant policy space in Bangladesh. Secondly that UPPR was a key driver of the inclusion of urban poverty in the UNDAF is important. Thirdly UPPR is the major contributor to the success of UNDAF Pillar 6 as 80% of the towns covered are where UPPR works.
% decision making positions (DMP) in community structures (CDC, Cluster and Federation) held by extreme poor and poor females and females from vulnerable and socially excluded households | The targets of 85% and 10% respectively are based on project planning and supported by initial findings from our database. Some additional analysis is required before populating. Wording was adjusted since previous version which was in wrong order
Output Indicator 1.3: % of CDCs with a first Community Action Plan (CAP) and Repeat Community Action Plan (ReCAP) | As discussed in the meeting. The targets are based on expectations and initial findings from database. Some additional data cleaning is required before populating. There is a time lag in new CDCs undertaking CAP while some CDCs have been formed but are not funded so did not undertake a CAP.
Output Indicator 2.1: # of beneficiary households in supported low-income settlements to benefit from: - water facilities (tubewells and water reservoirs) - latrines - Drainage and footpath facilities | Wording of indicator changed for greater clarity with 2.2 and 2.3. Also targets for 2013 and 2014 adjusted in light of revised LGED unit costs.
Output Indicator 2.2: % HH members with access to improved water source | As discussed in the meeting, this will be a headline indicator but the score will be derived from a range of indicators including distance, water quality, security, etc.
Output Indicator 2.3: % HH members with access to improved latrines | As discussed in the meeting, this will be a headline indicator but the score will be derived from a range of indicators including distance, maintenance, security, etc.
Output Indicator 2.4: % of SIF community contracts completed within 12 months of commencement | Targets are based on expectations and initial analysis. There is a challenge in 2014 however given the shorter time frame for completion.
Output Indicator 3.1: # of beneficiaries receiving: -skills development training (apprenticeships) -small enterprise block grant | A target of 60% in line with the SEF guideline has been introduced for female participation.
Output Indicator 3.2:% of beneficiaries who found employment six months after receiving: -skills development training (apprenticeships) -small enterprise block grant | After consideration UPPR has opted to use employment rather than relevant employment since it is possible that training may have contributed to greater confidence and capacity to participate in the labour market.
Output Indicator 3.3: # of children supported towards achieving their Primary School Certificate (PSC) and Secondary School Certificate (SSC) | Re-worded in line with DFID advice however it should be noted that the emphasis is not on actually obtaining the certificates, but contributing to that process. This is as a child may receive three years support but may not yet have reached their final year of education.
Output Indicator 3.4: % of beneficiaries in supported low-income settlements receiving: -Iron and folic acid (IFA) -Deworming tablet (DT) -Deworming Suspension (DS) | This has been adjusted to a 85% target as 95% was judged to be unrealistic.
Output Indicator 3.5: # and % of primary group households saving and having access to credit through savings and credit groups | A 50% target was derived from the previous targets (70% of CDC households in PGs and 35% of CDC households in Savings and Credit Groups). Targets have not increased as while the overall tagret has been met, this belies variation at town level. With a focus on achieving greater sustainability over the remainder of the project, it is advised that the focus be on ensuring that towns are achieving at least 50%.
Output Indicator 3.6: % of SEF community contracts completed within 12 months of commencement | Targets are based on expectations and initial analysis. There is a challenge in 2014 however given the shorter time frame for completion.
# of programme towns where low-income settlements are officially recognised by Municipal and Pourashava Mayors through signing the Settlement Map | Given lack of clarity, we have updated the indicator to reflect recognition by Mayor through sigining the maps of poor settlements developed by UPPR. Two have been signed so far. Tagrets revised to reflect this. Please note Dhaka was not mapped.
Output Indicator 4.2: # of press and television reports covering urban poverty issues in UPPR low-income settlements | The indicator has been adjusted to reflect both press and television reports about UPPR settlements. The media fellowship is being discontinued. However previously articles written about UPPR towns at the local level outside of the Fellowship were not counted and should be.
Output Indicator 4.3: # of town-led partnerships and linkages established through the programme | The linkages target for 2013 and 2014 has been reduced as it was unrealistic for towns. It should be noted that many more linkages and partnerships are formed through the Clusters with support of the UPPR town teams but these are not recored in the Log Frame. This might be considered.
Output Indicator 5.4: % of female staff at HQ and Town levels | The targets have been reduced to a more realistic level.

## Baseline & Target Calculation
URBAN PARTNERSHIPS FOR POVERTY REDUCTION (UPPR)
Impact Indicator 1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
Proportion of population below the national poverty line | It is assumed that this indicator considers the urban population only. Urban poverty decreased from 28.4% (HIES 2005) to 21.3% (HIES 2010), that is, 7.1% over a five-year period, or 1.4% yearly and 0.7% half-yearly. It is assumed that this same decrease will take place during the programme
Impact Indicator 2 | Assumptions to Calculate Planned Baselines, Targets and Milestones
Improved performance in reaching MDG goal 7 target 11 | Target 11 of MDG 7 is "Have achieved by 2020 a significant improvement in the lives of at least 100 million slum dwellers" and its Indicator 32 is "Proportion of households with access to secure tenure". UN-HABITAT defines the calculation of this indicator as: "1 minus the percentage of the urban population that lives in slums". The 2011 Bangladesh census will provide an estimate of this indicator in line with the official MDG Guidelines.The actual proportion of people living in slums is measured by a proxy, represented by the urban population living in households with at least one of the four characteristics: (a) lack of access to improved water supply; (b) lack of access to improved sanitation; (c) overcrowding (3 or more persons per room); and (d) dwellings made of non-durable material. Otherwise, UN-HABITAT defines a slum household as "a group of individuals living under the same roof who lack one or more (in some cities, two or more) of the following conditions: (a) security of tenure, (b) structural quality and durability of dwellings, (c) access to safe water, (d) access to sanitation facilities and sufficient living area". Bangladesh 2009 MDG report: According to the 2001 Population Census, approximately 31 million people (23% of the population) lived in urban areas, of which 7.8% resided in slums. The vast majority lives in six city corporations and approximately 300 municipalities. The urban population is increasing at the rate of 3-6% per annum. The urban population is expected to reach 50 million 2050 surpassing the rural population before 2050. The 2009 MDG Report cites insufficient data to monitor this indicator and no target is defined for 2015. Indicator Metadata as described in the UNSD MDG database Goal 7. Ensure environmental sustainability Target 7.D: By 2020, to have achieved a significant improvement in the lives of at least 100 million slum dwellers Indicator: 7.10 Proportion of urban population living in slums The Proportion of urban population living in slums is the proportion of urban population living in slum households. A slum household is defined as a group of individuals living under the same roof lacking one or more1 of the following conditions: * Access to improved water * Access to improved sanitation * Sufficient-living area * Durability of housing * Security of tenure However, since information on secure tenure is not available for most of the countries, only the first four indicators are used to define slum household, and then to estimate the proportion of urban population living in slums. Access to improved water: Improved drinking water technologies are more likely to provide safe drinking water than those characterized as unimproved. A household is considered to have access to an improved water supply if it uses improved drinking water sources or delivery points (listed below). Improved drinking water sources include: piped water into dwelling, plot or yard; public tap/standpipe; tube well/borehole; protected dug well; protected spring; and rainwater collection. Unimproved drinking water sources include: unprotected dug well; unprotected spring; cart with small tank/drum; bottled water2 ; tanker-truck; and surface water (river, dam, lake, pond, stream, canal, irrigation channels). Access to improved sanitation: Improved sanitation facilities are more likely to prevent human contact with human excreta than unimproved facilities. A household is considered to have access to improved sanitation if it uses improved sanitation facilities (listed below). Improved sanitation facilities3 include: flush or pour-flush to piped sewer system, septic tank or pit latrine; ventilated improved pit latrine; pit latrine with slab; and composting toilet. Unimproved sanitation facilities include: flush or pour-flush to elsewhere4 ; pit latrine without slab or open pit; bucket; hanging toilet or hanging latrine; no facilities or bush or field. Durability of housing: A house is considered "durable" if it is built on a non-hazardous location and has a structure permanent and adequate enough to protect its inhabitants from the extremes of climatic conditions, such as rain, heat, cold and humidity. Sufficient living area: A house is considered to provide a sufficient living area for the household members if not more than three people share the same habitable (minimum of four square meters) room. Secure tenure: Secure tenure is the right of all individuals and groups to effective protection by the State against arbitrary unlawful evictions. People have secure tenure when there is evidence of documentation that can be used as proof of secure tenure status or when there is either de facto or perceived protection against forced evictions. 1 According to the situation in a specific city this definition may be locally adapted. For example, in Rio de Janeiro living area is insufficient for both the middle classes and the slum population and is not a good discriminator. It could either be omitted, or it could be formulated as two or more of the conditions such as overcrowding and durability of housing. 2 Bottled water is considered improved only when the household uses water from an improved source for cooking and personal hygiene. 3 Only facilities, which are not shared or are not public are considered improved. 4 Excreta are flushed to the street, yard or plot, open sewer, a ditch, a drainage way or other location.
Outcome Indicator 1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of beneficiary households multi-dimensionally poor Average % (intensity) of deprivations among beneficiary households multi-dimensionally poor | MPI Dimension | Indicator | Household is deprived if | Related to | Relative Weight
| Education | Years of Schooling | No household member has completed five years of schooling | MDG 2 | 16.7%
| Education | Child School Attendance | Any school-aged child is not attending school in years 1 to 8 | MDG 2 | 16.7%
| Health | Mortality | Any child has died in the family | MDG 4 | 16.7%
| Health | Nutrition | Any adult or child for whom there is nutritional information is malnourished | MDG 1 | 16.7%
| Standard of Living | Electricity | The household has no electricity | MDG 7 | 5.6%
| Standard of Living | Sanitation | The household's sanitation facility is not improved (according to MDG guidelines), or it is improved but shared with other households | MDG 7 | 5.6%
| Standard of Living | Water | The household does not have access to clean drinking water (according to MDG guidelines), or clean water is more than 30 minutes walking from home | MDG 7 | 5.6%
| Standard of Living | Floor | The household has dirt, sand or dung floor | MDG 7 | 5.6%
| Standard of Living | Cooking Fuel | The household cooks with dung, wood or charcoal | MDG 7 | 5.6%
| Standard of Living | Assets | The hosuehold does not own more than one of: radio, TV, telephone, bike, motorbike or refrigerator, and does not own a car or a truck. | MDG 7 | 5.6%
A household is considered multi-dimensionally poor if it is deprived in 30% or more dimensions UNDP estimates that 57.8% of households in Bangladesh are multi-dimensionally poor and that the average intensity of deprivations among multi-dimensionally poor households is 50.4%.
Outcome Indicator 2 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of beneficiary extreme poor children under 5 years old: -stunted -underweight -wasted -anaemic | DFID will conduct impact evaluation to obtain the baseline.
Then targets will be interpolated using the nutrition intervention logframe, which assumes the following changes fom the baseline:
|  | Year 1 | Year 2 | Year 3
| Stunting | 1% reduction | 2% reduction | 3% reduction
| Underweight | 2% reduction | 4% reduction | 6% reduction
| Wasting | 1% reduction in wasting | 2% reduction | 3% reduction
| Anaemia | 5% reduction for children below 2 years 1% reduction for children 2-5 years | 10% reduction for children below 2 years 2% reduction for children 2-5 years | 15% reduction for children below 2 years 3% reduction for children 2-5 years
Outcome Indicator 3 | Assumptions to Calculate Planned Baselines, Targets and Milestones
Average % Improvement in UPPR Community Living Conditions Index*, after 3 years of joining the programme
Outcome Indicator 4 | Assumptions to Calculate Planned Baselines, Targets and Milestones
Average % Improvement in UPPR Women's Empowerment Index
Outcome Indicator 4 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of poor and extremely poor beneficiary households in supported low-income settlements where at least one member is accessing to Government or other safety nets and social assistance | According to the UPPR Pilot Census conducted in Bihary Colony in Naogaon, in 8.5% of households a member is accessing Government safety nets and social assistance. This estimate includes non-poor households. The sample surveyed was 271 households. These were asked "Does any household member access to Government safety nets and/or other assistance?" 0-No Access (91.5%), 11-Maternity Allowance (0%), 12-VGF/VGD (0%), 13-Rehabilitation of divorced/abandoned woman (0%), 14-Girl's education stipend (0%), 15-Old-aged allowance/pension (8.5%), 16-Disability allowance (0%), 17-Freedom fighter's allowance (0%), 18-100 days employment programme (0%), 19-SOS children's village (0%), 20-Juvenile Center (0%), 21-Orphanage (0%), 22-Other (0%).
Output Indicator 1.1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of households in supported low-income settlements socially mobilised into primary groups (PGs) | It is assumed that 70% of all mobilized households will be organized into PGs. Once mobilisation is complete in 2012, it is assumed that this percentage will increase to 74% by the end of 2013 and to 75% by the end of the programme. It is assumed that these percentages must also hold for the four categories of vulnerable households. While it is possible to estimate mobilization rates for all households, this remains complex in the case of vulnerable households. Average household size is estimated at 4.31 individuals per household (national average).
Output Indicator 1.2 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# poor homeless people supported under the programme | It is assumed that 2,500 homeless people will be supported by the programme each year from 2010 to 2013, and that in 2014 1,250 homeless people will be supported.
Cumulative Number
| Number of homeless people supported under the programme by end 2010 |  |  | 2500 | 2500
| Number of homeless people supported under the programme by end 2011 |  |  | 2500 | 5000
| Number of homeless people supported under the programme by end 2012 |  |  | 500 | 5500
| Number of homeless people supported under the programme by end 2013 |  |  | 500 | 6000
| Number of homeless people supported under the programme by August 2014 |  |  | 500 | 6500
Output Indicator 1.3 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of households satisfied with CDCs/PGs performance | It is assumed that at least 70% of households will be satisfied with the performance of CDCs and PGs.
Output Indicator 2.1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of beneficiary households in supported low-income settlements provided with improved access to: -water facilities (tubewells and water reservoirs) -sanitation facilities (latrines) -drainage facilities -footpath facilities -cooking stoves | The estimated number of beneficiary households per SIF investments are: -Shallow tubewell: 15 HH -Deep tubewell: 50 HH -Water Reservoirs: 50 HH -Latrines with septic tanks: 3 HH -Community latrines: 50 HH -Improved cooking stoves: 1 HH -Drainage: 500 HH per km -Footpaths: 500 HH per km
The SIF Budget Projection Tool 2007-2011 was used in previous logical frameworks to estimate the number of planned tubewell, water reservoir, latrine and drainage beneficiaries. The tool did not contain information on footpaths or improved cooking stoves. For 2012-2014 Targets see SIF Budget and Beneficiaries Projection Tool 2012-2014 sheet
| Number of Tubewell Beneficiaries |  |  | Yearly Target | Cumulative
| Number of Tubewell Beneficiaries in 2008 |  |  | 13580 | 13580
| Number of Tubewell Beneficiaries in 2009 |  |  | 20680 | 34260
| Number of Tubewell Beneficiaries in 2010 |  |  | 51800 | 86060
| Number of Tubewell Beneficiaries in 2011 |  |  | 51800 | 137860
| Number of Water Reservoir Beneficiaries |  |  | Yearly Target | Cumulative
| Number of Water Reservoir Beneficiaries in 2008 |  |  | 27000 | 27000
| Number of Water Reservoir Beneficiaries in 2009 |  |  | 12900 | 39900
| Number of Water Reservoir Beneficiaries in 2010 |  |  | 23700 | 63600
| Number of Water Reservoir Beneficiaries in 2011 |  |  | 23700 | 87300
| Number of Latrine Beneficiaries |  |  | Yearly Target | Cumulative
| Number of Latrine Beneficiaries in 2008 |  |  | 12426 | 12426
| Number of Latrine Beneficiaries in 2009 |  |  | 23055 | 35481
| Number of Latrine Beneficiaries in 2010 |  |  | 31869 | 67350
| Number of Latrine Beneficiaries in 2011 |  |  | 31869 | 99219
| Number of Drainage Beneficiaries |  |  | Yearly Target | Cumulative
| Number of Drainage Beneficiaries in 2008 |  |  | 13580 | 13580
| Number of Drainage Beneficiaries in 2009 |  |  | 20680 | 34260
| Number of Drainage Beneficiaries in 2010 |  |  | 51800 | 86060
| Number of Drainage Beneficiaries in 2011 |  |  | 51800 | 137860
Output Indicator 3.1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of beneficaries in supported low-income settlements receiving: -skills development training (apprenticeships) -small enterprise block grant | The SEF Budget Projection Tool 2007-2011 was used since 2007 to estimate the number of planned apprenticeship and BG beneficiaries
For 2012-2014 Targets see SEF Budget and Beneficiaries Projection Tool 2012-2014 sheet
Apprenticeship Beneficiaries
|  | Planned |  | Achieved
|  | Yearly | Cumulative | Yearly | Cumulative
| # Beneficiaries in 2007 | 289 | 289 | 346 | 346
| # Beneficiaries in 2008 | 2698 | 2987 | 2651 | 2997
| # Beneficiaries in 2009 | 8145 | 11132 | 7422 | 10419
| # Beneficiaries in 2010 | 13334 | 24466 | 14372 | 24791
| # Beneficiaries in 2011 | 13334 | 37800 | 13942 | 38733
Block Grant Beneficiaries
|  | Planned |  | Achieved
|  | Yearly | Cumulative | Yearly | Cumulative
| # Beneficiaries in 2007 | 127 | 127 | 89 | 89
| # Beneficiaries in 2008 | 498 | 625 | 638 | 727
| # Beneficiaries in 2009 | 8446 | 9071 | 6731 | 7458
| # Beneficiaries in 2010 | 12638 | 21709 | 12583 | 20041
| # Beneficiaries in 2011 | 12638 | 34347 | 35498 | 55539
Output Indicator 3.2 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of female and male beneficaries in supported low-income settlements who are employed 3 months to 1 year after receiving: -skills development training (apprenticeships) -small enterprise block grant | It is assumed that 60% of apprenticeship and block grant beneficiaries will be employed 3 months to 1 year after receiving the training or grant.
Output Indicator 3.3 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of female and male children-years of education delivered in supported low-income settlements by: -primary school -secondary school | The SEF Budget Projection Tool 2007-2011 was used since 2007 to estimate the number of planned children-years of education
For 2012-2014 Targets see SEF Budget and Beneficiaries Projection Tool 2012-2014 sheet
Education Grant Beneficiaries
|  | Planned |  | Achieved
|  | Yearly | Cumulative | Yearly | Cumulative
| # Beneficiaries in 2007 | 20 | 20 | 0 | 0
| # Beneficiaries in 2008 | 1412 | 1432 | 1108 | 1108
| # Beneficiaries in 2009 | 6554 | 7986 | 8395 | 9503
| # Beneficiaries in 2010 | 14182 | 22168 | 14650 | 24153
| # Beneficiaries in 2011 | 14182 | 36350 | 23224 | 47377
Output Indicator 3.4 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of beneficiaries in supported low-income settlements receiving: -Iron and folic acid (IFA) -Micronutrient powder (MNP) | Nutrition Intervention logframe targets are used.
Output Indicator 3.5 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of households saving and having access to credit through savings and credit groups | It is assumed that 70% of all mobilized households will be organized into PGs. Once mobilisation is complete in 2012, it is assumed that this percentage will increase to 75% by the end of the programme. It is assumed 50% of PG members will join savings and credit groups, that is, 35% of all mobilised households. As it is assumed that PG coverage will reach 75% by the end of the programme, savings and credit group coverage will increase to 37.5%.
Output Indicator 4.1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of programme towns where low-income settlements are officially recognised by Pourashava Mayors | This indicator reflects the number of towns where the Settlement and Vacant Land Mapping (SLM) findings have been presented to authorities and results have been endorsed. By the end of 2011, this exercise had taken place in Gopalganj, Tongi, Narayanganj and Savar. It is expected that by 2013 all presentations will have been conducted. Dhaka was not included in SLM, thus total number of towns is 22.
Output Indicator 4.2 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of press reports covering urban poverty issues in low-income settlements by: -UPPR-commissioned -Others | The number of press reports will be based on the number of media fellows joining UPPR from March 2012 to August 2014. Media fellows will produce one report on urban poverty per month during each of the 30 months
| Number of Media Fellows joining UPPR from March 2012 - August 2014 |  |  | 8
| Number of Months from March 2012 - August 2014 |  |  | 30
| Number of News Reports Produced per Media Fellow per Month |  |  | 1
| Number of Total News Reports Produced |  |  | 240
| Number of Tenure Security News Reports Produced by end 2012 (Month 10) |  |  | 80
| Number of Tenure Security News Reports Produced by end 2013 (Month 22) |  |  | 176
| Number of Tenure Security News Reports Produced by August 2014 (Month 30) |  |  | 240
Output Indicator 4.3 | Assumptions to Calculate Planned Baselines, Targets and Milestones
# of town-led partnerships and linkages established by the programme
Output Indicator 5.1 | Assumptions to Calculate Planned Baselines, Targets and Milestones
Amount of SIF budget delivered (in GBP and USD) | Revised SIF Budget
| Year | Budget in GBP | Cumulative Budget in GBP
| 2007 | 61670.7067 | 61670.7067
| 2008 | 1185593.7351 | 1247264.4419
| 2009 | 2715507.7922 | 3962772.2341
| 2010 | 1225233.1169 | 5188005.351
| 2011 | 5103362.9245 | 10291368.2755
| 2012 | 6988120.195 | 17279488.4705
| 2013 | 6568277.3585 | 23847765.8289
| 2014 | 152234.1572 | 23999999.9862
| Year | Budget in USD | Cumulative Budget in USD
| 2007 | 128275.07 | 128275.07
| 2008 | 2193348.41 | 2321623.48
| 2009 | 4181882 | 6503505.48
| 2010 | 1886859 | 8390364.48
| 2011 | 8114347.05 | 16504711.53
| 2012 | 11111111.11 | 27615822.64
| 2013 | 10443561 | 38059383.64
| 2014 | 242052.31 | 38301435.95
Output Indicator 5.2 | Assumptions to Calculate Planned Baselines, Targets and Milestones
Amount of SEF budget delivered (in GBP and USD) | Revised SEF Budget
| Year | Budget in GBP | Cumulative Budget in GBP
| 2007 | 13172.0813 | 13172.0813
| 2008 | 37964.4108 | 51136.4921
| 2009 | 2156726.513 | 2207863.0051
| 2010 | 3150698.6364 | 5358561.6414
| 2011 | 3299648.2956 | 8658209.937
| 2012 | 3494060.0981 | 12152270.0351
| 2013 | 2269652.2013 | 14421922.2364
| 2014 | 125786.1635 | 14547708.3999
| Year | Budget in USD | Cumulative Budget in USD
| 2007 | 37276.99 | 37276.99
| 2008 | 70234.16 | 107511.15
| 2009 | 3321358.83 | 3428869.98
| 2010 | 4852075.9 | 8280945.88
| 2011 | 5246440.79 | 13527386.67
| 2012 | 5555555.556 | 19082942.226
| 2013 | 3608747 | 22691689.226
| 2014 | 200000 | 22891689.226
Output Indicator 5.3 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of project human resource positions staffed | Year | Number of Staff Planned | Number of Staff Hired | % of HR Positions Filled
| End 2010 | 382 | 354 | 92.67%
| End 2011 | 390 | 360 | 92.31%
Output Indicator 5.4 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% of new female staff recruited (yearly) | Year | Number of new staff recruited | Number of new female staff recruited | % of New female Staff recruited
| Year 2010 | 87 | 15 | 17.24%
| Year2011 | 24 | 5 | 20.83%
Output Indicator 5.5 | Assumptions to Calculate Planned Baselines, Targets and Milestones
% implementation of Strategic Management Review Recommendations and Organizational Development Plan

## SIF Budget & Benef. '12-'14
ORIGINAL CALCULATION | [8 empty] | REVISED BUDGET | [8 empty] | USING GOVERNMENT RATES FOR 2013 AND 2014
2012 SIF Budget | 11000000 | [7 empty] | 2012 SIF Budget | 10500000 | [7 empty] | 2012 SIF Budget | 10500000
SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH | Achieved to 2011 | SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH | Achieved to 2011 | SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH | Achieved to 2011
Latrines | 34% | 3740000 | 350 | 10686 | 3 | 32057 | 135708 | 89901 | Latrines | 34% | 3570000 | 350 | 10200 | 3 | 30600 | 133626 | 89901 | Latrines | 34% | 3570000 | 350 | 10200 | 3 | 30600 | 133626 | 89901
Community Latrines | 5% | 550000 | 2000 | 275 | 50 | 13750 |  |  | Community Latrines | 5% | 525000 | 2000 | 262.5 | 50 | 13125 |  |  | Community Latrines | 5% | 525000 | 2000 | 262.5 | 50 | 13125
Shallow Tubewells | 5% | 550000 | 400 | 1375 | 15 | 20625 | 139618 | 113070 | Shallow Tubewells | 5% | 525000 | 400 | 1312.5 | 15 | 19687.5 | 138411.3462 | 113070 | Shallow Tubewells | 5% | 525000 | 400 | 1312.5 | 15 | 19687.5 | 138411.3462 | 113070
Deep Tubewells | 7% | 770000 | 6500 | 118 | 50 | 5923 |  |  | Deep Tubewells | 7% | 735000 | 6500 | 113.0769 | 50 | 5653.8462 |  |  | Deep Tubewells | 7% | 735000 | 6500 | 113.0769 | 50 | 5653.8462
Water Reservoirs | 2% | 220000 | 850 | 259 | 50 | 12941 | 23187 | 10246 | Water Reservoirs | 2% | 210000 | 850 | 247.0588 | 50 | 12352.9412 | 22598.9412 | 10246 | Water Reservoirs | 2% | 210000 | 850 | 247.0588 | 50 | 12352.9412 | 22598.9412 | 10246
Drains (km) | 10% | 1100000 | 15000 | 73 | 500 | 36667 | 97512 | 60845 | Drains (km) | 10% | 1050000 | 15000 | 70 | 500 | 35000 | 95845 | 60845 | Drains (km) | 10% | 1050000 | 15000 | 70 | 500 | 35000 | 95845 | 60845
Footpaths (km) | 11% | 1210000 | 9000 | 134 | 500 | 67222 | 209471 | 142249 | Footpaths (km) | 11% | 1155000 | 9000 | 128.3333 | 500 | 64166.6667 | 206415.6667 | 142249 | Footpaths (km) | 11% | 1155000 | 9000 | 128.3333 | 500 | 64166.6667 | 206415.6667 | 142249
Comm. Piped Water Supply | 2% | 220000 | 75000 | 3 | 1000 | 2933 | ?? |  | Comm. Piped Water Supply | 2% | 210000 | 75000 | 2.8 | 1000 | 2800 |  |  | Comm. Piped Water Supply | 2% | 210000 | 75000 | 2.8 | 1000 | 2800
Cooking Stoves | 9% | 990000 | 12 | 82500 | 1 | 82500 | 124805 | 42305 | Cooking Stoves | 9% | 945000 | 12 | 78750 | 1 | 78750 | 121055 | 42305 | Cooking Stoves | 9% | 945000 | 12 | 78750 | 1 | 78750 | 121055 | 42305
Tubewell Platform | 2% | 220000 | 40 | 5500 | 15 | 82500 |  |  | Tubewell Platform | 2% | 210000 | 40 | 5250 | 15 | 78750 |  |  | Tubewell Platform | 2% | 210000 | 40 | 5250 | 15 | 78750
Market Shades | 0% | 33000 | 7000 | 5 | 200 | 943 |  |  | Market Shades | 0.3% | 31500 | 7000 | 4.5 | 200 | 900 |  |  | Market Shades | 0.3% | 31500 | 7000 | 4.5 | 200 | 900
Street Lights | 0% | 22000 | 120 | 183 | 50 | 9167 |  |  | Street Lights | 0.2% | 21000 | 120 | 175 | 50 | 8750 |  |  | Street Lights | 0.2% | 21000 | 120 | 175 | 50 | 8750
Pond Excavations | 0% | 22000 | 6000 | 4 | 200 | 733 |  |  | Pond Excavations | 0.2% | 21000 | 6000 | 3.5 | 200 | 700 |  |  | Pond Excavations | 0.2% | 21000 | 6000 | 3.5 | 200 | 700
Faecal sludge management | 2% | 220000 | 19000 | 12 | 1000 | 11579 |  |  | Faecal sludge management | 2% | 210000 | 19000 | 11.0526 | 1000 | 11052.6316 |  |  | Faecal sludge management | 2% | 210000 | 19000 | 11.0526 | 1000 | 11052.6316
WASH in School | 3% | 330000 | 8000 | 41 | 300 | 12375 |  |  | WASH in School | 3% | 315000 | 8000 | 39.375 | 300 | 11812.5 |  |  | WASH in School | 3% | 315000 | 8000 | 39.375 | 300 | 11812.5
community center | 3% | 330000 | 40000 | 8 | 1000 | 8250 |  |  | community center | 3% | 315000 | 40000 | 7.875 | 1000 | 7875 |  |  | community center | 3% | 315000 | 40000 | 7.875 | 1000 | 7875
Shelter improvement | 3% | 330000 | 200 | 1650 | 1 | 1650 |  |  | Shelter improvement | 3% | 315000 | 200 | 1575 | 1 | 1575 |  |  | Shelter improvement | 3% | 315000 | 200 | 1575 | 1 | 1575
Others | 1% | 143000 | [6 empty] | Others | 1.3% | 136500 | [6 empty] | Others | 1.3% | 136500
| 100% | 11000000 | [7 empty] | 100% | 10500000 | [7 empty] | 100% | 10500000
2013 SIF Budget | 11000000 | [7 empty] | 2013 SIF Budget | 10000000 | [7 empty] | 2013 SIF Budget | 10000000
SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH | Target for 2012 | SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH |  | SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH |  | in Log Frame | LGED RATE 2012
Latrines | 30% | 3300000 | 350 | 9429 | 3 | 28286 | 177744 | 135708 | Latrines | 34% | 3400000 | 350 | 9714.2857 | 3 | 29142.8571 | 175268.8571 | Latrines | Latrines | 34% | 3400000 | 410 | 8292.6829 | 3 | 24878.0488 | 169279.9108 | Latrines | 350 | 410
Community Latrines | 5% | 550000 | 2000 | 275 | 50 | 13750 |  |  | Community Latrines | 5% | 500000 | 2000 | 250 | 50 | 12500 |  | Community Latrines | Community Latrines | 5% | 500000 | 2320 | 215.5172 | 50 | 10775.8621 |  | Community Latrines | 2000 | 2320
Shallow Tubewells | 5% | 550000 | 400 | 1375 | 15 | 20625 | 166166 | 139618 | Shallow Tubewells | 5% | 500000 | 400 | 1250 | 15 | 18750 | 162545.9615 | Shallow Tubewells | Shallow Tubewells | 5% | 500000 | 460 | 1086.9565 | 15 | 16304.3478 | 159231.823 | Shallow Tubewells | 400 | 460
Deep Tubewells | 7% | 770000 | 6500 | 118 | 50 | 5923 |  |  | Deep Tubewells | 7% | 700000 | 6500 | 107.6923 | 50 | 5384.6154 |  | Deep Tubewells | Deep Tubewells | 7% | 700000 | 7750 | 90.3226 | 50 | 4516.129 |  | Deep Tubewells | 6500 | 7550
Water Reservoirs | 2% | 220000 | 850 | 259 | 50 | 12941 | 36128 | 23187 | Water Reservoirs | 2% | 200000 | 850 | 235.2941 | 50 | 11764.7059 | 34363.6471 | Water Reservoirs | Water Reservoirs | 2% | 200000 | 975 | 205.1282 | 50 | 10256.4103 | 32855.3514 | Water Reservoirs | 850 | 975
Drains (km) | 10% | 1100000 | 15000 | 73 | 500 | 36667 | 134179 | 97512 | Drains (km) | 12% | 1200000 | 15000 | 80 | 500 | 40000 | 135845 | Drains (km) | Drains (km) | 12% | 1200000 | 17250 | 69.5652 | 500 | 34782.6087 | 130627.6087 | Drains (km) | 15000 | 17250
Footpaths | 10% | 1100000 | 9000 | 122 | 500 | 61111 | 270582 | 209471 | Footpaths | 11% | 1100000 | 9000 | 122.2222 | 500 | 61111.1111 | 267526.7778 | Footpaths | Footpaths | 11% | 1100000 | 10250 | 107.3171 | 500 | 53658.5366 | 260074.2033 | Footpaths | 9000 | 10250
Comm. Piped Water Supply | 4% | 440000 | 75000 | 6 | 1000 | 5867 |  |  | Comm. Piped Water Supply | 4% | 400000 | 75000 | 5.3333 | 1000 | 5333.3333 |  |  | Comm. Piped Water Supply | 4% | 400000 | 75000 | 5.3333 | 1000 | 5333.3333
Cooking Stoves | 7% | 770000 | 12 | 64167 | 1 | 64167 | 188972 | 124805 | Cooking Stoves | 0% | 0 | 12 | 0 | 1 | 0 |  |  | Cooking Stoves | 0% | 0 | 12 | 0 | 1 | 0
Tubewell Platform | 1% | 110000 | 40 | 2750 | 15 | 41250 |  |  | Tubewell Platform | 2% | 200000 | 40 | 5000 | 15 | 75000 |  |  | Tubewell Platform | 2% | 200000 | 40 | 5000 | 15 | 75000
Market Shades | 1% | 110000 | 7000 | 16 | 200 | 3143 |  |  | Market Shades | 0.3% | 30000 | 7000 | 4.2857 | 200 | 857.1429 |  |  | Market Shades | 0.3% | 30000 | 7000 | 4.2857 | 200 | 857.1429
Street Lights | 0.2% | 22000 | 120 | 183 | 50 | 9167 |  |  | Street Lights | 0.2% | 20000 | 120 | 166.6667 | 50 | 8333.3333 |  |  | Street Lights | 0.2% | 20000 | 120 | 166.6667 | 50 | 8333.3333
Pond Excavations | 2% | 220000 | 6000 | 37 | 200 | 7333 |  |  | Pond Excavations | 0.2% | 20000 | 6000 | 3.3333 | 200 | 666.6667 |  |  | Pond Excavations | 0.2% | 20000 | 6000 | 3.3333 | 200 | 666.6667
Faecal sludge management | 5% | 550000 | 19000 | 29 | 1000 | 28947 |  |  | Faecal sludge management | 5% | 500000 | 26000 | 19.2308 | 1000 | 19230.7692 |  |  | Faecal sludge management | 5% | 500000 | 26000 | 19.2308 | 1000 | 19230.7692
WASH in School | 3% | 330000 | 8000 | 41 | 300 | 12375 |  |  | WASH in School | 0% | 0 | 8000 | 0 | 300 | 0 |  |  | WASH in School | 0% | 0 | 8000 | 0 | 300 | 0
Community center | 2% | 220000 | 40000 | 6 | 1000 | 5500 |  |  | Community center | 3% | 300000 | 40000 | 7.5 | 1000 | 7500 |  |  | Community center | 3% | 300000 | 40000 | 7.5 | 1000 | 7500
Shelter improvement | 3% | 330000 | 200 | 1650 | 1 | 1650 |  |  | Shelter improvement | 3% | 300000 | 200 | 1500 | 1 | 1500 |  |  | Shelter improvement | 3% | 300000 | 200 | 1500 | 1 | 1500
Others | 2.8% | 308000 | [6 empty] | Others | 6.3% | 630000 | [6 empty] | Others | 6.3% | 630000
| 100% | 11000000 | [7 empty] | 100% | 10000000 | [7 empty] | 100% | 10000000
2014 SIF Budget | 240000 | [7 empty] | 2014 SIF Budget | 1076756 | <budget in 2014 | [6 empty] | 2014 SIF Budget | 1076756 | <budget in 2014
SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH | Target for 2013 | SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH |  | SIF Benefits | Proj. Share of Budget | Proj. Budget | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiary HH | Proj. Cumulative Number of Beneficiary HH
Latrines | 10% | 24000 | 350 | 69 | 3 | 206 | 177950 | 177744 | Latrines | 34% | 366097.04 | 350 | 1045.9915 | 3 | 3137.9746 | 179752.7768 | Latrines | Latrines | 34% | 366097.04 | 410 | 892.9196 | 3 | 2678.7588 | 173118.9671
Community Latrines | 0% | $- | 2000 | - | 50 | - |  |  | Community Latrines | 5% | 53837.8 | 2000 | 26.9189 | 50 | 1345.945 |  | Community Latrines | Community Latrines | 5% | 53837.8 | 2320 | 23.2059 | 50 | 1160.2974
Shallow Tubewells | 0% | $- | 400 | - | 15 | - | 166166 | 166166 | Shallow Tubewells | 5% | 53837.8 | 400 | 134.5945 | 15 | 2018.9175 | 165144.6707 | Shallow Tubewells | Shallow Tubewells | 5% | 53837.8 | 460 | 117.0387 | 15 | 1755.5804 | 161473.6804
Deep Tubewells | 0% | $- | 6500 | - | 50 | - |  |  | Deep Tubewells | 7% | 75372.92 | 6500 | 11.5958 | 50 | 579.7917 |  | Deep Tubewells | Deep Tubewells | 7% | 75372.92 | 7750 | 9.7255 | 50 | 486.2769
Water Reservoirs | 0% | $- | 850 | - | 50 | - | 36128 | 36128 | Water Reservoirs | 2% | 21535.12 | 850 | 25.3354 | 50 | 1266.7718 | 35630.4188 | Water Reservoirs | Water Reservoirs | 2% | 21535.12 | 975 | 22.0873 | 50 | 1104.3651 | 33959.7166
Drains (km) | 6% | 14400 | 15000 | 1 | 500 | 480 | 134658 | 134178 | Drains (km) | 12% | 129210.72 | 15000 | 8.614 | 500 | 4307.024 | 140152.024 | Drains (km) | Drains (km) | 12% | 129210.72 | 17250 | 7.4905 | 500 | 3745.2383 | 134372.847
Footpaths | 5% | 12000 | 9000 | 1 | 500 | 667 | 271249 | 270582 | Footpaths | 11% | 118443.16 | 9000 | 13.1604 | 500 | 6580.1756 | 274106.9533 | Footpaths | Footpaths | 11% | 118443.16 | 10250 | 11.5554 | 500 | 5777.7151 | 265851.9184
Others | 79% | 189600 | [6 empty] | Others | 24% | 258421.44 | [6 empty] | Others | 24% | 258421.44
Comm. Piped Water Supply | 0% | $- | 75000 | - | 1000 | - |  |  | Comm. Piped Water Supply | 4% | 43070.24 | 75000 | 0.57427 | 1000 | 574.2699 |  |  | Comm. Piped Water Supply | 4% | 43070.24 | 75000 | 0.57427 | 1000 | 574.2699
Cooking Stoves | 2% | 4800 | 12 | 400 | 1 | 400 | 189372 | 188972 | Cooking Stoves | 0% | 0 | 12 | 0 | 1 | 0 |  |  | Cooking Stoves | 0% | 0 | 12 | 0 | 1 | 0
Tubewell Platform | 0% | $- | 40 | - | 15 | - |  |  | Tubewell Platform | 2% | 21535.12 | 40 | 538.378 | 15 | 8075.67 |  |  | Tubewell Platform | 2% | 21535.12 | 40 | 538.378 | 15 | 8075.67
Market Shades | 0% | $- | 7000 | - | 200 | - |  |  | Market Shades | 0.3% | 3230.268 | 7000 | 0.46147 | 200 | 92.2934 |  |  | Market Shades | 0.3% | 3230.268 | 7000 | 0.46147 | 200 | 92.2934
Street Lights | 0% | $- | 120 | - | 50 | - |  |  | Street Lights | 0.2% | 2153.512 | 120 | 17.9459 | 50 | 897.2967 |  |  | Street Lights | 0.2% | 2153.512 | 120 | 17.9459 | 50 | 897.2967
Pond Excavations | 0% | $- | 6000 | - | 200 | - |  |  | Pond Excavations | 0.2% | 2153.512 | 6000 | 0.35892 | 200 | 71.7837 |  |  | Pond Excavations | 0.2% | 2153.512 | 6000 | 0.35892 | 200 | 71.7837
Faecal sludge management | 0% | $- | 19000 | - | 1000 | - |  |  | Faecal sludge management | 5% | 53837.8 | 26000 | 2.0707 | 1000 | 2070.6846 |  |  | Faecal sludge management | 5% | 53837.8 | 26000 | 2.0707 | 1000 | 2070.6846
WASH in School | 0% | $- | 8000 | - | 300 | - |  |  | WASH in School | 0% | 0 | 8000 | 0 | 300 | 0 |  |  | WASH in School | 0% | 0 | 8000 | 0 | 300 | 0
community center | 0% | $- | 40000 | - | 1000 | - |  |  | community center | 3% | 32302.68 | 40000 | 0.80757 | 1000 | 807.567 |  |  | community center | 3% | 32302.68 | 40000 | 0.80757 | 1000 | 807.567
Shelter improvement | 5% | 12000 | 200 | 60 | 1 | 60 |  |  | Shelter improvement | 3% | 32302.68 | 200 | 161.5134 | 1 | 161.5134 |  |  | Shelter improvement | 3% | 32302.68 | 200 | 161.5134 | 1 | 161.5134
Operations and Maintenance | 72% | 172800 | [6 empty] | Other | 6.3% | 67835.628 | [6 empty] | Other | 6.3% | 67835.628
| 100% | 240000 | [7 empty] | 100% | 1076756 | [7 empty] | 100% | 1076756
| 22240000 | [8 empty] | 21576756 | TOTAL | [7 empty] | 21576756 | TOTAL
[10 empty] | 663244 | variance with original | [7 empty] | 663244 | variance with original

## SEF Budget & Benef. '12-'14
2012 SEF Budget | 6100000
SEF Benefits | Proj. Share of Budget | Proj. Budget | Spending without carry over | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiaries per Unit | Proj. Number of Beneficiaries | Proj. Cumulative Number of Beneficiaries | Remarks
Apprenticeships | 20% | 1220000 | 857941 | 110 | 7799.4636 | 1 | 7799.4636 | 46532.4636 |  | 2012 | 2013
Block Grants | 35% | 2135000 | 2127218 | 60 | 35453.6333 | 1 | 35453.6333 | 90992.6333 | APPRENTICESHIP GRANT DETAILS | Budget | Budget | Budget
Education Grants | 20% | 1220000 | 839215 | 60 | 13986.9167 | 1 | 13986.9167 | 61363.9167 | Trainees under multi-year budget | 362059 | 79876.8 | 28920114331.2
Social Development Grants | 20% | 1220000 | 1220000 | N/A | N/A | N/A | N/A | N/A | New trainees | 857941 | 1870123 | -28918164331.2
UFP Grants (SIS) | 5% | 305000 | 305000 | 10 | 30500 | 1 | 30500 | 77311 | Total | 1220000 | 1949999.8 | 1950000
2013 SEF Budget | 6500000
SEF Benefits | Proj. Share of Budget | Proj. Budget | Spending without carry over | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiaries | Proj. Cumulative Number of Beneficiaries | EDUCATION GRANT DETAILS: |  | Budget | Budget
Apprenticeships | 30% | 1950000 | 1870123 | 110 | 17001.1182 | 1 | 17001.1182 | 63533.5818 | Students under multi-year budget | 380785 | 341460 | 130022846100
Block Grants | 25% | 1625000 | 1625000 | 70 | 23214.2857 | 1 | 23214.2857 | 114206.919 | New students | 839215 | 1738450 | 1458933316750
Education Grants | 32% | 2080000 | 1738540 | 55 | 31609.8182 | 1 | 31609.8182 | 92973.7348 | Total | 1220000 | 2079910 | 2537490200000
Social Development Grants | 8% | 520000 | 520000 | N/A | N/A | N/A | N/A | N/A |  |  |  | 4126446362850
UFP Grants | 5% | 325000 | 325000 | 10 | 32500 | 1 | 32500 | 109811 | BLOCK GRANT DETAILS: |  | Budget
2014 SEF Budget | 500000 | [7 empty] | Beneficiaries under multi year grants | 7782 | 0
SEF Benefits | Proj. Share of Budget | Proj. Budget | Spending without carry over | Est. Unit Cost | Projected Number of Units | Est. Number of Beneficiary HH per Unit | Proj. Number of Beneficiaries | Proj. Cumulative Number of Beneficiaries | New beneficiaires | 2127218 | 0
Apprenticeships | 30% | 150000 | 150000 | 110 | 1363.6364 | 1 | 1363.6364 | 64897.2182 | Total | 2135000 | 0
Block Grants | 24% | 120000 | 120000 | 70 | 1714.2857 | 1 | 1714.2857 | 115921.2048 | NOTE
Education Grants | 32% | 160000 | 160000 | 55 | 2909.0909 | 1 | 2909.0909 | 95882.8258 | AG, 2012; Carryover grant of 362,059 USD for 11,531 trainees and new 7,799 trainees will receive the grant.
Social Development Grants | 9% | 45000 | 45000 | N/A | N/A | N/A | N/A | N/A | EG, 2012; Carryover grant of 380,785 USD for 18,817 students and new 19,070 grants will be given.
UFP Grants | 5% | 25000 | 25000 | 10 | 2500 | 1 | 2500 | 112311 | BG, 2012; Carryover grant of 7,782 USD for 2,199 bussiness starter and new 36,444 grants will be given.
AG, 2013; Carryover grant of 79,877 USD for 2322 trainees and new 17,001 trainees will receive the grant.
EG, 2013; Carryover grant of 341,460 USD for 11,382 students and new 23,214 grants will be given.