Type of Review: Annual Review

Project Title: Adaptation knowledge for policy and programming
Date started: March 2012	Date review undertaken: March 2014
## Introduction and Context

What support is the UK providing?
£2.29[1] million over 2 years to support a programme on adaptation knowledge and tools to be used to maximise the effectiveness of the UK’s International Climate Fund (ICF) on climate change adaptation. This includes the development of guidelines and tools on adaptation programming including on monitoring and evaluation, and economic appraisals to ensure that funds generate maximum results and value for money. The programme will also support work on coordination and coherence around adaptation thinking across the global adaptation community. The programme will share information on adaptation including through the Climate and Environment themesite to DFID’s country offices.
[1] I.E.: £3.15 as per the original business case minus £860,000 for an activity that was transferred to another project. The allocation is for a 3 year period split into 2 phases, this Annual Review relates to the second year of the first phase.

What are the expected results?
The programme aims to ensure that international investments in climate change adaptation (including from the UK) are informed by relevant knowledge, lessons learnt and design tools. This is intended to ensure that results from adaptation programmes – numbers of poor people helped to cope with the impacts of climate change – are achieved. The expected outputs are: / Output 1: Better knowledge around what constitutes best practice in adaptation including on social protection, local accountability and on private sector engagement. / Output 2: Better international coherence and coordination of climate change adaptation including adaptation monitoring and evaluation, frameworks, and communities of practice. / Output 3: ‘Tools of the trade’ to support the effective delivery of ICF spending on adaptation including on value for money, low regret options, guidance on cost benefit appraisals, and decision tools on uncertainty.

What is the context in which UK support is provided?
Adaptation is a vital element of international action on climate change, and up to 50% of the UK’s International Climate Fund (ICF) is targeted at adaptation programmes. The objectives of the UK’s adaptation activities under the ICF are to: / Develop the building blocks for adaptation – knowledge, evidence, capacity, and institutions; / Support programmes in agriculture, disaster risk and reduction, infrastructure, urban, health, coastal zone and eco systems, social protection, and water resources management. / Support effective national and international climate architecture on adaptation financing. / To deliver the UK objectives on adaptation through the ICF, three major gaps have been identified that need to be filled to ensure successful programmes and results: / Firstly, there is a knowledge gap – no clear agreement exists internationally about what adaptation “looks like” or how to measure or demonstrate successful interventions especially in the short term. / Secondly, there is a coordination and coherence gap – this leads to limited understanding across the international development community of how adaptation actions and investments should be prioritised and how adaptation can be programmed most effectively. / Thirdly, there is a gap in the ‘tools of the trade’ – for example project management tools such as M&E and economic appraisal, and options development have not been extensively applied, or adapted, for adaptation programmes

## Section A: Detailed Output Scoring

Output 1 Better knowledge around what constitutes best practice in adaptation including on social protection, local accountability, on private sector engagement.
Output 1 score and performance description: A+ / Last year’s annual review mentioned 1 completed study on ‘adaptive social protection and migration’. This year saw the completion of an additional 6 studies; a further 2 studies are on-going, due to report in April and May. These include: / 1 study on how economies respond to disasters / 2 studies on public finance related issues (one on country preparedness to manage international climate funds and one on the role of international public finance for adaptation); / 4 sectoral guidance products on adaptation and value chains of major agricultural commodities, water, sanitation and hygiene, risk transfer mechanisms and hydropower sector performance / 1 study on the opportunities and barriers for private sector engagement in adaptation. / Five of the 6 newly completed studies were assessed as highly relevant to the global knowledge pool on adaptation; the other being of medium relevance. Three of those 6 represent outstanding quality products; the other 3 being of moderate to good quality. One product was tied in to a specific policy process (PPCR) but has been used in other forums (LDCF, AF, WB, AsDB, ADB, IADB etc) and shared with other donors (GIZ, USAID, AUSAID/DFAT) and another was used as input into a business case design process (risk transfer); the other products consisted of stand-alone products that are directly relevant to a range of adaptation aims. / Specific Examples of Knowledge Products use and impacts/uptake. / Climate Finance Report exploring the role of international public finance for adaptation - Used to inform UNFCCC and GCF negotiations on adaptation finance, report highlighted that current flows were not targeted at the most vulnerable and the need for explicit criteria to be used to target adaptation funding to avoid political bias in allocation decisions. / Assessment of opportunities and barriers for private sector innovation, and investment from the private sector on disaster risk resilience and climate change adaptation – joint report with CHASE to highlight potential for Private Sector support in adaptation - directly targeted to inform GCF design, evidence of influence in current GCF documentation. / Monitoring and Evaluation The Knowledge fund has worked on a number of M&E projects to address the complex issues of measuring climate adaptation and resilience. / Strengthening and developing Key Performance Indicators relevant for adaptation / Support on national approaches to adaptation M&E through OECD; and / Joint USAID/ GIZ/ DFID workshop in Bonn to advance the international discussion on adaptation M&E - These projects have defined the adaptation indicators for the UK International Climate Fund (ICF), informed the design of the GCF and are informing the UNFCCC and DAC approaches to monitoring of climate adaptation to establish international norms that will also be used in the Post 2015 MDG framework. / This work is continuing through current programmes , for example: / Measuring the impact of DFID programmes on resilience - which has developed the monitoring framework for the £150m BRACED programme. Help compare selection of partners’ adaptation results frameworks and their indicators to find similarities and identify where core indicators may be developed. - Being used to inform the M&E framework of the GCF, OECD-DAC adaptation indicators and the UNFCCC Adaptation Committee work on M&E. / Sectoral Products / Analysis of the risks to deliver water, sanitation and hygiene results posed by climate change: / Highlights issues and quantifies the economic benefits of integrating climate change into water and sanitation programmes. Used to develop Business Cases (Sudan, Kenya, Tanzania in the 2014 ICF bidding round). / Evaluate how cash transfers enable households and communities to choose migration as an effective adaptation strategy, what systems, mechanisms and policies could improve this choice. This project directly informed the design of the Sahel adaptive social protection programme under ARD and the 2014 current ICF bids for migration support proposal from DFID Burma and social protection support from DFID Nepal. / Expand the knowledge base on risk transfer mechanisms in managing risks from climate change impacts, and provide support to Africa Risk Capacity (ARC). This programme developed economic models on the impacts national/regional of risk insurance which provided additional evidence to support the £100m ARC programme implemented by DFID’s Africa Regional Team.
Progress against expected results: / Actions on last year’s recommendations: most projects were completed within acceptable time limits for these kinds of deliverables. The products related to this output are those that are most used by teams internally (see further). Three products were aimed at specific international processes (PPCR, negotiations and GCF). The piece on private sector engagement in adaptation is a very nice example of a strategically commissioned knowledge product that has fed important lessons into the design of the GCF. The original business case intended this output to deliver 6 products – with 8 produced so far, delivery has so far moderately exceeded expectations. / Recommendations: / 1. Most of the studies commissioned under this output were aimed at particular policy processes. It is now important to draw out the main lessons from each one of those studies and publish them under a common format to serve as general guidance to policy makers in and outside DFID / 2. Product quality could in some cases be improved – a couple of the sector guidance notes tended to veer off focus and used less credible evidence sources. The project team must ensure standards by putting in place a more rigorous quality assurance process. / Impact Weighting (%): 33 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Better international coherence and coordination of climate change adaptation including adaptation monitoring and evaluation, frameworks, and communities of practice around adaptation.
Output 2 score and performance description: B / Last year’s annual review reported on the completion of 1 workshop on tracking successful adaptation through smart monitoring approaches. This year saw the completion of the OECD study of monitoring experiences in 3 distinct national settings. A comparative study of development partners’ results frameworks is due to report in April, which will inform further discussions with OECD DAC and key development partners, OECD-DAC, GIZ, WB and USAID. A number of products under output 3 have relevant lessons that contributed to progress under this output. / The newly completed study is highly relevant to the global knowledge pool on monitoring and evaluation of national resilience and is good quality. It was tied in to a specific cross-donor policy process (OECD), which has contributed to its impact and lesson learning.
Progress against expected results: / Last year’s annual review suggested that the project team make efforts to extend the results of this work to the wider community, ie: UNFCCC, OECD and bilateral donors. This has been followed up; this is continuing with active engagement of CED advisers in UNFCCC, Post MDG, OECD and GCF work on climate adapation M&E. / The original project intended to provide support to 2 international adaptation learning forums. On querying this particular issue it has become clear that those initiatives are not yet in a position to receive support from us. The original business case intended this output to deliver 3 products – with 3 produced so far, delivery of knowledge products for M&E has so far met expectation. The focus, however, has been on monitoring and evaluation products, and less on facilitating international coherence– hence the categorisation of B for this component. / Recommendations: / 1. Ensure the 3rd product under this output is delivered, quality assured and communicated internally and externally in good time / 2. This output has two distinct foci: (i) to strengthen international lesson sharing on adaptation in general (M&E, frameworks and communities of practice) and (ii) help define best practice in adaptation monitoring and evaluation and facilitate agreement on international networks. The team will need to develop a strategy, with specific indicators, to address both aims. / Impact Weighting (%): 33 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y / There is a risk that this output will not be achieved. Mitigating action: Engage more pro-actively in these international forums.

Output 3: ‘Tools of the trade’ to support the effective delivery of ICF spending on adaptation including on value for money, low regret options, guidance on cost benefit appraisals, and decision tools on uncertainty
Output 3 score and performance description: B / Last year’s annual review reported the completion of 1 knowledge product on KPI’s for use by the ICF. An additional 2 projects were commissioned under this output, which are close to being delivered, on: early value for money for adaptation and how to measure project impacts (particularly on resilience) from ICF investments. / A preview of the 2 on-going studies shows that they are highly relevant to both DFID and the international community and of very high quality. While designed specifically to help inform the design and impact assessment of ICF funded projects, both pieces of work are likely to move the global discourse on adaptation planning and evaluation significantly forward. They also represent a very significant contribution towards Future Fit and the reform process of the climate and environment assessment.
Progress against expected results: / Last year’s Annual Review suggested that the team develop TOR’s for the second phase of the value for money study. This recommendation was followed up. The business case mentions ‘number of hits on the adaptation theme-site’, ‘uptake of the approach in BC design’ and ‘visible replication of UK practice elsewhere’. It has not been possible to measure progress against those indicators as the work is not yet complete; however, reaction to the various internal and external audiences where the preliminary results from this work were aired shows that both pieces of work will become highly influential once completed in March/April. The reviewer has used the draft versions of the ‘early value for money’ in his own work on Future Fit tools and in international conferences and workshops on evidence based adaptation planning and tools. The original business case intended this output to deliver 6 products – with 3 produced so far and some delays in implementation, delivery under this output has been moderately below expectation – hence the categorisation as B. / Recommendations: / 1. Follow delivery by consultants very closely and ensure no further delays in delivery are experienced. / 2. Liaise with the Head of Profession, Climate and Environment and Head of Profession, Economists to ensure the material is translated into technical guidance and exposure to it promoted through CPD conferences. / 3. Develop and implement dissemination strategies for products. / Impact Weighting (%): 33 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / The programme has no log-frame. A log-frame must be developed as a matter of urgency. / 1.2 Overall Output Score and Description: B / 1.3 Direct feedback from beneficiaries / A simple questionnaire was sent across the climate and environment advisory cadre in DFID to check levels of awareness and rating of the products that have been delivered so far. One third of respondents (15% of people targeted) were not aware of any of the project’s products – this is an underestimate: the majority of those who did not respond will have used/seen products probably but are unaware that they are funded under this project. Respondents were aware of 5 out of the ten products completed so far. One third of the respondents declared that they had used the products in their work. Most aware / used are the sector guidance products, followed by those that were aimed at particular policy outcomes. There is direct evidence that those products aimed at particular international fora (6 out of the 10) have been used externally. / Feedback on quality of the products, where received, was positive. The reviewer, who is a rated most of the products as of high relevance and quality – see details under each output.
1.4 Summary of overall progress / The project outputs largely met expectations, except for output 2 where activities have so far been restricted to monitoring and evaluation and the project team need to increase the amount of work with international forums to ensure good use of the products. The majority of the products delivered by this project are of high relevance and quality – some are outstanding and are poised to influence the international debates on adaptation planning, finance and measuring.
1.5 Key challenges / This project faces 3 challenges: strategic focus, communication and management. / Strategic focus: The products developed under this project have, on the whole, addressed the objectives as defined in the business case. Six out of the 15 projects funded so far have responded to immediate policy / project needs – the other 9 were developed more systematically around the original thematic foci. The specific deliverables aimed at immediate needs were, on average, much smaller (mean budget: £19,500) than those that were developed systematically around the original thematic foci (mean budget: £63,500), which means that only 17% of the budget allocated so far has been used to respond to immediate opportunities. / While this proportion between ‘response’ and ‘planned’ modes of delivery is about right, and could possibly be stretched further in favour of ‘opportunistic’ responses, the project team need to be clearer on how specific topics are selected, and how demand is identified.
Communication: while efforts seem to have been made to disseminate and use the products generated by this project, the large numbers of climate and environment advisors who were unaware of this project / products seem to indicate a challenge of communication. Not all products are in a form that can be shared immediately as they were developed for specific internal / external processes. / Management: this is a potentially management intensive project, as each individual piece of work needs contracting separately. The fact that there are some delivery delays and there exists a significant shortfall in financial outlay in comparison to the budget foreseen for this project, seems to indicate that management is a challenge. / The products are not presented under a common format and the fact that some products tended to veer off target in places seems to indicate that there is a quality assurance issue. / It has been hard to trace the final products, and the reviewer has had to revert back to the individual product leads to gain access to them. This seems to indicate an archiving challenge. / Finally, the project doesn’t have a log-frame, which makes measuring progress difficult and subjective. Some of the success indicators in the Business Case are not necessarily as easy to measure as the project team had assumed. / 1.6 Annual Outcome Assessment / The project outcome has been stated as follows: / ‘International investments in climate change adaptation (including from the UK) are of a higher quality as a result of strengthened tools, knowledge about adaptation and international coordination’. / The aim of the project is to improve the development of adaptation projects under the ICF. A large number (if not all) of individual product leads play an instrumental role in ICF adaptation projects, either as developer or as peer reviewer in the concept not stage. It is very likely, therefore, that the learning from the individual products has been reflected in individual ICF projects. Measuring the extent to which the project has managed, thus far, to effect influence beyond this point would require a separate impact evaluation which should be considered as part of next year’s annual/project completion review. / Given the time-bound nature of this particular investment and the long term nature of the outcome as originally stated in the business case, it is probably safer to consider it as the project impact rather than as outcome, and define an intermediate, immediately measurable result as outcome – e.g: ‘increased availability of project development knowledge and tools to International Climate Fund adaptation projects’. This should be considered in the development of the project log-frame.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / Using the sum of the individual budget allocations commissioned so far (£677,793), it appears that the project has disbursed well below the original budget of £2.29m. This is partly due to slow commissioning of products. In addition given that the team has managed to deliver the number of products originally intended in the business case, this indicates that the BC had originally over-estimated the unit costs of these deliverables and has managed to deliver them at lower cost. / 2.2 Key cost drivers / Costs of researchers and consultants employed to deliver the individual knowledge products. / 2.3 Is the project on-track against original timescale: Y / By year 2 of the project, the team has managed to commission and deliver the forecast number of products that had originally been foreseen in the business case.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are a growing number of actors nationally and internationally who are contributing to the subject matter targeted by this project, but these changes have not diminished the need for specific guidance to aid project development in adaptation. DFID continues to be considered as a thought leader in this area and the products generated so far are of a quality that will ensure DFID maintains this reputation. As such the project remains as relevant as ever. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation has been planned for this project yet. It should however be considered for inclusion in the evaluations considered in the CED M&E programme for 2015.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / Last year’s risk assessment continues to apply this year: i.e: there is a moderate risk that key knowledge products are not used as well as they could be. The project team must tackle this risk in a more pro-active manner as part of the programmes performance improvement plan.
Risk of funds not being used as intended / Low. There is a risk that knowledge generating initiatives such as this one are used as a short-cut for project development. The reviewer has only seen 1 instance out of the 15 studies looked at and the proportion of funds allocated to satisfy immediate needs is low (15% of the total allocated so far). / 4.4 Climate and Environment Risk / There are no significant environmental and/or climate risks attached to the activities funded by this project. In fact the opposite, the project represents a very significant contribution to DFID’s climate change objectives

5. Value for Money
5.1 Performance on VfM measures / Value for money has been ensured through the competitive bidding for small-scale procurement contracts whilst being proportionate for smaller/specialist pieces of work. The programme has also strengthened knowledge partners’ capacity to deliver adaptation policy and programming advice. In addition, through reducing staff time by removing the need for full business cases for each individual piece of work, and taking advantage of the economies of scale provided through other knowledge frameworks, and policy coherence built from the framework VFM had been maintained. / The products and tools provided will ensure an improved quality and lower risk profile to ICF investments. The programme will regularly assess VFM and achievements of impacts, including through annual reviews, as part of the monitoring framework. / 5.2 Commercial Improvement and Value for Money / The programme is managed by the Adaptation and Water Resources Management team in Climate and Environment Department. Procurement is being handled through individual contracts and through the Professional Evidence and Applied Knowledge Services (PEAKS) framework agreement. Where projects have been tendered VFM criteria have been central to decisions on the award of contracts. / 5.3 Role of project partners / Direct contracting and use of existing frameworks are the main implementation modality. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
This project represents a worthwhile investment, generating knowledge that is essential to measuring and maximising the benefits from the ICF (and other international CC funds) investments in CC adaptation. The knowledge generated so far is generally of a high standard and has directly informed UK investments, and climate negotiation positions and activities and investments by other players. In many cases it has been used directly in programme design and international negotiation and lesson learning forums. / The project could increase its effectiveness in 3 ways: / 1. by more systematically identifying and prioritising knowledge needs; / 2. by converting the final products into forms that are directly usable as tools in project design/management and M&E; and / 3. by engaging pro-actively in international fora to disseminate lessons learnt (there are some examples of this already but this needs to be done more systematically). / There are a number of management issues that MUST be addressed: / 1. contracting out core project management actions such as procurement, payments etc., to reduce the load on admin staff / 2. systematic and effective archiving of final products to facilitate access – including by external users (via the DFID external web) / 3. develop a log-frame, standard reporting formats and a consistent quality assurance process. / As a result of these shortcomings it is recommended that: / The programme immediately develops a performance improvement plan to address the management shortcomings identified above, e.g. logframe, product archive/knowledge management and Quality assurance. / Reduce the management load of the programme e.g. by better use of the PEAKs framework to provide knowledge and management services. / Identify opportunities for working more closely with related programmes, in particular CDKN, the CED Monitoring and Evaluation Programme and the Research and Evidence Department’s Climate and Environment research programme. / Develop a well-defined delivery plan for 2014/15 based on clearly identified research knowledge product priorities / Identify opportunities for merging the programme with other programmes (M&E programme or CDKN) by March 2015.

8. Review Process
The review was conducted by a senior climate and environment adviser with extensive experience in the subject matter and external to the Team and Division. The process involved: / An evaluation of all project documentation and of 90% of project deliverables / A one to one discussion with the team – leader of the adaptation team / A simple questionnaire to all C&E advisers to gage awareness and use of the products generated under this project / Triangulation of evaluation findings against product leads.

Strengthening Knowledge and Tools for Climate Change Adaptation – Project List

Proj No.	Title	Countries supported	Amount
	Evaluate how cash transfers enable households and communities to choose migration as an effective adaptation strategy, what systems, mechanisms and policies could improve this choice	Malawi, Kenya, Ethiopia and Tanzania	£71,608
	Strengthening and developing Key Performance Indicators relevant for adaptation and suggestions for second tier indicators	Global	£26,394
	Deliver a joint USAID/ GIZ/ DFID workshop in Bonn which would seek to / advance the international discussion on adaptation M&E	Global	£9,063
	Assessment of national institutional arrangements and coordination for PPCR	Nepal, Bangladesh, Tajikistan, Zambia, Bolivia and Mozambique	£13,220
	Support on national approaches to adaptation M&E through OECD - Phase 1	Nepal case study	£50,000
	Supporting climate resilience in value chains	Pakistan Tanzania, Bangladesh and Kenya, Rwanda and Ethiopia	£14,447
	Analysis of the risks to deliver water, sanitation and hygiene results posed by / climate change	Malawi, Tanzania and Sierra Leone	£85,000
	Research study to identify options for climate change adaptation that offer / good value for money	Zanzibar and Rwanda	£121,704
	Hydropower sector performance study and the impact of climate change	Case study countries are Malawi, Nepal, India and Ethiopia	£86,375
	Assessment of opportunities and barriers for private sector innovation, and investment from the private sector on disaster risk resilience and climate change adaptation	Case study countries were Bangladesh, Kenya, Mozambique and Pakistan	£94,724
	Expand the knowledge base on risk transfer mechanisms in managing risks from climate change impacts, and provide support to Africa Risk Capacity (ARC)	Africa regional	£10,100
	Report exploring the role of international public finance for adaptation	Global	£38,508
	Help understand how economies respond to natural disasters	Global	£30,020
	To measure the impact of DFID programmes on resilience, to inform improved value for money of future programmes	Global	£28,630
	Help compare selection of partners’ adaptation results frameworks and their / indicators to find similarities and identify where core indicators may be developed	Global	£8,000
	DFID Tanzania support for building resilience	Tanzania	£60/70k
	Increasing the resilience and low carbon characteristics of schools	Pakistan, India, Nepal, Bangladesh, Burma	£80k
	Agriculture and UNFCCC		£10k
	Topic guide – climate smart agriculture		£25k
	Community-based adaptation		£30k
	Contribution to WB report on Climate Change and Poverty

Key:

Complete
Ongoing
About to start