Annual Review - Summary Sheet (2016)

Title: Investments in Forests and Sustainable Land Use
Programme Value: £60m		Review Date: 9th December 2016
Programme Code: GB-1-202745	Start Date: 09/12/2016	End Date: 08/12/2020

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020
Programme Score	A	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review (Year 2)
Progress has been good. The Tropical Forest Alliance (TFA) has demonstrated its value as an effective platform for public-private collaboration. Partner engagement is increasing, with an important rise in developing country participation. The TFA Africa Palm Oil Initiative achieved a major milestone with the Marrakesh Declaration for the sustainable development of the palm oil industry in Africa.

Support to the Amsterdam Declarations, initiated by the Netherlands in December 2015 and signed by Norway, Germany, France, Denmark and the UK, is helping to establish this initiative as a platform for governments to promote cooperation on demand-side policy measures for sustainable commodities.

The technical assistance facility, Partnerships for Forests (P4F), completed its inception and is now operational. A strong team has been mobilised, through a UK office and hubs in Accra, Addis Abba and Jakarta, covering West and Central Africa, East Africa and Southeast Asia respectively; effective management systems have been established; and a gender and social inclusion strategy has been adopted to ensure that programme interventions realise maximum development impact.

A portfolio of public-private partnerships is under development. Engagement by the P4F team is helping to catalyse action to establish or strengthen partnerships, encourage innovation and assist partners to set out ambitious plans (see key results). A first call for proposals has also been concluded for the West and Central Africa region, highlighting demand for the programme which greatly exceeded expectations.

Progress to establish management arrangements for development capital investment has been slower, but options for this are still under review. The tender for the Evaluation Manager has been completed.

Summary of recommendations for the next year
Work with TFA partners to maintain a sharp focus on realising supply chain sustainability commitments, and work with donors, companies and NGOs to catalyse investment and support for implementation of the TFA Africa Palm Oil Initiative;

Work with Amsterdam Declaration signatory countries to establish the initiative as an effective platform for cooperation on demand-side measures;

Expand the partnership portfolio across the three programme regions; conclude calls for proposals in Southeast Asia and East Africa; undertake learning around characteristics required for partnerships to advance through the early decision gates in the programme operating model.

Work with DFID’s Private Sector Department (PSD) to continue exploring options for development capital investment, as outlined in the programme business case.

Draw lessons from early-stage support to public-private partnerships, and share findings with other donors, supply chains companies, potential private investors and other key stakeholders.

See below for further detailed recommendations.
A. Introduction and Context

DevTracker Link to Business Case:	Business case
DevTracker Link to Log frame:	Log frame

Investments in forests and sustainable land use
The Global Goals (2015) and the Paris Agreement (2015) set out a pathway towards sustainable economic development which limits climate change well below 20C. Over one billion people depend on forest products for their livelihoods, while deforestation and wider land use change account for one quarter of global greenhouse gas emissions. Better management of forests is important to realising both the Global Goals and the Paris Agreement.

With this framework in place, the agenda now turns urgently to implementation, putting commitments into practice and establishing the partnerships required to realise the aims of the Global Goals and the Paris Agreement. Clearance of forests for a small number of agricultural commodities accounts for over two-thirds of annual deforestation in developing countries, but over 400 companies now have commitments to reduce deforestation caused by agricultural commodity supply chains.

Investments in Forests and Sustainable Land Use (IFSLU) has been established to accelerate this opportunity, supporting new partnerships and developing new business models which bring about a transformation in existing supply chains and business practices, and developing new models of doing business which create value and support economic growth through the sustainable use of forests and land.

The business case sets out a £137.4m programme, comprising £60m for grants and technical assistance and £70m development capital investment as the initial phase of a 10-15 year programme. Only the grant and technical assistance is currently operational.

Impact: Reduced deforestation leading to reduced greenhouse gas emissions, reduced poverty and conservation of biodiversity. Progress indicators include:
- Rate of deforestation in developing countries.
- Volume of CO2e emissions from avoided deforestation and degradation and reforestation.

Outcome: Increased private investment in forestry and ‘reduced-deforestation’ agriculture support economic growth, improved livelihoods and reduced poverty.
- Level of private investment mobilised.
- Area of land under improved (sustainable land use) management.
- Number and description of cases where there has been a change in livelihoods and / or employment and / or reduced poverty.

Outputs: The four programme outputs are focused on creating the conditions which facilitate investment by companies in forests and sustainable land use. These comprise:

Demand-side measures: An enhanced market for sustainably sourced products through public and private commitments to sustainable sourcing.

Enabling conditions: Improved business environment for investments in sustainable forests and sustainable land use.

Partnerships and investments: Partnerships between private sector, public sector and communities supported that seek to deliver investment in forests and sustainable land use.

Leadership, collaboration and learning: Models, learning and leadership that support collaboration and investment in forests and sustainable land use.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Mobilising the Partnerships for Forests technical assistance facility has been the Year 2 priority, and this has been successfully accomplished. It is still too early to make a definitive statement on the programme outcome, but the extensive pipeline of potential projects identified, high demand evident through the first call for proposals, and level of interest amongst potential investors, suggests that there are good prospects for achieving the programme outcome, subject to the assumptions identified in the programme theory of change.

Overall output score and description
The programme is assessed as ‘A: outputs met expectations’.

The inception phase for Partnerships for Forests commenced on 1st January 2016 and was concluded on 30th June 2016. A strong team has been mobilised; an office has been established in Bristol, with regional hubs in Accra (West and Central Africa), Addis Ababa (East Africa) and Jakarta (Southeast Asia); strategies for the three regions were developed; robust financial management, due diligence and project review systems were established; monitoring, evaluation and learning systems were established; the theory of change was refreshed; and the programme logical framework was updated.

A Gender and Social Inclusion Strategy has also been developed to integrate gender issues across programme activities, including overarching principles, assessment criteria for partnerships, and identification of opportunities for specific support to increase gender impacts. Regional teams are receiving specific training on the gender strategy. The P4F programme will also undertake an annual gender and social inclusion health check to monitor the implementation of the strategy.

Consultation and outreach has been undertaken to identify a pipeline of potential projects and partnerships, and the first call for proposals has been concluded in the West and Central Africa region, attracting 116 concept notes. A shortlist of high potential partnerships has been taken forward at an accelerated rate, to ensure that the programme begins to make progress against its specified outputs at the earliest possible opportunity. Many of these fast-tracked partnerships now form the initial portfolio which is in place at the time of this annual review.

Output 1 (demand-side measures) is meeting expectations. Continued progress has been made towards establishing the Tropical Forest Alliance as an effective platform for convening companies and governments on the sustainable sourcing of agricultural commodities associated with deforestation. Through the Amsterdam Declarations, initial steps have been taken to establish cooperation between governments on demand-side policy measures which give further impetus to private sector-led initiatives.

Output 2 (enabling conditions) is meeting expectations due to support delivered through and around the TFA, focused on enhancing the enabling conditions for sustainable palm oil development and the realisation of zero deforestation sourcing and production commitments. In West Africa this support has resulted in the engagement of ten countries in the TFA Africa Palm Oil Initiative, which is setting out a framework for the sustainable development of the palm oil industry in the West and Central Africa regions. In Indonesia, support to the secretariat for the Indonesian Palm Oil Pledge (IPOP), delivered through the TFA, has faced significant challenges but has also contributed towards some positive developments.

Output 3 (finance and investments) is meeting expectations, with grant and technical assistance agreements established for the first forest partnerships in East Africa and Southeast Asia. Further partnerships are close to approval in all regions of interest to the programme; and the first call for proposals has been concluded in the West and Central Africa region, attracting a very strong response. Options for development capital investment are still under review.

Output 4 (leadership, collaboration and learning) is meeting expectations, through drawing initial lessons on establishing public-private collaboration around the challenges which the programme has been set up to address; and through collaboration to make a success of high profile events, such providing support to the ministerial signing ceremony for the TFA Africa Palm Oil Initiative in Marrakesh.
Key results
West and Central Africa is a new frontier for palm oil development. This offers an opportunity for economic development, growth, jobs, livelihoods and food security, but it also poses a risk, illustrated by the rapid and poorly planned expansion of the industry in Southeast Asia, and its legacy of environmental destruction, land conflict, dispossession of local communities and annually recurring peatland fires.

A strong portfolio of interventions is being established around the emerging African palm oil industry. This includes interventions through the TFA (private sector sustainable sourcing commitments) and the Amsterdam Declarations (public sector policy to support sustainable sourcing of palm oil); commitment to regional and national reforms for a sustainable palm oil industry, secured through a consensus-building multi-stakeholder process under the TFA’s Africa Palm Oil Initiative; and public-private partnerships with companies present in the region to catalyse investment in sustainable palm oil.

Individually, each of these interventions is significant. Taken together, they offer transformational potential, ensuring the industry contributes to development whilst avoiding the negative impacts associated with the rapid and poorly planned expansion of palm oil investment in Southeast Asia. They also illustrate the programme theory of change, through influencing markets (demand-side); securing key reforms (enabling conditions); and leveraging investment into sustainable production (supply-side).

Key lessons
Validation of business case: Engagement with companies during the inception of Partnerships for Forests has confirmed the business case for the programme, highlighting that public funds can play a strategic role in accelerating private-sector initiatives to address deforestation, if used in flexible and adaptive ways to unite public and private agendas.

Focus on implementing existing commitments: Private voluntary commitments to address deforestation now span over 400 companies across the palm oil, timber, soya, beef, cocoa, coffee and other supply chains. The focus of the programme needs to be on implementing existing commitments rather than generating new commitments.

Make markets work for smallholders: Smallholders play a major role in most commodity supply chains, and fulfilling private sector voluntary commitments requires a major shift in the smallholder production base. This is challenging for both public and private sectors. Issues which need to be considered include legal tenure to land, access rights to resources, access to capital and technical expertise, as well as models of working with large numbers of smallholders efficiently.

Adapt to changing conditions: The programme is working with a dynamic partnership approach while operating in a dynamic context, and needs to remain nimble and flexible to achieve the greatest impact.

Leverage private and public finance: The demands for support from the programme greatly exceed the available funds. Leveraging additional sources of public funds, such as the Green Climate Fund, and private finance, will be critical to its success. Implementing the development capital investment set out in the business case will add value to efforts to leverage additional private finance.

Key actions
See recommendations on summary sheet.

Has the log frame been updated since the last review?
The log frame has been updated to reflect the mobilisation of Partnerships for Forests. Impact and Outcome remain unchanged, but relevant indicators have been improved and embedded within the monitoring, evaluation and learning framework. Output Indicators, Milestones and Targets have also been updated. A new Output 4 covering Leadership, Collaboration and Learning has been introduced, along with relevant indicators, reflecting the important role which these themes will play in developing, demonstrating and replicating sustainable business models. The log frame and theory of change will be reviewed again in 2017, in collaboration with the newly appointed Evaluation Manager. Steps will also be taken to ensure that gender disaggregated data is collected where possible, to document how the programme is delivering a gender sensitive and progressive approach for women and girls.
## C: DETAILED OUTPUT SCORING

Output Title	Demand-side measures: An enhanced market for sustainably sourced products through public and private commitments to sustainable sourcing
Output number per LF		#1	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
# and description of cases where P4F have supported demand side policy change and development, at public (sub-national, national or international) or corporate level, that enhance forests and sustainable land use investment.	1 case by 2017	On track: Financing provided to a secretariat for the Amsterdam Declarations. This has not yet resulted in policy change, but is creating the conditions for change to happen.
# and description of cases where P4F have contributed to value or commodity chain change with regards to enhanced forests and sustainable land use.	N/A (Target: 1 case by 2019)	On track: Ethiopia wild coffee partnership emphasises links to high-value US and European roasters and retailers, with initial contacts established. Other forest partnerships will also require complementary demand-side support.

Key Points
Good progress has been made towards establishing the Tropical Forest Alliance as an effective platform for public-private cooperation to realise sustainable supply chains. Funding for the TFA secretariat, hosted in the World Economic Forum, is provided in collaboration with Norway. The Netherlands also committed funding to the secretariat in 2016, increasing the funding base and broadening ownership, while the US, as the founder of the alliance, remains strongly engaged.

TFA Regional Coordinators have been appointed in Latin America, Southeast Asia and West and Central Africa, hosted by partner organisations (The Nature Conservancy, the Indonesian Business Council for Sustainable Development and Partnerships for Forests West and Central Africa Hub respectively). Developing country engagement has increased, with six African governments joining, along with Colombia as the first Latin American government represented in the alliance. The first general assembly of partners was held in Indonesia in March 2015, and six key regional and thematic work streams have been established and are engaging diverse partners in the alliance.

The Amsterdam Declarations, initiated by the Netherlands in December 2015 and signed by Norway, Germany, France, Denmark and the UK, offer an opportunity to engage governments and promote cooperation on demand-side policy measures which support and complement private sector-led initiatives. DFID engagement has helped to bring early direction to the initiative, helping to convene a dialogue on sustainable sourcing with a Chinese delegation, chairing the group following initial Netherlands leadership, and providing funding to a secretariat which is helping the signatory countries to deepen their collaboration.

Recommendations
Continue to offer strong support to the TFA, aiming to ensure that the alliance maintains a sharp focus on realising supply chain sustainability commitments; maintains a high level of private sector engagement; and establishes a strong and effective regional presence;

Establish the Amsterdam Declarations as an effective network and demonstrate the added-value of the initiative through a shared work plan and initial cooperation on demand-side measures;

Identify opportunities to maintain and enhance UK engagement on demand-side measures, in the lead-up to and after British exit from the European Union, working in collaboration with BEIS and Defra.

Output Title	Enabling conditions: Improved business environment for investments in forests and sustainable land use
Output number per LF		#2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
# and description of cases where P4F has supported organisational change or national / international initiatives designed to enable private investment in forests and sustainable land use.	1 case by 2018	On track: Support for ministerial signing ceremony for the Marrakesh declaration on sustainable palm oil in Africa; and two further years of support to the initiative confirmed and announced by UK minister at the event. Support confirmed to operationalise zero deforestation production standards.
# and description of cases of Forest Partnerships that have benefitted from an enabled business environment as a result of P4F support.	2 cases by 2018	N/A: Forest Partnerships not yet at a stage of maturity that requires supplementary enabling support.

Key Points
The TFA is having a significant impact on enabling conditions for sustainable palm oil development and the realisation of zero deforestation sourcing and production commitments. In West Africa this support has resulted in the engagement of ten countries in the TFA Africa Palm Oil Initiative, which is setting out a framework for the sustainable development of the palm oil industry in the West and Central Africa regions (addressing environment, jobs, rights, gender equality and other core sustainability issues).

Ministers from seven of the participating countries signed the Marrakesh Declaration for a sustainable palm oil industry in Africa, at an event hosted in the UK Pavilion at COP22, demonstrating the impact which can be achieved through combining TFA convening power with adaptive and flexible support. The UK State Minister for Climate Change also announced a further two years of support for the initiative, provided through P4F.

In Indonesia, support to the Indonesian Palm Oil Pledge (IPOP) secretariat has faced significant challenges, highlighting both the influence of strong vested interests with a stake in unsustainable business-as-usual, and the disruptive power of market-driven sustainability commitments. The IPOP pledge was disbanded by the six Indonesian signatory companies earlier in 2016, after they faced heavy fines under the country’s anti-monopoly law. However, Indonesia has since embarked on a nationally-led process of reform, setting up a working group on sustainable palm oil under the Coordinating Ministry for Economic Affairs and developing a credible reform plan. Not all of this positive development can be attributed to the IPOP, but the market-driven approach to a zero-deforestation standard which it embodied clearly played an important catalytic role.

Important support to operationalise private sector zero deforestation commitments is also being provided through Partnerships for Forests, focused on the development and widespread adoption of a common standard for companies to meet zero deforestation commitments. UK support is enabling the work of a powerful coalition spanning major producers, buyers and environmental and social non-governmental organisations. Significant private sector financial commitments have also been made to this work.

Recommendations
Maintain facilitation support to the Africa Palm Oil Initiative; work with donors, companies, NGOs and through P4F to catalyse investment and support for implementation in signatory countries;

Identify and initiate further strategic and high-impact enabling interventions as opportunities are identified;

Consider the role of enabling interventions in developing the Southeast Asia and East Africa portfolios and related regional strategies.
Output Title	Partnerships and investments: Partnerships between private sector, public sector and communities supported that seek to deliver investment in forests and sustainable land use
Output number per LF		#3	Output Score	A
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
# and description of concept notes that are accepted into the FP maturity funnel following pre-funnel assessment and due diligence checks (FPMF entry).	20 by 2017, subject to demand, quality control and commercial viability assessment.	On track: a long-list of 60 potential partnerships has been identified and considered for support; first regional call in West and Central Africa attracted 116 submissions.
# and description of FPs with an MoU and full proposal accepted as a result of P4F support (Decision gate 1).	7 by 2017, subject to quality control and commercial viability assessment.	On track: a short-list of high potential partnerships has been identified across the three regions, with teams providing close support to ensure innovative and ambitious proposals; support confirmed to three partnerships.
# and description of FPs with a business plan as a result of P4F support (Decision gate 2).	8 by 2017, subject to quality control and commercial viability assessment.	On track: as above
Etc. – please see programme log frame	N/A	N/A at this stage in the programme.

Key Points
A structured approach to programme management has been established, under which high potential partnerships receive support to develop and pilot innovative business models, working towards commercial investment at scale. Rigorous evaluation at a series of staged decision gates will ensure that only partnerships with the potential to reach commercial viability and deliver significant development benefits will be supported by the programme over the medium-term. Systems have also been developed to support the effective management of a portfolio of innovative partnerships, including robust financial management and due diligence systems.

A portfolio of high potential partnerships is under development, through direct solicitation from strategic partners, through unsolicited applications and through open calls for concepts. The first grant and technical assistance agreements have been established, including to support a wild coffee value chain in Ethiopia, conserving forests and supporting poor farmers to access high-value markets; and supporting the holders of a new class of ecosystem restoration concessions in Indonesia to develop self-sustaining business models.

The first open call for concepts was concluded in October 2016 and focused on building sustainable supply chains for cocoa, palm oil, rubber and fuelwood/timber in West and Central Africa. A total of 116 concepts were received and evaluation is ongoing.

Progress to mobilise development capital investment has been slower and options are still under review. Encouraging progress has been made in establishing contacts with a number of other relevant investment funds.

Recommendations
Expand the partnership portfolio across the three programme regions, focusing on high-impact, scalable interventions;

Conclude calls for proposals in Southeast Asia and East Africa. The number of applications under the West Africa call indicates strong demand and competition for funding, which will help to drive value for money when building the portfolio in the other two regions;

Continue exploring options for development capital investment, as outlined in the programme business case; identify opportunities for strategic collaboration with land sector investors.
Output Title	Leadership, collaboration and learning: Models, learning and leadership that support collaboration and investment in forests and sustainable land use
Output number per LF		#4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Understanding of FPMF dynamics; patterns and reasons for pass / fail / return of FPs to each decision gate.	Forest Partnerships Performance Analysis 2018	On track: Forest Partnerships portfolio is under development.
# and description of P4F knowledge products published and communicated	9 by 2019	N/A: insufficient time to develop this aspect of the programme to date.
# of people accessing P4F publications, associated resources and messages.	TBC by 2019#	N/A: insufficient time to develop this aspect of the programme to date.
# and description of initiatives with enhanced or high value collaboration undertaken by P4F.	10 by 2019	N/A: insufficient time to develop this aspect of the programme to date.

Key Points
The focus in the past year has been on developing capability to understand the progress of partnerships through the decision gates in the programme operating model, carrying out learning-focused research and building knowledge partnerships and increasing our participation at events.

As partnerships start to move through initial review and the first decision gates, a framework to understand which projects are moving towards maturity has been developed. After the first open call in West and Central Africa and further year of implementation, a rich body of evidence will be available to inform the programme strategy and provide wider learning for external audiences.

The Global Landscapes Forum (GLF), funded through DFID’s International Forest Knowledge (Knowfor) programme, has been identified as a key platform for sharing programme learning and developing collaboration. The programme team were present at the GLF Investment Case in London on 6 June 2016 and hosted an exhibition stand.

The team has also increased its collaboration with TFA2020, introducing the programme and sharing learning at several key events, as well as hosting the TFA’s regional coordinator for West and Central Africa within the West Africa hub in Accra, Ghana.

Engagement with the TFA included speaking roles at regional palm oil initiative meetings in West Africa and an event in New York City as part of Climate Week, the latter providing an opportunity to showcase P4F’s leadership role in catalysing investment to a high-level audience (Helen Clark, UNDP Administrator, Vidar Helgesen, Norwegian minister of climate and environment, and provincial and district leaders from Indonesia). As a social media partner for the event, P4F gained significant exposure through official Climate Week channels, with twitter messages reaching as many as 10,000 people.

The P4F team has also started to use these partnerships to publish news and learning from the programme. The GLF website and TFA2020 online collaboration platform both carried news on the first open call. Data from stakeholder research undertaken during the inception phase will also be shared with TFA in order to populate the TFA2020 platform’s initiative mapping section.

Recommendations
Continue to build the programme presence in key international, regional and national platforms for learning and developing collaboration.

Undertake learning to develop a better understanding of characteristics required to advance through the initial decision gates in the programme operating model. This information should be used to inform programme strategy, refinement of log frame indicators and provide wider learning for external audiences.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The main cost driver is technical assistance, which is paid for against milestones tied to the identification and progression of public-private partnerships through Partnerships for Forests. This output-based model is resulting in the rapid generation of a portfolio of high quality, innovative public-private partnerships. Early-stage support to partnerships has consisted largely of technical assistance, to support the development of business plans and establish necessary partnerships structures (for example, industry associations), but the rate of expenditure will increase in the coming year as grant support is also committed and disbursed.

Within the programme portfolio, value for money has been identified as a key issue for the replicability of public-private partnerships. A framework focused on economy (buying inputs of the required quality at the lowest price); efficiency (producing outputs of the required quality at the lowest cost); effectiveness (how well outputs produce outcomes); cost-effectiveness (producing outcomes at the lowest cost); and equity (ensuring development results are targeted at the poorest) is used to guide management decisions.

Practical ways in which value for money approaches are applied through the programme include decision gates to enable rapid divestment of unviable partnerships; implementation of strong operational and contracting procedures that focus on cost management; rigorous contracting, negotiation and monitoring of grants and technical assistance expenditure; rigorous monitoring and evaluation of activities, outputs and outcomes; and competitive allocation of grants and technical assistance.

VfM performance compared to the original VfM proposition in the business case
The operational framework developed during the first year of Partnerships for Forests operations has strengthened the original value for money proposition set out in the programme business case.

Assessment of whether the programme continues to represent value for money
The Paris Agreement and continued momentum around corporate voluntary sustainability commitments offers a conducive operating environment for the programme. The flexible and adaptive model means that the programme is well placed to be effective in this dynamic operating context, and support companies and other stakeholders to turn commitments into positive change on the ground.

Quality of financial management
Robust programme management and financial management systems have been established, providing clear and timely information on work flows and related expenditure; establishing appropriate and proportionate due diligence processes; and providing accurate financial forecasts.

Improvements have been made to simplify contract milestones, and link payments more explicitly to programme operations and work flow, providing greater transparency and a clearer link between outputs and payments, as well as helping to improve the accuracy of forecasting and providing field teams with the correct incentives to encourage innovation.

Expenditure to date (Table 1) has resulted in the effective inception of the programme (see Performance and Conclusions), the development of a strong initial portfolio (see Outputs 1-3 and Monitoring and Evaluation), as well as an important commitment to a future sustainable palm oil industry in West Africa (see Key Results).

Table 1: Programme expenditure
Item	Committed (£m)	Realised (£m)	Realised (%)
Tropical Forest Alliance	2.0	0.875	44%
Partnerships for Forests	56.5	5.1	9%
Evaluation manager	1.4	0	0

Date of last narrative financial report	P4F contract invoiced monthly in arrears, most recently 18 November 2016. Most recent certified statement for TFA dated 27 May 2016.
Date of last audited annual statement	Audit of TFA secretariat account dated 7th Oct 2016. Grant payments under the programme are just beginning. Audit of the P4F client account will be requested before the next AR.

E: RISK

Overall risk rating:
Moderate

Overview of programme risk
The programme is innovative and represents a calculated risk. Risk relates to the programme operating context, in a challenging sector with competing interests and strong incumbent interests around unsustainable business-as-usual. Decision gates in the programme operating model are designed to manage the risk that partnerships do not progress as far as workable business models.

Fiduciary risk is low, with programme funds disbursed through an external service provider with strong due diligence and financial management systems in place. Reputational risks associated with the private sector will require continuous monitoring. Risk mitigation includes due diligence; the integration of gender and social equity considerations into appraisal and decision-making, to ensure that partnerships deliver strong development benefits; and a programme focus on developing shared value through public-private-people partnerships. Realising shared value is a vital element of sustainable business models, which retain a social licence to operate, in remote, rural regions of developing countries.

Outstanding actions from risk assessment
As the portfolio develops in the year ahead, DFID will ensure a regular dialogue on risk with the Partnerships for Forests management team.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme is on track. The inception phase was concluded on schedule. All deliverables during this period were high quality and submitted on time. The programme has become operational rapidly since the conclusion of the inception phase. Grant and technical assistance agreements have been confirmed under Output 1 (demand-side measures), Output 2 (enabling conditions) and Output 3 (finance and investments), while activities have also commenced under Output 4 (leadership, learning and collaboration). The Tropical Forest Alliance has also made good progress, establishing regional committees, recruiting regional facilitators, convening the first general assembly of partners, while building up regional and thematic work programmes and securing an important result at COP22 with the Marrakesh Declaration on a sustainable palm oil industry in Africa.

Performance of partnership (s)
A strong and collaborative working relationship has been established between DFID and the Partnerships for Forests management team, including through strategy workshops, regular management meetings, joint outreach and engagement with partners, and field visits. The consortium, comprising Palladium and McKinsey, have also formed a strong partnership, combining Palladium’s development experience and McKinsey’s business advisory experience.

The TFA is also making good progress and establishing strong partnerships. The Netherlands has committed funding, joining Norway and the UK, while the US also remains closely engaged. Progress has been made with engaging developing country governments, with six West and Central African governments becoming members, along with Colombia as the first Latin American government represented in the alliance. Private sector engagement with the alliance remains acceptable, with key manufacturers, traders and producers making important contributions, however, efforts are needed to broaden the range of companies engaged and to sustain high quality private sector participation over time.

As the programme portfolio expands, systems to facilitate ongoing monitoring of the delivery chain will need to be made operational, to ensure early identification of reputational, political and fiduciary risks which may arise in relation to Tier 2 and 3 partners.

Asset monitoring and control
N/A
G: CONDITIONALITY

Update on partnership principles (if relevant)
There is no conditionality in the programme.

H: MONITORING & EVALUATION

Evidence and evaluation
The Evaluation Manager tender has been completed and a preferred bidder identified. Contract negotiations are ongoing, with mobilisation expected in 2017. Once operational, the evaluation manager will support learning across the programme, strengthen the evidence base and provide an independent view of progress towards the intended outcome. Working arrangements will be established to ensure coherence with Compass technical teams responsible for learning and evaluation within the International Climate Fund (ICF).

Monitoring progress throughout the review period
A Monitoring, Evaluation and Learning (MEL) strategy has been established for Partnerships for Forests and is generating good quantitative and qualitative data to support tracking of progress. In the first year of operations (six months of which were taken up with inception), Partnerships for Forests has catalysed policy action by six European governments in support of sustainable supply chains (Output 1 – demand-side measures: Amsterdam Declarations support unit); engaged ten African governments in a commitment to a sustainable palm oil industry, and engaged major palm oil producers in a commitment to operationalise zero deforestation production standards (Output 2 – enabling conditions: TFA Africa Palm Oil Initiative; and High Carbon Stock Working Group); and committed to three initial partnerships and established a strong pipeline of further investments which are now in the final stages of review (Output 3 – finance and investment).

Current highlights from the partnership portfolio include developing a business model for a new class of Ecosystem Restoration Concession in Indonesia, which will play an important future role in rehabilitating heavily degraded lands, stabilising greenhouse gas emissions and creating rural jobs; improving livelihoods through an enhanced value chain for high-end forest coffee grown in Ethiopia; and a strong nascent West and Central Africa portfolio with a focus on palm oil and cocoa, as strategic areas of intervention with high impacts in terms of economic growth, jobs, livelihoods and climate change.

Progress with this emerging portfolio is tracked against a results framework, which has been established for Partnerships for Forests. The results framework includes a set of learning questions, to ensure a focus on continuous improvement and adaptive management. The programme log frame is embedded within this wider results framework. The programme theory of change has been updated and refreshed, with a learning culture and a process of continuous review and improvement set up around it. This will help to ensure that lessons from implementing the programme are identified and shared, as well as being applied to support adaptive programme management, a key requirement given the innovative nature of the programme and the dynamic context in which it is operating.

In 2017, further attention will be needed to ensure that gender impacts are identified and reported. The Tropical Forest Alliance has established a gender working group to ensure that gender issues are integrated into the supply chain sustainability agenda. women and girls. Attention will be given in 2017 to ensure that gender disaggregated data is also collected where possible under Partnerships for Forests, to document how the programme is delivering a gender sensitive and progressive approach for women and girls. A number of potential partnerships identified in 2016, including initiatives in the cocoa sector in West Africa and in coffee in East Africa, have the potential to deliver significant livelihood benefits for women and girls. It will be important to ensure this is properly documented and reported.

Programme-level monitoring, evaluation and learning will be undertaken in coordination with the Compass programme undertaking monitoring and evaluation of the ICF portfolio. Partnerships for Forests will track progress against relevant ICF key performance indicators, and collaborative working arrangements have been established between the programme and the Compass technical teams.