## Intervention Summary / Project Completion Review for projects below £1m that were approved prior to January 2011.

Project Title: 114129–Safeguarding Children in the Overseas Territories

Date Project Started:01/04/2009 Date Review Undertaken: Nov 19 2013

Why was UK support required and what did we provide?
The purpose of the SCOT project was to support decision-makers and practitioners to design and implement robust policies and institutional arrangements to ensure that boys, girls and young people are safeguarded in the Overseas Territories. With a project budget of £475,246.95, the project was designed to assist the Governments of selected Overseas Territories in ensuring their children and young people are able to grow up in an environment in which they flourish and are protected in all aspects of their lives. The project was active in Montserrat, Anguilla, the Turks and Caicos Islands and the British Virgin Islands in the Caribbean; and in St Helena, Ascension Island and the Falklands in the South Atlantic; Pitcairn Island and other OT’s received expert technical support at a later stage, in order to strengthen their response to child safeguarding. The project started on 1 April, 2009, was extended three times, to 28 February, 2012, then to 30 June, 2012 and finally to September 2013. / The final extension was to enable a child safeguarding review to take place in Pitcairn and to establish expert technical support to HMG and to other overseas territories specified by HMG. A total of 48 days a year were dedicated to the South Atlantic Territories, of which approximately 24 were to be spent on visits and 24 providing distance support. This was sufficient for one visit a year to St Helena and Ascension, and one visit to the Falkland Islands during the project. / A total of 63 days a year were dedicated to the Caribbean Territories, of which approximately 27 were for visits and 36 for distance support. This was sufficient for three visits a year to Anguilla, Montserrat and TCI, and up to three days a month for distance support. / Up to 110 days were added to the project in the final six months to provide additional training and advice from the Lucy Faithfull Foundation to the island of Pitcairn, other OT governments as necessary and HMG.

Did the actual results achieved meet those we expected to achieve?
Output 1: Strengthened interagency collaboration in participating Overseas Territories -The project would have been greatly enhanced by having a local coordinating committee to keep up momentum. Output 1 was fully achieved only in St Helena and Ascension. In the other Territories some progress was made through the delivery of training. Reasons varied for the slow progress, but these included high staff turnover, a difficult cultural and political environment, and the absence of local champions to push the agenda in the physical absence of the consultants. In the Caribbean particularly there was no agreement on what were adequate safeguarding standards, so they varied considerably between islands and from the accepted norm in the UK / Score B / Output 2: Greater government ownership of the safeguarding agenda within the participating Overseas Territories / The second output was only achieved to a fairly limited extent. The development of national protection plans suffered from an adverse reaction to the complexity of the plans produced by the predecessor programme, and the lack of local champions, except in St Helena and Ascension. The UNCRC committee recommendations do not appear to have been used by the project, and this indicator should have been changed at some stage. The participation of civil society in child protection did not increase, partly because it was decided to use the project grant funding exclusively for training and technical support, and not support civil society with it, and partly because civil society is anyway weak in most of the Territories. In view of the manifold problems relating to safeguarding children, the TCI need an extensive programme of special measures, especially concerning the legislative framework. / Score B / Output 3: Policies and procedures developed and in place within appropriate government departments / The third output was the most successful. Policies and protocols were developed and disseminated in St Helena, Ascension and Anguilla, and practitioners gained a working knowledge of them. In Montserrat and TCI, legislation has not yet been developed to ensure adequate State responsibility for the welfare of children. Officials in the criminal justice system, and education and health departments need to be made much more aware of their roles and responsibilities in safeguarding children. / Score A / Output 4: Greater regional collaboration/lesson learning and sharing No real attempt was made to forge partnerships with regional bodies. This would have required government leadership beyond the capacity of the project to deliver. Some networking took place between Anguilla and Montserrat but it is unclear whether this will have a lasting impact. Although all the territories need support for safeguarding children not all of them want it, so building increasing demand was always going to be difficult. No links have been established with UK departments or organisations due to the lack of local champions who would have made a sustained effort to develop, nurture and maintain them. The territories themselves are isolated and remote which makes operating a regional project incredibly difficult. Although the islands have a lot in common they each have a variety of different issues and priorities. / Score C / The project did not fully achieve its purpose of enabling decision makers and practitioners to design and implement robust policies and institutional arrangements to ensure that boys, girls and young people are safeguarded in the OT’s. However significant progress has been made in St Helena, Ascension and Anguilla. Less progress was made in Montserrat and TCI, and there was a limited amount of work done in Falklands, BVI and Pitcairn. / A new business case is being designed to follow on from this project. / Score B

Value for Money Assessment.
The work done in the Caribbean and South Atlantic was put out to tender, this ensured best price was delivered to DFID by procurement department. / The two consultants selected provided excellent value for money, they were experts in a very specialised field, their fee rates were competitive and they were highly regarded by stakeholders in the project. / The fee rate paid to all the consultants was reasonable, all consultants worked hard under difficult conditions, to achieve the best possible outcomes for the project. / There will always be difficulties involved in working in these remote islands. Each territory has different issues, which need looked at individually. Logistics can ramp up expenditure to an enormous extent, but it is impossible to consider working on this type of project without having budgeted for regular visits. In this case I believe the project achieved good value for money in fee rates and expenses claimed.