DFID Annual Review
Raising Learning Outcomes DFID-ESRC Research Programme
Start date: January 2014	Review undertaken: January 2015

Summary Sheet

Title: DFID-ESRC Joint Research Fund on Raising Learning Outcomes
Programme Value: £20 million (£5million ESRC)		Review Date: January2015
Programme Code: 204324	Start Date: 10th January 2014	End Date: 30th March 2022

Summary of Programme Performance
Year	2014 (1)
Programme Score	A+
Risk Rating	Medium

Summary of progress and lessons learnt since last review

- This is the first annual review of this programme. The overall programme score is A+ (moderately exceeding expectations) based upon progress made within the first year.
- Solid foundations for this programme have been established in this first year. The Raising Learning Outcomes programme establishes a new education partnership between DFID and ESRC. This is a strong partnership with each bringing comparative advantage to drive the ambition and progress of the programme. The programme is a significant component of DFID’s education research portfolio, and represents the step change that DFID has taken towards the commissioning and use of rigorous evidence that explains how effective education systems can work to raise learning outcomes for all.
- The first call for proposals, focused on effective teaching, has selected a high quality portfolio of 12 grants with a good focus on learning outcomes. Teaching effectiveness was identified as the primary issue constraining education systems with poor learning outcomes, on the basis of the current evidence base and consultations. Efforts to expand the base of research suppliers were fairly successful, in particular in the USA.
- ESRC’s rigorous commissioning process was applied efficiently, and had a good focus on appraising applications’ methodological rigour and fit to the research call. The selected portfolio reflects these high standards, although several of the unsuccessful applications did not respond to requirements to consider systemic education issues. This indicates that the ambition of this programme to shift demand away from input-driven research will take time to achieve. The majority of selected grants will use mixed research methodologies; future calls will be shaped to appeal further to multi--disiplinary teams of researchers.

Summary of agreed actions for the next year

- The portfolio of Call 1 grants is expected to start from March 2015 with all grants commencing by July. Plans are underway to recruit a ‘thematic research lead’ from amongst these to work across all grantees, building a community of practice and cohering emerging thematic findings from across the body of evidence. DFID will work with country advisers to ensure appropriate country engagement strategies and outreach.
- The second round of commissioning will be undertaken incorporating learnings from call 1 and to a slightly longer timeframe, including a pre-call notice. DFID and ESRC will consider how best to meet the ambitions of this programme to shape demand for questions that unpack education systems and for multidisciplinary research, and will design Calls 2 and 3 accordingly.
- The Evidence and Policy Directorate (EPD) will be established across two DFID-ESRC programmes: Poverty and Education. This process, led by Evidence into Action and under procurement in early 2015, will be focused on maximising the communication and impact of research funded through the programmes on policy and practice, as well as maintaining and enhancing their international profile and reputation, and strengthening efficiencies within the partnership.
A. Introduction and Context (1 page)

DevTracker Link to Business Case and log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-204324/documents/

Outline of the Raising Learning Outcomes (RLO) research programme

- A £20 million joint programme between DFID and ESRC to fund a portfolio of research on critical policy areas that are currently constraining education systems in developing countries from translating resources into better learning. DFID will provide up to £15 million; ESRC £5 million.
- The aim of the research is to provide policymakers and practitioners with concrete ideas on how to improve learning and understanding of how these will translate to their specific context and institutions.
- Awards will be made through three annual research calls. Each call will have a core thematic focus. The focus of the first call was on “Effective Teaching”, with subsequent calls likely to expand to cover additional areas including accountability and financing

Given the strong inequalities that exist within education, particularly for girls, this research will focus on how to raise learning outcomes for all by considering equity as well as quality dimensions of education. This focus is part of larger debates around defining and assessing learning outcomes. The research will be embedded within government systems or large private sector providers to ensure findings are relevant for scale up. .

Expected Results

The impact of this programme will be the use by policymakers and decision makers of evidence generated from this programme in education planning and programming to raise learning outcomes. This will be enabled by increased knowledge and evidence on ‘what works’ to raise learning outcomes. Three outputs contribute towards this outcome (the current lograme is included in Annex 1):
- High quality research on raising learning outcomes is generated and disseminated;
- Production of strong multi-disciplinary research with a strong focus on measuring learning outcomes and underpinned by the use of disaggregated data; and
- Research results are effectively communicated to academics, policymakers and research users.

Contribution to Education Research Team Operational Plan

The RLO programme contributes to each of the ERT’s 2014-5 Operational Plan objectives:
1. To improve DFID’s profile as a funder of high quality, timely and relevant education research.
2. To increase the supplier market for high quality multi-disciplinary education research
3. To put evidence at the heart of DFID’s education policies and practice by ensuring that key audiences are aware of and make use of research results and value evidence
4. To improve the education cadre’s reputation within DFID for the commissioning and uptake of quality evidence.
5. To contribute to strengthening policy debates in LICs through increasing the profile and use of evidence on education research in LICs.
6. To ensure continued success & uptake of education research evidence as a global public good.

Contribution to DFID international objectives

Education is the largest sector in DFID’s portfolio with £2.7bn allocated to education programmes in partner countries between 2010/11 and 2014/5. Yet investment in education research has historically been low when compared with other sectors. This programme is part of DFID’s new education research programming, which aims to provide a coherent framework that responds to the needs of DFID education advisers and our partner governments.

This programme is aligned with the DFID business plan, which includes honouring international commitments as a key priority. This incorporates a specific action on expanding access to and improving educational outcomes for poor children.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Good progress has been made in this first year of the RLO programme towards the outcome of ‘increased knowledge and evidence on what works to raise learning outcomes’. However, it is too early to assess progress against milestones. No new knowledge or evidence has yet been produced, but ESRC led a comprehensive commissioning process for the first research call. This is almost complete. ESRC and DFID worked well together to ensure a dual emphasis to shape the quality and direction of research supply, encouraging (i) strong mixed methods approaches, and (ii) research questions that sought to unpack effective teaching as an element of education systems (rather than as a simple, stand-alone input). The strengths of this commissioning process have been externally recognised, including the following feedback from the chair of the commissioning panel for Call 1, Robert Moon:: “This was a complex call and all aspects of the administration were professionally organized with meticulous attention to detail... I thought the partnership between ESRC and DFID also functioned well. The outcome is a portfolio of varied but related projects that will contribute significantly to knowledge and experience in this important area.”

The first portfolio looks likely to contain 12 grants. Final confirmation of the number of grants is dependent on the ongoing recognition of some institutions by ESRC. Through mixed methods approaches and RCTs, these research grants will generate a body of knowledge about how effective teaching can help to drive improved learning outcomes. Across the portfolio, evidence will be generated about how this link (between effective teaching and learning) works (and does not work) in a variety of contexts (e.g. conflict affected or rural low-income), using a variety of interventions (e.g. educational technology or formative assessment) and for diverse and particularly marginalised groups (e.g. children with disabilities or those socially excluded through a variety of contributing factors).

Research findings from this first portfolio of grants will start to emerge in 2016, and until 2019. However, the production of research alone will not enable the desired programme outcome of ‘increased knowledge’. Towards this, and alongside the commissioning of Call 1 grants this year, a procurement process was undertaken to set up an ‘Evidence and Policy Directorate’ to disseminate research findings and facilitate policy uptake. This was initially sought in partnership across three of the DFID-ESRC partnerships (poverty, China in Africa and education), however supplier outreach by UK Shared Business Services (ESRC’s procurement service) did not generate any applications. Reasons for this were identified, and significant outreach has been undertaken by ESRC, DFID and UKSBS for a re-tender, which will cover the poverty and education programmes. This included a pre-tender meeting, which elicited strong response, prior to the tender being relaunched at the start of December with the aim to establish the EPD by March 2015. Finally, plans are underway to recruit a thematic research lead from amongst call 1 grantholders in early 2015 in order to build understanding across that cohort of the larger programme objectives, and to draw out patterns and themes emerging from across the 12 different projects.

Overall output score and description

We are at the appropriate stage in the programme to set milestones against each of the three outputs, and this is planned for the January 2015 Quarterly Programme Meeting. While good foundational work has been undertaken this year towards the achievement of each output, it is too early in the programme to report on the achievement of milestones.

1. High quality research on raising learning outcomes generated and disseminated: The first research findings are expected to emerge from early 2016. Grantees will work with the Evidence and Policy Directorate to disseminate their research, and to develop their ‘Pathways to Impact’ strategies. Plans are underway to recruit a thematic research lead for the portfolio on ‘effective teaching’ and the role of this individual in cohering the evidence as it is generated is under discussion.

2. Production of strong multi-disciplinary research with a strong focus on measuring learning outcomes and underpinned by the use of disaggregated data: 10 of the 12 research projects that are due to be launched in early 2015 will use mixed methods; the other two will undertake quantitative research. This represents a strong response to the call for more robust, rigorous research methodologies. However, considerable difference was found across the range of applications in the definition of ‘mixed method’.

3. Research results effectively communicated to academics, policy makers and research users: The Evidence and Policy Directorate, responsible for supporting and enhancing the dissemination and uptake of research, will be established as the first round of grants are being set up (February-March 2015).

Key lessons

- Overall, the programme is on track towards planned outcomes and outputs. While too early to measure progress against specific programme milestones, the strength of the partnership between ESRC and DFID, and recognition of the successful commissioning process for Call 1 and consultation process for Call 2 mean that the programme is moderately exceeding expecations to date.
- While the portfolio of Call 1 grants is strong, the full range of applications highlighted a tendency to address teaching effectiveness from an input-driven perspective, focusing for example on teacher training with the assumption made that this would inevitably produce student learning outcomes. This programme is asking grantees to unpack what effective teaching is, as part of complex, shifting and context-specific education systems, and to provide evidence that links this to improved student learning outcomes. A lesson taken from Call 1 is that contributing to a shift in the focus of education research towards a systems lens will be challenging, and that Calls 2 and 3 need to be designed with this in mind.
- Lessons from the experience of Call 1 will be built into decisions on the process and format of Call 2. For example, the simultaneous call for small, medium and large grants in Call 1, each of which asked for a different degree of adherence to the call specification, was too complicated and confusing for applicants. The small grant call, used effectively this time to test market response, can now be dropped.
- Learnings and opportunities for efficiency and collaboration within the DFID and ESRC team should continue to be identified and incorporated. The process of cross-programme learning has been useful and the EPD will play a crucial role as research grants commence in March 2015. Learnings from emergent findings from research grants will be captured through the role of the ‘thematic research lead’ identified from within the cluster of 12 grant holders for Call 1.

Key actions

Action	Deadline	Responsible
Review the logframe	January 2015	Joint – ESRC and DFID
Finalise the logframe	March 2015	Joint – ESRC and DFID
Launch of Call 2 following consultation process	Pre-call in January 2015; call to be opened in March and closed in May.	ESRC
Procurement and contracting of EPD	March 2015	ESRC
Recruitment and contracting of Thematic Research Lead for Call 1	March 2015	ESRC

Has the logframe been updated since the last review?
The logframe used for this review and included in Annex 2 is that developed at the inception of this programme.
ESRC and DFID will review milestones and targets in the logframe at the first quarterly progress meeting of 2015, on 29th January, to ensure appropriate reflection of the programme now that it is fully underway. This would also enable identification of more meaningful and process-driven indicators for each output, including research quality, in line with similar discussions being undertaken across the DFID-ESRC Strategic Partnership. The logframe will be finalised in March 2015, as part of a partnership-wide review of logframes designed to maximise consistency and best practice across the joint programmes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output 1	High quality research on raising learning outcomes generated and disseminated
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone 1	Progress
1. Number of research proposals approved which have therefore reached quality standards of the scheme	6 (medium to large) grants allocated in 2014	12 grants (6 small, 5 medium, 1 large) successfully passed the 3 phase review process; contracting is ongoing. / The total cost from approved research proposals is £4.4million, this is under the initial spending estimated
2. Quantity of research completed, measured by end of award reports received	100% to be submitted by November 2022	First end of award report will be due in mid 2016 for small grants

Key Points:
- The first call was structured through three simultaneous small, medium and large streams, with the aim of testing the market in this first round.
- A comprehensive procurement process included five review stages: first proposal sift, peer review, shortlisting, commissioning panel, final decision making.
- Leading academics were engaged in the review processes, including Leon Tikly and Sheila Aikman, and Robert Moon chaired the commissioning panel. The relatively small pool of academic experts in this field and high demand for this funding from within this group creates challenges, however the good relationships built and strength of the process will contribute to further supplier expansion for calls 2 and 3.
- Call 1 portfolio quality standards are high and stem from UK, US and (one) African institutions.
- The grants awarded funding are of high quality, having been reviewed and assessed through a rigorous process. However, it has been noted that the overall quality profile of the applications received to call 1 was lower than some other calls within the ESRC-DFID Strategic Partnership, although direct comparisons are difficult due to the different assessment processes used.
- There was some underspend from initial estimates, the remainder will support future calls.

Recommendations
- Format of call 2 to be streamlined by ESRC into a medium/large combination (March 2015).
- Learnings from call 1 commissioning process to be incorporated by ESRC, in order to clarify procedures for applications, in particular greater communication and clarity around criteria and guidelines needs to be made by DFID and ESRC to applicants (March, 2015), and for reviewers through the IT portal used (May, 2015).
- ESRC to increase advanced notice to reviewers and commissioning panel participants where possible to enhance opportunities to: (i) select reviewers of the highest quality; (ii) ensure applicants receive constructive feedback; and (iii) ensure reviewers have clear understanding of DFID and ESRC expectations for fit to call and research methodologies sought.
- ESRC and DFID to continue to use multiple step review processes – the different stages were valuable in examining methodologies and programme fit and the final decision panel creates the space to reflect on the portfolio as a whole and endorse commission panel decisions (ongoing).
- Strategies for ambitions to increase Southern leadership and involvement in high quality research to be developed by ESRC and DFID; ambitions to be noted in the logframe and monitoring of countries/regions holding grants to be documented (March 2015).
- A thematic research lead will be recruited in early 2015 from the pool of 12 Principal Investigators for Call 1, with responsibility for supporting grantholders’ theories of change, cohering emerging findings, and building a community of practice.
Output 2	Production of strong multi-disciplinary research with a strong focus on measuring learning outcomes and underpinned by the use of disaggregated data.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones / target	Progress
2.1. Proportion of projects using mixed methodology	Not less than 95% in 2017	83% of applicants report use of mixed methodologies in grant proposals
2.2. Proportion of projects collecting internationally benchmarked learning outcome data	Not less than 80% by 2017	n/a (see below)
2.3. Proportion of projects incorporating analysis by gender and/or income quintiles.	Not less than 95% by 2017	n/a (see below)

Key points:
The programme is at procurement stage for Call 1; complete information on progress against output 2 indicators will only be available once the grants are running and reporting to ESRC. Information provided in the applications offers an indicative overview outlined below.
Indicator 2.1: 10 of the 12 funded grants (83%) indicate they will be using mixed research methodologies.
- Indicator 2.2: 9 of the 12 funded grants (75%) state they will be producing a new dataset as part of their research, however the extent to which these will collect internationally benchmarked learning outcome data should not be assumed to be the same.
- Indicator 2.3: 3 of the 12 funded grants (25%) explicitly mentioned incorporating analysis of gender within their applications
- Call 1 encouraged multi-disciplinary and mixed-methods approaches, and gender analysis, although these were not required. Quality remains the over-riding determinant of funding, and therefore some high quality but single discipline and/or single method research was expected. It is anticipated that a significant proportion of grants not explicitly focused on gender will disaggregate and analyse this data.
- The collection of internationally benchmarked learning outcome data, and analysis of income quintiles, were not included in the specification for call 1.
- Consultation processes for Call 2 are currently underway: external and internal DFID consultations on possible call themes within a systems lens have taken place, and a roundtable discussion at the British Academy will be held in February 2015.
Recommendations:
- Revise the lograme to ensure appropriate indicators, as part of ESRC and DFID’s continuing use of the logframe as a strategic tool. Output 2 indicators need to be developed to appropriately measure research quality, including expectations on methodology, learning outcome data and gender analysis (January-March 2015).
- The thematic focus of Call 2 will be designed to appeal further to multi-disciplinary researchers through a structural focus around context and dynamics. The possibility of a Research Council UK Supplier Expansion meeting in Washington DC towards this aim is currently being considered (February 2015), and a roundtable arranged at the British Academy for February 2015.
- Take greater advantage of cross-disciplinary learning opportunities from across the different ESRC-DFID partnership programmes (ongoing).
Output 3	Research results effectively communicated to academics, policy makers and research users
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
3.1. Number of synthesis reports produced by call topic.	9 by 2018	N/A
3.2. Number of research papers disseminated as policy briefs to policy makers and development practitioners	25 by 2018	N/A
3.3. Number of dissemination workshops/seminars held with local stakeholders (i) organised by research teams/Programme Champion and (ii) with participation from research teams	(i) 25, (ii) 40 by 2018	N/A

Key points
- As no grants have yet started, it is not possible to report against these indicators.
- Procurement of the EPD is underway in partnership with the ESRC-DFID Joint Scheme for Poverty Alleviation Research. The EPD will lead on securing and enhancing the uptake and impact on policy and practice of research funded through the Education Programme and the Poverty Programme. Following an earlier unsuccessful attempt to procure this function in 2014, a revised specification is now being advertised. The aim is to establish the EPD by March 2015. This was developed through a more extensive process of consultation with potential bidders to both clarify the EPD function and increase the supplier base. A 6.5% of the programme budget allocation to the EPD represents a significant commitment to research uptake and impact. There was strong cross-team collaboration within DFID on this process, led by Evidence into Action.
Recommendations:
- Further develop appropriate metric and associated targets for Output 3 through logframe review process and in line with learning emerging from other ESRC-DFID partnership programmes. These should be discussed by ESRC and DFID with the aim to capture research outputs and their dissemination (March, 2015).
- ESRC and DFID to ensure EPD activities and workplan is reflected in Output indicators, once EPD is appointed (May, 2015).
- Use the ResearchFish data gathering and reporting system (currently used by ESRC) to enable easier generation of accurate data on research outputs and impact, as well as findings and grant characteristics. ESRC to ensure appropriate training for DFID staff where needed and to enable it to be utilised by all grants within this programme from the outset (March, 2015).
- DFID to work with country advisers to develop country engagement strategies where research grants are taking place and to support outreach (March, 2015).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The overall scheme budget profile and payments are maintained and managed by the ESRC Finance Team. DFID payments are made in arrears.

Overall, spend is on track. This first year has seen a number of changes made within the budget (for example, inclusion of funding for a future evaluation) and also a slight delay in commissioning. The Call 1 portfolio represents a slight underspend against anticipated allocations. However, DFID and ESRC remain confident that overall the programme will spend its projected budget. Some flux at this stage in a programme is to be expected.

VfM performance compared to the original VfM proposition in the business case
ESRC assess cost effectiveness at three key stages during the application, review and award contracting process:
- At the application stage ‘value for money’ is a stated assessment criterion in the scheme specification and applicants are required fully cost all elements of their proposed research and provide detailed justification for each item of expenditure. Peer reviewers and panel assessors are asked to consider VFM as part of the grant assessment and is one of the factors which panel members consider when making final funding recommendations. The focus of analysis at this stage is cost drivers.
- At the award contract stage all costs are subject to detailed scrutiny by the ESRC Secretariat. Any unjustified or excessive costs may be removed from the budget if further justification is not provided by the host RO- or is not satisfactory.
- Throughout the period of the grant, award holders must submit annual budget reconciliation statements to ensure spend is on track and report on any significant budget issues in their annual progress reports. Projects are barred from exceeding their awarded budget. On average, projects are completed for just under the full budget cost (97%). Where awards have contracted project partners, the ESRC contract is with the host institution. The host institution will set up ‘sub-contracts’ with any partner organization. The host organization will thus take the financial responsibility of tracking partner spend and the risk of any overspend or default.

DFID will share with ESRC its guidelines for Value for Money, to ensure that at each of these stages a full assessment of efficiency, effectiveness and equity is integrated.

Quality of financial management

ESRC have been responsive to financial requests and have shown an ability to re-profile based on actual needs and DFID requests for up to date financial information. The team will receive the first audited financial statement by March 2015 and will assess the ESRC performance on narrative financial reports.

Date of last narrative financial report	03.2014
Date of last audited annual statement	N/A

E: RISK (½ page)

Output risk rating: Medium

Overview of programme risk
Overall the risk rating for this programme is medium – the full risk matrix is included in annex 2

Some of the risks identified for this programme have already been encountered and mitigating actions are taking place. These include the initial unsuccessful attempt to secure the EPD: ESRC and DFID are currently undergoing mitigating actions through a new procurement process following consultations.

Risks around the quality of research proposals, particularly from Southern institutions, are shown through the underspend on Call 1 grants and where 30% of applications were from outside the Global North, only 8% of the selected grants were from outside. DFID and ESRC will continue to discuss strategies to address this and are incorporating the learnings from Call 1 into future call specifications to address concerns around quality. Risks to increasing multi-disciplinary research grants are indicated through the concentration of education specialists selected for Call 1 on ‘effective teaching’ – consultation processes to determine the Call 2 and 3 thematic foci are directly addressing this through concentrating on contexts and dynamics of education systems.

Outstanding actions from risk assessment
The Business Case determined that a full due diligence assessment of ESC as a non-departmental UK government body was not appropriate and therefore is not measured against in the AR.

Several risks are mitigated through ESRC mechanisms that only award grants to institutions recognised as bona-fide research institutions and provided those institutions and award holders are willing to adhere to ESRC terms and conditions. Unrecognised institutions funded under this scheme are required to gain full RCUK recognition before contracts can be issued and funding can commence. In order to ensure compliance, ESRC operates a number of sanctions against institutions or individuals that fail to comply with the terms and conditions of their grants. The ESRC risk assessment strategy recognises this research funding environment.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Delivery is largely on track against planned timeframes.
- There have been slight delays in Call 1 commissioning to ensure a comprehensive process was undertaken.
- The EPD recruitment was delayed due to lack of applications to first tender, but that this will not affect the education programme as grants are not yet set up.
- Recruitment of a thematic research lead is on track to be in place as the first grantees set up their projects, though a decision on a broader research advisory function across the DFID-ESRC partnership is still pending.

Performance of partnership

This is the first DFID-ESRC joint programme on education but it builds on ESRC-DFID partnerships in poverty, health systems and growth research. Working with a Research Council presents significant opportunities for DFID to commission high quality research by utilising the ESRC’s rigorous and trusted systems for bid selection and management, benefitting from the ESRC’s strong networks and reputation in academic institutions and leveraging additional funds from the ESRC.
Given the maturity and expanding scope of ESRC and DFID’s jointly-funded research programmes, the last year has seen considerable work towards harmonisation across these at strategic, governance, policy and delivery levels. As well as maintaining and strengthening relationships at the scheme lead level in the last year, the Education programme has also benefited from cross-programme working at partnership executive and programme management levels, the EPD being one example of the impact of this for the programme.

Staff changes at ESRC and DFID: on both sides the teams working to deliver the programme have seen some changes over the last 12 months, which inevitably poses a challenge. However, considerable effort has been put into maintaining effective and regular communications between and across the two organisations, holding both quarterly meetings and less formal updates. Both ESRC and DFID agree that this has enabled both organisations to positively respond to changes and challenges in the delivery of the programme.

‘Bedding in’ a new programme and mutual learning: the start of a new programme, even within an existing partnership, is a challenging time and involves a lot of learning. ESRC recognise in particular that their commissioning policies, processes and procedures can at time be complex to understand, and have worked hard to ensure that these are transparent and accessible to DFID colleagues throughout the year.

Asset monitoring and control : N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant) : N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

No evidence has emerged over the past year to change the rationale or direction of this programme. The assumptions made in the original Business Case still apply.

Monitoring progress throughout the review period:

DFID and ESRC engage regularly to review and monitor progress on the process of grant commissioning and management:
- Quarterly programme meetings (including financial)
- Weekly progress update calls
No monitoring data is available on the research itself, as no grants are yet active. All funded projects are contracted to produce an annual progress report using a tailored pro-forma for the programme, as set out above. This provides confirmation that research timetables and contracted work are on track, as well as an opportunity for award holders to highlight emerging findings and research outcomes. Grantholders are also required to submit data on their grants, findings, outputs and impact to the ResearchFish system, which is subject to an annual validation process. At a programme level, ESRC and DFID have identified the need to set aside specific funding for this, and the programme budget and profile was amended appropriately during this year. This is likely to be informed by learning from the evaluation of other programmes, specifically the Poverty Programme, including an ongoing impact evaluation of that scheme due to report in summer 2015.
Evaluation
We aim that the next Annual Review will involve external reviewers, and an evaluation of progress by Call 1 grant holders. DFID and ESRC plan that an external evaluation of the programme be undertaken, likely in 3-4 years’ time. There is potential to yield learning from the impact evaluation of the Poverty programme, and to link up with a planned evaluation of the Effective Education Systems research programme.
ANNEXES

1. Logframe ESRC DFID Join Fund for Raising Learning Outcomes: see Quest document 4212265
2. Risk Matrix (page 12)
3. ESRC Call 1 Grants: see Quest document 4744395
4. Call 1 Commissioning Process (page 13)
Annex 2: Risk Register			ESRC Review Date: 7 November 2014
General Risk and Current Programme Specific Issues (if required)	Risk Type	Controls in place		Likelihood of Occurrence	Severity of Impact	Current Rating	Senior Managerial Responsibility
Programme management
DIFD or ESRC need to cut/ alter the funding to the programme due to changes in the internal/ external environment / Current specific issues: On-going ODA spend pressures on DFID require continual monitoring of actual spend against profile.	Operational / Programme / Financial / Reputational	The MoU between ESRC and DFID includes commitment to continue to honour existing contracts and financial obligations e.g. awarded research grants should either partner decide to withdraw from the programme. The MoU also establishes a clear requirement for notice of any such withdrawal. / The need for any financial adjustment to the Programme will be discussed with ESRC Council and DFID and any agreed changes will be considered in the context of what’s best for the research programme. Decisions will be reached on the basis of consensus. Underspends from a research call can be incorporated into the configuration of future calls.		Low	High		Team Heads & SRPM/SA
Funds disbursed exceed the total financial commitment and funding requirements of either/both funders.	Financial / Reputational / Programme / Operational	The total available budget for the research calls does not exceed the contribution of either party, and there are regular budget profile reviews to assess the nominal distribution of funds between the two agencies. This includes discussion of identified areas of under and overspend, and appropriate re-profiling within the total programme budget. / ESRC regularly provides up to date reports on actual spend to DFID. / If insufficient funds are being spent on UK research (i.e. if funds disbursed outside the UK exceed the DFID contribution), the need for adjustments will be discussed with ESRC Council and DFID, and changes agreed incorporated into future call configuration.		Low	High		Teams Heads & SRPMs/ SA
DFID and ESRC disagree on key components of the scheme	Programme / Partnership	DFID and ESRC ensure good collaboration by representing and identifying key strategic alignments between each organisation’s research priorities. / Both agencies collaboratively work out their expectations from the scheme and conclude their mutual and complementary interests. This is articulated the MoU. / All programme management decisions are deliberative and arrived at by consensus. Both agencies are involved at all key stages. Quarterly bilateral programme management meetings are held between ESRC and DFID, and regular communication maintained. / The ESRC-DFID Strategic Partnership Executive Board will discuss and provide decisions on components of the scheme as required.		Low	High		Team Leads, SRPMs, SA
Staff changes in ESRC and/or DFID lead to ineffective or delayed delivery through reduced capacity or loss of expertise / Current specific issues: Staff changes at ESRC and DFID have occurred but continuity of management and communication has been maintained throughout. The move from call 1 to call 2 will involve change at RPM level but overlap has been built in to ensure a seamless transition.	Operational / Programme / Partnership	The structure and governance of the Strategic Partnership Executive Board, Programme Management Group and the Secretariat should provide an overarching structure to support the on-going delivery of the programme, where changes in staff at either funder occur. / The project team at ESRC has appropriate and dedicated staff to develop and implement the project. Each member is multi-skilled and flexible in the scope and nature of their duties to maximise responsiveness to change, and the team is supported by colleagues within the broader organisation as appropriate. 4% of the programme budget is allocated to administration to ensure maintenance of appropriate resource levels at ESRC. / DFID’s Programme Lead will work with SRPM and RPMs in ESRC around programme development and implementation, and appropriate handovers to be arranged to enable continuity in programme management.		Medium	Moderate		Partnership Executive Board, SRPMs & SA
Strategic support functions such as the Evidence & Policy Directorate do not provide the strategic input required to support successful delivery of the programme. / Current specific issues: The initial failure to procure the EPD which will serve the programme will not delay support for scheme-level impact activities given that no grants have yet started. Plans are in place to commission the EPD which both ESRC and DFID have confidence in, and this should be completed in early 2015. Contingency plans may need to be developed in the event that an EPD cannot be recruited.	Operational / Programme	The specification for the EPD includes a requirement that its strategies and performance reports are reviewed quarterly by the PMG and changes to deliverables have to be approved by both funders. / The EPD as specified will report quarterly to the PMG and develop annual plans with clear measurable deliverables against which reporting will take place. / The EPD contract under procurement will include a break clause if it does not meet expected deliverables.		Medium	High		SRPM, RPM, SA
Research commissioning
Over-subscription to calls leading to loss of morale and confidence in the scheme	Reputational / Operational	Applicants and their departments are encouraged to focus on high-quality, rather than quantity, of applications. / ESRC rules do not allow uninvited re-submission to subsequent calls. / Call documentation emphasises quality and alignment of proposals to the scheme as a pre-requisite for funding and supporting material is made available to guide applicants. / If the call budget is fully committed, the sponsors could initiate a reserve list for projects to be supported from funds unspent after future calls if the quality threshold is not maintained in later calls. / Options that could be put in place in future if needed include examining the scope for involving unsuccessful applicants through existing or new networking activities, exploring the possibilities for low-cost, high volume activities to maximise the number of participants in the scheme, and exploring the potential to increase the budget envelope in future rounds of the scheme.		Low	Medium		RPMs, SRPMs
Under-subscription to calls leading to underspend of allocated funds / Current specific issues: Call 1 did not allocate all of the funding provisionally set aside for it. This was not reflective of the number of applications received but of the quality profile of those applications (see further below)	Operational / Programme / Reputational	The call is widely publicised and academics are encouraged to apply regardless of perceived chances of success. / The funders will advertise the call widely, organise town-hall events and other events as appropriate, and consider working with subject associations and learned societies to stimulate interest in the call and to brief potential researchers on eligibility requirements, application procedures and research themes. / Learning and reflection from call 1 will inform strategies for maintaining good application rates but also encouraging high-quality applications to future calls, as discussed below.		Low	High		RPMs, SRPMs
Difficulties in the use of the Je-S system, discouraging or preventing applicants, and leading to missed opportunities and loss of reputation for ESRC and Je-S	Operational / Reputational	The Je-S team is familiar with ESRC/DFID collaborative calls and are experienced at dealing with queries and issues from non-UK applicants. / Amendments to the Je-S form have been made which reduce the difficulties previously experienced by non-UK applicants. / A good working relationship with the Je-S team is in place which facilitates good communication of issues and a timely response. / Significant ESRC staff resource is dedicated to supporting potential applicants through the application process. / Clear advice and guidance is provided to applicants about how to use the system and encouragement to engage with the system as soon as possible. / We encourage applicants who are experiencing difficulties to alert ESRC if there is a potential problem. / ESRC allow flexibility where possible to re-open the call for specific cases if justified.		Low	High		RPMs
Application of FEC regime is a disincentive to applicants and their host institutions, especially confusion about the applicability of the 80% rule in an overseas context	Operational / Programme / Reputational	Detailed guidance ensures that the rules about fEC and their application are understood in the UK and non-UK context. / Non-UK applicants are excluded from TRAC methodology but applications must include full and transparent costing from all non-UK applicants, making clear the full range of costs that be claimed. / The 80% rule has been removed for non-UK applicants in this programme and while mention of the fEC/80% rule is unavoidable in forms etc., advice is provided to ensure that non-UK applicants understand this.		Low	High		RPMs
Either/both funders are disappointed with the overall quality of the applications and/or funded projects / Current specific issues: The underspend in call 1 reflected a lower than anticipated quality of applications, although all those awarded funding are of a high quality. Possible reasons for this have been identified and ameliorating strategies are being put in place for call 2, including a consultation workshop with academic/user experts.	Reputational / Operational / Partnership	Supporting material and call spec workshops are made available to guide and support researchers to ensure proposals are high quality and relevant to the programme. / Call specifications are distributed widely throughout the social science community and other communities of interest within and beyond the UK to ensure good reach. / The ESRC’s funding processes ensure research is of the highest quality, is independent, and demonstrates impact. / The ESRC peer review process ensures only high quality and well-focused proposals make it through the commissioning process. The quality of proposals (including evaluating methodology) is a key criterion for grant selection. / Learning from all calls is incorporated into the development of future calls.		Medium	High		RPMs, SRPMs
The quality of applications received from Southern lead organisations is poor, leading to a low proportion of applications being funded / Current specific issues: 30% of applications to call 1 came from outside the global North, which translated into only 8% of grants (a further 25% of grants did include southern researchers). 37% of applications received from outside the global North were rejected at office check stage due to fit to call, compared to 10% of Northern applications. The success rate for Southern applications was 6%, compared to 20% for Northern applications. Discussion of how to address this issue in future calls is required.	Reputational / Programme	Full guidance is provided explaining the scheme to all applicants, including step-by-step guidance through the JeS system. / The ESRC Office works with potential applicants to answer queries and offer support and guidance for completing the form. / Supporting material is available to all applicants, including non-UK researchers and the ESRC office provide advice and hold workshops and seminars for potential non-UK applicants. ESRC continuously monitors schemes to identify mechanisms to remove barriers to and actively encourage developing country participation. The EPD will support these activities where appropriate / All potential applicants and their departments are being encouraged by ESRC and other Research Councils at a high level to focus on high-quality, rather than quantity, of applications. / The call documentation emphasises that quality and alignment of proposals to the scheme as a pre-requisite for funding.		High	Medium		RPMs, SRPMs
Peer review presents challenges due to the interdisciplinary nature of applications or the narrow thematic focus of calls / Current specific issues: This issue impacted on the commissioning process in call 1, causing delays to the original timetable. The timetable for call 2 is being developed to ensure a more realistic schedule given the challenges of identifying reviewers from a relatively small research community.	Operational / Programme / Reputational	The assessment of proposals will be based on the most appropriate model of peer –review for the specific call, incorporating consideration of both the thematic and disciplinary content. / Significant effort is taken to ensure that peer reviewers are selected appropriate to the disciplinary and thematic focus of the project drawing upon existing expertise and experience across ESRC.		Medium	High		RPM, SRPMs
Logistical disruptions and/or resource constraints cause problems for the peer review and commissioning panel processes	Operational / Programme / Reputational	A realistic time table is established to allow each stage of the assessment process, with contingency planning for unintended consequences. / Electronic communication is used as far as possible. / Panel members travelling a large distance will be provided with accommodation for the evening prior to the panel meeting to reduce the risk from travel disruption.		Low	High		RPM, SRPMs
Award Management
Internal issues within projects result in significant delays or a failure to complete research	Financial Programme Reputational	Strong supportive relationships are built with award holders and we encourage them to contact us directly for support with progress or problems experienced within their projects. / We allow some flexibility within budgets, staffing/management and duration of funded awards to allow for unforeseen changes in circumstance. While we allow a no-cost extension to grants there is a 12 month maximum limit to this and all significant changes to grants must be approved by ESRC.		Medium	High		RPMs
Award holders do not adequately deliver the expected level and quality of academic and impact-related outputs	Financial Programme Reputational / F	Project research and impact strategies are assessed as part of the peer review process. / ESRC’s Pathways to Impact and Impact toolkit and DFIDs Research Uptake provides guidance to award holders about how to best maximise the impact and uptake of their research. / The EPD will support grant holders to communicate project activities and outputs during the project’s life. / Some delays in outputs can be expected due to the unpredictable nature of the research environment, but where a problem is identified through the monitoring processes below, ESRC will investigate and if necessary apply sanctions or terminate the grant. ESRC’s Research Funding Guide makes clear the conditions for this and is available online for applicants.		Low	High		RPMs, SRPMs
Grant monitoring processes do not adequately identify issues of progress, delivery and quality of funded awards	Financial / Programme / Reputational	ESRC requires annual reports from Programme grant holders, as part of its own reporting processes, which capture the development and progress of grant holders’ research projects. An annual questionnaire is sent to award holders asking them to report on the progress of the research, project management, financial management and impacts made. / The secretariat also invites award holders to contact the International Development Research team directly and update them on the progress or problems experienced with their projects. / All awards are required to upload research outputs onto Researchfish and this data will available to the scheme secretariat for further analysis.		Low	Medium		RPM/ SRPM
ESRC and DIFD are unable to account for proper disbursements of funds spent on projects.	Financial / Reputational / Operational	All award holders must be based in institutions recognised as eligible to hold Research Council awards. Full eligibility checks for those projects whose PI is not from an UK organisation are carried out. / A checklist will be used to ensure full checks are made on all applications and host institutions that are recommended for award. / The host organisation of the principal investigator is responsible for any sub-contracting arrangements. / All awards made to overseas institutions are subject to annual financial reporting and reconciliation. / The appropriateness and capacity of the research environment and the track record of applicants are considered in peer review and panel discussions. / All awards are subject to annual progress and financial reporting.		Low	High		Team Heads, RPM/SRPMs and SA
Cash limits expressed in sterling cause problems for lead institutions due to currency fluctuations	Operational / Programme / Reputational	If funds allow, promissory notes will be issued to awards adversely affected by significant changes to exchange rates, to ensure that the research can be completed. / Where necessary DFID will be approached to approve additional funds to affected awards to ensure research is completed.		Low	Medium
Programme impact
Scheme awards at an individual and/or programme level fail to make any significant impact on policy or practice / Current issues: The appointment of the EPD has been delayed, although plans are in place for this procurement to complete in early 2015, minimising impact on support to scheme awards.	Reputational / Programme / Financial / Partnership	Applicants are required to submit a Pathways to Impact plan which outlines how the research will benefit end users. The impact plan forms part of the peer review and assessment process. / ESRC and DFID operate an Open Access Policy so all outputs from programmes are accessible to a wide range of international development stakeholders. / Currently the ESRC has a final reporting and evaluation process that captures impact and research findings annually and for 5 years after the end of a grant. / The forthcoming EPD will support the researchers’ individual and collective engagement with policy processes, synthesising and supplementing the results of the individual research projects and presenting the results in national and international fora to enhance the impact of scheme awards on policy and practice. / The EPD will work closely with ESRC and DFID teams responsible for research uptake and impact. / The scheme secretariat also works in close conjunction with colleagues from across the ESRC to ensure maximum impact is derived from project awards.		Medium	High		SRPMs, RPMs, SA, Team Heads
Impact tracking processes fail to capture or are unable to determine the impact of scheme-funded research on policy and practice.	Programme / Operational	ESRC requires annual progress reports from Programme grantholders, as part of its own reporting processes, which capture the development and progress of grant holders’ research projects, including impact. / The secretariat also invites current and former award holders to contact the International Development Research team directly and update them on progress with their projects, including impacts achieved. / All awards are required to upload research outputs onto the Researchfish and this data will be available to the scheme secretariat for further analysis. / The specification for the EPD includes a specific role in monitoring the achievement of impact and identification and dissemination of impact case studies. / Significant resource will be dedicated to pro-actively identifying impacts within the expanded ESRC team moving forwards.		Medium	High		RPMs, SRPMs
KEY TO RISK ASSESSMENT / Traffic Light Assessment Interpretation / High Is expected to occur, almost certain. Greater than 80% / Medium Could occur, this is possible. Measures to reduce likelihood exist, but may not be fully effective. Between 10 and 20% / Low Rare, may occur in exceptional circumstances. No or little experience for a similar failure. Less than 5% / RPM – Research Portfolio Manager, ESRC / SRPM – Senior Research Portfolio Manager, ESRC / SA – Senior Advisor, DFID

ANNEX 4. Call 1 Commissioning Process

The following description of the Call 1 Commissioning Process is provided by ESRC:
In line with the agreed call specification developed in late 2013/ early 2014, Call 1 in this programme made available three streams of grant in terms of scale and focus:
- small/ pilot grants of 1 year duration and £50-£150k, which may or may not address the call theme of ‘effective teaching’
- medium grants of 2-3 years duration and £200-£500k, which must address the call theme of ‘effective teaching’
- large grants of up to 5 years duration and up to £1m, which must address the call theme of ‘effective teaching’ and normally also analysis of other system dynamics, and which will produce/ provide access to a major dataset for secondary analysis
The call specification identified an ambition to fund approximately 8-10 small grants, 5-7 medium grants and 2 large grants, with £5 million made available for the call, although made clear that the scale and shape of the funded portfolio of research would be determined by the quality of proposals received within and across the three streams.
The call opened on 20 January 2014, and a full range of guidance documentation was provided to support applicants in developing their proposals. One-to-one support and advice was also provided on request via the ESRC Secretariat, and a webinar providing information on the call and application process was also held in February 2014.
The call closed on 25 March 2014, and a total of 89 applications were received (see table below for overview). Following a process of office checking, in which applications were checked to ensure fit to call, including budgetary issues, 73 applications progressed to an initial assessment stage in which they were reviewed and scored by a mixture of members of an assessor pool and peer reviewers (dependent on which stream was applied for). Following this, a shortlisting meeting was held, consisting of the Commissioning Panel chair (Professor Bob Moon), and the programme leads from DFID and ESRC, which confirmed which applications would progress on to a second stage of assessment, based on the reviews and scores received to date. A total of 42 applications were shortlisted for this second stage of assessment, in which applicants were provided with an opportunity to respond to comments from the first stage and the applications, reviews and responses then informed assessment of each application by members of the commissioning panel. That panel – consisting of a mixture of academic and ‘user’ members from the policy/practice communities – met in October 2014 to agree final scores and make recommendations for funding. A small panel consisting of the Panel chair, and team heads from ESRC and DFID met shortly after to confirm the final funding decisions.
Data on the applications received and their progress through the different stages of the commissioning process is presented in table 1 below:
Table 1: Call 1 applications by stream and commissioning stage
Stream		Large	Medium	Small	Total
Applications received	Number	10	40	39	89
Applications progressing to review	Number	10	34	29	73
	% of received	100%	85%	74%	82%
Shortlisted applications	Number	7	17	18	42
	% of reviewed	70%	50%	62%	58%
Applications recommended / for funding	Number	1	5	6	12
	% of shortlisted	14%	29%	33%	29%
	% of total submitted	10%	12.5%	15%	13.5%

A total of 12 grants representing a total spend of £4,079,685 have been signed off for funding: 6 small grants, 5 medium grants and 1 large grant. It is worth noting that the total amount of funding from Project Partners which will supplement the ESRC/DFID funding is £627,992. Please see appendix A for further details of the funded grants. These grants are currently progressing through an awarding process which includes thorough costings checks, in which ESRC will work with grantholders and their research offices to resolve any queries to ensure value for money, and which also ensures that any conditions for funding put in place by the commissioning panel have been addressed by grantholders to the satisfaction of panel members as required.
While not captured in the logframe, data on the country of origin of applications provides insight into the success of the call in realising its ambitions to fund world-class research originating from the global research community, as set out in table 2 below.
Table 2: Lead institution country/region
Lead institution Country/ Region	Applications received / n=89		Applications progressing to review n=73		Shortlisted applications / n=42		Funded grants / n = 12
	Number	%	Number	%	Number	%	Number	%
India	2	2%	1	1%	-	-	-	-
Africa	19	21%	12	16%	9	22%	1	8%
Asia (excl. India)	6	7%	4	7%	1	2%	-	-
Australasia	1	1%	1	1%	-	-	-	-
North America	17	19%	15	20%	10	24%	5	42%
Europe	3	3%	3	4%	1	2%	-	-
UK	41	46%	37	51%	21	50%	6	50%

While UK-based PIs were broadly able to maintain their success in translating applications (46%) into funded grants (50%), those from North America strongly increased their share of the portfolio (19% of applications to 42% of grants), while those from outside the global North were less successful (30% of applications to 8% of grants), with one grant led by a PI from a Low/Middle Income Country (Ghana). The overall success rate for Southern-led applications was 6%, compared to 20% for Northern-led applications. However, of the remaining 11 grants, 3 (25%) named researchers from Southern institutions either as co-investigators or named staff within their proposals. Interestingly all three of these grants will be held by UK institutions. Other significant patterns are that 37% of applications received from outside the global North were rejected at office check stage (due to fit to call or technical issues), compared to 10% of Northern applications.
While Southern-leadership or involvement is not incorporated in the logframe, ESRC remains committed to encouraging this. ESRC experience suggests that, while quality and fit to call issues are often a factor in such applications to ESRC-DFID research programmes, we have been able to achieve higher success rates for Southern –led and particularly Southern-involved bids in other schemes. The combination of the challenges to the call as a whole identified below, and the lack of inclusion of Southern partners in non-UK grants, may explain this issue in the case of this call. It is suggested that further discussion of this issue is prioritised in the development of future calls.
Again, while not captured in the logframe, we are able to present data on the geographic focus of grants awarded, which speaks to the scheme ambition to increase the body of research specifically relevant to low-income countries and a select group of other priority countries. 8 of the 12 awarded grants focus solely on one or more countries in Sub-Saharan Africa (Malawi; DRC; Ethiopia; Kenya; Ghana; Botswana; Uganda), one solely on Honduras, and one on India and Pakistan. Two grants focus on countries in different regions: one on India, Ghana and Uganda; and one on Afghanistan, Sudan, Sierra Leone, India, Morocco and Tunisia.

Commissioning challenges:
Multiple funding streams: With 3 streams of funding, each with effectively different themes, this has been a highly complicated call to manage, commission and review. This made the process of commissioning more complex and required mitigation at a number of stages. Firstly, a number of applications were sifted out at the outset if their applications did not fit the call remit or the budgets were incorrect. Secondly, the first assessment stage was tailored to ensure an appropriate level of review for each stream (i.e. a higher number of reviewers for the larger scale proposals, including assessments from reviewers with expertise in large datasets and analysis). Thirdly, the complex nature of the call also made it more challenging for panel members and assessors to familiarise themselves with the call in order to undertake assessments, which was noted at both shortlisting and panel stages. This was addressed at the commissioning panel meeting in a way which ensured fit to call issues were appropriately factored in to final decision-making, but in future calls a more streamlined and less complex call specification would help to address this issue. These lessons are being built in to the development of call 2.
Limited research community: The research community in this area is not large and this produced significant challenges in finding the most appropriate reviewers and panel members within the timescales initially allocated to delivering the call. The commissioning timetable was however adjusted in order to help resolve issues for proposals which were not fully reviewed by the original deadline. By increasing the time given to peer review, further comments and grades were sought to ensure the process was robust. This provided the necessary support to the panel members considering the applications by providing further review comments and grades, as well as to the applicants themselves in terms of feedback on their proposals. Learning from this should inform the timetable for future calls so that sufficient time is allocated to ensure space to deal with this challenge, as well as processes that most effectively make use of the expertise available. It is important to note however that the process of commissioning call 1, including extensive input from DFID, has resulted in the ESRC having a strong database of experts from which to draw in future calls, which should help mitigate the impact of this challenge.
Quality of applications: The final funding decisions do represent an underspend against the maximum available budget, and funding of fewer small and large grants than set out in the call spec. However, as indicated in the call spec the final shape and size of the portfolio represents a decision based on the quality of applications received. The panel recommended for funding all proposals scored above the fundable threshold of 7, and therefore the final portfolio, although smaller than anticipated, does reflect the best quality of the applications received to the call. As the data presented in table 3 below illustrates, 45% of applications initially received were not assessed as of fundable quality during the first round of assessment, and more than 60% of those shortlisted were ultimately not considered to be of fundable quality. The quality of the large grant applications was notably lower than those received in other streams.
Table 3: Quality assessment across streams and stages of commissioning process
	Average grade at shortlisting / (1-6 scale: fundable threshold=4: n=73)			Average grade after panel meeting / (1-10 scale: fundable threshold=7: n=42)
	Average grade	No. 4 or above	% 4 or above	Average grade	No. 7 or above	% 7 or above
Small	4	18	62%	6.7	8	41%
Medium	3.7	16	47%	6.8	7	44%
Large	3.9	6	60%	6.2	1	14%
All	3.8	40	55%	6.6	16	38%

The grants awarded funding are of a high quality, having been reviewed and assessed through a rigorous two-stage process which has guaranteed the final funding outcome meets the ambitions of the scheme. However, it has been noted that the overall quality profile of the applications received to call 1 was somewhat lower than that of some other calls within the ESRC-DFID Strategic Partnership, although direct comparisons are difficult due to the different assessment processes used. For example, in Call 1 of Phase 3 of the Joint Scheme on Poverty Alleviation, 62% of full proposals received an average assessor score of 7 or above. These are broadly comparable to the 38% of shortlisted Education call 1 applications receiving this assessment at the panel meeting, although it should be noted that the Poverty applications had been through an extra round of assessment, which will have raised the overall cohort quality.
There are a number of reasons why this possible difference in quality may have occurred. Firstly, the Education Programme is new, while the Poverty programme is well-established and understood within the research community. Some period of familiarisation by the research community with the requirements of the programme is to be expected. Secondly, as noted above, the research community in this area is not large and the thematic nature of the call further restricted the potential applicant pool. One programme ambition is to attract researchers from a range of disciplines to undertake research on education in developing country contexts, but this message may take time to be absorbed. A third related reason for lower quality at the second stage of assessment specifically is that a number of under-reviewed applications were shortlisted for equity reasons, in line with best practice. As noted above, under-reviewing was a reflection of the smaller pool of available expertise within the research community, and mitigating this may have resulted in some lower quality applications progressing which would not have done so if fully reviewed. Finally, the complexity of this call discussed above may have made it more challenging for potential applicants to clearly understand whether their proposal was appropriate, leading to poor fit to call and thus lower grades. This issue is being taken into account in the development of subsequent calls.

ESRC and DFID are already engaged in an active process of learning and review, drawing on lessons from call 1, including issues around the selection and presentation of thematic calls, grant size, and commissioning timetables and processes. Issues identified at all levels are being incorporated into planning for calls 2 and 3, which is currently underway and will include a consultation with senior members of the research and policy community to ensure any changes made are appropriately responsive to the priorities, needs and demand from those stakeholders.