Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: The Queen Elizabeth Diamond Jubilee Trust: UK Contribution
Programme Value: Up to £50 million		Review Date: December 2016
Programme Code: 203754	Start Date: 25.11.13	End Date: 30.06.19

Summary of Programme Performance

Year	2014	2015	2016
Programme Score	A	B	A
Risk Rating	Moderate	Major	Minor

Summary of progress and lessons learnt since last review

This is the third annual review of DFID support to the Queen Elizabeth Diamond Jubilee Trust (the Trust), which was set up with the specific aim to tackle avoidable blinding diseases and increase the capacity of eye health care systems across the Commonwealth. The Trust initiatives address: trachoma in Africa and the Pacific; diabetic retinopathy in India, Pakistan, Bangladesh, Caribbean and the Pacific; retinopathy of pre-maturity in India, and focuses on improving eye healthcare systems across the Commonwealth by strengthening knowledge, tools and people.

In 2016, the Trust commissioned independent mid-term reviews[1] of all its major initiatives. These reviews provide robust external oversight of the Trust’s initiatives, looks at how the programme is progressing, makes recommendations to ensure that the Trust is on track to meet its goals, and identifies broader learning opportunities. The mid-term evaluations report that all of the Trust’s initiatives are now well into the implementation phase and delivering results; progress has been very strong (described in detail under each of the output areas) and the programme is on track to be completed and meet intended outcomes by June 2019.
[1] Review of Sightsavers two Africa Trachoma Initiatives Nov 2016 (Tropical Health LLP), Mid-term Evaluation of Avoidable Blindness in India Nov 2016 (Amaltas Consultancy) and Commonwealth Eye Health Consortium Mid-term Evaluation Nov 2016 (Lucy Lee)

The Trust has used its convening, advocacy and influencing role to increase the profile of avoidable blindness and secure support from partners and national governments. A priority for the Trust’s Chief Executive in this reporting year has been to meet government representatives and stakeholders across the Commonwealth to cement partnerships and reinforce commitments from Ministries of Health, to ensure that the Trust’s programmes are aligned with national and local priorities and on course to make a permanent difference. In addition, the Trust has raised the profile of its work through international meetings and exhibitions (see under output 5), which is all part of securing a long term legacy for the Trust.

The Trust has made strategic funding decisions in response to the burden of disease and the results of programmes. In the Pacific, new data has shown lower prevalence of trachoma. In response, the Trust has shifted a portion of the funding from trachoma to diabetic retinopathy, which is on the rise in the Pacific. The Trust is also now working with the Fred Hollows Foundation to tackle diabetic retinopathy in Tonga and Samoa.

The Board of Trustees also approved an additional £4.3 million to expand the work of the Commonwealth Eye Health Consortium (CEHC). The mid-term evaluation of the CEHC reports that it has achieved excellent results across the Commonwealth. The agreed expansion includes support for additional scholarships for eye health professionals, development of online educational resources, and training networks for retinoblastoma and retinopathy of prematurity.

Summary of recommendations from the last Annual Review

2015 Annual Review recommendation	Response/Action
1. As many of the milestones set were based on outdated information and affected by circumstances out of the partners’ control it is very important that all the partners recalibrate milestones as soon as they are aware that is needed. The Trust must then present the changes and justification to DFID for approval.	Implemented - ongoing / The Trust coordinated with grantees throughout the year to ensure that milestones are accurate based on the data available and any suggested changes to milestones have been presented to DFID for approval.
2. DFID and the Trust have agreed that for DFID’s annual reporting needs, where partner reporting cycles differ from the calendar year, we will use (i) progress against partners’ previous report and (ii) % progress in the current reporting year. This is relevant to outputs 1 and 4.	Implemented / Mid-year milestones have been added for the Trachoma Initiative in Africa.
3. The Trust and DFID SAFE should collaborate between themselves in offering primary data, co-funding and expertise to the World Health Organisation (WHO) for this venture.	Implemented - ongoing / The mid-term review of the Trust’s Trachoma Initiative (in collaboration with the DFID SAFE Trachoma programme), has generated data and learning that will be shared with key stakeholders in trachoma elimination, including the WHO.
4. The Trust should re-run the cost benefit analysis of the programme This can be done in conjunction with the DFID-funded SAFE programme in 2016 and results should support WHO-led work on improving the evidence of the cost-effectiveness/economic impact of trachoma control.	Implemented - ongoing / In order to improve understanding of the economic benefit of investing in avoidable blindness programmes, the Trust, along with several key NGOs and pharmaceutical companies, is funding the production of a ‘Vision Atlas’ by the International Association for the Prevention of Blindness. The Vision Atlas will be published in 2017 and will provide comprehensive and up-to-date data on the burden of blinding diseases across the world. This information will enable governments and other funding agencies to make strategic choices about the scale and scope of their interventions, and enable them to targets those most in need.
5. The Trust to consider other milestones (other than Mass Drug Administrations to use a proxy towards achievement of Ultimate Intervention Goals (UIG). The Trust to explore if there is, or could be, a methodology to measure progress towards UIG per country that can be used.	Implemented / The Trust consulted with the grant manager and the International Coalition for Trachoma Control (ICTC) to establish if there are suitable proxy milestones to indicate progress towards achieving ultimate intervention goals. The Trust is proposing to use the percentage of districts where criteria are met to stop mass drug administration. Although this still refers to mass drug administration, it is really a proxy indicator that shows that the prevalence of trachoma has dropped to a low enough level (<5%) that interventions are no longer required. As the overall impact goal is achieving elimination criteria in countries, these milestones show the progress that is being made in achieving elimination at the district level.
6. The Trust to commence strategic deliberations over end of programme sustainability. To ensure each initiative is clear on what its legacy will be: what skills and knowledge and assets will be ensured to partners, what the funding requirements are and possible sources of funding. This should be done in fuller collaboration with the ICTC who has commenced exploring this.	Ongoing / Sustainability has always been foremost priority for the Trust, and was a key focus of the mid-term review of the Trachoma Initiative. The Trust works closely with the ICTC, and is one of the leading partners in the ‘Trachoma Free Africa’ campaign, along with DFID and USAID, to attract support to ensure trachoma elimination targets are met.

Summary of recommendations for the next year

The recommendations/actions for the Trust and DFID are set out in detail under each of the output areas. Two key recommendations for the Trust next year are:

Implement the recommendations from the mid-term reviews of the Trust’s Initiatives, consulting with DFID where recommendations lead to substantive changes in DFID support.

Continue to prepare for exit and explore end of programme sustainability, particularly for countries (e.g. Nigeria) where the elimination of trachoma may not be within the lifetime of the Trust programme. DFID remain keen that the Trust maximises its impact by putting in place exit strategies that leave a lasting legacy.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203754/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203754/documents

The Queen Elizabeth Diamond Jubilee Trust was formally established on 6 February 2012 under the chairmanship of the Rt. Honorary Sir John Major KG CH, former Prime Minister of the United Kingdom. Its purpose, with the contributions it has received, is to create and manage programmes that will bring life-changing benefit to people across the Commonwealth.

DFID is providing up to £50 million in matched funding to support the Trust’s avoidable blindness programme. International efforts are underway to eliminate the main causes of avoidable blindness worldwide, providing a unique moment to join and help progress the global Vision 2020 initiative (a joint programme of the World Health Organization and the International Agency for the Prevention of Blindness).

The Trust’s avoidable blindness programme comprises four initiatives:

Trachoma management in Africa (£40.1m) and the Pacific (£2m). This is managed through a partnership with International Coalition for Trachoma Control (ICTC) who appointed Sightsavers to manage the initiative in 6 African countries working to support the elimination of trachoma in Malawi, Kenya and Uganda, and significant reductions in the burden of trachoma in Mozambique, Nigeria, and Tanzania. Trachoma is a neglected tropical disease which affects the eyes, if left untreated, it can lead to blindness. Elimination of trachoma is possible through the adoption of the World Health Organisation’s SAFE strategy (Surgeries, Antibodies, Facial cleanliness and Environmental components). In the Pacific, the Trust it is working with ICTC and the Fred Hollows Foundation to, support elimination in four countries; Fiji, the Solomon Islands, Vanuatu and Kiribati (the Trust also supports work in Australia but not with DFID funds).

Diabetic retinopathy (DR). An increase of 60% in DR is predicted in the Commonwealth by 2030[2]. Diabetes increases the risk of many eye health problems, with DR being the main cause of blindness. The Trust is supporting a partnership between the Public Health Foundation of India (PHFI) and the London School of Hygiene and Tropical Medicine (£4.2m) to improve prevention, detection and treatment of DR in India. The Trust is also supporting the Caribbean Council for the Blind to reduce rates of DR in the Caribbean (£1.4m), and the Fred Hollows Foundation to reduce rates of DR in Bangladesh, Pakistan and the Pacific (£2m).
[2] 4th QEDJT Annual Report and Audit Report for 1 July 2015 to 30 June 2016

Retinopathy of prematurity (ROP). The major stream of work is in India through a partnership with the Public Health Foundation of India (PHFI) and the London School of Hygiene and Tropical Medicine (£3.5m), who are working with federal and state governments to integrate services to prevent, detect and treat ROP within Special Newborn Care Units. These units are being rolled out at district level with a target of 1000 units operational in 2017. The initiative covers supporting strategy and guideline development, training physicians, new patient record and management systems and the development and testing of more affordable equipment for ROP diagnosis.

Strengthening of knowledge, tools and people to improve eye health care across the Commonwealth managed by the International Centre for Eye Health (CEHC), hosted by the London School of Hygiene and Tropical Medicine (£11.5m). The Consortium supports fellowships to increase eye care expertise in low income Commonwealth countries, provides a knowledge platform to facilitate learning and information exchange, and a technology programme to develop, validate and rollout low cost eye health diagnostic and management tools.

In addition, the Trust has established The Queen’s Young Leaders Programme in partnership with Comic Relief and The Royal Commonwealth Society to honor Her Majesty the Queen’s 60 years of service to the Commonwealth. As well as awarding 60 inspirational young people each year for the life of the programme (youth working on a wide variety of important issues including tackling climate change, providing education for girls and improving maternal health), grants are made to organisations in selected Commonwealth countries that can demonstrate they are improving the lives of young people.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The evidence assessed in this annual review shows that the work of the Trust is accelerating. A review of the evidence has shown that fewer people need trachoma surgery than had originally been expected but the assessment is that the Trust is on track to achieve the outcomes agreed with DFID relating to its avoidable blindness initiatives. With the emergence of new data, DFID and the Trust will review and adjust current logframe targets to ensure they reflect the new evidence.

The 2013 DFID Business Case for the Trust indicated that the trachoma initiative (Output 1) would protect more than 18 million people from blinding trachoma through antibiotic treatment and prevent blindness in a further 405,000 through surgery. New data on trachoma prevalence has led to a significant downscaling of the coverage needed. It is now estimated that 10 million will receive antibiotics and 123,000 will receive surgery.

Overall output score and description

A – Met expectations.

Key lessons and actions

Action on the trachoma global agenda has reached its highest point. Funding (from DFID and USAID in the main) has facilitated a huge expansion of care. The intensive global technical collaboration has ensured a strong focus on the SAFE strategy which alongside a strong network of implementation partners has ensured effective use of the resources. The drug company Pfizer, critically donated drugs on a major scale.

The trachoma programme’s success holds learning for other neglected tropical diseases. At global level, information from the programmes is being shared, disseminated and used for policy and decision-making. At country level, information is shared within national trachoma programmes but less so across countries and more opportunities for sharing of information and learning across countries is needed[3]. The Trust has a critical role to play in that process.
[3] Sightsavers Report on the Trust Trachoma Initiative (April to September 2016)

Has the logframe been updated since the last review?

Yes, some indicators have been altered, and new indicators have been added to bring out the advocacy and influencing component by the Trust and its implementing partners, as per recommendations from the DFID 2015 Annual Review (see below). Other indicators have been amended as the evidence has informed the scale of the issue and impacted on baseline data and expected beneficiary numbers. The targets for quantitative indicators are now cumulative, rather than annual, to more clearly highlight the impact of the Trust’s progress over the years.

Output Indicator 1.2

2015 Indicator:	Number of people treated with antibiotics in endemic target communities

New indicator:	% of endemic districts achieving >80% coverage of mass drug administration (MDA) in the year

Interrupting the transmission of trachoma requires >80% coverage of antibiotic distribution within a district. Achieving this level of coverage is more significant than the total number of people who have received antibiotics. This indicator may be considered more of an outcome indicator than an output indicator, but the structure of the Trust’s logframes, with multiple programmes in one table, means that only the high-level indicators have been included.

Output Indicator 2.3

2015 Indicator:	Number of health professionals trained on prevention, detection and management of diabetic retinopathy

New indicator:	At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system

The Diabetic Retinopathy initiative focuses on ensuring that diabetic retinopathy models of care can be integrated into the public health system. This has involved more time spent on advocacy with government health officials to ensure that the public system has sufficient buy-in. Success for the Diabetic Retinopathy initiative would be the incorporation and adoption, by public health systems, of the models of care piloted by our partners. The new indicator provides the opportunity to recognise important activities such as national summits, meetings with state government health officials, and signing of agreements between the government and health care providers.

Output Indicator 3.3

2015 Indicator:	Number of health professionals trained in screening and treatment of retinopathy of prematurity (ROP)

New indicator:	At least two examples of how the Public Health Foundation of India have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system

As with the Diabetic Retinopathy initiative, output indicator 3.3 will now reflect the advocacy work being conducted by the Public Health Foundation of India to incorporate retinopathy of prematurity models of care into the public health care system.

Output Indicator 5.4

New indicator:	At least two examples of how the Trust has influenced global policy and/or leverage with respect to scaling up preventable blindness programmes

To monitor and acknowledge the Trust’s global policy leverage, a new output indicator 5.4 has been added. The Trust engages in significant advocacy activities in order to promote support for avoidable blindness and ensure strong national ownership of eye health care plans. The Trust is able to utilise its position to leverage more support for its initiatives and to engage more actors in the eye health sector. The Trust has extensive networks across the Commonwealth and actively seeks to engage with governments and ministries of health.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective implementation of selected elements of the SAFE (Surgery, Antibiotics, Facial Cleanliness, Environmental Improvements) strategy
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		Yes, revised downwards from moderate.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Percentage (%) reduction in Trachoma Trichiasis (TT) surgery backlog target	Expected reduction: 56% / Kenya 62% / Malawi 52% / Mozambique 51% / Nigeria 18% / Tanzania 64% / Uganda 88%	Exceeded expectations - 63% reduction in TT surgery. / Kenya 65% / Malawi 66% / Mozambique 59% / Nigeria 13% / Tanzania 78% / Uganda 94%
1.2 Percentage (%) of endemic districts achieving >80% coverage of mass drug administration (MDA) in the year.	Expected MDA coverage: / Kenya 100% / Malawi 100% / Pacific Islands 100%	Met expectations. / Kenya 100% / Malawi 100% / Pacific Islands* n/a / *Mass drug administration took place in the Pacific Islands end of 2016, coverage rates will be reported in early 2017.
1.3 Number of endemic districts where Facial cleanliness is implemented through effective behaviour change programmes.	Expected target: / Kenya 12 / Malawi 17 / Uganda 17	Met expectations. Implemented in 35 districts. / Kenya 12 / Malawi 17 / Uganda 6** / ** A lower target for Uganda was agreed with the DFID Programme Team in May 2016, which has been met. A decision was made to review/change logframe targets for output indicator 1.3 and 1.4 as part of the 2016 Annual Review process.
1.4 Number of endemic districts where environmental improvement is implemented.	Expected target: 46 districts / Kenya 12 / Malawi 17 / Uganda 17	Met expectations. Implemented in 35 districts. / Kenya 12 / Malawi 17 / Uganda 6** (see above)

Key points

The Trust Trachoma Initiative continues to make a huge contribution to trachoma elimination programmes globally by providing support, and in some cases, leading innovation and learning.

Africa
- The number of people receiving surgery is high and the programme is on track to meet avoidable blindness elimination goals. Since March 2014 to date, more than 60,000 surgery cases have been managed and 10.4 million people have been treated with antibiotics.
- The programme has successfully used a combination of different approaches, including providing surgery at health centres, having multi-day surgery outreach camps in communities, and using dedicated mobile teams, to provide surgery wherever it is needed.
- Despite some initial delays in 2015, in the production of antibiotics by the pharmaceutical company Pfizer, all districts that have since received antibiotics have exceeded their coverage targets and no major problems have been encountered.
- A key strength of the initiative has been its commitment to ensuring that national governments play a strong role in the leadership and coordination of programme planning and implementation with support from partners.
- In Uganda, the Trust approved an expansion of trachoma activities in 2016, to scale up from two regions to cover endemic regions across the entire country. It also took longer to find appropriate implementing partners for the facial cleanliness and environmental improvements elements of the programme, as WASH organisations wanted to do more generic water and sanitation activities, rather than focusing specifically on the elimination of blinding trachoma. Consequently, more time was spent with the partners developing their plans and working on establishing baselines and agreeing indicators.
- In Malawi, progress towards achieving elimination goals has been very strong and new data indicates that the country will be able to cease outreach activities and enter the surveillance period in 2017.

Pacific
- The National Trachoma Action Plan (TAP) meeting was held in Vanuatu in February 2016 and the plan was endorsed in April. Commitment by all participating organisations was commended for driving the trachoma programme forward. Memoranda of understanding and sub-grant agreements were signed by the Ministries of Health for Kiribati, Solomon Islands and Vanuatu.
- Mass drug administration of antibiotics was carried out in Vanuatu in August/September 2016.
- The WHO Alliance for the Global Elimination of Trachoma by 2020 (GET2020) meeting in Sydney (April 2016) provided the opportunity for Pacific Trachoma Initiative representatives to meet and network with other trachoma experts across the globe.

Summary of responses to issues raised in previous annual reviews

2015 Annual Review Recommendation	Response/Action
Intensify actions to address the poor progress reported in Nigeria.	As part of understanding more fully the under performance against planned targets in Nigeria, the Ministry of Health and partners are trialling an intensive approach and providing special reports. Sightsavers and their technical experts have engaged on monitoring visits to Nigeria to track progress and work with coordinating partner Helen Keller International to improve service delivery.
Revise output indicator 1.2 to percentage (%) of endemic districts achieving >80% coverage of mass drug administration in the year, rather than the absolute number of antibiotic doses distributed.	Implemented
Revise output indicators 1.3 and 1.4 to better reflect the impact of facial cleanliness and environmental improvements.	Revised facial washing and environmental (F&E) improvement indicators are being developed to align with the reporting indicators for the DFID SAFE programme. Each country has a detailed F&E framework, and output indicators 1.3 and 1.4 are intended to aggregate the outputs from these different frameworks.
As Sightsavers’ reporting year is April to March, the Trust to also provide mid-year milestones to enable reporting against the DFID reporting year.	Mid-year milestones have been added to output indicator 1.1 (trachoma surgery) to align with the DFID reporting year. The other three output indicator targets apply to both the programme year and the DFID reporting year.

Recommendations

The mid-term review[4] found that the Trachoma Initiative has significantly strengthened national health systems. The Initiative has provided unprecedented trachoma surgical services, capacity building, financing, coordination, planning and has promoted the use of data for decision making. Furthermore, most stakeholders interviewed as part of the review concurred that health and non-health staff is gaining long-term capacity that will be sustained beyond the life of the programme. The Trust should:
[4] Mid-term Review of Sightsavers two Africa Trachoma Initiatives Nov 2016 (Tropical Health LLP)

support the implementation of the recommendations from the mid-term review;

increase efforts/support in Nigeria to enable it to achieve the WHO GET2020 target. The mid-term review noted that Nigeria has one of the highest burdens of trachoma in the Commonwealth and will need concerted, sustained efforts over the next two years to meet the SAFE targets; and

focus on planning for the end of the project, its lasting legacy and sustainability of the programme. The Trust should have a clear idea of who will finish the job it has started on the trachoma initiative (looking to other donors).

Output Title	Increase in the number of patients with sight threatening retinopathy treated in targeted Commonwealth countries
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of patients with diabetes screened for diabetic retinopathy annually.	Expected total: 17,900 patients	Exceeded expectation. / 18,308[5] patients screened for diabetic retinopathy.
2.2 Number of screened patients with diabetes treated for diabetic retinopathy annually.	Expected total: 2,990 patients	Exceeded expectation. / 3,402 patients treated.
2.3 At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system.	Expected targets for following implementing partners: / Public Health Foundation of India (PHFI): meetings held with all state governments where diabetic retinopathy screening is planned. / Caribbean Council for the Blind (CCB): start-up consultation meetings completed in all 4 countries with partners and Ministries of Health. / Fred Hollows Foundation (FHF): Diabetic retinopathy eye screening integrated into government health systems in project locations.	Met expectation. / PHFI - meetings held with all 8 States where diabetic retinopathy screening was planned (Rajasthan, Maharashtra, Goa, Karnataka, Kerala, Tamil Nadu, Andhra Pradesh and Odisha). In addition, PHFI increased awareness of the programme by publishing a special supplement of the ‘Indian Journal of Endocrinology and Metabolism (April 2016)’ focused on diabetic retinopathy. The Journal has a circulation list of 3,500 and is accessible to a global audience online. / CCB - Start-up consultation meetings were completed in 4 countries (Belize, Dominica, Jamaica and Saint Lucia) with partners and Ministries of Health to sensitise them on the relationship between diabetes and diabetic retinopathy. Screening for diabetes and treatment of patients has commenced in these countries. / FHF – The Foundation is the Trust’s implementing partner in Bangladesh and Pakistan and in 4 focus countries in the Pacific (Fiji, Kiribati, Solomon Islands and Vanuatu). Diabetic retinopathy eye screening has been integrated into government health systems in these locations, and work is progressing in line with detailed national government work plans. Progress is reported below.
[5] Progress on Output 2.1 and 2.2 - Reporting from Public Health Foundation India (Community Health Centre records, District Hospital records), The Fred Hollows Foundation (in the Pacific - monthly reports from clinic administration staff) and WHO Tool to Assess Diabetes and Diabetic Retinopathy Services (TADDS).

Key Points

Public Health Foundation India (PHFI)
- Advocacy efforts have resulted in strong commitment from the Government of India’s Ministry of Health and Family Welfare, and the respective State Governments where the district programmes are being implemented. Tripartite memoranda of understanding have been signed between the implementing partners, State Governments and PHFI for implementing the diabetic retinopathy programme, with a commitment to continue the programme beyond the Trust funding period and therefore ensuring sustainability. Additional State Governments outside of the Trust’s diabetic retinopathy programme have requested technical or programme support as a result of hearing about the programme, e.g. Gujarat and Chhattisgarh States.
- Programmes to train ophthalmologists and allied eye care personnel including ophthalmic assistants in screening for diabetic retinopathy has been initiated in two states and will be undertaken in all pilot districts.
- PHFI also launched a certificate course in ‘Evidence-based Management of Diabetic Retinopathy’ to build capacity among physicians across 10 cities in India. Physicians from the pilot districts are being encouraged and supported by the Trust to attend this course. The first course was completed in April 2016 and was attended by 186 practicing physicians. A second course has been planned for November 2016.

Caribbean Council for Blind (CCB)
Rates of diabetes in the Caribbean are up to 50% higher than the global average. In June 2016, the Trust’s Chief Executive held meetings with key government stakeholders to cement their commitment to integrating the work on diabetic retinopathy in to long term plans. Jamaica held a Vision2020 planning workshop in collaboration with the Ministry of Health and the Pan American Health Organisation, to develop a strategic eye care plan, including provision for screening and treatment of diabetic retinopathy.

Fred Hollows Foundation (FHF) – Bangladesh, Pakistan and the Pacific
- In Bangladesh and Pakistan, the Foundation carried out a baseline Knowledge Attitude and Practices (KAP) Survey on Eye Health Services related to diabetes in 2016. The findings from these surveys have been a valuable advocacy tool, and used to establish baseline data for monitoring and evaluation and focus programme interventions. Community awareness programs with diabetic retinopathy messages and training of medical officers is underway throughout the target districts.
- In the Pacific, the Foundation has worked closely with the Ministry of Health in each target country and carefully built up good relationships which will enable a sustainable programme of work to be undertaken. The focus has been on building capacity within the Pacific region by strengthening the workforce through training initiatives.
In May 2016, six students from the Pacific successfully completed a Post Graduate Certificate in Diabetic Eye Care, which is vital to expanding the limited professional eye health care capacity in-country. The Foundation also ran training workshops, where 150 community health nurses received training to assist with screening and treatment of diabetic retinopathy.

Summary of responses to issues raised in previous annual reviews

2015 Annual Review Recommendation	Response/Action
Changes to the logframe - set the milestones for output indicators 2.1 and 2.2	Milestone targets have been agreed with the India National Diabetic Retinopathy Taskforce, the Caribbean Council for the Blind and the Fred Hollows Foundation.
Amend output indicator 2.3 to capture the advocacy work undertaken by the Trust’s implementing partners.	For the Diabetic Retinopathy initiative the Trust’s partners are focusing more of their efforts on ensuring that diabetic retinopathy models of care can be integrated into the public health system, making them sustainable. This has involved more time spent on advocacy with government health officials to ensure that the public system has sufficient buy-in. Success for the Diabetic Retinopathy initiative would be the incorporation and adoption, by public health systems, of the models of care piloted by the Partners. The Trust has added the following indicator: / ‘At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system.’ / This indicator provides the opportunity to include important activities such as national summits, meetings with state health officials, and signing of agreements between the government and health care providers.

Recommendations

The Trust’s partner in India, the Public Health Foundation of India (PHFI) commissioned an external agency to conduct a mid-term review of the progress made so far. The review[6] found that the diabetic retinopathy (DR) programme has got off to a good start in India, although considerable lead time was required to sensitise the government and bring them on board, the Government of India is now fully on board with the National Programme for Control of Blindness. The Trust should:
[6] Mid-term Evaluation of Avoidable Blindness in India Nov 2016 (Amaltas Consultancy)

support the implementation of the mid-term review recommendations;

create opportunities for cross-learning and communication between partner institutions so that knowledge transfer between States can happen; and

undertake cost-benefit analysis as part of its exit strategy, to inform other donors/stakeholders of operational benefits in DR (and retinopathy of prematurity). Cost effectiveness data could also be a valuable input to decisions regarding scale up.

Output Title	Increase in the number of infants treated for retinopathy of prematurity (ROP)
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of infants screened for ROP in Special Newborn Care Units (SCNUs) in quality improvement programme area annually	Expected number screened: 1,960	Moderately short of expectation. 1,652
3.2 Number of infants treated for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area annually	Expected number treated: / 82	Moderately short of expectation. 37
3.3 At least two examples of how the Public Health Foundation of India (PHFI) have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system	Expected outputs: / National Operational Guidelines for ROP adopted by the Ministry of Health / ROP is included in the Government’s online database for neonatal intensive care units	Met expectation. / National Operational Guidelines for ROP have been adopted by the Indian Ministry of Health in May 2016. / The fields for tracking ROP have been agreed with UNICEF (who manage the Government’s online database for neonatal intensive care units) and will be added in by a technician early 2017. / In addition, PHFI published a special edition of the ‘Journal of Indian Paediatrics’ focusing on ROP, with articles commissioned from nurses, neonatologists and ophthalmologists. The Journal has a circulation list of 22,000 and is accessible to a global audience online.

Key Points

- Five States were finalised for the retinopathy of prematurity (ROP) programme, based on existing infrastructure, Government interest and findings of the situational analysis that was carried out earlier.
- The ROP programme fell short of meeting the expected milestone targets because it had only been implemented in 4 of the 5 intended districts. Tripartite Memoranda of Understanding for implementing the ROP programme was signed between the implementing partners, Public Health Foundation India (PHFI) and four State Governments (Maharashtra, Madhya Pradesh, Telangana, and Odisha). Work has yet to start in the fifth State, Rajasthan.
- The Indian State of Tamil Nadu, which is not part of the ROP programme, has requested technical support in tackling ROP in response to advocacy work by the Trust’s coordinating partner, PHFI.

Summary of responses to issues raised in previous annual reviews

2015 Annual Review Recommendation	Response/Action
Changes to the logframe – revise down the milestones for output indicator 3.1 and 3.2 based on programming in Niloufer Hospital in Hyderabad (India).	These targets have been revised utilising the data from Niloufer Hospital in Hyderabad. The Trust has kept in close contact with the Public Health Foundation of India (PHFI) throughout the year to ensure that targets are accurate as more data becomes available from other partner hospitals. The revised targets for 2016 were agreed by the National Retinopathy of Prematurity Taskforce at their meeting in New Delhi in July 2016.
Revise down the milestone for output indicator 3.3	The output indicator has been revised to capture the advocacy work being done by PHFI to incorporate retinopathy of prematurity models of care into the public health care system. The Trust has added the following indicator: / ‘At least two examples of how PHFI have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system.’

Recommendations

The Trust’s partner in India, the Public Health Foundation of India (PHFI) commissioned an independent mid-term review of the progress made so far. The review[7] found that although the retinopathy of prematurity programme had made steady progress to date, it had faced a number of challenges, such as limited availability of ophthalmologists at the district level, who are often overburdened with other hospital duties including cataract surgeries (which can be more lucrative). The Trust should:
[7] Mid-term Evaluation of Avoidable Blindness in India Nov 2016 (Amaltas Consultancy)

support the implementation of the mid-term review recommendations; including

exploring new strategies with State Governments to address the limited availability of ophthalmologists at the district level.

Output Title	Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools
Output number per LF		4	Output Score	A+
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Number of health care professionals trained	Expected results: / 40 / Clinical Fellowships: 30 / MSc students: 10	Exceeded expectation. / 53 healthcare professionals trained. / Clinical Fellowships: 45 / MSc students:8
4.2 Number of countries with domestic institutions that have agreed and implemented national frameworks for diabetic retinopathy screening and treatment	Expected results: / 2 countries agree national diabetic retinopathy (DR) frameworks / 2 countries establish their Ministry of Health DR frameworks / 4 countries working towards a national DR framework	Met expectation. / Botswana and Zambia have agreed national diabetic retinopathy (DR) frameworks. / The DR frameworks for the Ministry of Health in Kenya and Tanzania are being established. / Jamaica, Malawi, Nigeria and Uganda are working towards their national DR frameworks.
4.3 New eye care technologies developed	Expected results: / Completion of validation studies / Public release of Portable Eye Examination Kit (PEEK)	Exceeded expectation. / Validation studies completed / Public release of Peek Acuity (smartphone app) / Paediatric visual acuity tablet app Peekaboo released

Key Points

- Training in public health for eye care has been provided through Masters programmes at the International Centre for Eye Health at the London School of Hygiene and Tropical Medicine, UK and the University of Cape Town, South Africa. This training investment will expand the active network of leaders in eye care health in Commonwealth countries, which will have a long lasting impact on the prevention of blindness in these countries. It is anticipated that graduates from these courses will strengthen district and national level programmes in the delivery of universal eye health coverage in priority Commonwealth countries.
- The Diabetic Retinopathy Team Training Network (DR-NET) workshop was held in Durban, South Africa in October 2016. During the workshop the delegates used a toolkit to work through the steps needed to develop a national framework for diabetic retinopathy services. The workshop reviewed progress made by each partner on the Action Plans prepared at the first workshop in November 2014 and helped participants to put together a plan to further develop their diabetic retinopathy services over the next three years.
- Through the DR-NET Programme, training visits have taken place between partnered diabetic retinopathy institutions in the UK, sub-Saharan Africa and the Caribbean, to improve services available across the Commonwealth. For example, the lead diabetic retinopathy specialist at Frimley Park Hospital in Surrey, together with the team in Kitwe, Zambia, have persuaded the Ministry of Health in Zambia to provide essential equipment for each of five treatment centres in Zambia.
- The first Massive Open Online Course (MOOC) on Eliminating Trachoma was launched on the 3rd October 2016. This is a five-week course targeted at District Programme Managers in 57 trachoma-endemic countries. The course was accessed by 2,784 participants from 134 countries. https://www.futurelearn.com/courses/eliminating-trachoma
- 17,000 children have been screened for eye conditions using smartphone device Peek in Kenya. The first phase of the Botswanan Peek School Screening programme was complete with almost 13,000 children screened across 50 schools.
- Paediatric visual acuity app Peekaboo Vision was registered as a Class 1 Medical Device with the Medicines and Healthcare Products Regulatory Agency, and has been released to the UK Apple AppStore and is accessible via:
https://itunes.apple.com/gb/app/peekaboo-vision/id1111577266?mt=8
- Smartphone visual acuity app Peek Acuity has been released and is available for public download
- https://play.google.com/store/apps/details?id=org.peekvision.public.android&hl=en_GB

Summary of responses to issues raised in previous annual reviews (where relevant)

2015 Annual Review Recommendation	Response/Action
Scale down the milestone for output indicator 4.2 given progress to date.	The Trust has consulted with the VISION 2020 LINKS Programme Manager (Marcia Zondervan) at the Commonwealth Eye Health Consortium, about the expectations for the Diabetic Retinopathy Network over the next three years and has revised the milestones in agreement with DFID.

Recommendations

The mid-term evaluation[8] Commonwealth Eye Health Consortium (CEHC) reports that it has achieved excellent results across the Commonwealth. As a result the Trust’s Board of Trustees has approved an additional £4.3 million to expand the work of the CEHC, which includes support for additional scholarships for eye health professionals, development of online educational resources, and training networks for retinoblastoma and retinopathy of prematurity. The Trust should:
[8] Commonwealth Eye Health Consortium Mid-term Evaluation Nov 2016 (Lucy Lee)

support the implementation of the mid-term review recommendations; including

reviewing programme monitoring and evaluation tools to ensure they capture the impact of returning health care professionals on service delivery, and the impact of DR-Net LINKS services.

Output Title	A robust, responsive and supportive Trust
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
5.1 Unqualified audit of accounts received and annual results reporting aligned to common indicators presented in a manner consistent with results-based management principles	Expected results: / Compliant accounts and reporting. Clear lines of communication.	Met expectation. / The Trust’s 2015/16 Annual Report and Audited Accounts for year ending 30 June 2016 have been approved by Board of Trustees and will be signed off by the Chair of the Board in January 2017. Good clean audit opinion.
5.2 Proportion of grantees satisfied by implementation and value added by the Trust	Expected results: / Grantee responses to satisfaction question included in reporting to the Trust	Exceeded expectation. / Positive grantee responses to the value added by the Trust. Two examples include the Eye Health Consortium stated the Trust has “been immensely helpful and supportive” (Aug 2016) and the Fred Hollow Foundation “is very pleased with the relationship with the Trust” (Aug 2016).
5.3 Development of monitoring indicators and evaluation reports showing capacity building and lessons learned	Expected results: / Mid-term evaluations completed	Met expectation. / Mid-term evaluations[9] were completed on all of the Trust’s initiatives, with the recommendations used to inform future programme implementation and monitoring.
5.4 At least two examples of how the Trust has influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes	Expected results: / Diabetic Retinopathy partners to be brought together in October to produce a declaration for the 2017 Commonwealth Health Ministers meeting / Trust support of Commonwealth Health Hub with the Commonwealth Secretariat to produce a policy brief on eye health services and health systems strengthening for Commonwealth governments	Met expectation. / In May 2016, the Trust held an information hub the Commonwealth Health Ministers Meeting in Geneva and in October 2016, brought together Diabetic Retinopathy partners resulting in the production of a manifesto for the 2017 Commonwealth Health Ministers meeting (further information below). / The Trust has supported the Commonwealth Health Hub within the Commonwealth Secretariat, including a short placement in the Secretariat for an ophthalmologist from Nigeria with a public health background. Her task, with the support of an advisory group from across the Commonwealth, is to draft a policy brief on eye health in the context of health service strengthening, which will be presented at the Commonwealth Health Ministers meeting in 2017. / The Trust held events in Nigeria (April 2016) and Tanzania (July 2016) with DFID and senior Ministry of Health officials to promote the Trachoma Initiative.
[9] Mid-term Review of Sightsavers two Africa Trachoma Initiatives Nov 2016 (Tropical Health LLP), Mid-term Evaluation of Avoidable Blindness in India Nov 2016 (Amaltas Consultancy) and Commonwealth Eye Health Consortium Mid-term Evaluation Nov 2016 (Lucy Lee)

Key Points
The Trust’s Chief Executive met Health Ministers and senior Ministry of Health officials in a range of programme focus countries in 2016: Nigeria, Tanzania, Jamaica, Belize, Dominica, St Lucia, Vanuatu, Solomon Islands and Fiji. In each case, the aim was to ascertain that the Trust programmes were fully integrated into government strategies and plans; to strengthen collaboration; to present the programmes as a success for governments and to secure their commitment to continuing them after Trust closure. Different approaches were taken: besides meetings in some cases an event was held (Nigeria, Tanzania, and Solomon Islands); in others there was a joint visit to the programme (Jamaica, Belize). In all cases there was extensive supporting media and social media activity.
The Trust hosted a Commonwealth Diabetic Retinopathy (DR) Symposium in Durban in October 2016, bringing together a broad range of stakeholders from across the Commonwealth: from practitioners involved in planning and delivering DR services in a variety of countries, to eye health organisations including Trust partners, to specialists in diabetes to health ministry representatives. The lessons of different Trust supported DR programmes were presented and discussed, and a ‘manifesto’ drawn up setting out the symposium’s vision of the key features of a successful DR services, as a basis for advocacy. The symposium also discussed how best to target advocacy to strengthen DR services. The Manifesto focused on eight key features of quality care for diabetic retinopathy: Universal, Patient-centred Care, Evidence-based, Quality Service, Integrated Service, Appropriate Human Resources, Accessible, and Cost Effective and Sustainable.
- In November 2015, the Trust’s photo exhibition ‘Time to See’ showcasing the impact of avoidable blindness across seven Commonwealth countries and the efforts underway to end it, was on display at the Commonwealth Heads of Government meeting in Malta. The exhibition was seen by a range of stakeholders, including DFID and FCO Ministers. A selection of images was exhibited at the dinner hosted by Her Majesty the Queen, for Heads of Government. At that dinner the Trust’s chairman, Sir John Major, gave a speech about the Trust’s progress and impact.
- In 2016, the successful ‘Time to See’ exhibition was displayed in London at the Palace of Westminster (January); in Australia at the Sydney Museum of Contemporary Art, in conjunction with the WHO Global Alliance meeting to end Trachoma (GET2020 / April); in Canberra at an event hosted by the British High Commissioner on the occasion of The Queen’s 90th birthday (June); in New Zealand at Government House and, for the first time for the general public, on the waterfront in Wellington and Auckland (November to December).
- The Trust has continued to use its presence in relevant fora, including the International Agency for the Prevention of Blindness (umbrella body for organisations in the eye health sector) and the neglected tropical diseases community, to bring its support and influence to shaping and launching promising collaborative, strategic initiatives aimed at encouraging action and broadening engagement in efforts to combat avoidable blindness. Two examples are the Trachoma Free Africa Campaign launched in September 2016 and plans for a side event on avoidable blindness at the 2017 World Health Assembly, coinciding with the mid-term report on the WHO’s Global Action Plan on universal eye health (2014-2019).

Summary of responses to issues raised in previous annual reviews (where relevant)

2015 Annual Review Recommendation	Response/Action
DFID appreciates the Trust’s Annual Report responds to the needs and interests of wide range of stakeholders. The Trust to consider its presentation of results achieved as part of its Annual Report.	The Trust has added a results table to the programmes section of its Annual Report.
The Trust to develop, as part of its monitoring and evaluation strategy, more on strategic communications including the Trust’s approach to networking and influencing. The Trust delivers important objectives through its influencing role and should include an appropriate indicator to measure this work; for example the number of countries receiving support to develop eye health policies or x example of policy influence delivered.	The Trust has added an additional output indicator under this section (5.4), which states: ‘Provide at least two examples of how the Trust have influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes’ to capture the Trust’s networking and influencing role. The Trust has included the most significant advocacy activities conducted in 2016 under the key points.
The SEQAS report made recommendations about equity in monitoring processes. The Trust should disaggregate data by gender (at least) as recommended in the report.	The Trust will continue to report gender disaggregated results where possible for its initiatives.

Recommendations

There are no specific recommendations for the Trust but, given their value, we intend to continue the monthly programme management meetings with QEDJT and will facilitate increased liaison between them and the DFID SAFE programme team.

## D: VALUE FOR MONEY (VfM) & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The main cost drivers for the programme are: human resource and logistics costs incurred through implementing partners. These vary by initiative and the delivery channel (for example, clinic-based services or outreach teams). Pharmaceutical costs for prevention of trachoma are met by the International Coalition for Trachoma Control. Costs for surgical equipment, training materials, and diagnosis of diabetic retinopathy and retinopathy of prematurity vary by country programme.

VfM performance compared to the original VfM proposition in the business case
VfM is well understood amongst the partners. Sightsavers has developed a VfM strategy for the DFID Eliminating Blinding Trachoma programme as part of their ongoing work on the DFID SAFE programme. The strategy looks at cost per case managed, cost per mass drug administration treatment and implementation of the SAFE monitoring and evaluation framework. The Public Health Foundation India, will be undertaking cost effectiveness studies for diabetic retinopathy and retinopathy of prematurity in 2017, now that the programme has been given time to bed down. Ongoing examples of VfM assessment include:

Economy
- Sightsavers negotiated a contract for Trachoma Trichiasis surgery kits that were procured at 15% below cost price.
- Antibiotics are delivered through existing, sustainable community volunteer networks.
- The Pfizer drug donation programme has, and will continue to donate antibiotics, avoiding costs to the project of around £1 billion.

Efficiency
- Automated online web-based programme monitoring and payment system (CLAIMS), enables delivery partners to report against budget (the system enforces budget ceilings and ensures that explanations are captured for line item overspends).
- Quick access to mapping and progress data enables timely decision-making so that SAFE interventions are targeted in the most prevalent areas.
- ICTC seeks integration with other health interventions. For example, Unilever’s schools toolkit for hand washing promotion is being adapted to include facial cleanliness.

Effectiveness
- Supporting better donor coordination and collaboration with partners delivering trachoma and WASH programmes that will deliver more effective programmes that support national priorities.
- The original DFID business case noted that 15 successful retinopathy of prematurity interventions would be required for the programme to break even – this figure has already been exceeded.

Equity
- All partners across the initiatives have a poverty focus on selection of service sites which are predominately public sector sites.
- The trachoma initiative has found that trachoma endemic districts in Kenya have higher than national poverty rates.

Assessment of whether the programme continues to represent VfM
The Trust has met or exceeded the expected output results and is therefore offering good value for money for our contribution.

Quality of financial management
The Trust is governed by a Board of Trustees who set the Trust’s strategic direction and approves all operational and financial plans. An Audit Committee comprising two Trustees, the Chief Executive and four external advisory members meets at least three times a year to consider financial matters and reports to the Trustees accordingly.

The spend profile for 2016/17 was £9.7 million, paid in three instalments to reduce the risk of payment in advance of need (£3m in April 2016, £3.7m in August 2016 and £3m in October 2016).

Following underspend in the previous years; DFID amended the Trust payment schedule, to accurately reflect the need for draw down of future funds. These changes have been captured in an amendment to the current Memorandum of Understanding (MoU). The format of reporting to support each payment request is also detailed in the MoU, which requires the Trust to supply a certified letter with any payment request setting out the detailed actual expenditure to date (committed and spent), a forecast of funds to be disbursed or committed during the next 6 months, a statement supporting new funding raised to which DFID will be viewed as eligible to match and an explanation of the disparity between the forecast commitments and disbursements and funding already held by the Trust.

The Trust’s Annual Report and Audited Financial Statements for the period 1 July 2015 to 30 June 2016 will be published in January 2017, once it has been countersigned by the Trust’s Chairman. The Auditors gave a clean audit opinion and confirmed that there had been no evidence of any financial risk or fraud.

Date of last narrative financial report	28 October 2016 (certified financial letter from the Trust)
Date of last audited annual statement	30 June 2016 (done by auditors Crowe Clark Whitehill, LLP)

E: RISK (½ page)

Overall risk rating: Minor/moderate.

Overview of programme risk
This is a complex multi-initiative, multi-country programme, with several implementing partners and multiple sub-contractors.

Day-to-day risk management processes are embedded across the Trust through the effective implementation of policies and procedures. A central risk register is maintained at a corporate level, and each individual programme and initiative has its own risk register. The corporate risk register is reviewed and updated monthly by the Trust Executive Team and it is shared with the Audit Committee. The Trustee Board formally reviews it and approves it annually. In addition, robust internal controls exist and are complied with to mitigate risks to which the Trust is exposed in administering DFID’s contribution.

The Trust has Policies on Anti-Fraud and Corruption and the Bribery Act which are issued to all staff and are included in the staff handbook. All grantees are required to have their own policies on this which are included in their grant agreements. The Trust has conducted a Due Diligence assessment on all grantees. The Trust’s grant contracts require the grantee be responsible for all sub-grantees.

In addition, the Trust’s Implementing Partners report on risk in the six-monthly progress reports presented to the Trust, including identifying any new risks.

Most of the risks identified in the original DFID Business Case and subsequent due diligence assessment were linked to the Trust being a new entity and therefore no track record of delivery and programme/financial management. These risks have now reduced, as the Trust no longer falls into the ‘new’ bracket and as demonstrated under each output, they are on track to meet or exceed all initiative targets.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The Trust’s programmes are all underway, delivering results and on track to deliver intended outcomes as reported in the Trust’s 2015/16 Annual Report[10] and the Mid-term Evaluation Reports for each of the initiatives[11]. Progress Reports from grantees are delivered in a timely manner to the Trust and to the expected standard of performance and financial reporting.
[10] 4th QEDJT Annual Report and Audit Report for 1 July 2015 to 30 June 2016
[11] Mid-term Review of Sightsavers two Africa Trachoma Initiatives Nov 2016 (Tropical Health LLP), Mid-term Evaluation of Avoidable Blindness in India Nov 2016 (Amaltas Consultancy) and Commonwealth Eye Health Consortium Mid-term Evaluation Nov 2016 (Lucy Lee)

Performance of partnership (s)
Feedback from central and country level implementing partners, and reports from national symposia, taskforces and launches, suggest that excellent partnerships have been established for each initiatives and within each country. All of the implementing partners interviewed for this annual review, confirmed that the Trust is ‘adding value’ in terms of advocacy and influencing at global policy and programme level (as presented under output 5), resulting in leveraging additional financial contributions from public/private organisations. The performance of the partnership has been summed up by the Commonwealth Eye Health Consortium, which is echoed by other delivery partners too:

‘The Consortium has benefitted from an excellent working relationship with the Trust. The culture of joint decision-making and openness to supporting new and revised approaches to implementation enjoyed by this partnership to date are to be celebrated…’

Asset monitoring and control
Not applicable.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant) - Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

External mid-term reviews have been conducted on all four of the Trust’s main avoidable blindness initiatives in 2016.

(1) Trachoma management
The Trust, DFID, Sightsavers and the International Coalition for Trachoma Control formed a steering group to jointly commission an evaluation of the Trust’s trachoma initiative and the DFID SAFE trachoma programme. Both programmes are coordinated by Sightsavers and are using the same World Health Organisation approved SAFE strategy. The joint evaluation was an excellent example of partnership, reducing costs and the burden on implementation partners as well as providing more opportunities for learning and dissemination of findings. The evaluation was conducted by Tropical Health during the summer, with in-country visits to Ethiopia (DFID), Kenya (Trust), Nigeria (Trust) and Zambia (DFID). These countries were selected by the steering group to include both programmes and to review countries that were making good progress and those that were facing significant challenges. Findings from the evaluation will feed directly into programme planning for the remainder of the initiative.

(2) Diabetic Retinopathy and (3) Retinopathy of Prematurity
In India, the Trust and the Public Health Foundation of India commissioned a joint evaluation of the diabetic retinopathy (DR) and retinopathy of prematurity (ROP) programmes. The evaluation considered government ownership to ensure sustainability and potential scalability of the DR and ROP work (i.e. supported by policy and financial commitment by the Government of India) and how to ensure the programme can be replicated across India by different State Government Ministries of Health.

(4) Strengthened eye health systems in the areas of people, knowledge and tools
An evaluation of the Commonwealth Eye Health Consortium (CEHC) was conducted by a team from the London School of Hygiene and Tropical Medicine Mental Health department, who have significant experience in conducting evaluations for portfolio level grants. The evaluators facilitated sessions with Consortium members to appraise progress of the programme against its Theory of Change and indicators, and made recommendations for the next phase of implementation. The findings from the mid-term evaluation will feed into a review of the Theory of Change which will aim to revise and confirm expected outcomes, indicators and targets for the final evaluation of the programme in 2019.

DFID Monitoring progress throughout the review period
DFID officials have monthly programme meetings with the Trust to discuss progress on the logframe and financial management issues. In addition, DFID has representation on the Scientific Advisory Board, which meets twice a year (around March and September).

Annual review process
This desk-based review was carried out by the DFID Commonwealth Deputy Programme Manager with inputs from the DFID Senior Responsible Owner and Trust Programme Team. Interviews were held with the DFID Health Adviser (who sits on the Trust’s Scientific Advisory Board), DFID SAFE Programme Team, Trust Implementing Partners (Sightsavers, Public Health Foundation India, London School of Hygiene and Tropical Medicine).