## Logframe
PROJECT NAME | Libya Security, Justice & Defence Programme
IMPACT | Impact Indicator 1 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
Progess towards a stable political settlement in Libya,in which national, regional and global security threats arising are minimised. | Level of threat posed to Libyan government by social protest | Planned | 4.3 | 4.3 | 4.2 | 4 | 4
Achieved
Source
Political Instability Index - http://viewswire.eiu.com/site_info.asp?info_name=social_unrest_table&page=noads
| Impact Indicator 2 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| Impact of terrorism in Libya | Planned | 93/159 | 93/159 | 92/159 | 90/159 | 88/159
Achieved
Source
Global Terrorism Index - http://www.visionofhumanity.org/#page/indexes/terrorism-index/2010
OUTCOME | Outcome Indicator 1 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017 | Assumptions
Libyan authorities able to provide more effective, accountable and sustainable security, justice and defence for citizens | Impact of crises on the stability of the political transition in Libya | Planned | 2 | 2 | 2 | 3 | 4 | Sustained HMG political engagement with Libyan polity; Direction of political transition sustained; wider political environment remains enabling; public financial management improves allowing Libyan funds to replace UK support; militia accommodated/controlled
Achieved
Source
Independent Assessment based on political reporting: 1: Severe - government unable to function 2: Limited - government has limited functionality in key Ministries i.e. Interior and Defence adversely affecting the acheivement of key milestones 3: Moderate - government has control of all Ministries and able to achieve basic milestones in the political transition 4: Good - government has full control, clearly setting and deleivering against milestones towards securing an agreed political outcome.
| Outcome Indicator 2 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| % of citizens who view Govt as a legitimate S&J service provider | Planned | no baseline (to be established in 2012) | to be determined | to be determined | to be determined | to be determined
Achieved
|  |  | Source |  |  |  |  | RISK RATING
|  |  | National Security Dialogue (CP funded): (disaggregated by age and gender) |  |  |  |  | High
INPUTS (£) | (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | HMG SHARE (%)
| 62.580m |  | 62.580m |  |  | 62.580m | 100%
INPUTS (HR) | DFID (FTEs)
1 x A1; 1 x A2
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017 | Assumption
Threats to the political transition caused by insecurity reduced | Strength of VIP protection Unit to protect process critical individuals (supported through direct mentoring and training provided by UK police advisers) | Planned | 1 | 1 | 2 | 3 | 4 | Politicians remain in post long-enough to deliver; Political appetite for National Security Architecture; Security conditions allow access to controlled sites
Achieved
Source
Programme reporting and DIPTELs: 1: Very Poor - goal can be accomplished only with significant external assistance 2: Weak - goal can be accomplished but significant external assistance still required 3: Good enough - goal can be accomplished only with some external assistance 4: Strong - goal can be accomplished with limited need, if any, for external assistance.
| Output Indicator 1.2 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| Strength of Libyan Government's strategic approach to national security challenges (supported through work of PMs Decision Making Support Unit advisers) | Planned | 1 - No National Security Strategy. Disjointed National Security Architecture. Limited Coordination across Security Agencies. | 2 | 3 | 4 | 4 - National Security Strategy exists. National Security Architecture in place. Improvements in coordination across Security Agencies.
Achieved
Source
Independant assessment and political reporting: 1: Very Poor - there is no national security strategy 2: Weak - there is a draft national security strategy 3: Good enough - national security strategy developed and fully consulted on 4: Strong - national security strategy and architechture implemented.
| Output Indicator 1.3 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| No of sensitive stockpiles and other controlled facilities more secure and increasingly under Govt control (supported through the work of the Disarmament Adviser). | Planned | # of insecure stockpiles and other controlled facilities | additional 1 | additional 2 | additional 4 | additional 5
Achieved
Source
Programme reporting
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
30% | No of former fighters integrated into Armed Forces and Police (supported through work of UK DATT and police teams) | Planned | At least 140,000 former Thuwaar | 145000 | 155000 | 165000 | 180000
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Official Libyan Government figures (from Warrior Affairs Commission & Police) | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 13430000 | [5 empty] | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017 | Assumptions
Government security, justice and defence institutions increasingly capable, accountable, responsive and coordinated | Level of administrative and organisational capacity of government (PM's office, MoI, MoD and MoJ) (supported through 4 UK insitutional development advisers) | Planned | 1 - Management & Functional reviews undertaken of MoJ, MoI and MoD; | 1 | 2 | 3 | 4 | Capacity exists within Ministries to take advantage of TA provided; Willingness of Ministries to collaborate with each other and engage the public; political process allows for policy making
Achieved
Source
Independant assessment and political reporting: 1: Very Poor - there is very limited administrative and organisational capacity 2: Weak - there is some administrative and organisational capacity 3: Good enough - basic administrative and organisational capacity 4: Strong - there is credible administrative and organisational capacity.
| Output Indicator 2.2 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| Responsiveness of government to engage in dialogue on defence, security and justice issues | Planned | Outcome of initial National Security Dialogue inception phase | TBD | TBD | TBD | National Security Dialogue occurs regularly with limited external facilitation; public perception of Govt responsiveness improves
Achieved
Source
National Security Dialogue Process (15 locations)
35% | Output Indicator 2.3 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| Government capacity to develop policies on security, justice and defence (supported through 4 x UK institutional development advisers) | Planned | 1 - Embryonic Defence White Paper process; initial National Security Architecture discussion | 1 | 2 | 3 | 4 - Clear National Security Policy involving public consultation; Policy informs approach of key security & justice institutions; enhanced coordination between line Ministries at national level;
Achieved
|  | Source | [5 empty] | RISK RATING
INPUTS (£) |  | Independant assessment and political reporting: 1: Very Poor - there is no capapcity to develop strategy 2: Weak - there is a draft strategy strategy 3: Good enough - strategies developed for security, justice and defence, and fully consulted on 4: Strong - strategies and architechture implemented. | [5 empty] | Medium
| DFID (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | 12320000
DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017 | Assumptions
Improved security, justice and defence service delivery by Libyan Government | Number of police trained in investigative techniques (supported by Police advisory team) | Planned | TBC during inception | 5000 | 15000 | 30000 | same as 2016 | Sufficient evidence available to track progress of justice services; Local people consent to work with formal security providers, and share opinion without fear of reprisal
Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| Number of people detained without trial, or beyond the length of their tariffs (supported by detentions adviser) | Planned | TBC during inception
Achieved
Source
Programme reporting
| Output Indicator 3.3 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
| Number of judicial police trained (supported by Judicial Police training adviser) | Planned | very poor training if any provided to JP | training curricula developed and piloted | 500 | 1000 | 1500
Achieved
Source
Programme reporting
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2017
35% | Improved public trust in Government security, justice and defence institutions (supported by the programme management team) | Planned | TBC during inception |  |  |  | % increase in citizens reporting increased trust in security & justice actors (disaggregated on basis of age and gender); perceptions of the role of women in security and justice institutions improved;
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Public Perception Tracker Surveys | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
36830000
INPUTS (HR) | DFID (FTEs)

## Results Chain
Libya Security, Justice & Defence Programme
OUTPUTS |  |  | OUTCOME | IMPACT
1 | Threats to the political transition caused by insecurity reduced | 30% | Libyan authorities able to provide more effective, accountable and sustainable security, justice and defence for citizens | Progess towards a stable political settlement in Libya,in which national, regional and global security threats arising are minimised.
2 | Government security, justice and defence institutions increasingly capable, accountable, responsive and coordinated | 35%
3 | Improved security, justice and defence service delivery by Libyan Government | 35%
4 | Improved security, justice and defence service delivery by Libyan Government | #REF!
5 | #REF! | #REF!

## Logframe Summary
Libya Security, Justice & Defence Programme
Results Chain |  |  | Indicators | Baseline 2013 | Target 2017 | Source
IMPACT | Progess towards a stable political settlement in Libya,in which national, regional and global security threats arising are minimised. |  | Impact of crises on the stability of the political transition in Libya | 4.3 | 4 | Political Instability Index - http://viewswire.eiu.com/site_info.asp?info_name=social_unrest_table&page=noads
|  |  | Impact of terrorism in Libya | 93/159 | 88/159 | Global Terrorism Index - http://www.visionofhumanity.org/#page/indexes/terrorism-index/2010
OUTCOME | Libyan authorities able to provide more effective, accountable and sustainable security, justice and defence for citizens |  | Impact of crises on the stability of the political transition in Libya | 2 | 4 | Independent Assessment based on political reporting: 1: Severe - government unable to function 2: Limited - government has limited functionality in key Ministries i.e. Interior and Defence adversely affecting the acheivement of key milestones 3: Moderate - government has control of all Ministries and able to achieve basic milestones in the political transition 4: Good - government has full control, clearly setting and deleivering against milestones towards securing an agreed political outcome.
|  |  | % of citizens who view Govt as a legitimate S&J service provider | no baseline (to be established in 2012) | to be determined | National Security Dialogue (CP funded): (disaggregated by age and gender)
|  |  | #REF! | #REF! | #REF! | #REF!
OUTPUTS | Threats to the political transition caused by insecurity reduced | 30% | Strength of VIP protection Unit to protect process critical individuals (supported through direct mentoring and training provided by UK police advisers) | 1 | 4 | Programme reporting and DIPTELs: 1: Very Poor - goal can be accomplished only with significant external assistance 2: Weak - goal can be accomplished but significant external assistance still required 3: Good enough - goal can be accomplished only with some external assistance 4: Strong - goal can be accomplished with limited need, if any, for external assistance.
|  |  | Strength of Libyan Government's strategic approach to national security challenges (supported through work of PMs Decision Making Support Unit advisers) | 1 - No National Security Strategy. Disjointed National Security Architecture. Limited Coordination across Security Agencies. | 4 - National Security Strategy exists. National Security Architecture in place. Improvements in coordination across Security Agencies. | Independant assessment and political reporting: 1: Very Poor - there is no national security strategy 2: Weak - there is a draft national security strategy 3: Good enough - national security strategy developed and fully consulted on 4: Strong - national security strategy and architechture implemented.
|  |  | No of sensitive stockpiles and other controlled facilities more secure and increasingly under Govt control (supported through the work of the Disarmament Adviser). | # of insecure stockpiles and other controlled facilities | additional 5 | Programme reporting
|  |  | No of former fighters integrated into Armed Forces and Police (supported through work of UK DATT and police teams) | At least 140,000 former Thuwaar | 180000 | Official Libyan Government figures (from Warrior Affairs Commission & Police)
| Government security, justice and defence institutions increasingly capable, accountable, responsive and coordinated | 35% | Level of administrative and organisational capacity of government (PM's office, MoI, MoD and MoJ) (supported through 4 UK insitutional development advisers) | 1 - Management & Functional reviews undertaken of MoJ, MoI and MoD; | 4 | Independant assessment and political reporting: 1: Very Poor - there is very limited administrative and organisational capacity 2: Weak - there is some administrative and organisational capacity 3: Good enough - basic administrative and organisational capacity 4: Strong - there is credible administrative and organisational capacity.
|  |  | Responsiveness of government to engage in dialogue on defence, security and justice issues | Outcome of initial National Security Dialogue inception phase | National Security Dialogue occurs regularly with limited external facilitation; public perception of Govt responsiveness improves | National Security Dialogue Process (15 locations)
|  |  | Government capacity to develop policies on security, justice and defence (supported through 4 x UK institutional development advisers) | 1 - Embryonic Defence White Paper process; initial National Security Architecture discussion | 4 - Clear National Security Policy involving public consultation; Policy informs approach of key security & justice institutions; enhanced coordination between line Ministries at national level; | Independant assessment and political reporting: 1: Very Poor - there is no capapcity to develop strategy 2: Weak - there is a draft strategy strategy 3: Good enough - strategies developed for security, justice and defence, and fully consulted on 4: Strong - strategies and architechture implemented.
Improved security, justice and defence service delivery by Libyan Government
|  | 35% | Number of police trained in investigative techniques (supported by Police advisory team) | TBC during inception | same as 2016 | Programme reporting
|  |  | Number of people detained without trial, or beyond the length of their tariffs (supported by detentions adviser) | TBC during inception | 0 | Programme reporting
|  |  | Number of judicial police trained (supported by Judicial Police training adviser) | very poor training if any provided to JP | 1500 | Programme reporting
|  |  | Improved public trust in Government security, justice and defence institutions (supported by the programme management team) | TBC during inception | % increase in citizens reporting increased trust in security & justice actors (disaggregated on basis of age and gender); perceptions of the role of women in security and justice institutions improved; | Public Perception Tracker Surveys
|  | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!

## Annual Review (hidden)
Libya Security, Justice & Defence Programme
Results Chain |  |  | Indicators | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk
|  |  |  | 2014 |  | 2014 |  | 2014 | 2015 |  | 2015 |  | 2015 | 2016 |  | 2016 |  | 2016 | Target 2017 |  | 2017 |  | 2017
IMPACT | Progess towards a stable political settlement in Libya,in which national, regional and global security threats arising are minimised. |  | Impact of crises on the stability of the political transition in Libya | 4.3 | 0 |  |  |  | 4.2 | 0 |  |  |  | 4 | 0 |  |  |  | 4 | 0
|  |  | Impact of terrorism in Libya | 93/159 | 0 |  |  |  | 92/159 | 0 |  |  |  | 90/159 | 0 |  |  |  | 88/159 | 0
OUTCOME | Libyan authorities able to provide more effective, accountable and sustainable security, justice and defence for citizens |  | #REF! | 2 | 0 | n/a | 0% |  | 2 | 0 | n/a | 0% |  | 3 | 0 | n/a | 0% |  | 4 | 0 | n/a | 0%
|  |  | % of citizens who view Govt as a legitimate S&J service provider | 2 | 0 |  |  |  | to be determined | 0 |  |  |  | to be determined | 0 |  |  |  | to be determined | 0
|  |  | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
OUTPUTS | Threats to the political transition caused by insecurity reduced | 30% | Strength of VIP protection Unit to protect process critical individuals (supported through direct mentoring and training provided by UK police advisers) | 1 | 0 | n/a | 0% |  | 2 | 0 | n/a | 0% |  | 3 | 0 | n/a | 0% |  | 4 | 0 | n/a | 0%
|  |  | Strength of Libyan Government's strategic approach to national security challenges (supported through work of PMs Decision Making Support Unit advisers) | 2 | 0 |  |  |  | 3 | 0 |  |  |  | 4 | 0 |  |  |  | 4 - National Security Strategy exists. National Security Architecture in place. Improvements in coordination across Security Agencies. | 0
|  |  | No of sensitive stockpiles and other controlled facilities more secure and increasingly under Govt control (supported through the work of the Disarmament Adviser). | additional 1 | 0 |  |  |  | additional 2 | 0 |  |  |  | additional 4 | 0 |  |  |  | additional 5 | 0
|  |  | No of former fighters integrated into Armed Forces and Police (supported through work of UK DATT and police teams) | 145000 | # of insecure stockpiles and other controlled facilities |  |  |  | 155000 | 0 |  |  |  | 165000 | 0 |  |  |  | 180000 | 0
| Government security, justice and defence institutions increasingly capable, accountable, responsive and coordinated | 35% | Level of administrative and organisational capacity of government (PM's office, MoI, MoD and MoJ) (supported through 4 UK insitutional development advisers) | 1 | 0 | n/a | 0% |  | 2 | 0 | n/a | 0% |  | 3 | 0 | n/a | 0% |  | 4 | 0 | n/a | 0%
|  |  | Responsiveness of government to engage in dialogue on defence, security and justice issues | TBD | 0 |  |  |  | TBD | 0 |  |  |  | TBD | 0 |  |  |  | National Security Dialogue occurs regularly with limited external facilitation; public perception of Govt responsiveness improves | 0
|  |  | Government capacity to develop policies on security, justice and defence (supported through 4 x UK institutional development advisers) | 1 | 0 |  |  |  | 2 | 0 |  |  |  | 3 | 0 |  |  |  | 4 - Clear National Security Policy involving public consultation; Policy informs approach of key security & justice institutions; enhanced coordination between line Ministries at national level; | 0
|  |  | #REF! | # of insecure stockpiles and other controlled facilities | # of insecure stockpiles and other controlled facilities |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
| #REF! | 35% | Number of police trained in investigative techniques (supported by Police advisory team) | 5000 | # of insecure stockpiles and other controlled facilities | n/a | 0% |  | 15000 | 0 | n/a | 0% |  | 30000 | 0 | n/a | 0% |  | same as 2016 | 0 | n/a | 0%
|  |  | Number of people detained without trial, or beyond the length of their tariffs (supported by detentions adviser) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of judicial police trained (supported by Judicial Police training adviser) | training curricula developed and piloted | 0 |  |  |  | 500 | 0 |  |  |  | 1000 | 0 |  |  |  | 1500 | 0
|  |  | Improved public trust in Government security, justice and defence institutions (supported by the programme management team) | #REF! | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | % increase in citizens reporting increased trust in security & justice actors (disaggregated on basis of age and gender); perceptions of the role of women in security and justice institutions improved; | 0
| Improved security, justice and defence service delivery by Libyan Government | #REF! | #REF! | #REF! | #REF! | n/a | 0% |  | #REF! | #REF! | n/a | 0% |  | #REF! | #REF! | n/a | 0% |  | #REF! | #REF! | n/a | 0%
|  |  | #REF! | 0 | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | n/a | 0% |  | #REF! | #REF! | n/a | 0% |  | #REF! | #REF! | n/a | 0% |  | #REF! | #REF! | n/a | 0%
|  |  | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
OVERALL OUTPUT SCORE |  | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
| Value | Threshold
A++ | 150% | 137.5% | Outputs substantially exceeded expectation
A+ | 125% | 112.5% | Outputs moderately exceeded expectation
A | 100% | 87.5% | Outputs met expectation
B | 75% | 62.5% | Outputs moderately did not meet expectations
C | 50% |  | Outputs substantially did not meet expectations
n/a | 0%
Risk
Low | 1
Medium | 2
High | 3