Type of Review: Annual Review
EDRM: 4004563

Project Title: Support to Harnessing Non-State Actors for Better Health for the Poor (HANSHEP) Phase 1, 2010-2015
Project 201101

Date started:	2010	Date review undertaken: June 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Results framework / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meetexpectation C

## Introduction and Context

What support is the UK providing?
DFID is contributing £12.5 million over 5 years (FY 2010/11- 2014/15, as approved by the former Secretary of State in April 2010. This funding has been committed to 6 projects and DFID’s contribution to the HANSHEP Secretariat costs. In June 2012, the Director, International Finance Department approved additional DFID funding of £22 million over 5 years (FY 2012/13- 2017/18) for African Health Markets for Equity, a HANSHEP project to be co-funded with the Bill and Melinda Gates Foundation (BMGF) also committing £22 million. This brings the total number of HANSHEP Phase 1 projects supported by DFID to 7. A business case for £75 for HANSHEP Phase 2 is currently under design.

What are the expected results?
According to the original results framework, the goal of HANSHEP is to improve the health status of the poor. This is to be achieved by supporting better quality and more affordable, or free, health services for the poor as a result ofnon-state actors (NSAs) playing a more effective role. Results sought are: / Strengthened developing country government capacity to plan, legislate, regulate and engage in relation to non-state actors (NSAs) in the health sector; / NSAs have better access to the information, best practice models, capital, inputs and other factors of production that enable them to make a more effective contribution to health systems that serve the poor well; and / Information, knowledge and best-practice about NSAs in the health field generated and disseminated.

What is the context in which UK support is provided?
To increase utilisation of good quality essential health services by poor people, public and private health care providers and patients must be involved. DFID already provides significant support to provide essential health services through the public sector in many countries, through bilateral programmes and through multilaterals and global funds. But the non-state sector, both commercial for profit and not-for-profit (simply termed the “private sector” among health specialists), plays a critical role in the provision of healthcare and health commodities, in many countries, is larger than the public sector. In sub-Saharan Africa, where public resources are limited, around 60% of healthcare financing comes from private sources - mostly out-of-pocket payments made by individuals when they need care - and about 50% of total health expenditure goes to non-state providers. However, across the developing world, private healthcare providers tend to be fragmented and unregulated, often low quality and unaffordable to the poor. For example, in urban and rural India, a standardized patient study showed low levels of provider training and huge quality gaps, (Das et al, Health Affairs 31, No. 12 (2012): 2774–2784). To compound matters, regulatory failures are very common, including inappropriate, excessive and weakly enforced regulations. / HANSHEP is a group of development agencies and countries, established by its members with an MOU in 2010, seeking to improve the performance of the non-state sector in delivering better healthcare to the poor by working together, learning from each other and co-financed programmes, and sharing this learning with others. Current HANSHEP members are: DFID; KfW and GiZ on behalf of the German Government; USAID; Gates Foundation; Rockefeller Foundation; the World Bank Group; the African Development Bank; the Governments of Rwanda and Nigeria; and the Public Health Foundation of India. During most of the period under review, DFID was Chair of HANSHEP (March 2012 to March 2013), and has now handed over to the World Bank Group. / HANSHEP members and the Secretariat manage a portfolio of 8 active projects. / Active projects with a DFID financial contribution are listed below. These projects fall under the umbrella business case for HANSHEP Phase 1, apart from African Health Markets for Equity, which had a separate business case. / Pilot Health PPP Facility, managed by IFC, to test the use of PPPs as an innovative finance mechanism to leverage private sector investment for better delivery of health services to the poor in low income countries. On 11 November 2011, the Head of PSD approved a DFID contribution of £3.6 million towards a total budget of £10.25 million over 4 years (2011/12 to 2014/15). Other funders are IFC, South African Development Bank and the Netherlands Government. / Center for Health Markets Innovation (CHMI) is an online resource on health market innovations, including a database of well over 1000 projects. In May 2012, the Head of PSD approved a DFID contribution of £3.536 million to a total of £7.676 million over 4 years (2012/13 to 2015/16). The programme is managed by the Results for Development Institute (R4D) and is co-funded by Gates and Rockefeller Foundations. / HANSHEP Health Enterprise Fund to uncover innovative and replicable solutions that address critical health priorities in sub-Saharan Africa. The fund provides grants coupled with technical assistance to health enterprises addressing these health priorities in Kenya and Ethiopia. In March 2013, the Head of PSD approved a DFID contribution of £2.1m to match USAID funds over 3 years (2013/14 to 2015/16). Rockefeller Foundation had contributed £300,000 to fund design. This project is managed by Abt Associates, as part of USAID’s programme Strengthening Health Outcomes through the Private Sector. / Making Markets work to Transform Treatment for Child Diarrhoea to support scale-up of zinc and oral rehydration salts to treat diarrhoea in children in Nigeria. This will involve the private sector through four key intervention areas: generating awareness and demand; improving availability and affordability; increasing provider awareness; and securing a conducive policy environment. In May 2013, the Team Leader, Health and Education, PSD approved a DFID contribution of £1.84m to be spent in partnership with the Gates Foundation over 2 years (2013/14 to 2015/16). / HANSHEP Training and Capacity Building to support Private Sector Health Policy and PPPs - to provide quality assured training content and courses in private sector health care policy and PPP, tailored for public officials from Low and Lower-Middle Income Countries. In May 2013, the Team Leader, Health and Education, PSD approved a DFID contribution of £0.71 to be spent through the World Bank Institute (WBI) over 2 years (2013/14 to 2015/16). / African Health Markets for Equity (AHME) to deliver high quality basic healthcare through the private sector and targeted at the poor in Ghana, Nigeria and Kenya. DFID’s contribution is £22 million (US$33.7 million) to a total programme budget of £44 million over 5 years (2012/13 to 2017/18), jointly funded with the Gates Foundation. / Active projects with no DFID financial contribution: / International Health Economics Association (iHEA) 2013 one-day symposium- to progress international discussions on the performance of health markets in low and middle income countries and interventions aimed at improving this performance. / HANSHEP Knowledge and Learning a range of initiatives designed to (a) improve cross-agency learning between HANSHEP member agencies and their in-country staff, and (b) build capacity in knowledge generation, management and dissemination of non-state actors in Rwanda, India and Nigeria. This is funded by a World Bank Development Grant of US$1.5 million from 2012/2013 to 2014/15. / One HANSHEP project has been completed: / Mining PPPs for Better Health Study– a research project to understand how the mining sector can contribute to better health for the poor in low income countries. This 18 month programme was initiated in September 2011, with a DFID contribution of £510,000 out of a total budget of £572,000. Other funders are IFC, AusAid and the Rockefeller Foundation. / Pipeline projects include: / Global Health Investment Fund - to provide affordable financing to advance the development of drugs, vaccines, diagnostics and other interventions for diseases that disproportionately burden low-income countries. Potential contributions from IFC and KfW about to be publicly announced at the launch of the Fund. / Making Markets work to Transform Treatment for Child Diarrhoea (see active project 4) - scaling this Nigeria pilot project up and supporting the work in a potential total of 10 countries. Potential additional contributions by DFID, USAID, the Gates Foundation and other members. This project is already underway, / Global Advisory Facility for PPP in health - combining health sector and private sector policy expertise to support countries to improve health outcomes through public-private engagement in health. This project is in the design phase, and is likely to involve contributions from DFID, the Gates Foundation the World Bank Group; / In-depth evaluations - new primary studies under two thematic windows addressing key questions related to NSAs and health. Potential contributions by DFID, the Gates Foundation and other members. Work is underway to define the focus of these evaluations. / DFID financial support for existing and new pipeline projects would be dependent on the Secretary of State’s approval of further funding for HANSHEP. A business case for an additional £75m for HANSHEP is currently under design and will be submitted to the Secretary of State in Autumn 2013. / peline projects include:en US latformion (ibution: / on, PSD approved a DFID contribution of £1.84m to be spent in partnership wThe project portfolio is managed by a Secretariat (after an OJEU competition was won by MDY Legal). Key documents are accessible on the HANSHEP website, www.hanshep.org.
[note] IFC (2008): The Business of Health in Africa: Partnering with the Private Sector to Improve People’s Lives.

## Section A: Detailed Output Scoring

Output 1: Strengthened developing country government capacity to plan, legislate, regulate and engage in relation to NSAs in the health sector
Score: A (met expectation) / Progress against expected results: / Several HANSHEP projects have contributed to strengthening developing country capacity. / The Pilot Health PPP Facility managed by IFC has been operational since February 2012. Three training workshops for government officials (mostly from Ministries of Health and Finance) were conducted during the year. The target for the first year of the programme was 5 signed health PPP mandates, but demand was much higher than expected. To date, IFC, has signed a total of 14 mandates with the governments of Lesotho, Benin, Rwanda, Nigeria, Ghana, Bangladesh, and the Indian States of Jharkand and Meghalaya. Three mandates have concluded and resulted in PPP agreements. The expected impact of the 3 PPPs include improved health services for 1.34 m poor people (510,000 women) and increased private investment of US$30m. There is a robust pipeline of further health PPP mandates in Mozambique, Zambia, Tanzania, and in the Indian states of Orissa and Uttar Pradesh. The HANSHEP Mining Health Initiative (MHI) produced Good Practice Guidelines for mining companies offering health services. The Guidelines were based on case studies on mining health services in Ghana, Madagascar, Mozambique, Papua New Guinea and Zambia, The MHI outputs were distributed to the 3 focus countries and throughout Africa, including at the African annual mining conference INDABA in February 2013. The MHI recommendations are being followed up by the IFC as part of the Pilot Health PPP Facility. / Additional projects/elements of projects are under development to further contribute to capacity building over the coming year. The newly approved HANSHEP Training and Capacity Building to support Private Sector Health Policy and PPPs will train up to 100 public officials from Low and Lower-Middle Income Countries. It will also develop a massive open online course (MOOC), to support on-going learning. This project will be managed by the World Bank Institute and will become operational in June 2013. / Discussions are on-going with the World Bank, IFC and World Bank Institute regarding potential DFID support to the proposed Global Advisory Facility, to provide advice to governments on policies, laws, regulations and institutions in relation to working with the private sector in health. / In addition, various projects include elements of support to governments regarding legal and regulatory reform to support the role of NSAs. These include African Health Markets for Equity, where the IFC will work with the governments of Ghana, Nigeria and Kenya to support social franchising and public financing of privately provided health services, Making Markets work to Transform Treatment for Child Diarrhoea will also include support for public policy reform. Neither of these projects has progressed far enough to demonstrate results at this point. / Recommendations: / HANSHEP support to developing country governments should be consolidated, as far as possible, in a single project. The proposed Global Advisory Facility should incorporate existing projects such as Health in Africa, the PPP Facility, and the Training and Capacity Building project. Any new Facility should build upon and not duplicate existing HANSHEP projects. / The Pilot Health PPP Facility programme has highlighted the challenge that many low income countries (LICs) face in preparing broader health strategies and plans that would allow non-state actors to take a more active role. DFID should continue to support the establishment of a Global Advisory Facility to directly address LICs’ health planning and policy needs and appropriate entry points for health PPPs. / Accurate measurement of programme beneficiaries including disaggregation by gender and income quintiles remains problematic for many HANSHEP project. Attention should be paid to reinforcing M&E components of HANSHEP projects, to satisfy these demands and to build LIC capacity to undertake such measurement routinely.
Impact Weighting (%): 30%(original results framework) / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? Yes, revised down from medium due to recent progress and increased number of projects focusing on capacity building.

Output 2: NSAs have better access to the information, best practice models, capital, inputs and other factors of production that enable them to make a more effective contribution to health systems that serve the poor well
Score: A (met expectation)
Progress against expected results: The original Project Memorandum suggested a number of examples of potential projects, e.g. supporting programmes to raise NSA standards through training, professional associations, and franchising, and developing models for joint venture arrangements with large long-term employers such as extractive industries. Regarding increasing NSA access to information and best practice models, more information is given under Output 3, below. / The Pilot Health PPP Facility has generated 14 health PPP mandates that provide new, large-scale investment opportunities for NSAs. For 3 of these, public tenders have already taken place. NSAs have also benefited from the dissemination of the projects communications outputs. / The Center for Health Market Innovations (CHMI) is an on-line, global, public good providing information on non-state health innovations from mostly low and middle income countries. CHMI operates several hubs around the world that link up health officials with providers in order to maximise public uptake of the most promising models and approaches. CHMI also manage several forums to engage stakeholders including policymakers in priority areas such as universal healthcare, health insurance for the poor, and social franchising to serve the poor. / Two projects are explicitly supporting NSAs as part of broader health systems, tackling constraints to supply and demand of health services (so covering a range of factors of production), as well as the legal and regulatory environments in which NSAs operate. African Health Markets for Equity launched in January 2013. To date, efforts have largely been focused on project design in each of the 3 target countries, and training of health clinic staff to deliver a broader range of good quality healthcare services. Over the coming year, activities to improve quality standards, range of services offered, and capital available for NSAs will increase. Making Markets work to Transform Treatment for Child Diarrhoea will also take a health systems approach. This project is still under design by DFID and the Gates Foundation, though DFID funding has been approved. / The recently launched HANSHEP Health Enterprise Fund builds on the recommendation from the last annual review that DFID seek projects through HANSHEP to support inclusive business, social entrepreneurs and innovation. The first round of the challenge fund attracted 150 initial applications from enterprises in Kenya and Ethiopia. After a workshop to explain the business planning process, 39 full applications were received in Kenya, and 11 in Ethiopia. The Fund managers plan to make 20 awards in June, and successful enterprises will receive both funding and in-depth technical assistance to help them grow their businesses. A range of businesses applied, addressing issues such as health financing, service delivery, manufacture, and mobile technology. / HANSHEP Training and Capacity Building to support Private Sector Health Policy and PPPs becomes operational in June 2013. Over the coming year, it is expected to significantly increase training available to NSAs through a free massive open online course (MOOC) on private health sector policy and PPPs. / A HANSHEP members sub-group has been working to support NSAs to engage with governments in member countries (Nigeria, Rwanda and India), for example through strengthening the Rwanda Health Federation. / Recommendations: / To further achieve progress against this output, DFID should continue to support a range of projects through HANSHEP and maintain a balance between knowledge and evidence, and innovative projects delivering goods and services on the ground. / DFID should also seek to support a larger number of health systems projects through HANSHEP, rather than projects with focus on addressing a limited number of NSA factors of production. / HANSHEP members should continue to invite NSAs to participate as guest speakers at HANSHEP quarterly meetings, to learn from their experiences. / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? Yes, revised from low to medium. Although an increased number of projects will provide access to information, best practice, capital, and other factors of production, achieving effective contributions to health systems is a challenge. Only AHME and the Making Markets Work to Transform Child Diarrhoea projects are taking a market systems development approach, to address holistically the constraints of NSAs contributing to improve health outcomes for the poor.

Output 3: Information, knowledge and best-practice about NSAs in the health field generated and disseminated
Score: A (met expectation)
Progress against expected results: The Project Memorandum suggested a number of activities under this output, such as supporting CHMI, and increasing pricing transparency. / The HANSHEP website launched in April 2012, and usage has continued to grow, Since its launch, the website has attracted over 8,000 visits from people in over 140 countries. Exchanging knowledge and learning between HANSHEP members and external parties has continued to afford greater profile for the HANSHEP group, which has been featured in high profile international reports (e.g. the 2012 G8 Accountability Report, the 2013 EU Options Paper for Private Sector Development in Global Health), and industry publications such as the inaugural issue of the newsletter for the Association of Private Health Facilities in Tanzania. The ‘New Perspective’ online blogs written by the HANSHEP Programme Manager and others have also generated positive feedback, and are frequently cross-posted by organisations such as Results for Development and the International Health Economists Association (iHEA). The Secretariat also continues to respond to a range of enquiries submitted through the website, including from practitioners in Ghana, Pakistan, Zimbabwe, Kenya, Sierra Leone, Bangladesh and Liberia, demonstrating the continually increasing awareness and reach of HANSHEP’s work / The lead up to the IHEA Private Sector in Health Symposium has started, with the launch of a series of monthly webinars, on 5 Februrary focusing on lessons from India, and 7 March on the future of health markets. More than 220 participants registered for the events. / The Center for Health Market Innovations (CHMI) provides information on promising NS health innovations as well as wider lessons learned gleamed from literature and its various health forums. The information CHMI has generated serves to help providers and investors identify opportunities to replicate and up-scale promising models and approaches. / An Environmental Scan exploring ways to enhance cross-sectoral learning and knowledge exchange among government and non-state actors, including an overview of key resources and learning preferences of different groups, was completed in February 2013 by Results for Development as the first in a series of activities supported through the US$1.5m World Bank grant awarded to HANSHEP. A team of knowledge and learning specialists has since been recruited through an open tender process to design a range of activities that will enhance cross-agency learning between HANSHEP member staff at both HQ and in-country levels, while also funding priority knowledge management initiatives among non-state actors in India, Nigeria and Rwanda / The Pilot Health PPP Facility has generated some early lessons, including around contracting NSAs, which have been disseminated as part of the communications strategy. / The Mining Health Initiative (MHI) published 18 reports which, among other things, highlight the good practices and lessons learned by mining companies while instituting and managing health care programmes for their staff and local communities. This information, combined with literature sources, provided the evidence to produce the Good Practice Guidelines. / All remaining projects include a target regarding the generation and dissemination of information, knowledge and best practice, though it is too early to report on these. In-depth independent evaluations are also being commissioned for DFID’s largest investments, including African Health Markets for Equity. / Recommendations: / HANSHEP works harder to translate knowledge and evidence on NSAs into tangible actions that result in better quality healthcare for the poor. / Ensure coherence and complementarity between range of online resources, and run a series of training sessions for staff of HANSHEP members, implementing partners and others. / Impact Weighting (%): 40% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the Results Framework been updated since last review? A revised results framework was suggested at the time of the last Annual Review. However, approval of this logframe was delayed to accommodate feedback from the Head, PSD, Evaluation Advisers and a Health Economist. The revised logframe is now ready for approval, and will be submitted to the Secretary of State alongside the business case for additional funding for HANSHEP. Active DFID-funded HANSHEP projects have been nested within the overarching Results Framework. HANSHEP programme and individual project results directly attributable to DFID can be estimated from the document. Milestones will be updated on an on-going basis as new HANSHEP project targets are achieved, with all individual HANSHEP project outputs and outcomes incorporated into the overarching HANSHEP Results Framework. Where DFID is co-funding projects with other HANSHEP members, either results areattributable to DFID based on the % of overall project funding provided by DFID or the nested logframe specifically states the DFID attribution. The original logframe (used for this review) is at EDRM 3526879. The revised logframe is at EDRM 3581306. / 1.2 Overall Output Score and Description: A (Outputs met expectation) – project scoresheet at 4017851. / This represents an improvement from last year’s output score of B (outputs moderately did not meet expectation), which was largely due to HANSHEP’s relatively slow rate of progress that year. This year, there has been good progress in priority areas, with the number and breadth of projects increasing, and the pace of implementation picking up substantially. / 1.3 Direct feedback from beneficiaries: Not applicable at this point as majority of projects have not been operational for long. However, this feedback will be sought to inform the evaluation of HANSHEP proposed for 2015. And direct feedback will be sought from beneficiaries of individual projects after a maximum of 2 years of operation of each individual project.
1.4 Summary of overall progress / Progress documented above relates to specific HANSHEP projects. It is also worth reflecting on the progress of the HANSHEP Secretariat, Membership and the overall project portfolio. / The HANSHEP Secretariat continues to handle the day-to-day administration of HANSHEP for its members. This includes managing the website, the quarterly members meetings, the HANSHEP Knowledge and Learning project, and information on all HANSHEP projects. Recently, the Secretariat and DFID agreed a Programme Funding Arrangement (PFA) to give the Secretariat additional responsibilities related to the HANSHEP projects DFID funds. The PFA means the Secretariat invoices DFID quarterly for funds DFID owes to HANSHEP project implementing partners. This quarterly invoice is accompanied by a summary of progress (narrative and financial) for all relevant projects). DFID makes a single payment to the Secretariat which is then disbursed to project implementers based on DFID being content with progress of each project. / HANSHEP members continue to meet once a quarter to discuss new issues in the field of non-state health, update one another on their own strategies and priorities, and agree funding priorities. / The Secretariat continues to perform well. During the period in which DFID served as the Chair of HANSHEP, the Secretariat received positive feedback from all members. For example, member feedback from the face-to-face quarterly meetings this year (Windsor September 2012, and Kigali, March 2013) rated the Secretariat’s preparation for the meetings, and the HANSHEP Programme Manager’s presentations as good/excellent. Members discussed whether the Secretariat should take on additional technical or representational capacity, but it was not deemed necessary during the period under review, as Members themselves provided these functions. / Over the past year, the Government of Nigeria and the Public Health Foundation of India (representing the Government of India) joined HANSHEP as non-funding members. The Australian Agency for International Development left the group in 2012 citing a change in priorities and resource constraints. However, during the same period the African Development Bank joined as a funding member. This meant the number of HANSHEP partners increased from 9 to 11 under DFID’s chair of HANSHEP. The group aims to increase the total number of funding members in the coming year and discussions are underway to invite new members. / At the time of the last Annual Review, DFID and the Gates Foundation were the two major financial contributors to HANSHEP projects. This situation is changing. Funding members are putting more resources into an increasing number of active projects. Total commitments to programme funding, across all members, grew from £10.9m in 2011/12 to £70.6m in 2013/14. The HANSHEP Programme Manager’s quarterly report (March 2013) indicates a further four projects (potentially worth up to £50m) are under development. These include the Global Health Investment Fund (GHIF), which was introduced to the HANSHEP group by DFID in early 2012. KfW and the Gates Foundation have committed funding to GHIF through the Global Health Investment Corporation (GHIC), and the IFC has made public the fact that is reviewing a potential investment in GHIF and dialogue is ongoing. Investments are expected to be $10m from the IFC and $13m from KfW. (EDRM 4002184: Programme Funding Dashboard as of March 2013). / Increasingly active member involvement in HANSHEP and member collaboration is also evidenced by DFID and the Gates Foundation signing an MOU for partnership in non-state health (EDRM 3680694). The range, focus, and involvement of members in the presentations at the quarterly meetings also exemplifies increased member engagement, for example, with different members proposing focus teams for quarterly meetings and presenting on topics of interest.
1.5 Key challenges / There continues to be variation in terms of the numbers of projects different Members propose for funding, and the level of funding they are able to commit. However, over the past year, there have been positive changes, with all Members due to be funding at least one project by September 2013, apart from the African Development Bank, which only joined the group in early 2013. / Members’ approach to funding HANSHEP projects is to favour opportunistic funding opportunities, rather than drawing up a more defined strategy for proposing and selecting HANSHEP projects. This has meant a lack of open competition in some cases where members have proposed implementing partners. Wherever possible, DFID pushes for open competition. In the HANSHEP Phase 2 business case, a strategy for DFID funding through HANSHEP will be outlined and work will be undertaken to encourage other Members to adopt this. For example, we will advocate for an increase in projects which focus on sustainable health market change, rather than having a narrow project focus such as e.g. delivery of family planning commodities to the poor in the short term. / The HANSHEP Programme Funding Arrangement (PFA) set up to route funds through the Secretariat is so far only used by DFID. Certain other members have voiced concerns over the use of Secretariat funds (including for management and legal costs) to set up an arrangement which is only used by DFID. These costs should reduce now the PFA is up and running.
Annual Outcome Assessment / It can be expected HANSHEP will achieve the project Outcome, ie improve the health status of the poor. This will be achieved through the current portfolio of projects to which DFID and other funders contribute. Potential additional results will be gained from the pipeline portfolio, although these will not be attributable to DFID’s £12.5m (HANSHEP funding) and £22m (AHME funding) as this funding has been fully committed to active projects. The revised Results Framework for Non-State Health (EDRM 4004993) gives quantitative detail of outcomes to be achieved by 2015, including 4.7 million additional poor people using new or enhanced health services provided by the non-state sector.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / The key cost drivers (input costs) for the HANSHEP Secretariat and the individual HANSHEP projects are staff, consultant and travel costs, followed by minimal costs of supplies (including equipment and communications costs). Value for money of the HANSHEP Secretariat at the individual projects is detailed in Section 5 below. Projects are meeting implementation milestones and are in line with financial forecasts. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are no changes in evidence at this stage. / How does the evidence from the implementation of this project contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Generating knowledge and evidence is a priority for HANSHEP. Funded projects are already contributing to a relatively weak evidence base in terms of how to improve the poor’s access to free/affordable health services provided by the non-state sector as part of the broader health system. For example, the Mining Health Initiative produced Good Practice Guidelines (GPG) on mining health PPPs in low income countries (LICs) and another 17 reports in the public domain on lessons learned from first-hand experience of mining companies operating in Africa. CHMI will document an additional 500 programmes in its database and 15 new publications on health market innovations. The Pilot Health PPP Facility will publish at least 9 reports highlighting the costs, benefits and risks of health PPPs in LICs. / All projects include a focus on generating evidence by piloting new approaches, and include deliverables related to documenting and sharing evidence generated. Where projects involve operations on the ground to improve the health outcomes of poor people, results are disaggregated by socio-economic status and gender, as well as by age in terms of indicators related to averting deaths of children under the age of 5 years old. / 3.2 Where an evaluation is planned what progress has been made? / Evaluations of individual HANSHEP projects are built into their design. For example, African Health Markets for Equity includes a $7m independent evaluation; CHMI will undergo evaluation in 2014; and the Health Enterprise Fund model will be evaluated in 2014/15. / As part of the business case for HANSHEP Phase 2, DFID is proposing an independent process evaluation of HANSHEP overall to be commissioned in 2014. This evaluation would feed in to the next Annual Review of HANSHEP, would influence the Terms of Reference for the retendering of the Secretariat contract and the level and nature of DFID’s ongoing investment. The evaluators will be required to recommend the scope of a final evaluation of HANSHEP at project close in 2015.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The overall risk assessment for the project is judged as low. The key risks listed in the original Programme Memorandum for HANSHEP are being addressed through detailed attention to risk mitigation in the design of HANSHEP projects. However, some remain significant. For example: / Insufficient capacity among developing country governments to engage better with NSAs. Capacity building for governments is required and is being delivered by several HANSHEP interventions. This risk is compounded by a lack of sufficient global capacity, in terms of good technical assistance, to address the capacity gaps in developing countries. / Insufficient commitment or interest among NSAs (particularly the for profit private sector) to provide free or affordable healthcare services to the poor, or to make an effort to improve quality of care provided. All HANSHEP projects involve a focus on poor people’s access to essential health services. Projects are seeking to work with a broader range of private sector providers to increase access and learn lessons. Some of this risk can be mitigated by separating financing and provision of services, so that NSAs can be paid for providing services to poor people without those people having to pay out of their own pockets. The AHME project, for example, is working simultaneously on increasing the quantity and quality of services provided, and promoting a transition to state financing of good quality services delivered by non-state actors for the poor. / HANSHEP programme funding absorbed by NSAs and developing country governments does not lead to demonstrable improvements in the quality of healthcare services provided to the poor. This risk continues to be reduced by HANSHEP members focusing rigorously on the outputs and outcomes that will be generated in selecting projects for funding, and by ensuring that robust M&E systems are established for each intervention. / Other risks include insufficient capacity by agencies supported to implement programmes effectively, corruption and diversion of funds by recipient organisations, and HANSHEP Group members not sustaining their commitment to the initiative or not sufficiently harmonising efforts with each other. These risks will continue to be mitigated through e.g. due diligence of implementing partners, on-going financial monitoring and audits, and by continued engagement with and amongst HANSHEP group members, and by reallocating resources as required. / Risk of funds not being used as intended / The HANSHEP Secretariat carries out all its activities in accordance with relevant UK anti-bribery and corruption legislation, and provides both monthly narrative updates to members and quarterly financial reports detailing expenditure against budget. In administering the HANSHEP Programme Funding Arrangement on behalf of DFID, all funds are held and disbursed by Crown Agents Bank, who provide monthly statements on all HANSHEP-related financial transactions and who are authorised and regulated by the Financial Conduct Authority in the UK. / All implementing organisations are required to submit detailed quarterly or half-yearly financial statements illustrating actual / anticipated spend against budget. These financial reports are accompanied by narrative progress reports dealing with any challenges / alterations to scheduled programme implementation. The HANSHEP Secretariat also conducts KYC (Know Your Client) checks on each partner where appropriate to ensure their legal and financial integrity. / Two projects will be funded through the Gates Foundation which has/will draw up Grant Arrangements with implementing partners. (AHME and Shaping Markets for Treatment of Child Diarrhoea). For these projects, DFID will match BMGF’s’ own expenditure and commitment pattern with annual payments. Prior to disbursing funds, DFID will review information provided by BMGF to support the claim, including information regarding how DFID funding has been disbursed by BMGF. In addition, DFID and BMGF will jointly review and assure the quality of quarterly financial and narrative reports as laid out in the MOU and relevant Grant Arrangements. DFID has the right to withhold funds for any individual project until DFID is content with the progress of any such project. FCPD confirms (EDRM 3688396) this “just in time” funding means there will be no risk of funds sitting unused in BMGF or implementing partners’ accounts for any significant time. Regarding implementing partners, for AHME, MSI has been subject financial due diligence by DFID and found to be performing satisfactorily. The implementing partner for the second project has not yet been selected / 4.4 Climate and Environment Risk / HANSHEP overall has negligible impacts on the climate and environment. Impacts of individual projects are assessed prior to project approval by HANSHEP members, and actions taken to mitigate any potential negative impacts.

5. Value for Money
5.1 Performance on VfM measures / All projects are regularly reviewed for value for money. For example, the Pilot Health PPP Facility was expected to reach 800,000 beneficiaries over 4 years and to leverage US$100 m of private investment over the same period. After the first year, the project is expected to reach 1.34 m poor people and leverage US$30m. The Facility had originally estimated that each mandate would cost approximately US$1.4 m to conduct, made up of contributions by DFID, IFC and client governments. So far, the actual costs have been about half the expected cost, at US$756,000 per mandate although client governments have been able to contribute less than expected. The lower overall costs mean that DFID is contributing less to each mandate and that twice as many mandates (i.e. 24) may be possible instead of the planned 12. / For CHMI, there are 3 VfM indicators, but for 2 of these, the figures will only be captured starting in the second year of the programme. The third indicator estimated the cost per programme identified and documented on CHMI as £694. During the first year of operation, the actual cost has been £835 (20.3% higher) due to higher start-up expenses. As the programme profiling continues, there will be economies of scale that will significantly reduce this cost. R4D are confident that the average cost per profile will reduce to the level agreed in the business case. First, the website is being redesigned in part to make the uploading of profiles easier and less time consuming. Second, a large number of the new profiles are coming from DFID and HANSHEP programmes (such as the Health Enterprise Fund) and these will already be standardised in their content and format thus reducing costs further. / It is too early to judge VFM performance for many of the remaining projects. There will be on-going monitoring of value for money, particularly when reviewing quarterly narrative and financial reports and at quarterly meetings with implementers. See point 5.3. / 5.2 Commercial Improvement and Value for Money / The HANSHEP Programme Manager continues to be a high performer who has met deadlines and produces quality outputs. He has been able to lead the additional part-time contributions of other Secretariat staff to generate quality outcomes, on time and to budget. As a result of various efficiency enhancing measures under the Programme Manager’s direction, the Secretariat budget was reduced by US$60,000 from $499,960 in 2012 to $439,958 in 2013, largely due to the reduced need for external technical assistance from consultants. This represents an excellent improvement in value for money considering the increased demands on the Secretariat over the year, including: the design, set up and management of the HANSHEP website; Programme Funding Arrangement; management in partnership with the World Bank of the HANSHEP Knowledge and Learning project; oversight of a growing project portfolio and servicing a growing number of members. The workload of the Secretariat will continue to rise as the project portfolio grows, though the Secretariat costs are not expected to rise. This will mean continual improvements in terms of value for money. / The Secretariat contract will be re-tendered in 2014. Like the current contract, any future contract will include a break clause triggered by poor performance. The Mining Study was procured through an OJEU competition. For the other HANSHEP projects, implementers were/are being selected for their proven expertise in relevant areas. Where DFID is funding with other HANSHEP members, these members selected implementing partners- justification for their decisions is laid out in detail and has been approved in each individual DFID business case or project approval submission. DFID will monitor for VFM any subcontracting arrangements, including ensuring fee rates for sub-contractors are in line with accepted international development consultancy rates. / 5.3 Does the project still represent Value for Money? Yes / The HANSHEP partnership and its Secretariat represent good value for money (See 5.2). The HANSHEP partnership provides the platform for Members to co-fund innovative projects. DFID’s current commitment of £34.5 million is more than matched by other donors. Business cases for each individual HANSHEP project include rigorous value for money assessments, and performance, results and VfM will continue to be monitored on an on-going basis. / 5.5 If not, what action will you take? / If the Secretariat fails to deliver good value for money, remedial action will be taken by Members in consultation with the Secretariat. If corrective action does not work, the Secretariat contract will be terminated. / All HANSHEP projects are innovative. If they fail to deliver agreed activities and outputs, projects will be redesigned, or failing that, halted altogether and the lessons learned disseminated.

6. Conditionality
Not applicable

7. Conclusions and actions
Overall, HANSHEP is making promising progress. During the past year, the group has agreed an appropriate balance of knowledge/evidence and operational work for its growing project portfolio. Positive collaboration and trust between members has increased, and significant funding has been mobilised for HANSHEP projects. DFID’s role as Chair of HANSHEP provided an opportunity to drive forward the growing portfolio of projects, and to increase international awareness of the HANSHEP group and how it can contribute in the field of non-state health. The overall Actions are listed as recommendations above.

8. Review Process
This review was conducted by Sarah Bloom, DFID Lead Adviser for HANSHEP. Inputs and advice were provided by Julia Watson, Sr Health Economist, Human Development Department and Martin Johnston, Adviser, Non-state Basic Services, PSD, particularly in relation to the 2 active and one completed HANSHEP project which he manages for DFID. Tom Feeny, Programme Manager for the HANSHEP Secretariat was consulted. / The review drew on the original Programme Memorandum and Results framework for HANSHEP (EDRM 3526879), as well as documents prepared for HANSHEP quarterly meetings, and the minutes of those meetings (www.hanshep.org;username dfid; password access). The review drew on the terms of reference and business cases for the 6 active and 1 completed project. / The revised HANSHEP logframe is at EDRM 3581306