Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: World Health Organisation (WHO) – Voluntary Core Funding 2011-2014
Programme Value: £54 million		Review Date: January 2015
Programme Code: 202715	Start Date: 01/04/2011	End Date: 31/03/2015

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	N/A	B	A	A
Risk Rating	N/A	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

The Ebola virus disease outbreak hit West Africa at an unprecedented scale and has stretched the capacity of the World Health Organisation (WHO) for the past 6-months. The Ebola outbreak has had a significant impact on WHO reform implementation and the pace and delivery of work in other priority programmes. In particular, certain reform initiatives, such as the review of the hosted partnerships, have had to be delayed due to organisational assets being redirected to the Ebola response. This crisis comes in the midst of other persisting and emerging crises in other parts of the world in which WHO is also heavily involved. Sustaining this effort over a significant period is anticipated to have an impact on delivering the programme budget 2014–2015. DFID has been working closely with WHO to strike the right balance between not diverting resources and efforts in WHO away from the immediate response, while ensuring lessons are learned in a timely way to adapt our reform agenda accordingly. We are currently exploring changes in our logframe indicators on the basis of the lessons being learned from the Ebola crisis. However, for the purposes of this Annual Review, the progress assessment is based on pre-Ebola indicators.

The MAR Update in 2013 identified a set of four reform priorities for WHO. These formed the basis for DFID’s recommendations for strengthening WHO’s performance in the 2013 Annual Review. Lessons learned and progress against these recommendations are presented below.

Recommendation 1: To continue to strengthen the delivery and measurement of results in developing countries, and to develop an effective operational plan, which transforms strategic priorities into action and results (contribution to results)

Progress and lessons learned: The WHO adopted a new programme budget for the biennium 2014-15, which provides a clear set of indicators to measure results. This new monitoring framework is a welcomed development and DFID will be monitoring closely how WHO uses it to report on the implementation of the 2014-15 programme budget and for managing organisational performance.

Recommendation 2: To improve the performance management of staff - including overcoming continued reluctance of some staff to embrace change, and to strengthen staff management to ensure a more coherent and positive approach to managing poor performance and encouraging staff development (strategic performance and management)

Progress and lessons learned: The WHO is making good progress to develop policies that will change the performance management culture of the organisation, however, we will monitor closely how these policies are implemented.

Recommendation 3: To ensure that the Financing Dialogue process meets its objectives of predictability, transparency and accountability and that WHO provides greater transparency of how funds are allocated (financial resources management)

Progress and lessons learned: The WHO has made some progress to develop guiding principles for strategic budget space allocation. We will be monitoring closely how these principles are used to develop the 2016-17 programme budget.

Recommendation 4: To continue to look for ways of making savings, using the independent review of administration and management costs as an instrument to streamline administrative systems (cost and value consciousness).

Progress and lessons learned: The WHO is working on streamlining its administration and management costs, and on a proposal for fund these. We will monitor closely how these changes to administration and managements costs will bring new efficiency savings to the organisation.

Summary of recommendations for the next year

While the 2014 Annual Review notes that WHO has made progress across all of its logframe outputs, it makes a number of recommendations for the agency to further strengthen it performance in areas where milestones for 2014 have either been partially met or not met. Specifically, it recommends that WHO:

1. focuses on using its monitoring framework as a tool for managing and improving the overall performance of the organisation. This will require at least annual reporting of progress against indicators on the web portal and actions to improve performance where progress is slow.
2. accelerates progress on developing a corporate resource mobilisation strategy and ensure it is ready for implementation in advance on the 2016-17 Programme Budget;
3. sets-out for each year its policy for efficiency savings and reports on progress made;
4. accelarates progress in rolling-out the corporate risk register at all three-levels of the organisation and ensure its effective use;
5. continues progress to implement its new staff performance management system and wider human resources reforms in the WHO Human Resources Strategy;
6. continues progress to finalise the new mobility policy for staff.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202715/documents/
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4495651.xlsx

Outline of the programme

WHO is central to international health. It is the only international organisation which is mandated as the directing and coordinating authority on global health. Its global importance is based on a number of roles: convening international actors on critical health issues; the setting of the global health standards; the provision of associated health policy guidance; and monitoring of progress against the health MDGs. WHO also provides the foundations for the work of other health actors on the health MDGs. The UK Government and DFID have strong and active engagement with WHO on all these issues.

Under the current funding period DFID is providing £54m of voluntary core funding to the World Health Organisation (WHO) over the period 2011- 2014. DFID core funding focuses on the central role that WHO plays in relation to poverty reduction and international development, namely – MDGs 4, 5, and 6 focused on reducing child mortality, maternal health, and combating HIV/AIDS, tuberculosis, malaria and other diseases. Progress on these MDGs is necessary for achieving the broader goal of eliminating poverty globally. It supports WHO in fulfilling its leadership role in global health and development:

1. Convening for better health, bringing together multiple actors to address key issues, for example leadership for the Second International Conference on Nutrition (ICN2) in 2014..
2. Generating evidence on health trends and determinants, providing internationally recognised evidence to guide action. One example of this is its work in data collection on malaria control.
3. Providing advice for health and development, building on its reputation for impartial and authoritative advice. This will include work to support countries to implement policies and programmes to reduce maternal mortality.
4. Coordinating health security, playing a critical global monitor and response role, for example preparing for and co-ordinating the response to global pandemics such as Ebola.
5. Strengthening health systems and institutions, for example supporting Member States in implementating the International Health Regulations.

DFID’s funding is also contributing to WHO’s continued progress on delivering the targets set out in the WHO’s 2014-2019 general programme of work, alongside continued attention to other important components of reforms set out in the MAR and MAR Update (e.g. contribution to results, strategic performance and management, financial resources management, cost and value consciousness).

As WHO is a Member States organisation, DFID along with other UK Government departments works with other Member States through the Programme, Budget and Administration Committee (PBAC), the Executive Board and the World Health Assembly to provide oversight over the organisation.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The expected outcome for DFID’s funding to WHO is the: Improvement in efficiency and effectiveness at all three levels of WHO. Progress towards achieving this outcome is tracked using two indicators for how well WHO is (a) implementing its programmatic, governance and managerial reforms, and (b) performing against results targets set for its programme budget. An assessment of WHO’s performance at the outcome level is provided below.

Outcome Indicator 1: WHO makes significant progress on its three reform pillars (programmatic, governance and managerial)

WHO started a major reform process in 2010-2011 to increase its responsiveness and to strengthen its coordinating role in global public health. Reform aims to improve WHO’s priority setting, ensure the agency focuses on its comparative advantage, and improves governance structures and management. The agency has developed a strategic approach to reform with 8 clearly defined sub-pillars under the three main reform pillars. Progress is under-way in all three pillars with 64.5% of reform outputs having reached implementation stage. WHO has made greatest progress on programmatic reform, while governance and managerial reforms are lagging behind.

Key areas of concern are slow progress in developing and implementing a new framework for WHO’s engagement with non-state actors, lack of progress strengthening the institutional links between WHO headquarters and regional and country offices, and slow progress in implementing human resource management reforms. Member States are partly responsible for slow progress on governance reform, as they are not able to reach consensus on a number of priorities, for example - adoption of a new framework for WHO’s engagement with non-state actors at the 67th World Health Assembly. The Annual Review assesses that WHO’s progress in implementing reforms has now slowed as the organisation has had to allocate both financial and human resources to shore up its response to the Ebola outbreak affecting West Africa.

Yet, the Ebola outbreak also highlights the crucial need for WHO to scale-up its current reform efforts. WHO needs to strengthen its institutional capacity to be better placed to respond to newly emerging, changing and complex public health challenges, including by being able to work with all relevant actors in global health. The Ebola response has stretched the organisation’s capacity and highlighted persisting weaknesses, including slow human resources processes failing to deploy in a timely manner the right people, with the right skills in the field and at headquarters to manage and coordinate effectively the response. It has underlined the weak institutional links between different levels of the organisation (headquarters and regional and country offices), and WHO’s limited managerial capacity to coordinate an international response to deal with large scale global health security threats. In light of these challenges, WHO would need to reflect on the lessons being learnt and ensure that these are addressed in its continued reforms efforts.

Outcome Indicator 2: Proportion of expected results (outputs) included in the programme budget 2014/15 which are fully realised by WHO.

Due to the lag in reporting results, this Annual Review was not able to assess progress against this outcome indicator; WHO is still to report results against the Programme Budget 2014-15. The Annual Review has however assessed progress based on the latest results report available (the 2012-13 programme cycle). The Annual Review assesses the evidence to show that for 5 of the 13 strategic objectives, WHO substantially did not meet the expected results (i.e.more than 33% of indicator targets were not achieved). These strategic objectives include Communicable Diseases; HIV, TB & Malaria; Emergencies; Improved access, quality and use of medical products; and Organisational Performance Management. For 2 strategic objectives, Non-Communicable Diseases and Capacity Building, WHO moderately met results targets.

The Annual Review anticipates that the Ebola crisis is also impacting the pace of implementation of the 2014-15 Programme Budget and will impact most likely future non-emergencies programmatic results. This is because WHO has had to re-allocate financial and human resources from regular programmes to the Ebola response effort.

Overall output score and description

The WHO scored an overall A (outputs met expectations) for its 2014 outputs. The Annual Review assesses that the WHO has met expectations for human resources management reforms, improvement in oversight and effective financial management. However, WHO needs to accelerate its efforts in reporting and managing results, as it moderately did not meet expectations in this area.

Key lessons

WHO continues to make progress in implementing its reform priorities and strengthening its organisational performance. However, there are a number of areas where progress has only‘partially met’ or ‘not met’ expectations as represented by milestones in the logframe for DFID voluntary contribution to the organisation. The ongoing Ebola crisis is also highlighting that WHO’s capacity to respond to a large global health emergency is limited due to a range of institutional, resourcing and management challenges. In responding to the Ebola crisis, WHO has had to reallocate financial and human resources away from other strategic priorities in the programme budget and from implementation of organisational reforms.

Key actions

DFID recommends that WHO:	WHO’s key actions include to:
1. Focuses on using its monitoring framework as a tool for managing and improving the overall performance of the organisation. This will require at least annual reporting of progress against indicators on the web portal and actions to improve performance where progress is slow.	1. Present organisation-wide annual reports for Mid-Term Review and End of Biennium Assessment to the PBAC each May.
2. Accelerates progress on developing a corporate resource mobilisation strategy and ensure it is ready for implementation in advance on the 2016-17 Programme Budget.	2. Consolidate the existing strategies on resource mobilisation and ensure it is ready for implementation in advance of Programme Budget 2016-17.
3. Sets-out for each year its policy for efficiency savings and reports on progress made.	3. a) Report annually to PBAC on efficiency measures, including a commentary in the results reporting; / b) Incorporate a target of 10% reduction in travel costs into 2016-17 operational planning.
4. Accelarates progress in rolling-out the corporate risk register at all three-levels of the organisation and ensure its effective use.	4. a) Report to senior management on risk analysis; / b) Have a dialogue with risk owners regarding risk mitigation.
5. Continues progress to implement its new staff performance management system and wider human resources reforms in the WHO Human Resources Strategy.	5. a) Implement the new performance management policy in 2015. Amendments to the Staff Rules and Regulations, as well as WHO eManual, will support the new approach; / b) Build capacity by training staff members and supervisors, including face-to-face training, e-learning and a Guide for Managers; / c) Roll-out of the enhanced performance management and development system (i.e. “Enhanced ePMDS+”) in HQ and HQ Out-posted Offices in 2015; / d) Hold training and briefing sessions for staff members and supervisors on ePMDS+ to ensure smooth implementation.
Continues progress to finalise the new mobility policy for staff.	6. a) Amend Staff Rules and Regulations, following Member States approval in the World Health Assembly in May 2015; / b) Establish a list of non-rotational posts; / c) Design a governance mechanism; / d) Design placement procedure from the annual compendium; / e) Finalise the geographical mobility policy.

Has the logframe been updated since the last review? Yes

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	WHO has an effective system for reporting and managing results
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 DFID’s assessment of quality of WHO’s delivery of its results framework	WHO regularly updates its web portal to show progress on its results	The WHO web portal is now set-up and is being updated on a quarterly basis. Reporting has so far focused mainly on reform progress and on presenting financial information. WHO is yet to report on the status of results achieved on the web portal. [milestone not met]
1.2 DFID’s assessment of WHO annual reporting on results	Draft new monitoring framework for programme budget 2014-15 developed	WHO has developed its monitoring (results) framework for 2014-15, and will be reporting against it at the next World Health Assembly in 2015. [met]

Key Points

The web portal was officially launched in November 2013 as part of the WHO Financing Dialogue. It is populated with a range of information, including programme objectives, financial status of the organisation (resources vs. budget ceilings), and outcome and output indicators from the monitoring framework. The web portal is updated on a quarterly basis and Members States are alerted by email of any new information. So far, WHO has reported extensively on financial resources available and gaps in funding, but is still to report on progress of its programmatic work as informed by results being achieved or progress in implementation. Without regular updates on results progress, there is hardly any information to allow for close to ‘real time’ monitoring of WHO’s performance – especially given the lag in formal reporting of results. This is a major gap in the web portal reporting, and DFID assesses the milestone for this output indicator as ‘not met’.

Overall, DFID assesses WHO’s monitoring framework as good. It communicates a clear theory of change from inputs - financial resources, to activities at country, regional and headquarters levels, and to outputs and outcomes. Indicators are well defined (SMART), with baselines and targets set to provide a good basis to tracking organisational performance. Main areas to strengthen for the development of the 2016-17 monitoring framework are (i) improving clarity of assumptions being made to complete the theory of change and understanding the risk to achieving results; (ii) improving clarity on how targets are set to communicate the level of ambition; (iii) continued improvement of indicator definitions; (iv) being clearer on how the tool is used by management to improve overall performance of the organisation.

Overall, outputs moderately did not meet expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable – see key points above.

Recommendations

Based on assessment of performance against the logframe, it is recommended that WHO:

focuses on using its monitoring framework as a tool for managing and improving the overall performance of the organisation. This will require at least annual reporting of progress against results indicators on the web portal and actions to improve performance where progress is slow.

Output Title	WHO has in place a budget cycle that enables effective management and demonstration of efficiency savings.
Output number per LF		2	Output Score	A
Risk:		medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 DFID’s assessment of progress on Financing Dialogue process and whether WHO has a fully funded budget for 2014-15	Web portal is up to date with relevant financial information and WHO develops a clear coordinated resource mobilisation strategy	The web portal is updated on an quarterly basis – financial information published is up to date. [milestone exceeded] / Work is still ongoing to develop a corporate and comprehensive resource mobilisation strategy. [milestone partially met]
2.2. A draft Programme Budget for 2016-17 is developed with realistic costing of outputs at all three levels of WHO	WHO develops a new approach to strategic resource allocation for discussion at governing bodies [and uses it for developing programme budget 2016-17]	WHO shared with Member States a paper presenting a new approach to strategic resource allocation in May 2014. Work is still ongoing to translate the principles presented in the paper into practical steps that the organisation will take to set budgets for different entities. [milestone met]
2.3 Corporate expenditures (category 6) of the programme budget 2014-15 do not exceed an agreed percentage of the overall budget	Srategic Objective 13 expenditure in 2012-13 is 12.5% of total	WHO expenditure for Strategic Objective 13 in 2012-13 represents 11.9% of total expenditure. [milestone exceeded]
2.4 DFID’s assessment of the efficiency measures taken by WHO	WHO develops expenditure coding and a policy for efficiency savings. / WHO continues to report on efficiency measures to governing bodies.	Progress has been made on expenditure coding, particularly on coding implementation activities at the country level. However, at the time of doing the annual review there was no clear statement of WHO’s policy with regards to generating further efficiency savings [milestone partially met] / WHO has reported efficiency savings in its Financial Statement for year ending December 2013. [milestone met]

Key Points

The web portal was officially launched in November 2013 as part of the WHO Financing Dialogue. The scope of the web portal increased in November 2014 with addition of a new section on funding. The last update of financial information on the web portal was received on 19 November 2014. DFID’s assessment is that WHO has reported extensively on financial resources available and funding gaps. This part of the milestone is met.

As part of the WHO Financing Dialogue, it was agreed that WHO would develop a coordinated resource mobilisation strategy that provides a corporate approach to fundraising. In August 2014, the Director General created a new Coordinated Resource Mobilisation Unit in her office. This unit will be responsible for the administrative functions linked to resource mobilisation and act as the point for strategic engagement with external partners for purposes of fundraising for the organisation. This new unit is meant to serve as the resource mobilisation channel for all three-levels of the organisation.

A separate Resource Mobilisation Coordination team has also been set-up – comprising 15 staff (each Regional Director and Assistant Director General have one representative). This team is developing a roadmap or strategy for funding WHO’s programme budget and will set-up the necessary tools for implementing the strategy. WHO is currently implementing the Financing Dialogue key principles of increased predictability, flexibility and alignment as part of their coordinated resource mobilisation strategy. However, DFID expected that by now WHO should have shared a complete corporate resource mobilisation strategy, which would articulate how fund raising would be managed for all three-levels of the organisation. This is not the case. As a result, the Annual Review assesses this part of the milestone as only partially met.

In May 2014, the WHO Secretariat presented to the Programme, Budget and Administration Committee (PBAC) a new strategic resource allocation approach being developed by the Working Group on Strategic Resource Allocation (now referred to as Strategic Budget Space Allocation). This approach is composed of seven guiding principles (based on needs and evidence, results-based management, fairness and equity, accountability and transparency, clear roles and functions, efficiency and effectiveness, and performance improvement) and divides the organisations into four operational segments (technical cooperation at country level, provision of global and regional goods, administration and management, and emergency response).

While DFID along with other Member States broadly agreed with the principles presented in the paper, there is need for the principles to be translated into practical steps for developing the 2016-17 Programme Budget. The Working Group on Strategic Budget Space Allocation met in November 2014 to discuss the different options for operationalisation of the principles and to finalise the recommendations, which will be presented to the next PBAC in January 2015 for review. To develop the 2016-17 draft programme budget, WHO is using key principles from the SBSA methodology. DFID’s assessment is that the new strategic budget space allocation approach has started to be used by WHO for the 2016-17 Programme Budget, therefore the milestone for the relevant indicator is assessed as met.

WHO have made improvements in expenditure coding. The new expenditure code for Direct Implementation, in particular, increases transparency and accuracy in coding implementation activities at the country level. WHO has also increased the number of regular expenditure analysis reports that facilitate the monitoring of expenditures organisation-wide and make it easier for management to identify and resolve emerging funding issues. Currently, WHO is issuing expenditure analysis reports on travel costs, direct financial contributions, staff costs, hospitality and courtesy, and imprest. The agency is working to add new monitoring reports on contractual services. However, at the time of the Annual Review, there was no clear statement of WHO’s policy with regards to generating further efficiency savings. DFID therefore assesses this part of the milestone as partially met.

WHO expenditure for Strategic Objective 13 in 2012-13 represents 11.9% of total expenditure, below the target of 12.5%. In May 2014, the Secretariat presented to Member States its annual audited financial statements, which presented some information about efficiency savings. The targets for reducing travel costs as well as measures accompanying the implementation of the new procurement strategy are expected to contribute to efficiencies. However, we would expect for the Secretariat to present a short comprehensive report every year, outlining its policy for efficiency savings – including targets and how the organisation is performing against these, for example, following the model of document EBPBAC17/INF./1. This information should be integrated and made more visible in the annual audited financial statement. DFID’s assesses the milestones for the relevant indicator as having met our expectations.

Overall, outputs met expectation.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable – see key points above.

Recommendations

Based on the assessment of performance against the logframe, it is recommended that WHO:

- accelerates progress on developing a corporate resource mobilisation strategy and ensures it is ready for use in finalising the 2016-17 Programme Budget;
- sets-out for each year its policy for efficiency savings and targets, and reports on progress made.

Output Title	WHO has effective financial accountability and oversight systems in place
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 DFID’s assessment of the improvement in level of country office compliance with corporate procedures	14% DFC reports overdue / Imprest accounts – less than 7% have items older than 90 days outstanding	% of DFC reports overdue decreased from 24% (Dec 2013) to 8% (Sept 2014) [milestone exceeded] / % of items older that 90% outstanding has decreased from 8.8% (Dec 2013) to 5.7% (Sept 2014) [milestone exceeded]
3.2 DFID assessment of rate of implementation and follow-up of audit recommendations	85% in progress or closed	85.3% of audit recommendations are in progress or closed as of 27 February 2014 [milestone marginally exceeded]
3.3 DFID’s assessment of staff and financial capacity of the office of internal oversight services	35% increase in staffing	While there has been 17% increase in IOS staffing capacity, this falls short of the approved staffing level for the unit. Recruitment is ongoing to fill a number of approved posts, which would contribute in meeting the milestone. [milestone partially met]
3.4 DFID’s assessment of WHO’s accountability framework in line with good international practice	Updated Delegation of Authority to ADGs and RDs, including a clear definition of responsibilities for the implementation of internal control framework. / CRE rolls out the organisation wide risk register and identify corporate risks.	WHO has developed an internal control framework, which was presented to PBAC in January 2014. Work is ongoing to implement the new framework. [milestone met] / CRE has developed and rolled out tools for identifying risks and developing a corporate risk register for the organisation. Work is ongoing and an update will be presented in January 2015. [milestone partially met]

Key Points

The percentage of overdue reports on Direct Financial Cooperation (DFC) contracts issued has decreased from 24% (December 2013) to 8% (September 2014). This progress is due to the fact that WHO is now strictly enforcing in all regions, its existing policy, which requires that no further DFC can be given where there are outstanding reports. In addition, the percentage of accounts with items outstanding by more than 90 days has decreased from 8.8% (December 2013) to 5.7% (September 2014). DFID assesses the milestone for the relevant output indicator as met.

Based on report A67/46 (annex 1), 85,3% of the audit recommendations were closed or in progress as of 27 February 2014. As a result, DFID assesses that this milestone is met.

Regarding staff and financial capacity of the office of internal oversight services, at the time of the 67th World Health Assembly, WHO reported that the Internal Oversight Services Department (IOS) had a staffing contingent of 20 approved posts of which 14 were filled. The approved posts included evaluation and investigation functions, as well as audit and oversight. In July 2014, two new internal auditors were recruited. In August 2014, the evaluation function was separated from IOS and integrated in the Director General’s Office (DGO). Two evaluation posts were transferred into the DGO. As of October 2014, the approved posts for IOS remained at 20 of which 14 are filled. A recruitment process is under way for three vacant posts expected to be filled in 2015. The reorganisation of the IOS unit makes it difficult to accurately track progress against this milestone. However, as there remains post in the IOS that are still to be filled, DFID assesses the milestone for the relevant indicator as partially met.

The 2006 WHO Accountability Framework has been revised and is currently subject to internal consultation.  The revised draft framework responds to many of the Joint Inspection Unit (JIU) and Independent Expert Oversight Advisory Committee (IEOAC) recommendations. One of the key elements of the revised Accountability Framework is the Internal Control Framework, which is supposed to provide reasonable assurance to WHO management regarding the achievement of objectives relating to operations, reporting and compliance. It aims to achieve effectiveness and efficiency in all operations. WHO’s Internal Control Framework, which is based on the COSO model (an international standard for control frameworks), has been developed and was presented to PBAC in January 2014. It is in the process of being implemented at all three-levels of the organisation.

In support of the implementation of the Internal Control Framework, a managers’ guide and a checklist for internal controls have been developed. These tools build on mechanisms that already exist across the different levels of WHO. The manager’s guide is designed to help ensure that managers understand their roles and responsibilities in applying the Internal Control Framework, including the related monitoring and reporting requirements. The delegations of authority from the Director-General to the Regional Directors and Assistant Directors-General have been revised to include the responsibility for upholding the internal control framework in the areas under their responsibility.  Furthermore, an “accountability compact” between the Director General and the Assistant Directors General has been introduced with performance objectives, including the effective implementation of internal controls.

A self-assessment checklist to help managers to better understand the strengths, weaknesses and adequacy of controls in their Budget Center is currently being piloted at all three-levels of the organisation. Results from the self-assessment checklist, will inform the risk management process, highlight areas of control strengths and weaknesses in areas covered, as well as the development of Internal Control Statement for the WHO. Even if work is still on-going to fully roll-out and operationalise the Internal Control Framework, DFID assesses the milestone for the relevant indicator in the logframe as met.

The Office of Compliance, Risk Management and Ethics (CRE) is developing an organisation-wide harmonized risk management approach, which will allow WHO to identify, assess, respond, monitor and review risks in a structured, systemic and prompt manner. A key objective for CRE is to ensure that risk management processes, across all levels of WHO, follow a consistent and coherent methodology and that a common risk language is used throughout the organisation. In the first quarter of 2014, CRE developed and piloted (at HQ, regional and country office levels) a risk register template taking into consideration existing risk management processes and regional risk registers across the organisation. The risk register roll out was planned and executed in two phases, which focus on: (1) risk identification and inherent risk assessment; and (2) risk mitigation and residual risk assessment (if applicable). Based on risk registers received within the deadline for the first phase, the list of risk names was revised to ensure maximum inclusion of all risks identified. The second phase of the roll out began in September 2014.

With the launch of WHO’s corporate risk register, WHO evolves progressively to a risk-defined culture organisation. CRE is now in the process of analysing the risks identified, defining corporate risks, and will report to the Executive Board in January on this process. With regards to continuous learning, WHO is in the process of refining and complementing the training modules that have been delivered as part of the roll out of the risk register, and are discussing structured systematic training with WHO’s human resources department. Simultaneously, CRE is working to develop a risk management framework that lays out the processes to fully operationalize risk management as a tool that supports decision-making across the organisation. Particular emphasis is given to embedding risk management in WHO’s accountability and internal control frameworks and in the budget and planning cycle as this is a key element to change management. DFID assesses the milestone for the relevant logframe indicator as partially met since work is still ongoing in this area.

Overall, outputs met expectation.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable – see key points above.

Recommendations

Based on the assessment of performance against the logframe, it is recommended that WHO:

accelerates progress in rolling-out the corporate risk register at all three-levels of the organisation and ensure its effective use.

Output Title	WHO has efficient human resources management systems in place
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 DFID’s assessment of WHO’s staff performance management system	WHO finalises and implements its new performance management system in HQ (including the policies on rewards and recognition and improving performance)	A new system has been developed and piloted in 2014. Work is ongoing to roll-out the system across all levels of the organisation in 2015 [milestone partially met]
4.2 DFID’s assessment of progress in implementing WHO’s Human Resources Strategy	The policy on mobility across the organisation is finalised / A corporate framework for learning and development is finalised	Draft mobility policy presented to Global Staff Management Council in October 2014. Work is still ongoing to finalise the policy, including setting out arrangements for implementation. [milestone partially met] / WHO has developed and finalised a corporate framework for learning and development, becoming effective from 15 August 2014 [milestone met]

Key Points

DFID recognises the significant amount of work handled by the Department of Human Resources Management in WHO, especially with the increased demand on its resources due to the Ebola crisis. Overall, WHO has made good progress on human resources reform, although not all these changes are reflected in the two indicators of this Annual Review. WHO has made progress in a number of areas including others not included in these milestones, for example:

- The selection process for heads of WHO country offices has been modified, with revised terms of reference and alignment of the selection process with the leadership priorities outlined in the General Programme of Work 2014–2019. A first round of selection under the new process took place in November 2014, with future sessions scheduled for February and March 2015.
- The harmonized selection process for international professional positions has been implemented, and the harmonized selection process for locally recruited positions will be promulgated in 2015.
- A comprehensive staff induction programme has been introduced for new staff members at headquarters, covering a wide range of topics and offered on a monthly basis.
- As a joint initiative with the WHO staff associations, the internal justice system has been reviewed. An action plan to implement the recommendations will be elaborated in 2015.

All changes to policies that impact on the working conditions of WHO staff must undergo a consultative process and be submitted to the Global Staff Management Council (GSMC). Performance was discussed during the GSMC meeting in October 2014, and it was decided that a new performance management system (enhanced ePMDS+) will be rolled out in headquarters and country offices in 2015. The new system has been piloted in the Department of Human Resources Management in headquarters to test the form as well as the process prior to its official launch. Training and briefing sessions are being organised for staff and managers in November 2015 before a communication campaign to launch the new systems.

Draft documents for a Performance Management and Development Framework, and policies for managing underperformance and for recognizing and rewarding excellence were also presented to the GSMC in October 2014. A communication campaign and information sessions on these policies will take place before they are rolled out in February 2015. DFID recognises the significant progress made in this area by the human resources department. However, as significant work is still on-going, the Annual Review assessment the milestone for the relevant indicator as partially met.

Mobility of staff was extensively discussed with staff representatives during the GSMC in October 2014, based on a draft Global Mobility Framework and a Draft Geographical Mobility Policy. The GSMC recommended for the draft Geographical Mobility Policy to be further developed and for the Secretariat to carry out a feasibility study and to develop a clear implementation plan in consultation with the staff representatives. The GSMC highlighted the need to support the link between mobility and the other components of career management, as indicated in the WHO Human Resources Strategy before changing staff rules. WHO is planning for this policy to enter into force by the end of 2015. As work is still on-going to finalise the policy on mobility, including setting out arrangements for implementation, DFID assesses the milestone for the relevant logframe indicator as partially met.

A Corporate Framework for Learning and Development was developed and finalised, with special emphasis on strengthening performance at country level. It was rolled-out through an Information Note published on 15th August 2014. DFID assesses this part of the milestone as met.

Overall, outputs met expectation.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable – see key points above.

Recommendations

Based on the assessment of performance against the logframe, it is recommended that WHO:
- continue progress to implement its new staff performance management system and wider human resources reforms in the WHO HR strategy.
- continue progress to finalise the new mobility policy for staff.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

WHO’s key cost drivers include its staff (approximately 60% of expenditure), the size and number of its programmes, its administration and management costs and the numbers and scale of public health emergencies it needs to respond to. The only cost driver that has changed significantly since the last Annual Review is level of resources needed for public health emergencies, mainly due to the Ebola outbreak in West Africa in 2014 and the refugee crises in Syria and Iraq.

VfM performance compared to the original VfM proposition in the business case

The value for money proposition for voluntary contributions to WHO remains unchanged. The organisation remains an important part of the global architecture for poverty reduction and for tackling global public health issues. It continues to play an important role in the achievement of MDGs 4, 5, and 6 – all health-related. DFID’s investments in WHO contribute towards supporting its convening role, bringing together parties around negotiated international health standards that address universally-shared problems and providing the means of bringing together experts to prepare independent and evidence-based guidelines. It is also responsible for generating evidence on health trends and determinants. WHO provides the foundation for other health actors to work on the health MDGs.

Assessment of whether the programme continues to represent value for money

This programme still represents value for money. WHO’s role as a convenor for global public health issues and in providing the foundations for other health actors to act remains important. With growing and changing global health security threats (e.g. anti-microbial resistance, Ebola) and continued demand for health systems strengthening in developing countries, investing in WHO continues to represent good value for money – especially as the organisation continues reform to improve its performance.

Quality of financial management

WHO’s financial management continues to improve. For the second year, WHO is implementing IPSAS, work is on-going on internal control framework, and the Financing Dialogue is showing results. In the past, WHO has encountered difficulties in fully funding its approved programme budget. Individual programmes were either under or over-funded. Funds were not flexible, transparent, predictable and aligned with WHO’s agreed priorities. To address this funding challenge, in June 2013 WHO launched the Financing Dialogue. This is part of the reform agenda and will form a central element of a more strategic and corporate resource mobilisation process. The Financing Dialogue has been successful in securing more funding at the start of the 2014-15 biennium in comparison with previous biennium (nearly 70% vs. 52% in 2010).

Date of last narrative financial report	May 2014
Date of last audited annual statement	May 2014

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The growing number of emergencies and global health crisis (Ebola, Syria, Iraq, Polio) currently represent the biggest threat to WHO achieving its expected results for its strategic objectives, as agreed in the 2014-15 programme budget. These emergencies are placing a stretch on WHO’s human and financial resources and wider organisational capacity, and are beginning to impact the organisation’s capability to deliver results on its non-emergency programmatic work and in implementing organisational reforms. The following are the main new risks identified linked to growing number of global health emergencies:

- Slower progress in implementing WHO reforms (especially organisational, governance and managerial reforms).
- Some 2014-15 programme budget categories do not achieve planned results as programmes are significantly delayed.
- WHO’s reputation is affected by the handling of the Ebola crisis, affecting its credibility as the convenor for global health issues.

We will use our role as Programme, Budget and Administration Committee (PBAC) Member and Executive Board (EB) Member to push for WHO reform, using the Ebola lessons learned, ensuring that WHO acts on the findings of its mid-term review, in particular in areas showing no progress as a result of the risks indicated above.

The overall risk rating for this programme remains to medium as we do not believe the new risks identified in this Annual Review are significant enough to impact on the delivery of the business case for WHO’s core voluntary funding. However, if the Ebola crisis was to persist at the same scale, then we would need to revisit the risk rating for this programme.

Outstanding actions from risk assessment

Key risk #3 identified in 2013 was: “WHO’s regional bodies dilute or fail to support reform”. DFID is committed to increase its engagement with AFRO to understand its priorities, interests and ways of working. Considering the overview of programme risks today, DFID will need to continue to engage with AFRO, in particular with the new AFRO Regional Director and to ensure WHO’s governance system do not slow reform implementation and more broadly the agency’s capacity to react to global health emergencies. We are also working with other Member States to include in the resolution for the Special Session of the WHO Executive Board on Ebola recommendations to improve regional structures and cohesiveness between all three-levels of WHO.

DFID will be conducting a Central Level Assurance Assessment of WHO in 2015. This will help us identify assurance risks in more details.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The WHO Commercial Expertise Review (CER) was finalised in April 2014. The first CER monitoring meeting with WHO took place on 27 November. It was agreed that we should aim to co-ordinate the bi-annual CER monitoring meetings with the DFID annual review process, to reduce administrative burdens for all.

Performance of partnership (s)

During the CER monitoring meeting, WHO provided DFID with a general update on relevant progress made since the CER report was finalised. Overall, WHO is making good progress on the CER recommendations. For example:

- The freight forwarding agent tender has been completed and a contract is in operation. This allows WHO to track the delivery status in real time, and to obtain good estimates of freight costs. The pricing model has also changed from a fixed price to a cost plus basis, which is expected to achieve significant savings. The contract’s been in place for eight months, so WHO will look at the savings after a year.
- A Risk Mitigation model has been developed, which includes better supplier management and performance monitoring, including for consultants. WHO is looking to limit the number of staff who can confirm receipt/delivery of goods as too many people are able to do this at the moment. The intention is to centralise these functions to include only those who are appropriately trained/experienced. Delegation authorities are also being streamlined to ensure complete segregation between procurement officers and approvers.
- A procurement strategy project was initiated in August and some analysis is ongoing. The target date is March or May 2015, at which point it will be submitted for approval, with an action plan developed to take it forward. The Risk Mitigation model will be incorporated into the procurement strategy; progress on this will be presented to Regional Directors to achieve their support for expansion to regions.

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not Applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

As part of its reform priorities, WHO is working on strengthening its evaluation function. To date the organisation has lacked a systematic approach to evaluating the impact of its programmes and functions. In August 2014, WHO set-up a new Evaluation Unit outside of the Internal Oversight Services Department. The aim of this new Unit is to establish a culture of evaluation at all levels of the organisation, ensuring that evaluation plays a critical role in WHO in improving performance, increasing accountability for results, and promoting organisational learning.

Monitoring progress throughout the review period

DFID will monitor progress throughout the review period by (1) participating in WHO Mission Briefings and governing body meetings (PBAC, EB, WHA – the UK through the Department of Health is a PBAC and EB member in 2014 for respectively two and three years), (2) holding regular bilateral meetings on specific issues (e.g. Commercial Expertise Review follow-up, results analysis and follow-up, Annual Review meeting, logframe update) and (3) engaging in regional grouping discussions on WHO reform (Geneva Group, WEOG, European Union). However, ongoing monitoring of WHO’s performance on delivery of results is currently not possible until WHO starts using its web portal to update regularly on progress against results.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process