Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Innovative Methods and Metrics for Agriculture and Nutrition Actions (IMMANA)
Programme Value: £7,190,323		Review Date: 7 May 2016
Programme Code: 203806	Start Date: 7 August 2014 (date contract with Managing Agent commenced)	End Date: 6 August 2019

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A	A	A
Risk Rating	Low	Low	Moderate

Summary of progress and lessons learnt since last review

The programme aims to stimulate innovation in methods to assess impact in agriculture and human nutrition/health, including the development of novel indicators and metrics, to support the delivery of nutritional results through agriculture. The programme has made very good progress this year in establishing a portfolio of innovative methods and metrics (through research grants, fellowships and networking events) to strengthen the evidence base on agriculture-nutrition research.

Since April 2015, the IMMANA team (London School of Hygiene and Tropical Medicine (LSHTM), the Leverhulme Centre for Intergrative Research on Agriculture and Health (LCIRAH) and Tufts University) have made substantial progress on all IMMANA work streams and achieved all the critical milestones. In this review year, the programme has:

- Awarded seven research grants from round one and successfully contracted with the lead institutions;
- Undertaken a second round call for grants, and received 99 concept notes;
- Awarded six Research Fellowships, which have now started;
- Undertaken a second round call for IMMANA Fellowships;
- Built up a membership of the new Agriculture, Nutrition and Health (ANH) Academy of 350; and
- Established three working groups/networks on food safety, food environments and sustainable diets.

There continues to be significant interest in both bidding for research funding and in the research programme and events. For Grants this is evidenced by 99 responses to the call for applications this year. Similarly 116 Fellowship applications were received for Round 2. Whilst it is too soon for any results to emerge from the Grants and Fellowships, the uptake of several blog posts and webinars produced and planned through these channels indicate high levels of motivation and enthusiasm amongst recipients. It also reflects consistent interest in their progress from the wider research community.

With the ANH Academy up and running, there is now a major focus on ensuring the success of the ANH Academy Week and Agri-Health Research Conference in June. The quality and breadth of the preliminary programme highlights the progress being made in this respect. Leading thinkers and figures from across the world have shown interest in running learning sessions, chairing panels and delivering keynote speeches, to the extent that it is no longer possible to accommodate any additional content. Over 165 abstracts were received for the Research Conference, with strong representation from sub-Saharan Africa (>40%) and South Asia (>20%). Approximately 90 researchers have been invited to give oral or poster presentations. Registration opened on Friday 22 April and within four days 74 people from 25 countries registered for the event.

The main lesson since the last review is that because there is significant demand for the programme, the IMMANA team has had to proactively manage the expectations of potential grantees and those that are awarded funding. The team have learnt the importance of making the terms and conditions available to potential grantees before they apply, in order to increase competition and drive value for money. Other lessons include having a rolling application process for fellowships to give the greatest opportunity for people to apply. On the Academy, the team are using other platforms e.g. disseminating news and reports through the CGIAR’s Agriculture for Nutrition and Health programme network of research practitioners, to deliver greater impact at no additional cost.

Summary of recommendations for the next year

To maintain a strong focus on ensuring the programme has the maximum impact, the IMMANA team should conduct a light touch ‘lessons learnt’ exercise following Round 2 to establish whether the changes made following the first exercise have been successful and to identify whether further improvements need to made to round 3 Fellowship Awards (by December 2016).

The team have effectively established a rigorous selection process to ensure that high quality proposals are selected at concept stage and accepted at the full proposal stage. The IMMANA team should continue to communicate the rigour and quality required from those submitting proposals to ensure that expectations about receipt of grants are better managed (by June 2016).

To ensure that potential grantees are fully aware of the Terms and Conditions of the grant agreement and that the process of contracting with grantees is managed in good time, the IMMANA team should review the Terms and Conditions of the grant agreement to establish whether the clauses need to be up-dated, prior to contracting with new grantees (by June 2016).

In order for the mid-term review to commence by the end of the year, the IMMANA team should set out plans for the review and establish what information they need for the baseline data (by August 2016).

The IMMANA team has established an International Steering Committee Advisory for the event in June to help set an ambitious agenda. In order to maximise the reach and impact of the event, the IMMANA team need to set an ambitious plan for communications before and after the event (by mid May 2016).

The Academy already has 350 members, which is indicative good progress, but in order to deepen its impact across disciplines IMMANA needs to attract more interest and increase its appeal to agriculture specialists (currently only 23% of members identify their main discipline as agriculture). The IMMANA team should develop a plan for how to do this as well as set a target for members from the agriculture research community (by June 2016).

The IMMANA team should develop a fund-raising strategy for the Academy to ensure that the Academy can be financially sustainable in the future once DFID funding ends. (by end of June 2016).

In order that the programme can provide thought leadership on the linkages between agriculture and nutrition and ensure the Academy focuses on the relevant issues, the IMMANA team have already identified the need for a strategic approach to deciding future working group topics, as well as how best to run them. It is critical that the Academy encourages member buy-in and focuses on research areas and issues that are both relevant and current. Hence by democratising this process it is expected that a greater degree of member ownership and relevance will be achieved. This needs to be put in place and additional funds sought and found for the Research Assistant position, which supports those groups and is due to end in November 2016 (by August 2016).

Forecasting in 2015/16 remained weak at an average of 9% variance against actual expenditure. DFID and IMMANA to discuss ways to improve forecasting. (May 2016 when new grants manager is in post).

A. Introduction and Context (1 page)

DevTracker Link to Business Case and Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203806/documents

The UK will provide up to £7,190,323 over a 5 year period to stimulate innovation in methods to assess impact in agriculture and human nutrition/health, including the development of novel indicators and metrics. The programme will contribute to the goal of a step change in the generation of high quality evidence linking agriculture and nutrition, which in turn is expected to drive more effective investments by DFID and others.

This support to measuring the impact of agriculture on nutrition is further demonstration of DFID’s global leadership on agriculture and nutrition. It enables us to focus on the delivery of nutritional results through agriculture, an area flagged as important by the UK Prime Minister and the Secretary of State at the Global Hunger Event held in Downing Street in August 2012. The programme aims to contribute to the goal of a step change in the generation of high quality evidence linking agriculture and nutrition.

The outcome from this funding will be:

A strong portfolio of innovative methods and metrics to strengthen the evidence base on agriculture-nutrition research widely available to researchers and practitioners

The programme is expected to contribute significantly to other existing major initiatives in agriculture, nutrition and health such as CGIAR Agriculture for Nutrition and Health (A4NH) by simulating advances in evaluation methods and metrics. The programme will also act as a facilitator to stimulate the research community to conduct innovative research on methodologies and metrics and share emerging findings. It includes a strong capacity building element. The programme is expected to stimulate and contribute to a step-change in research methods and metrics and practices in agriculture and nutrition.

Specific deliverables include:

- A portfolio of innovative methods and metrics for evaluating the impact of agricultural interventions on nutrition and health outcomes, both qualitative and quantitative;
- Peer reviewed publications on metrics and methods in evaluation of agriculture and health research;
- Strengthened community of practice, with larger pool of research and evaluation professionals with expertise in this area and greater depth of expertise within the agricultural research and evaluation; and
- Early career scientists equipped with technical skills and expertise as well as knowledge of application in developing country contexts.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Overall the programme is making solid progress and has delivered all of its major milestones this year. Grants and fellowships are underway, there is significant interest from the research community in the new ANH Academy, and networks of researchers in nutrition and agriculture and being brought together to identify new approaches to measure the links between the two areas.

Though there has been some staff turnover, the management of the programme remains strong, with excellent input and use of the Independent Expert Panel and Steering Committee. The governance arrangements also help to ensure transparency and avoid conflicts of interest. The IMMANA team have raised the profile of the programme and the wider research and policy issues that it seeks to address through effective use of multimedia channels and coalition building among other similar initiatives, such as the AG4NUT.

It is fully expected that the programme will achieve its outcome – ‘A strong portfolio of innovative methods and metrics to strengthen the evidence base on agriculture-nutrition research widely available to researchers and practitioners’. Although research is not yet completed, there are some innovative topics being explored e.g. indicators of affordability of nutritious diets in Africa. Lead organisations and the topic of research are listed on page 7 (grants) and page 10 (fellowships).

Overall output score and description

The overall output score is an A – Outputs met expectations.

The IMMANA team has spent this second year awarding and setting up the seven grants and six fellowships, and running the second round call for applications. Demand continues to be strong. The fear that the low success rate from the first round might deter applicants to the second has not been borne out. The Academy has established itself and continues to raise its profile and membership numbers (350). The IMMANA team now need to capitalise on progress made so far, and ensure the delivery of a successful Academy week in June 2016. The team are collaborating with A4NH, who are also a member of the Steering Committee, on the Academy week and who can draw upon the large CGIAR network in order to increase the involvement of agricultural researchers.

Gender

Consideration of gender issues are central to the programme. The Business Case identified that the evidence that Agriculture certainly holds promise for improving nutrition outcomes, but the evidence base urgently needs to be strengthened with additional methodologically robust research. The scale of the problem to be addressed is significant e.g. an estimated 33% (190 million) of preschool-age children and 15% (19 million) of pregnant women do not have enough vitamin A in their daily diet. Improved agricultural practices that produce more nutritious foods have the potential to help address nutritional deficiencies and poor health.

Though the programme was approved in March 2013, prior to the implementation of the Gender Equality Act 2014, the programme considers the impact on gender both in terms of the process of awarding grants and fellowships, and more importantly, in terms of the content and impact of the research. For example:

- 2 of the 7 grants awarded focus on developing metrics to measure women’s empowerment e.g. care practices focusing on women’s time use and intra-household resource allocation;
- 5 of the 6 fellowships have been awarded to women;
- A webinar has been held on the subject ‘Measuring women's time use in agriculture and nutrition’ with 143 registrants. A future webinar is planned for later this year on ‘Indices of women's empowerment in agriculture and nutrition’;
- The programme has produced a technical paper aimed at critically analysing the use of metrics in the study of women’s time-allocation in an agrarian context; and
- At the Academy Week in June, IFPRI will hold a workshop on Women’s Empowerment in Agriculture Index.

Key lessons

There is enormous interest in the IMMANA programme, highlighting the need for this innovative research from policy makers. There has been a vast response from stakeholders as demonstrated by a broad range of membership of the three working groups and 150 people registered for last webinar. The IMMANA team continue to work closely with partners and large online platforms (e.g. AG2NUT community of practice) to disseminate IMMANA news. This both meets and stimulates demand for exploration into the topic areas. The team have set up IMMANA’s main communications channels at a low cost, using existing channels (e.g. the LCIRAH website) and are raising additional funds delivering VFM. This approach has proved successful and will be continued. This year, the team have also managed to raise funds from CGIAR’s Agriculture for Nutrition and Health programme to support some key communications outputs, such as the IMMANA leaflet and the ANH Academy website.

Has the logframe been updated since the last review?

Yes. The log frame was revised in December 2015 (Quest ref. 5362507).

List of recommendations from 2015 review, with follow up in italics:

The IMMANA team (the Leverhulme Centre for Integrative Research on Agriculture and Health (LCIRAH) and Tufts University) including the Chair of the Independent Panel of Experts, should identify lessons learned from the competitive grants and fellowship process and timelines by end of June 2015. This should be presented by IMMANA to the Steering Committee for discussion by end July 2015.

Done. A report was shared with DFID and the Steering Committee in August. There is a summary of the key lessons under output 1.

The relatively low percentage of successful applicants anticipated at the second stage of competition (14% of applicants for research grants successful; 25% of applicants for fellowships successful) is appropriate in a competition of this type, and reflective of the drive for excellence in research quality. However, LCIRAH and Tufts University will need to consider in the next quarter (May to July) how to communicate this and manage expectations of applicants in order to encourage continued interest.

Done. Effective communication of the call for round two grants generated 99 applications and the fellowship call generated 116.

LCIRAH needs to be proactive in identifying how best to use the formal launch of the Academy to raise IMMANA’s external visibility and profile, which will provide a strong foundation for dissemination of results later on in the process. In particular it should develop a clear plan for communications for the event on June 3rd 2015 and use this to expand its social media presence.

Done. A plan was developed for the launch of the Academy, which was successfully launched in June. Between January and early March 2016, the IMMANA website attracted over 4,300 unique visitors (between 100 and 300 per day) who viewed nearly 18,000 pages. IMMANA has scaled up its presence on Twitter (@IMMANA_res) with close to 400 followers. This includes influential organisations such as Food and Agriculture Organisation, the CGIAR, Cornell and others. Over the past few months the team have sent nearly 500 tweets that were retweeted 379 times. They also have a Youtube channel with 11 videos.

LCIRAH to continue to assess the time inputs required into the Academy and ensure that this does not detract from management efforts into the oversight of the grants and fellowship components.

Done: Time required to set up and run the Academy is significant but the grants and fellowships are now underway and others (e.g. Tufts for the fellowships) manage that component.

Regular project management meetings should continue to be held between DFID and LCIRAH on a 2 monthly basis (or more if required), these should be focused on specific issues that LCIRAH or DFID identify.

Done and ongoing.

By end of July 2015, LCIRAH should review the logframe and share with DFID for approval by end of August.

Done.

LCIRAH needs to ensure that it is accurate in its quarterly forecasting to DFID, with no more than 2% variance against actual expenditure.

Forecasting in 2015/16 remained weak at an average of 9% variance against actual expenditure. DFID and IMMANA will discuss ways to improve forecasting in May 2016 when the new grants manager is in post. (Recommendation #9)

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Competitive research grants develop new methods/approaches and metrics
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	60%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1 Competitive research grants awarded and implemented to develop new methods and metrics	8 research grants awarded	7 research grants awarded (average £250k). / Institutions receiving grants include: / Indira Gandhi Institute of Development Research, University of Texas; / International Food Policy Research Institute; / Rollins School of Public Health, Emory University; / World Agroforestry Centre; / Tufts University; and / University of Michigan; Innovations for Poverty Action. / The Independent Panel of Experts (IPE) gave an unconditional recommendation for six grants to be awarded (out of 22 full proposals), which was subsequently approved by DFID and the Steering Committee (SC). The Panel provided a conditional approval for another grant, which was revised by the investigators and was eventually approved by the IPE, DFID and the SC. The SC did not agree to the 8th award. / LSHTM has finalised the contracts with all seven institutions and the projects are in initial implementation phase. The IMMANA Principal Investigator and Research Fund Manager have held the first round of monitoring meetings with each grantee. The projects are all on track and no major issues have been identified to date, as reported in their quarterly reports.

Key Points

The programme is on track and output 1 scores an A. Seven grants have been awarded and set up successfully, which is indicative of strong performance. The IPE did not agree to give the 8th institution the award (which was endorsed by the SC), which is evidence that high standards are maintained above and beyond meeting volume targets. The table below lists the grantees and the research topics.

Organisation	Title of Research
Indira Gandhi Institute of Development Research; University of Texas, Austin (US)	The Women’s Empowerment in Nutrition Index: Measuring nutritional empowerment to better link agriculture to nutrition
International Food Policy Research Institute (US)	Leveraging value chains to improve nutrition: collaborative learning initiative on methods and metrics for improving the identification, design and evaluation of interventions
Rollins School of Public Health, Emory University (US)	Women’s empowerment in livestock-focused agriculture: Identifying and understanding pathways to impact for maternal and child nutrition in East Africa
Tufts University (US)	Indicators of Affordability of Nutritious Diets in Africa
University of Michigan; Innovations for Poverty Action (US)	Developing an innovative approach to measuring the livelihoods of smallholder farmers and testing critical linkages from farmer livelihoods to nutrition
World Agroforestry Centre (Kenya)	Surveillance of Climate‐Smart Agriculture for Nutrition
World Agroforestry Centre (Kenya)	Probabilistic Causal Models for Nutrition Outcomes of Agricultural Actions

Immediately following the round one awards process, the IMMANA team compiled a comprehensive document on the lessons learnt and implications for round two. The full report was shared with the SC and with DFID. The key lessons were:

1. Call for applications
A large number of applications were received, including from Low and Middle Income Countries.	Given the strong response, a similar dissemination approach was adopted in round 2 e.g. use of online platforms, newsletters, professional networks.
The IPE & SC suggested a more thematic approach could be taken. Examples suggested included urban or dietary transition, global/national level metrics.	In round two, the call for applications indicated a clear preference for the thematic areas not covered in the existing portfolio of grants.
There were some common weaknesses of unsuccessful round one applications. Examples include not providing enough detail on data collection and analysis or not considering how to validate the metric/tool.	The team held a webinar as a part of the application process in order to clarify any queries potential applicants had about the call and the application process.
The fellowship call integrated FAQs that are applicable to all applicants.	FAQs integrated in round two call for applications.
2. Concept memos
The logging of applications took a long time given the large number of applications received.	In round two, the team utilised a software package (Submittable) for greater efficiency.
The IPE & SC suggested a more structured concept memo template to ensure that the fit with IMMANA objectives could be identified.	A much more structured concept note template was developed for round two, responding to the suggestions.
3. Shortlisting/initial review
The IPE suggested that the team should be more aggressive at the shortlisting stage, because a number of shortlisted applications and full proposals were considered out of scope with IMMANA.	The assessment process now includes a two-step approach. The first step covers eligibility of the applications while the second step includes scientific assessment. The latter also includes scoring thresholds (Innovation and overall score) that allows for more structured shortlisting of the applications.
More reviewers for each concept memo would have provided more scores for analysis, leading to a better consensus about which concept memos did not fit the IMMANA call.	The list of internal reviewers now also includes IPE members.
There was very little time (2.5 weeks) between the concept memo deadline and informing applicants about invitations for full proposals.	The shortlisting period, submission deadline and indicative date for an invitation to submit full proposals, is now six weeks.
4. Full proposal
The full proposal template could be improved and the IPE strongly suggested that the abstract be more structured.	The structure of the full proposal template was revised for round two.
Specific full proposal FAQs should be included.	FAQs were integrated in the information provided to short-listed applicants.
5. Grant award
There has been some push back on the terms and conditions, with one applicant questioning a number of core clauses.	To ensure applicants accept the terms and conditions of the grants, these have been shared with the round two call for applications. This point will further be emphasised in the letter to those short-listed.

The call for applications for round two of the IMMANA Competitive Research Grants was released on 1 November 2015 with the submission deadline of 15 February 2016. With 99 applications, the call received an expected level of interest given the streamlining and tailoring of the call to fit the strategic objective of the project more closely. The concept note assessment process is underway, involving a two-step approach with eligibility and scientific assessment. The team anticipates at least 50% of the submitted application will be relevant research grant applications and invited to submit full proposals.

Existing grantees provided positive feedback on the programme. Feedback confirmed that from the bidders and grantees perspective, the application process was clear. Effective communication between all parties ensured that the process ran smoothly.

Recommendations

1.	To maintain a strong focus on ensuring the programme has the maximum impact, the IMMANA team should conduct a light touch ‘lessons learnt’ exercise following Round 2 to establish whether the changes made following the first exercise have been successful and to identify whether further improvements need to made to round 3 Fellowship Awards (by December 2016. Recommendation #1).

2.	The team have effectively established a rigorous selection process to ensure that high quality proposals are selected at concept stage and accepted at the full proposal stage. The IMMANA team should continue to communicate the rigour and quality required from those submitting proposals to ensure that expectations about receipt of grants are better managed (by June 2016. Recommendation #2).

3.	To ensure that potential grantees are fully aware of the Terms and Conditions of the grant agreement and that the process of contracting with grantees is managed in good time, the IMMANA team should review the Terms and Conditions of the grant agreement to establish whether the clauses need to be up-dated, prior to contracting with new grantees (by June 2016. Recommendation #3).

Output Title	Research fellowships develop or adapt new methods/approaches and metrics
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 Early Career researchers awarded fellowships and mentoring to develop or adapt new methods and metrics	6 fellowships awarded	6 fellowships awarded. / Full proposals for the Fellowships were due on 1 March 2015. These were then screened by the Tufts Fellowships Office and sent to external reviewers. The Selection Committee recommended 6 candidates, which were endorsed by the IPE and SC. All the invited Fellows accepted the Fellowship award and started their Fellowships on time, in line with the dates described in the submitted full proposals.

Key Points

The programme is on track and output 2 scores an A.

Good communication has been developed between the fellows and the Fellowship Office at Tufts, and with the IMMANA team e.g. fellows have contributed blog posts on the IMMANA website. Topics being addressed by the six fellows include many of the most important pathways linking agriculture and nutrition. The table below lists the research topics and both the home organisation of the researcher (where the research is being conducted) and the organisation of individuals mentoring the Fellow (who provide guidance and help to accelerate research and sharing of ideas between the Fellow’s home and host environments).

Home and Host	Topic
Home mentor: Royal Veterinary College (UK) / Host mentor: Tanzania Veterinary Laboratory (Tanzania)	Food system dynamics, poultry improvement and nutrition in Tanzania
Home mentor: Ohio State University and Sokoine University. (USA/Tanzania) / Host mentor: Makerere University (Uganda)	Nutritional barriers to agricultural productivity in Uganda
Home mentor: McGill University (Canada) / Host mentor: University of Ghana (Ghana)	School feeding program implementation and child nutrition in Ghana
Home Mentor: Hawassa University (Ethiopia) / Host mentor: Dept. of Environmental Sciences, Emory University (USA)	Milk consumption, nutrition and health in southern Ethiopia
Home mentor: Cornell University (USA) / Host mentor: Southern African Institute for Policy and Research (Zambia)	Women's time use, agriculture and nutrition in Zambia
Home mentor: Delhi School of Economics (India) / Host Mentor: Columbia University. (USA/France)	Intra-household allocation and child nutrition in Bihar, India

Key lessons and implications for round 2:

- Publicise the selections so far and emphasise that proposals on complementary topics are particularly welcome;
- Encourage applications on regions and institutions not yet included in the portfolio;
- Publicise these data on applicants;
- Update round 2 call and the list of FAQs, and resend to an updated list of contacts;
- Invite optional concept notes on a rolling basis at any time up to one month before the full proposal due date; and
- Fellowship proposals in round 2 to be reviewed by two internal reviewers and a standing panel of three external reviewers.

Approval was sought from DFID to alter the review process in round 2.

The call for applications for round 2 was announced in October 2015. 98 research institutes were contacted and they sent the information to their networks. IMMANA’s analysis of the dissemination activity estimated that the call reached 30,000 people. The Tufts Friedman team worked with the Communications Manager and three Round 1 IMMANA Fellows to develop and hold a one-hour long information webinar, which took place on 3 December 2015 and was attended by 41 people from 21 countries. 116 concept notes were submitted by the 1 February 2016. 50 were invited for full proposal submission. 39 submitted full proposals, 23 of which were from sub Saharan Africa. The selection process is currently underway and will be announced in October 2016.

Recommendations

The IMMANA team should conduct a light touch ‘lesssons learnt’ exercise following round 2 Fellowship Awards to establish whether the changes made following the first exercise have been successful and to identify further improvements for round 3 (by August 2016. Recommendation #1).

The IMMANA team should set out plans for the mid-term review and establish what information they need for the baseline data (by August 2016. Recommendation #4).

Output Title	Platforms and mechanisms are in place to facilitate sharing of methods and metrics
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 The ANH Health Academy is established	4 regional stakeholder consultations and one online (global) consultation convened; Academy launched; meeting of major agriculture, health and nutrition initiatives convened.	4 regional stakeholder consultations and one online (global) consultation convened; Academy launched; meeting of major agriculture, health and nutrition initiatives convened
3.2 Mechanisms established to facilitate learning and sharing of methods and metrics amongst the global community engaged in agriculture-nutrition research	3 webinars; microsite and online knowledge management portal launched; 3 working groups convened	4 webinars; one Learning Lab (training events) at the Academy conference (now moved to June 2016; 3 technical working groups established.

Key Points

Very good progress has been made on this output, scoring an A+. There has been considerable activity, in-depth consultation and communication through webinars and working groups.

In the Spring and Summer of 2015, the IMMANA team worked with the CGIAR’s Agriculture for Nutrition and Health (A4NH) to organise a series of regional consultations in East (Nairobi) and West (Cotonou) Africa as well as South Asia (Delhi). Piggybacking on the consultation on an existing A4NH event encouraged key stakeholders to attend and provided a valuable opportunity to increase the reach of the IMMANA programme and its work streams. The team also conducted a consultation at the Federation of African Nutrition Societies (FANUS) 2015 conference in Arusha, Tanzania which also generated important, free exposure to the global research community.

The consultation sessions with stakeholders facilitated highly productive deliberation concerning the concept, scope and future development and direction of the Academy. Through these deliberations several key outputs were agreed upon and endorsed:

- The Academy should act as a catalytic platform and resource hub for agriculture, nutrition and health research;
- Membership should be individuals rather than institutions; and
- Working group topics should aim to address key gaps in methods and metrics and to advance research on a particular pressing problem.

The main purpose of the Academy is to facilitate learning and sharing among the global community of interdisciplinary researchers and research-users working on agriculture and food systems for improved nutrition and health. It was launched at the LCIRAH conference in London on 5 June 2015. The ANH Academy Week, 20-24 June 2016 in Addis Ababa was announced in February and preparations are underway.

Three technical working groups have been convened on food environments, food sustainability and food safety. The purpose of the working groups is to facilitate learning and sharing of methods and metrics amongst the global community engaged in agriculture-nutrition research, and identify current gaps or synergies.

The IMMANA webinar series was launched in December 2015 using a low-cost and efficient online solution (GoToMeeting with GoToWebinar) that also helps run smaller virtual meetings. Webinars to date include:-

- IMMANA Grants (34 registrants);
- IMMANA Fellowships (79 registrants);
- Sustainable Diets Working Group consultation (100 registrants);
- Sara Stevano, School of Oriental and African Studies, ‘Measuring women's time use in agriculture and nutrition’ (143); and
- Amy Webb, Emory University; Erin Lentz, University of Texas, Indices of women's empowerment in agriculture and nutrition (June TBC)

Recommendations

The IMMANA team has established an International Steering Committee Advisory for the event in June to help set an ambitious agenda. In order to maximise the reach and impact of the event, the IMMANA team need to set an ambitious plan for communications before and after the event (by mid May 2016. Recommendation #5).

The Academy already has 350 members, which is indicative of good progress, but in order to deepen its impact across disciplines IMMANA needs to attract more interest and increase its appeal to agriculture specialists (currently only 23% of members identify their main discipline as agriculture). The IMMANA team should develop a plan for how to do this as well as set a target for members from the agriculture research community (by June 2016. Recommendation #6).

The IMMANA team should develop a fund-raising strategy for the Academy to ensure that the Academy can be financially sustainable in the future once DFID funding ends. (by end of June 2016. Recommendation #7).

In order that the programme can provide thought leadership on the linkages between agriculture and nutrition and ensure the Academy focuses on the relevant issues, the IMMANA team have already identified the need for a strategic approach to deciding future working group topics, as well as how best to run them. It is critical that the Academy encourages member buy-in and focuses on research areas and issues that are both relevant and current. Hence by democratising this process it is expected that a greater degree of member ownership and relevance will be achieved. This needs to be put in place and additional funds sought and found for the Research Assistant position, which supports those groups and is due to end in November 2016 (by August 2016. Recommendation #8).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The IMMANA programme is managed by LCIRAH (contracted through London School of Hygiene and Tropical Medicine - LSHTM) and in partnership with Tufts University, who lead on the delivery of the Research Fellowship work stream. DFID uses the deliverables and milestones in the contract to track delivery of research outputs and outcomes.

A Steering Committee has been established to provide technical oversight and maximise the effectiveness of the programme. The SC comprises of the CGIAR Research Programme on Agriculture for Nutrition and Health (A4NH), DFID, the Bill and Melinda Gates Foundation and USAID. The Steering Committee was consulted on the calls for the first round of grants and fellowships, including the selection criteria, and made the final approval decisions following short-listing from the independent peer review process. The same process will apply in round two. The Steering Committee reserves the right to make final decisions, based on an overall assessment of the strategic value of the portfolio as a whole, whilst ensuring that only proposals of high quality and research rigour are funded.

VfM performance compared to the original VfM proposition in the business case

VfM was a major criteria in the procurement of the management group for IMMANA. The Business Case sets out a number of VfM measures for monitoring progress. Programme costs, including administration costs, are monitored on a quarterly basis, and value for money is a criteria in the awarding of sub-grants. The number of peer reviewed publications and other outputs will be monitored in order to track research outputs and the quality of research. By engaging the Steering Committee, value for money is further assured by strengthening the technical inputs available to DFID, and ensure coordination with other significant funders and investments in this area.

Assessment of whether the programme continues to represent value for money

LCIRAH has agreed a payment plan where payment is released quarterly in arrears on achievement of work plan milestones. This ensures a strong focus on delivery throughout the programme. Expenditure for IMMANA is monitored, reported and accounted for on a quarterly basis.
IMMANA has been designed in such a way as to ensure it remains flexible and adaptable to emerging needs. If deliverables and milestones are not being met, payments are withheld.
All projects are in an initial implementation phase. The Principal Investigator, with the IMMANA Research Funding Manager, held a first round of monitoring meetings with the grant holders. The projects are all on track and no major issues have been identified to date. IMMANA’s next annual report will include information on the results of the first round of the grants and the progress on the grants awarded in the second round. Further analysis and assessment of the VfM will be included in the mid-term review and final evaluation.

Quality of financial management

DFID will provide up to £7,190,323 over a 5 year period. The programme is led by LSHTM and coordinated by LCIRAH, which is a centre of the LSHTM. The programme is run in partnership with Tufts University, through a commercial contract that started in August 2014. DFID’s total expenditure to date on IMMANA is £508,092.47 (approximately 7% of approved budget). In year two expenditure has been lower than expected due to the following factors:

- Delays in finalising grant contracts due to issues on terms and conditions resulted in a late start of some of the projects. In addition, those grant contracts that have started on time invoiced on average 50% less than initially projected.
- Focus on driving cost-efficiency by minimising travel and communications related expenditure without sacrificing the quality of communication and consultations among partners and with stakeholders.
Spend on the IMMANA programme has been guided by Value for Money principles. Purchases by LSHTM have been determined by the project’s set milestones and budget and limited to what is needed for a successful project. These have been procured through a transparent process administered by LSHTM.

The percentage of forecasting against actual expenditure in 2015/16 was weak at an average of 9% variance. DFID and the IMMANA Management Team will discuss ways to improve forecasting in May 2016 when the new grants manager is in post (recommendation #9).

Date of last narrative financial report	21 March 2016
Date of last audited annual statement	Audited Accounts 1 August 2014 to 31 July 2015 and annual statement received 27 April 2016.

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

The risk profile has been reviewed as part of this Annual Review and has been assessed as moderate. Risk analysis uses the system adopted in DFID’s Research and Evidence Division of looking at output, management and intellectual risk.

Management risk is assessed as moderate. There have been a significant number of staff changes this year. The high turnover of staff has been linked to the part-time status of some of the positions. The Funding Manager is a 0.6 FTE position and the Program Manager is a 0.5FTE position. In order to minimise further turnover of staff, IMMANA propose minor restructuring, by combining the two posts to one full-time position. Combining the two positions at this stage will not compromise the Round 2 final application evaluation as key issues, in terms of conflict of interest in IMMANA Grants selection process, will be dealt with before the departure of the current IMMANA Grants Funding Manager.
The IMMANA team conducted a due diligence check on the grantees before awards were finalised. The expenditure for IMMANA is monitored, reported and accounted for on a quarterly basis and the Principal Investigator, with the IMMANA Research Funding Manager, have held a first round of monitoring meetings with the grant holders. The projects are all on track and no major issues have been identified to date.

Output risk is minor. The competitive grant rounds for both research grants and fellowships have had a strong response rate for round 2. The quality of the competitive process and rigorous peer review ensure that successful bidders are of high quality. However, IMMANA’s management continue to identify quality as an on-going risk, which they need to monitor pro-actively, and have noted the need for active support and supervision from their technical team. The team have quarterly meetings with grantees.

Research or intellectual risk is moderate for the portfolio as a whole. Though it is too early to assess quality of research outputs, the seven grantees and six fellowships selected are examining innovative metrics and tools for agriculture and nutrition.

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Overall the IMMANA programme is being delivered against its agreed timeframe, and the milestones are on track.

Performance of partnership (s)

The contract with LCIRAH commenced in August 2014. Project management meetings are held between DFID and IMMANA on a 2 monthly basis (or more if required), and these are focused on specific issues that IMMANA or DFID identify. There are no specific performance issues identified at this stage, although the high turnover of staff this year has raised some concerns. Despite this, systems and processes seem to have bedded down and the programme is delivering on its three outputs, suggesting that the staff changes have been managed effectively.

Asset monitoring and control

LSHTM has a clear policy on asset monitoring and this is applied in the IMMANA programme

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The partnership principles were not used in monitoring this project as it does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Evidence of the need to address the current gap in effective frameworks, methods, tools and indicators for measuring the nutrition and health impacts of agricultural programmes remains. The strong interest in this area within the international development and research community remains and is reflected in the high level of applicants to the second round, membership of the working groups and the interest the Academy week (165 abstracts submitted).

Monitoring progress throughout the review period

In addition to submission of an annual report by LCIRAH, progress is monitored through bi-monthly meetings between the LCIRAH and the DFID programme management teams. These are supplemented by email exchanges where necessary, enabling issues to be addressed promptly.

A Steering Committee has been established to provide technical oversight and maximise the effectiveness of the programme. The SC reserves the right to make final decisions in the research grant and fellowship competitions, based on an overall assessment of the strategic value of the portfolio as a whole, whilst ensuring that only proposals of high quality and research rigour are funded. The SC comprises of the CGIAR Research Programme on Agriculture for Nutrition and Health (A4NH), DFID, the Bill and Melinda Gates Foundation and USAID. The SC was consulted on the calls for the first round of grants and fellowships, including the selection criteria, and made the final approval decisions following short-listing from the independent peer review process. The same process will apply in round two.

The IMMANA Principal Investigator and Research Fund Manager have held the first round of monitoring meetings with each grantee. These will continue on a regular basis.

Evaluation
The Business Case identifies a need for an independent mid-term review at the end of 2016 and an evaluation in the final year of the programme. These reviews are intended to ensure that the programme responds to wider stakeholder interests, including those of developing country stakeholders. Both of these are included in LCIRAH’s work plan and budget and the IMMANA team will set out plans for the review and evaluation and establish what information they need for the baseline data by August 2016. DFID will approve each stage of the evaluation (inception report, interim report and final report) to ensure it is of high quality.

Approach for this Annual Review

The annual review was carried out by an internal DFID team, involving Louise Horner (Livelihoods Adviser, Agriculture Research Team, Research and Evidence Division) and Lorraine Healy (Deputy Programme Manager, Agriculture Research Team, RED). An external reviewer was not involved in this Annual Review as the programme is only in the very early stage of implementation. The next Annual Review will be done by a joint RED and Policy and Global Partnerships team.

All grantees were invited to provide feedback to DFID on the process of applying for grants and the support received from the IMMANA team. Comments were received from 2 grantees.

The Annual Review was shared with the members of the Steering Committee for comments.

The annual review team drew upon: the Annual Programme Report submitted by LCIRAH. The checklist guidance has been followed and a completed checklist saved in Quest.

Key Documents

IMMANA Business Case (Quest No. 3890364)
Latest Logframe (Quest No. 5362507)
Annual Review Terms of Reference & Checklist (Quest No. 5412761)
Annual Review - Project Score Calculator (Quest No. 5412798)
IMMANA Year 2 Annual Report and Appendices 1 April 2015 to 31 March 2016 (Quest No. 5412823 and 5412840)
Annual Review 2015 (Quest No.4930472)
http://www.lcirah.ac.uk/immana

Annex A

2015 Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Innovative Metrics and Methods for Agriculture and Nutrition Actions (IMMANA)
Programme Value: £7,190,323		Review Date: 7 May 2015
Programme Code: 203806	Start Date: 7 August 2014 (date contract with Managing Agent commenced)	End Date: 6 August 2019

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	Low	Low

Summary of progress and lessons learnt since last review

Overall the programme is making good progress, scoring an A. Since the contract was signed in August 2014, IMMANA has: established its project management team; launched the calls for the Research Grants and Fellowships; and initiated the global research network and community of practice. The call for the grants was launched on 1 October 2014 and the fellowship call went out on 11 November 2014. Proposals are currently being assessed by a 12 person Independent Panel of Experts, and the first round of grants and fellowships will be selected for award in early May 2015 by the Steering Committee (comprising DFID Nutrition Policy and Agriculture Research, BMGF, USAID, CGIAR’s Agriculture for Nutrition and Health programme Director). Whilst it is still early to assess quality and relevance of the research to be funded under the competitive calls, the management has been competent and the strong response to the research calls is promising.

There is significant interest in the international community (evidenced by the high response rate to the calls), and in DFID (evidenced by current discussions led by the agriculture and nutrition policy teams), in this area, illustrating the continued relevance of this research area.

Summary of recommendations for the next year

The IMMANA team (the Leverhulme Centre for Integrative Research on Agriculture and Health (LCIRAH) and Tufts University) including the Chair of the Independent Panel of Experts, should identify lessons learned from the competitive grants and fellowship process and timelines by end of June 2015. This should be presented by IMMANA to the Steering Committee for discussion by end July 2015.

The relatively low percentage of successful applicants anticipated at the second stage of competition (14% of applicants for research grants successful; 25% of applicants for fellowships successful) is appropriate in a competition of this type, and reflective of the drive for excellence in research quality. However, LCIRAH and Tufts University will need to consider in the next quarter (May to July) how to communicate this and manage expectations of applicants in order to encourage continued interest.

LCIRAH needs to be proactive in identifying how best to use the formal launch of the Academy to raise IMMANA’s external visibility and profile, which will provide a strong foundation for dissemination of results later on in the process. In particular it should develop a clear plan for communications for the event on June 3rd 2015 and use this to expand its social media presence.

LCIRAH to continue to assess the time inputs required into the Academy and ensure that this does not detract from management efforts into the oversight of the grants and fellowship components.

Regular project management meetings should continue to be held between DFID and LCIRAH on a 2 monthly basis (or more if required), these should be focused on specific issues that LCIRAH or DFID identify.

By end of July 2015, LCIRAH should review the logframe and share with DFID for approval by end of August.

LCIRAH needs to ensure that it is accurate in its quarterly forecasting to DFID, with no more than 2% variance against actual expenditure.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process