Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Khyber Pakhtunkhwa Education Sector Programme (KESP)
Programme Value: £203.5 million		Review Date: February 2015
Programme Code: 202328	Start Date: August 2011	End Date: August 2016

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	C	B	B	A
Risk Rating	High	High	High	High

Summary of progress and lessons learnt since last review

A radical refresh of KESP took place in March 2014. This set a new direction of travel and positive trajectory for the programme, using a reworked Results and Activities Framework (RAF), and built on the opportunity presented by a new reformist Government. The level of ambition and timeline at that stage, however, were too optimistic. The previous Annual Review in August 2014 noted positive improvements and the achievement of 50% of the RAF which led to disbursement of 60% of the available funds. It was therefore agreed to keep the programme under close scrutiny. A further assessment of the RAF took place in November 2014 followed by this light-touch Review in February 2015.

The Review took place in the aftermath of the school massacre in Peshawar on 16 December 2014. It is a tribute to the resilience of the Government of Khyber Pakhtunkhwa (GoKP) bureaucrats that they have continued to focus on KESP at the same time as dealing with the immediate aftermath and considering how best to enhance school security and safety across the province.

At the KESP Quarterly Steering Committee (20 October 2014) it was agreed that this Annual Review would concentrate on the remaining results in the RAF, the logframe indicators, budget execution, and additionality. The AR team also read a wide range of documentation which provided evidence to support the Review findings (detailed at Annex 2).

This fourth Annual Review concludes that there has been significant progress over the last six months. The Review team was particularly encouraged by the increased energy, confidence and capacity of key KP education officials. There is clearly a culture of lesson learning to improve delivery emerging within the education administration. Notable achievements include:
i) The launch of the new five-year Education Sector Plan (ESP 2015-2020) by GoKP. The ESP is realistic and covers key policy areas: better schools and facilities; more effective teachers; every child’s right to education; and good governance and management. It will be the first of three five year plans to deliver reforms to 2030.
ii) The Independent Monitoring Unit (IMU) is both impressive and catalytic. Data are driving accountability. It is recognised that more needs to be done to make information more accessible and user friendly. Although data are already being used by districts for budgeting and monitoring, more detailed information is required, at all levels, for better planning.
iii) Out-sourcing has been used by the Government to encourage partnerships with the private sector, especially for training, an area where the Elementary and Secondary Education Department (E&SED) lacks capacity. This has proved an important learning experience for future procurement.
iv) Work on teacher rationalisation across the province has been completed. One continuous development framework for teacher training has been introduced and a teacher competency framework piloted. Teacher Unions have been consulted about the planned reforms.
v) The newly-appointed Managing Director of the Elementary Education Foundation (EEF) reported ambitious plans to open new girls’ community schools and to significantly expand the voucher system.

A thorough review of the RAF (Annex 1) indicates that all results have now been met. This is an excellent achievement. A new short term RAF January - June 2015 (detailed at Annex 1) has also been agreed with GoKP to measure progress until the multi-year framework (June 2105 - 20), which will be used to monitor the new ESP, is agreed and in place.

Governance is a key priority for the Secretary Education and his team. The Internal Audit Cell is now functional and staff are undergoing training. The Audit Plan and subsequent audits will help reduce fiduciary risk and provide increased external confidence in the system. The IMU has produced baselines, although they are not yet approved by GoKP. This is an urgent issue to address to ensure that progress from now on can be measured.

Early signs suggest that improvements have been made to the provision of technical assistance sourced through ASI, particularly in the area of programme management. The technical assistance team still need to have a greater presence in Peshawar and to adjust the balance of technical skills within the team to ensure they can best support GoKP deliver against the new RAF and the ESP.

Budget execution has improved significantly compared with the same period in 2013-14. Absolute spend is higher; and execution rates for the development budget and non-salary recurrent budgets are 28% and 30% respectively, up from 9% and 6% in 2013-14. Execution will continue to be monitored closely for the rest of the financial year; there are positive signs, however, that the Department will continue its trajectory of strong spend over the coming months. This is a particularly significant achievement given that the 2014-15 education budget itself increased by 11% compared with the original 2013-14 budget and over 30% compared with final spend in 2013-14.

Progress on the school rehabilitation and construction component continues to be delayed due to the issues concerning the service provider’s (IMC) registration with the Board of Investment (BoI). This has delayed progress from the inception to implementation phase and will have a knock-on effect on the delivery of results as stipulated by the original terms of reference.

Key Achievements

Key achievements over the last year are:
- Over 28,000 government schools (96% of schools in KP) are being monitored monthly, for the first time by an Independent Monitoring Unit (IMU);
- Improved teacher rationalisation which has led to 4,817 teachers (around 4% of the workforce) being redeployed;
- An extra 6,000 teachers present in KP schools since May 2014; nearly half due to increased teacher attendance, which is being monitored by the IMU; and
- Dramatically improved budget execution. As of February 2015, budget execution in this 14/15 financial year for ‘development’ and ‘recurrent costs’ is now 30% and 28% respectively, up from 9% and 6% in February 2014.  Teachers and schools can now operate much more effectively than before.

All of the above mean the delivery chain for enabling children to learn is falling into place, and the reform process is making a substantial difference to the performance of the education system. Notwithstanding, it will take several more years and significant further support on quality in the classroom for cohorts of children to demonstrate that they are learning more.

Summary of recommendations for the next year

Immediate
1. Endorse the recommendation of the 2014 Annual Review to extend the programme for three to five years to encompass the ESP timeline. (Action: DFID)
2. Extend the IMC contract to deliver the school reconstruction and rehabilitation component to March 2018. (Action: DFID)
3. Use IMU data to establish a range of baselines. Make IMU data system more accessible and user-friendly so that data can be used for planning. Traffic lights and heat maps will give the findings more impact and effectiveness. IMU data could also be used to reflect a more gender-focused approach to communication and planning. (Action: ASI by April 2015).
4. Release the remaining £8.5 million (DFID) and £5.5 million (DFAT) funding now the RAF is fully met. (Action: DFID/DFAT)
5. Take a decision about the future scope of the OPM evaluation contract which is still in its inception phase. (Action DFID in March 2015)
6. Re-orientate the ASI technical assistance team so that it has a greater presence in Peshawar and has the technical capacity to support delivery of the new RAF and ESP. This view was expressed to the Annual Review team at the highest level. (Action: ASI by April 2015)
7. Review the KESP logframe against the new RAF to ensure greater alignment between the two documents (Action: DFID/ASI by April 2015)
8. DFID to strengthen its direct relationship with E&SED, associated implementing partners, and other relevant GoKP departments. As KESP is one of DFID’s largest projects, priority should be given to ensuring more regular visits Peshawar for the SRO and programme team. (Action: DFID)

Medium term
1. As planned, the GoKP should carry out an extensive review of the existing stipend programme, making comparisons with other schemes in Pakistan, with a view to: reducing transaction costs; considering electronic methods of transfer; strengthening governance and targeting; and measuring impact and effectiveness. This study should be made available to the next Annual Review in August 2015. (Action: ASI/DFID in consultation with E&SED)
2. GoKP to select a few competencies from the teacher development framework and concentrate on those within the training programme, year on year, so teachers accumulate an essential toolkit of skills. (Action: E&SED)

Long term
1. Long-term planning for KESP should reflect the priorities outlined in the ESP and Joint Review Framework. There should also be a greater focus on student learning and assessment, improving teaching and learning materials, and continuous professional development for teachers. (Action: DFID and ASI)
2. Ensure TA support supports the GoKP’s longer-term vision as articulated by the Secretary Education to:
- Improve communication at all levels within the department, between the department and its stakeholders, and among different departments at the provincial level;
- Ensure that the ESP remains front and centre in everything that the department does going forward, and that there is a delivery plan/implementation strategy to help translate this into action; and
- Improve accountability mechanisms to make the Government, and the department in particular, more responsive.
(Action: DFID and ASI)
The AR team to encourage E&SED to develop a plan to mainstream gender over the next twelve months given how critical issues such as access and retention are for girls’ education.

A. Introduction and Context

DevTracker Link to Business Case:	http://dfid.gov.uk/iati_document/3745014.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4562995.xlsx

Outline of the programme

DFID plans to invest up to £203.5 million through KESP to support the GoKP deliver education reform as articulated by the ESP. DFAT Australia is also contributing up to £41.3 million to KESP, through a Development Partner Agreement. KESP aims to support more children to stay in school longer, learning more. It is structured around four components:
1. Financial Aid to the GoKP on the basis of progress against a RAF (up to £ 123.5 million (DFID) and £21.3 million (DFAT)).
2. Technical assistance to the GoKP to support delivery of the RAF and the aims of the ESP. This is provided through Adam Smith International (ASI) (up to £20 million (DFID)).
3. An infrastructure component to upgrade schools. This is being implemented by IMC in partnership with GoKP but procured independently to manage fiduciary risk. (Up to £60 million (DFID) and £20 million (DFAT)).
4. Technical assistance through Oxford Policy Management (OPM) to inform and evaluate the effectiveness of interventions to date and to provide an evidence base on which to determine any future programme. (£1.37 million (DFID)).

Khyber Pakhtunkhwa’s (KP) education indicators are among the poorest in Pakistan, a country which accounts for more than one in ten of the world’s out of school children. An estimated 28% of men and 65% of women in the province are illiterate. There are currently at least 3 million children out of school in the province; two thirds of them are girls. Progress on education has historically been adversely affected by a range of issues including relatively weak Government bureaucracy, conflict, natural disasters, and strong cultural barriers to education for women and girls.

The programme has faced a number of challenges. Funds were initially slow to disburse as the GoKP allocated financial aid funds to specific projects through a PC-1 modality, each of which required Government approval. There were procurement delays, particularly concerning the infrastructure component. There were also issues with the quality and delivery of technical assistance provided through ASI. The evaluation component was consequently delayed and is currently still in its inception phase. KESP scored a ‘C’ in its first Annual Review (November 2012) and a ‘B’ in its second Annual Review (conducted in July 2103, but listed in ARIES as September 2013) A third Annual Review (August 2014) again gave KESP a ‘B’ score but noted significant improvement. It was decided that an informal review of the RAF should be carried out in November 2014 and another Annual Review in February 2015. This is therefore the fourth Annual Review of the programme.

Following the Pakistan national elections in May 2013, a new reform-orientated coalition Government was appointed in KP. Taking heed of this political opportunity, a decision was taken to rethink the financial aid component of KESP and to restructure it to align more closely with Government priorities and improved implementation. Disbursements were refocused through a RAF from March to August 2014 (and subsequently extended to the end January 2015), rather than the original disbursement linked indicators. The key components of the KESP refresh (agreed between GoKP, DFID and DFAT on 31 March 2014) were:

1. Six new results areas aimed at transforming the education sector in KP. These cover: institutional strengthening, data systems, public financial management, teacher management and development, infrastructure, and access. These results areas, with associated activities to deliver individual results, are set out in the RAF.
2. A new process for assessing and agreeing how much donor funding will be disbursed to Government.
3. The development of a new ESP agreed between key partners including Government, civil society and donors.
  .
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

Since the assessment of the RAF in November 2014 the focus has been on completing all the results in the framework. Considerable progress has been made since then and all the results have now been met. A new RAF for January to June 2015 has been agreed and is being approved by GoKP. This will act as an interim document before the five-year Joint Performance Framework for the ESP begins in July 2015.

There is general realisation that short-term targeting, while setting developmental building blocks in place, is not the optimal way to bring about transformation of an education system which requires a deeper level of institutional reform and capacity building over time. The finalisation and agreement of a new five-year ESP is therefore particularly welcome and timely. This ESP has been developed by GoKP and is deemed by them to be realistic and achievable. It takes account of existing capacity in the system and is a landmark step within a longer-term vision.

It will be important for GoKP and DFID to identify key areas of the ESP where technical assistance should be focused and to concentrate a high level of quality and expertise in the technical assistance team. It will also be important for ASI to identify a pool of short-term experts who can be called upon to assist in response to unplanned priorities.

The revitalisation of the Elementary Education Foundation (EEF), the appointment of a dynamic Managing Director, and the ambitious expansion plan for new community schools and vouchers for girls, offer an exciting new platform for increased access and quality. Going forward it will be important for GoKP assessments plans to include EEF schools to ensure there is better information available about learning standards across the education system.

There have been further improvements to budgeting practices since the Department produced its first ever output-based budget for 2014-15. In December, the Education Minister launched the Department’s Portfolio Budget Statement, a comprehensive planning document which links resource allocations to the ESP and medium-term fiscal framework. By the end of January 2015, the Department was the first to submit its initial budget for 2015-16, following a consultative process with all districts to discuss and improve their budget bids. The focus on district and school level planning is vital to ensure efficient allocation of resources. It is encouraging that forward plans include working closely with a selection of districts to develop needs-based education plans and budgets.

There is strong political commitment to the RAF and to the new ESP. The working relationship between DFID and the GoKP is open and there is space for support and challenge, including through the Strategic Development Partnership Framework and the KESP Quarterly Steering Committee meetings. This relationship needs to be nurtured and maintained. The ASI technical team have made progress and have the confidence of officials but need to ensure a greater core team presence in Peshawar so that they are truly embedded in the Government system; and also re-orientate their technical skill set to support delivery of the new RAF and ESP.

Progress on the school rehabilitation and construction component continues to be delayed due to the issues concerning the service provider’s (IMC) registration with the Board of Investment (BoI). This has delayed progress from the inception to implementation phase and will have a knock-on effect on the delivery of results as stipulated by the original terms of reference.

Overall output score and description

This Review has noted significant progress on multiple fronts since the last Annual Review in August 2014. All the recommendations have now been implemented.

Vacancies have been filled, capacity developed, and a culture of lesson learning and delivery is emerging. The revitalisation of EEF will enable many more children to access education in KP in the coming year.

Budget execution has significantly improved compared with the same period in 2013-2014. Absolute spend is higher. Execution rates for the development budget and non-salary recurrent budget are 28% and 30% respectively, up from 7% and 6% respectively. E&SED was the first department to submit its budget in February 2015, for the next fiscal year, after full consultation with the districts.

While concentrating on training, building capacity, establishing systems and on institutional building, GoKP has also taken significant steps that will lead to improved quality in the classroom. These include: teacher rationalisation, the teacher continuous professional development framework, and the attention given to assessing teacher competency. Going forward, the plan to establish an assessment system to measure learning outcomes is also key.

The development of a robust data system (the IMU) to inform planning and to hold the education system to account is already bringing about reforms and clarifying where bottlenecks exist and solutions are needed. There is now a clear, realistic action plan for the next five years in the form of the ESP.

All of these achievements have led to the Review team’s recommendation that the period of intense scrutiny of KESP is no longer necessary and that DFID now revert a more regular cycle of yearly Annual Reviews from August 2015.

Key lessons

One of the key lessons has been that even when there was general consensus about RAF targets and activities to be completed, in fact they take longer than envisaged. This will be an important lesson to bear in mind as the ESP is implemented. There will need to be regular reality checks. Despite the confidence and optimism of GoKP, experience of other Government systems suggests that it is unlikely that 100% of the ESP will be realised within the allocated timeframe. It will therefore be important for donors to be clear what the triggers for funding releases will be among the many actions to be taken by Government. For DFID, the challenge will be to ensure that these triggers are the core transformative measures that will result in improved learning outcomes and will build institutional capacity.

It is a challenge for DFID to be engaged in large-scale sector reform at a distance. Security constraints limit DFID officials’ access to much of the province. Creative solutions to this challenge need to be actively sought. In addition, the situation creates greater reliance on technical assistance than is normally the case for DFID programmes.

Effective programme management of such a large-scale, multi-faceted programme is essential. There have been a marked improvement by ASI regarding programme management of the technical assistance component and it is important that this continues. In future, ASI and DFID relations need to be more open and candid with an emphasis on the challenges, barriers to progress and problem solving. For security reasons, DFID will continue to have limited access to GoKP in Peshawar. ASI must therefore track, monitor and report more effectively and regularly. The use of a dashboard reporting tool has been proposed.

Little overt attention has been given to gender issues. A discussion with the Secretary Education indicated that he was aware of this gap. It was suggested that gender-sensitive approaches might be introduced gradually, given the scale of the challenge, starting with making IMU reporting more gender sensitive and disaggregated.

GoKP has made significant progress in building district capacity. This work is ongoing and will be vital if the Local Government Act results in elections (planned for summer 2015) and subsequent devolution of authority. Delegation of more authority to schools and strengthening school leadership and management will be the next step to drive school improvement and ultimately deliver better learning outcomes for boys and girls.

Has the logframe been updated since the last review?

Yes. The logframe was revised in December 2014. A further revision is planned following this Annual Review to ensure it aligns with the new RAF (January 2015 – June 2015).

## C: DETAILED OUTPUT SCORING

Output Title	Ensuring effective service delivery
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones ( Feb 2015)	Progress
1.1 Non-salary budget allocated and spent against identified district needs.	100% of public finance RAF indicators complete (RAF 3) / Control: Internal Audit Cell is established in E&SED	Complete
	Baseline for # districts budgeting and spending school operating determined	The ongoing five district pilot will set the baseline for needs-based district budgeting
	Improved budget execution	Complete but process is ongoing. Absolute spend and % spend of budgets higher than 2013-14. Further spend in pipeline for coming months. All budget lines reported active and positive signs that GoKP is meeting own funding commitments.
1.2 IMU data informs planning and management decisions.	100% of data collection RAF indicators complete (RAF 2) / District: Monthly district stock takes and follow up action based on IMU data by DEOs / School: Timely actions to address complaints received through the complaints hotline	Complete (in at least five districts) / Complete
1.3 Civil servants and teachers have the capacity to lead and manage the education system more effectively	(1) 100% of education management RAF indicators complete (RAF 1) for: / District - Initiate training and performance evaluation of DEOs against core competencies & JDs / School - Initiate training for principals of model high schools	Complete / Complete (plan required adjustment due to security concerns but is now back on track)
1.4 Effective Technical Assistance supporting the Government to deliver	1) Government achieves 100% of RAF indicators	Complete
	2) Action plan to improve programme management in place and implementation started	An action plan has been agreed with the TA and is being monitored on a fortnightly basis
	3) ASI Invoices and monthly reports submitted on time and of an adequate quality	In progress– happening and being closely monitored

Key points

1.1 Non-salary budget allocated and spent against identified district needs

Planning: A second draft of the ESP was shared on 29 January 2015 with a wide range of stakeholders for any final inputs and comments. The ESP will be approved by the Chief Minister by February/March 2015. The review team recommend that immediate next steps should include developing an action plan for E&SED for Year One of the ESP and work should start on some preparatory activities that will help lay the foundations of the five-year reform agenda that GoKP has identified. These should include the planned sample household survey to collect data on the population of school age children in the province, to triangulate with the data collected by the IMU.

Budget execution: Education spend has picked up substantially in the last few months. As of 2 February 2015, execution of the original development and non-salary current budgets stood at 28% and 30% respectively. This is a significant improvement in performance over the same period in 2013-14 when development budget execution stood at 7% (12% if revised estimates are used) and non-salary current budget execution stood at 6%. Absolute spend volumes are also higher: Rps 2.3bn non-salary spend and Rps 5.6bn development spend, compared with Rps 0.2bn and Rps 1.6bn respectively in 2013-14. This is a particularly significant achievement given that the 2014-15 education budget itself increased by 11% compared with the original 2013-14 budget and over 30% compared with final spend in 2013-14. E&SED highlighted a number of reasons for the improved spend, including better budgeting and planning, and strong oversight by the Minister, who holds fortnightly meetings on budget execution.

Procurement challenges have delayed disbursement on certain budget lines including for furniture and teacher training but these are being actively managed. Adverse weather conditions and issues of site identification have also delayed spend on some school upgrading works. On the quality of spend, the Department reported that all budget lines were active and there had been limited re-appropriation within these, with the exception of furniture where spend was delayed and savings identified. Some disbursements have also been delayed in the interests of quality. Schools are only entitled to conditional grants once a development plan is completed. Teacher training was re-tendered several times as the quality of proposals was deemed inadequate. This demonstrates a welcome focus on the quality of spend.

Budget execution has historically picked up in the final quarter of the fiscal year. Whilst substantial spend is still expected to take place in the final quarter of 2014-15 (ending in June), it is encouraging that the Department has been able to bring forward some spend. The Department is planning large disbursements in March and is confident that its strong performance on execution will reduce the risks of in-year re-appropriation of resources away from the education sector. The release of funds from the Department of Finance has ceased to be a constraint to spend. This provides some confidence that the GoKP will continue to meet its own funding commitments on education. With the majority of the budget still to be spent, however, ongoing monitoring is essential.

Internal audit: A decision was taken in 2012-13 to pilot the concept of Internal Audit (IA) in four departments of GoKP. E&SED is the first to have a functional IA Cell in place and is so far the only department that has managed to get staff posted. Three staff members have been appointed as Internal Audit Officer and Senior Auditors. Orientation on their role of and responsibilities has begun and three days of training will be provided each month. The IA Cell will also develop an Audit Plan for the next fiscal year by June 2015.

1.2. IMU data informs planning and management decisions

IMU: The Annual Review in August 2014 recorded the establishment of the IMU as a notable success for KESP. The Review also recommended improvement in the use of IMU data – at both the provincial and district levels – for monitoring and planning purposes. There has been significant progress since August 2014. Access at the provincial level is now available in real time through the website and dashboard. Districts also have access to the dashboard. Improvements to the detail available to districts on individual schools are underway. The Department has developed detailed Standard Operating Procedures (SoPs) on the use of IMU data, to ensure consistency. DEOs now have direct access to the IMU database which provides an overview of the status of schools in their districts. DEOs are also meeting with District Monitoring Officers on a weekly basis to review IMU findings and take decisions on remedial action. District Steering Committee meetings, chaired by District Commissioners, are being held more regularly to monitor action. The frequency of these meetings varies, but there is increasing evidence that responsive action is being systematised. Some examples of this include: the rationalisation of staff in the districts of Upper Dir, Lower Dir and Lakki Marwat; actions taken to address teacher absenteeism in Abbottabad, Buner, Karak, Kohistan, Battagram, Kohat, Hangu, and Lakki Marwat; and the clearing of illegally occupied schools in Kohat.

Orientation has now been provided initially to five districts on the use of the IMU database and how this will assist them carry out their responsibilities. Initial feedback from these orientation sessions has been positive. District Managers have reported that data provided by the IMU assists them in holding schools accountable. The Department has identified a few areas where definitions of IMU indicators need greater clarity e.g. what is considered a closed school; if teacher absenteeism should exclude authorized leave; and what defines a functional facility.

School Report Cards (SRCs): These cards are the way schools display information for parents and the community. E&SED has finalised the standard information to be included on SRCs. Data on the SRCs come from the IMU. Four districts in the first phase (one from each region) including Peshawar, Abbottabad, Dir Lower and Karak are rolling out the SRCs. Eventually this roll-out will be extended to the whole province. SRCs will be updated and distributed twice a year in March and October.

Administrative visits to schools: IMU weekly monitoring reports indicate that DEOs and other administrative staff visit low-performing schools regularly. Low-performing schools are defined as schools with low teacher and student presence, or schools that are closed. DEOs take disciplinary action, including salary deduction, for unauthorised teacher absence. Records of misdemeanours are kept by the district administration.

Complaints hotline: The timely redressal of complaints lodged with the education complaints hotline was identified as a major concern during the last Annual Review. A recommendation was made for the effective monitoring and tracking of complaints to ensure resolution. Issues related to the effective use and scaling-up of the complaints hotline were also noted. Again there is positive news to report. GoKP now has a functional education complaints redressal mechanism in place. There is also evidence that there is a robust management system in place to deal with an increased level of complaints.

1.3. Civil servants have the capacity to lead and manage education systems more effectively

Management capacity building: Since the last Annual Review (August 2014) there has been steady progress on filling vacant positions. This includes key appointments in EEF. There has also been a particular emphasis on capacity building for provincial and district-level officials especially in procurement, budgeting and sector planning. Officials have also been involved in the collaborative budgeting exercise and in the ESP preparation process.

The capacity of district education staff has been identified as a major challenge. E&SED has started an intensive capacity building programme for DEOs in five districts and is currently reviewing options to expand this to all districts. The Department also plans to set individual performance targets. Progress has also been made on the approval and notification of job descriptions and core competencies. Since November 2014 they are included as part of the regular Performance Evaluation Reports (PERs) of relevant staff. Evidence provided for this Review showed that these core competencies were assessed during PERs held in December 2014.

The Provincial Institute of Teacher Education (PITE) has outsourced leadership training for the principals of Higher Secondary School (HSS). Training for the first batch of 96 principals in five districts was completed in collaboration with GIZ. As planned, training for HSS principals in the remaining 20 districts started in January 2015. This training had to be put on hold when principals were recalled to their schools to supervise security work (raising boundary walls etc.) initiated by Government, in response to the attack on the Army Public School in Peshawar. This training restarted in February and all principals of HSS will have been trained by May 2015.

1.4. Effective Technical Assistance supporting the Government to deliver

Effective Technical Assistance: GoKP has achieved the RAF targets with technical support from the ASI team, as noted in detail in various sections of the review report. Within the review period, there has been a marked improvement by ASI regarding programme management of the technical assistance component and it is important that this continues. ASI and DFID have agreed an action plan to improve the programme management framework. Fortnightly programme management progress review meetings between DFID and ASI teams have helped to identify issues, agree next steps, and monitor performance on a regular basis. Improvement in the quality of progress reports is also noted by the Review team. The ASI technical team have made progress and have the confidence of the officials but need to ensure a greater core team presence in Peshawar so that they are truly embedded in the Government system; and also re-orientate their technical skills set to support delivery of the new RAF and ESP. This view was expressed to the Annual Review team at the highest level. ASI and DFID relations need to be more open and candid with an emphasis on the challenges and barriers to progress and solutions; rather than on, albeit welcome, good news stories.

Summary of responses to issues raised in previous annual reviews

A summary of the recommendations made in the previous Annual Review and actions taken to address these recommendations follows:

ESP
  - Recommendation: The finalisation and approval of the ESP after wide consultation.
  - Action: This is on-track. It was hoped that the ESP would be approved by the Provincial Assembly so that it becomes provincial policy that future Governments would endorse.
Budget execution
  - Recommendation: Continue close monitoring of sector budget and support measures to improve expenditure on development and non-salary recurrent budgets.
  - Action: Significant progress made on improving budget execution, particularly on the development and non-salary recurrent side, compared to the situation last year.
Internal Audit
  - Recommendation: Strengthen control mechanisms, and prioritize the establishment of a fully functional Internal Audit Cell.
  - Action: This is now complete. Staff are in place and supported to develop an audit plan.
IMU
  - Recommendations: Make IMU data available to all stakeholders; and put in place realistic plans to enable public access. Improve the use of IMU data - at both the provincial and district levels – for monitoring and planning purposes.
  - Action: Evident that data are being used in planning. A plan exists to provide public access to IMU data over the next five to six months.
Complaints hotline
  - Recommendation: Ensure effective monitoring and tracking of grievance redressal system to ensure complaints are resolved.
  - Action: Complaints hotline is functional and a robust system is in place to manage. Act upon increased volume of complaints.
Others
  - Recommendation: Given the immediate importance of system-wide reforms to the success of KESP, revise the logframe to increase the impact weighting of Output One from 25% to 40% as recommended in a previous review.
  - Action: The KESP logframe was revised accordingly (December 2014).

Recommendations

E&SED should develop an action plan for ESP and focus on preparatory activities in the period leading up to ESP implementation.

DFID should continue close monitoring of budget execution and undertake regular stocktakes with ASI/GoKP to identify pipeline spend and potential challenges to execution.

IMU to undertake a review/ stock take/lessons learned on how the IMU is functioning and what improvements could be made to ensure that this is useful for policy making, operational planning and decision making, as well as monitoring and evaluation.

Output Title	Improving teaching and learning
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones ( Feb 2015)	Progress
2.1 % of teachers present at school	(1) Agreed baseline for teacher attendance established	IMU data indicate that teacher absenteeism has gone down from 30% in March to 17% in November.
2.2 GoKP actions to improve teacher quality	(1) Teacher improvement RAF indicators completed - RAF 4: / - Pilot competency test for teachers is established / - Initiate training of teachers based on approved CPD framework	Complete / Complete
	(2) Teacher quality baseline to be defined by Aug 14 (using teacher competency assessment). Teacher quality baseline established	The pilot teacher competency assessment will provide the competency baseline
2.3 GoKP actions to improve curriculum implementation and student learning assessment	(1) Timeline for future assessments agreed / (2) Assessment design and strategy agreed	Complete / Complete

Key Points

2.1 % of teachers present at school

IMU data indicate that teacher absenteeism has gone down from 30% in March to 17% in November. Teacher attendance has therefore improved from 70% to 83%.

2.2 Government actions improve teacher quality

The 2014 Annual Review recommended that the Continuing Professional Development (CPD) framework be finalised, approved and notified by E&SED and that implementation should begin as early as possible. The Review also suggested the development of a holistic approach to monitor teachers’ performance and the expansion of the teacher competency assessment to cover all teachers. The CPD framework has now been approved and notified. This is the first time that all training activities planned by the Government and service providers have been mapped onto a calendar that is being maintained by PITE. This is a positive step which will assist the Department to monitor teacher training, year on year.

Training was initiated in January 2015 for 930 Grade 2 teachers in English as the medium of instruction. The Department has plans to provide training for 23,000 primary school teachers in English, and training for over 2,000 secondary school teachers in English and Mathematics from January to June 2015. Delivery of teacher training has been outsourced to private sector service providers. The Directorate for Curriculum and Teacher Education (DCTE) is quality assuring and monitoring training and DEOs ensure all teachers participate. DCTE has had to provide significant input to refining some of the training materials developed by the outsourced service providers. This has provided a considerable learning experience. The Department has had to go through four consecutive procurement processes to receive proposals of adequate quality. This has caused a delay but reflects a commendable commitment to transparency and concern for the quality of spend.

Teacher competency assessment: In August 2014, an E&SED working group developed a set of core teaching competencies. A pilot exercise using these teacher competencies to assess teacher levels of capability has been completed in two districts. Plans to scale up are under review and are expected to be finalised in March 2015. Head teachers must now conduct competency assessments with teachers to begin building a professional development ethos in their schools. The development of a communication strategy for teachers has been recommended. This will explain to teachers how assessing core competencies will support and improve training and professional development.

Teacher recruitment and rationalisation: The Government continues to prioritise teacher rationalisation. The Government began the teacher rationalisation exercise in five target districts in April 2014. These were chosen because of high enrolment numbers and high numbers of teachers. By September 2014 this exercise had been extended to the entire province. Using a pre-defined formula, teachers were transferred from schools with surplus teachers to schools where there were teacher shortages. 4,817 teacher transfer orders (3,793 at primary level) were issued across the province. The Government immediately placed a ban on further teacher transfers in order to minimise political attempts to reverse transfer orders. Genuine requests are being reviewed by a committee and decisions taken on a case by case basis.

A study to assess the impact of the teacher rationalisation effort is currently underway. The report is expected to be available by March 2015. This is expected to:
1. Verify if teachers are in their new schools;
2. Determine the factors influencing teacher compliance; and
3. Determine the extent to which this rationalisation process has fully addressed the teacher shortage problem.

The rationalisation process appears to have experienced little resistance in KP because the Department has taken a consultative approach, engaging more with teachers and responding to some of their concerns. Teachers appear to have a higher level of trust and confidence in the Department than exists in most education systems where teachers often oppose change. Since teacher rationalisation is a continuous exercise, the current momentum needs to be maintained.

Merit-based recruitment of new teachers is also on track. To address the 14,000 vacant teaching posts, the Department recruited 8,000 new teachers in 2014 and is currently in the process of recruiting an additional 5525 teachers by March 2015. Teachers are able to choose from five options and are then assigned to specific schools.

2.3. GoKP actions to improve curriculum implementation and student learning assessment

Student assessment: A plan for a sample-based early grades student learning assessment has been approved by the Department. An implementation strategy is currently being finalised. The Department plans to conduct the first assessment in April through the Provincial Education Assessment Cell (PEAC). The purpose of this assessment is to provide information about student learning at the end of grade two to enable remedial action to be taken before children fall too far behind. The information generated by the assessment will be used to inform improved teacher training. The plan is to conduct this assessment at least annually. In addition, the Department has also finalised plans to conduct a universal Grade 5 examination in KP in April. This activity is being outsourced but managed and monitored by PEAC.

Summary of responses to issues raised in previous Annual Reviews

A summary of the recommendations made in the previous Annual Review and actions taken to address these recommendations follows:

Teacher professional development
- Recommendations: Ensure that the CPD framework is finalised, approved and notified by E&SED as early as possible. Develop a holistic approach to monitor teachers’ performance and expand the teacher competency assessment to cover all teachers and include pedagogical improvements. Strengthen E&SED capacity for teacher professional development and outsource training activities to ensure sustainability.
- Actions: The CPD Framework has been approved and E&SED is currently reviewing plans to implement the CPD Framework. E&SED has piloted the teacher competency assessment and is considering scaling up incrementally, which is a key first step in assessing teacher performance. In the period since the last review, E&SED have procured significant teacher training providers who are in the process of delivering training to teachers and head teachers.
Teacher rationalization
- Recommendation: Monitor the impact of the teacher transfers and rationalisation process to determine if the measures taken are fit for purpose and sustainable.
- Action: An evaluation of teacher rationalization exercise has been completed and is currently under review by E&SED.
Student Assessment
- Recommendations: Review institutional mandates for student assessment and develop a clear strategy going forward. If a new Examination Commission is set up, and early grade assessments conducted by this new Commission, the types of assessment that the Provincial Education Assessment Commission (PEAC) was initially established to conduct, can be merged into this Commission. This would ensure that regular, systematic and comprehensive student assessments are taking place as opposed to the current sporadic assessments through PEAC. Learning assessment should be taken forward as a matter of priority. Thought should be given to how best to embed dialogue on learning and quality at the Provincial, District and school level.
- Action: E&SED has plans to conduct universal grade 5 student learning assessment as well as a sample based student learning assessment of grade 2 learning levels in the province over the next 3-4 months.

Recommendation

Carry out an evaluation of the effectiveness of teacher training and whether it is having an impact on improving learning and incorporate the findings in future teacher training programmes
Output Title	Improving Schools
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
3.1 # schools achieving optimal (TBC) student teacher ratio (primary, middle, urban and rural, gender)	(2) Baseline student teacher ratio to be defined and future targets set, using IMU data	According to teacher allocation formula set for teacher rationalisation in the province, the target student/teacher ratio for primary schools in KP has been set at 1:40
3.2 # schools with rehabilitated infrastructure	(1) RAF indicators on PTC training complete- RAF 5: Parent Teacher Councils are supported to rehabilitate school infrastructure - Training provided to PTCs in 5 districts	In progress
	(2) Progress on rehabilitation of 36 Higher Secondary Schools	In progress

Key Points

3.1 # schools achieving optimal (TBC) student teacher ratio (primary, middle, urban and rural, gender)

PTC capacity building: The KESP programme prioritises the capacity building of Parent Teacher Councils (PTCs). E&SED approved the plan and budget for this activity in the current fiscal year (2014/15). Provincial and district focal persons have been notified and orientation has been conducted in 25 districts in which 130 district officials participated. The printing of PTC training modules is complete and training has been completed in five districts in which 56 Assistant DEOs (male and female) participated.

Since the Department had taken a decision to outsource the delivery of PTC training, there has been a lengthy and rigorous procurement process. A Project Implementation Committee and a Procurement Committee had been notified and documents for tendering were prepared. Procedures for hiring the firms for training and printing were also approved by the Project Implementation Committee. After a review of Expressions of Interest (EOIs) submitted to the Department, eight companies were shortlisted and a request for proposals (RFP) was sent to these companies requesting proposals by 12 December 2014. The printing of training modules has been completed.

These preparatory activities suggested that plans for PTC training are on-track and that training for PTCs in the first five districts would commence in January 2015 with full coverage to follow. Due to procurement irregularities the Department has had to retender the training. This is another example of the challenges of outsourcing. The Review team sees this as another effort to ensure transparency in the procurement process and not as a failure to meet a target. The Department plans to complete training for 3,000 PTCs across five districts by June 2015. The proposal and budget (P-C 1) for PTC training has been approved for three years. Therefore any unspent funds can be carried forward into the next fiscal year if necessary.

3.2 # schools with rehabilitated infrastructure

Rehabilitation of HSS: Since the last Annual Review, IMC has come on board to deliver the school buildings and construction component of KESP. The plan is to build 18,026 additional primary and secondary classrooms according to priority needs (11,137 in boys’ schools and 6,889 in girls’) starting in three districts; Mardan, Peshawar and Charsada (Swat was included originally, but because of weather conditions has been replaced by Charasada and Swat will come on stream later). Delays caused by lack of relevant data on which to prioritise need and the requirement for IMC to acquire Board of Investment (BoI) registration have resulted in a delay in moving from the inception to implementation phase. IMC has managed the extension of the inception period to the end of February 2015 constructively, by increasing preparatory activities so that they are set to begin construction as soon as the registration issue is resolved and the contract for implementation is signed.

An initial scoping study in KP indicated that 8% of schools lack proper access to their premises, 20% of schools do not have land ownership records, 81% of schools have toilets, but 44% are not connected to a water supply, and 86% have boundary walls which are incomplete. IMC flagged a considerable variance with data reported by MEAs on school facilities of between 14 and 15%. This was largely due to the interpretation of what constituted functioning school facilities. A detailed study to establish an exact baseline for the current state of facilities in those schools identified for action is underway, but is being hampered by prevailing weather conditions and will be available in March 2015. The study is intended to set a baseline to avoid duplication with the GoKP’s own construction projects.

IMC have shown flexibility and responsiveness to GoKP’s request to assist with the refurbishment of Government Higher Secondary Schools. This is an important and ambitious initiative which indicates how much GoKP is prioritising reform of the whole school system. It is frustrating for the GoKP and for DFID that progress has been slow. Initially IMC was to provide a demonstration effect in 36 Higher Secondary Schools (HSS) in Peshawar, Kohat, Nowshera, Mardan, Lower Dir and Chirtal. However as IMC are still in the inception phase, limited funds of only £3,000 per school were available for the first phase of refurbishment. The AR team were shown photographic evidence that phase one has already had impact in term of the general appearance of the schools. The second and final phase will occur once implementation begins. To date phase one has been completed in 28 of the 36 Higher Secondary Schools, (HSS) in Peshawar, Mardan, Lower Dir. Work is partially completed in Kohat and Noweshera and has yet to be initiated in Chitral because of prevailing weather conditions. IMC has agreed to refurbish all 336 HSS schools during the implementation phase.

Overall, IMC give confidence in their ability to manage this large and ambitious school infrastructure programme. They also have a robust plan to identify, manage and mitigate risk. International evidence on child-friendly classrooms is also being incorporated. IMC are working collaboratively with other parts of the DFID Pakistan education portfolio. A design competition is being run to attract innovative classroom designs from university students. The planned approach to implementation is designed to be in collaboration with Parent Teacher Councils (PTCs), local civil society and community-based organisations to ensure buy-in and ownership of the new facilities. PTCs will engage with the school development plan. This will help them identify shortfalls and school facility needs. Plans to build PTC capacity to play this role are also in place.

IMC plans to use a mix of commercial and community contracting to make the most of local communities’ skills, expertise and ability to contract at lower cost, whilst recognising capacity limitations. This approach should offer maximum efficiency and encourage community ownership of construction projects. Measures are also in place to understand the local market rates and identify opportunities for cost savings.

Summary of responses to issues raised in previous Annual Reviews (where relevant)

A summary of the recommendations made in the previous Annual Review and actions taken to address these recommendations follows:

TACE
- Recommendation: Review the timeframe for the TACE component and extend it for two years to end March 2018 allow the construction of the original number of classrooms and missing facilities. It would also bring this component in line with the timeline for the TACE PESP II component also implemented by IMC through the same contract.
- Action: A request for the extension of TACE is being made through the business case addendum which will be submitted for approval in March 2015.

Asset management
- Recommendation: Develop an asset management system at province, district and school levels to monitor the status of assets and plan for regular maintenance.
- Action: This has been put on hold due to the delays in the infrastructure work.

Recommendations

GoKP to ensure that the Communication and Works Department (responsible for infrastructure) and E&SED take account of the IMC data and share their school construction plans to enable informed planning and avoid duplication of effort.

Output Title	Every child’s right to education
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
4.1 Transition rate of children in primary school (by gender)	(1) Transition rate baseline to defined using IMU data	IMU data has only been collected since March 2014 so transition rates have yet to be established
4.2 Economic incentives provided to students, especially girls	(1) First tranche of stipends released to districts/post office	Complete
4.3 Number of additional students enrolled in the private sector	(1) Plan for the extension of the voucher programme to another 3 districts approved and implementation started	Complete

Key Points

4.1 Transition rate of children in primary school (by gender)
IMU data has only been collected since March 2014 so transition rates have yet to be established.

4.2 Economic incentives provided to students, especially girls
Stipends: GoKP is providing stipends to all girls in Grades 6 to10 attending Government schools. E&SED has taken positive steps to improve stipend delivery through joint monitoring visits by the E&SED and Post Office staff. The mechanism of distributing stipends through the Post Office appears to be working efficiently, but is highly labour intensive. The disbursement of the first tranche of stipends was completed in November 2014. In previous years the first tranche was released six to seven months into the fiscal year, so this is a considerable improvement. The second tranche is expected to be released in March 2015. There are plans to conduct an impact evaluation of the stipends programme over the next few months. This study is expected to provide useful insights into high transaction costs and the efficiency, transparency and effectiveness of the stipends programme. This will assist the Department developing a new strategy.

The last third party validation finished on 30 August 2013. DFIDP will contract a third party validation to cover from 1 September 2013 until the end of the programme.

There is still a small risk of postmen taking stipends where the recipient cannot be identified. The GoKP should continue to develop monitoring mechanisms to ensure that this does not happen. It would be helpful to consider whether it is possible to reform the system of distributing the stipends. A system where the beneficiary is linked to the money transfer forms would help reduce the risk of fraud. An electronic transfer of funds to beneficiary families would have the potential to reduce delays in the transfer of funds and reduce the risks associated with handling cash. This may link through to the current electronic system used for the distribution of payments under the Benazir Income Support Programme.

4.3 Number of additional students enrolled in the private sector
Vouchers: A voucher scheme to improve enrolment in low-cost private schools was piloted in one district (Peshawar) in 2014. The Iqra Farogh-e-Taleem Education Voucher Scheme will eventually operate throughout the province, During 2014/15, at least four districts have been proposed for roll-out. They have been selected based on those with the highest number of out of school children; and districts with the availability of private schools. According to the Pakistan Social Living Standards (PSLM) survey data, Peshawar, D.I Khan, Swat and Mardan have emerged as districts with the highest estimated out of school population between the ages of 5 and 14 in the province. A proxy indicator for the availability of private schools has also been used that measures the number of children per private school in the district. Using both criteria, Peshawar, D.I. Khan, Swat, and Mardan have been confirmed as the target districts for 2014/15. The numbers of vouchers distributed and target areas will be finalised once a firm is on board and has conducted an area needs assessment.

Based on the lessons learnt from the voucher pilot, the extended programme has decided to cover uniform and textbooks costs, in addition to tuition through the vouchers. EEF is also planning to conduct a student learning assessment in schools receiving vouchers, to assess whether vouchers are having an impact on improving quality. The rigorous use of data by EEF for planning and monitoring of the vouchers programme is commendable. Plans to disclose details of voucher beneficiaries on the EEF website will further improve transparency and credibility.

Summary of responses to issues raised in previous annual reviews

A summary of the recommendations made in the previous Annual Review and actions taken to address these recommendations follows:
Stipends
- Recommendation: Ensure an impact evaluation of the stipends programme to assess its effectiveness and suggest future design changes.
- Action: E&SED has plans to complete this impact evaluation by June 2015.
Vouchers
- Recommendation: Conduct a review of the pilot voucher scheme to improve enrolment in low-cost private schools in order to gather evidence to inform any scale-up. This should include a focus on targeting out-of-school girls and prioritising conflict-affected beneficiaries belonging to displaced families.
- Action: The review has been completed, and findings are being used for scaling up the vouchers programme to three additional districts.

Recommendations

GoKP to consider whether an electronic transfer system is appropriate for the stipends programme.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Headline VfM statement

DFID’s financial aid together with technical assistance is supporting progress on a range of system reforms aimed at improving management of the education sector and driving efficient use of resources. Examples include the establishment of an Independent Monitoring Unit which has enabled the collection of real time data on the state of service delivery and has begun to feed into better management of the sector, including identifying absenteeism and missing facilities. A province-wide rationalisation of teacher posts has led to the issue of thousands of transfer orders, which for primary alone could lead to a reduction in teacher shortages by an estimated 29%. Improvements to public financial management have played out in improved budget execution performance this year with execution of the development and non-salary budgets at 28% and 30% of the original budget respectively, up from 9% and 6% in 2013-14. Re-appropriations within the budget have reportedly been limited. The government has increased its own allocations to education by around 10% in real terms compared with spend in 2013-14. These are positive signs that DFID support has successfully encouraged additional public funding and that funds are being allocated more efficiently. New enrolment data was not available but latest estimates of per child costs suggest that it costs relatively little to support a child in school – approximately £90 per year in public school and a projected £60 per child in private school. These low costs however need to be viewed against the quality of education delivered. The government is also helping marginalised groups by enrolling out-of-school children into low cost private schools through a new voucher scheme and offering stipends to girls to attend secondary school.

There is early evidence of the impacts of these system reforms on improvements in education delivery. Teacher absenteeism was down to 17% in November from 19% in May 2014. This means that there are approximately 2,375 more teachers attending school on a daily basis. The percentage of grade 2 children able to read Urdu to the correct level rose from 13.4% in 2013 to 17.9% in 2014. These rates are still very low however and show that much more still needs to be done to improve the overall effectiveness of the system. The percentage of children able to read English fell marginally since 2013 and students’ presence rate has remained unchanged at 79% between May and November last year. Longer term impact will depend on the success of deeper reforms planned over the coming years as part of the Education Sector Plan.

Key cost drivers and performance

Sector budget support
Sector budget support is funding delivery of the GoKP development and current education budgets. Teacher salaries are the largest component of current expenditure. Allocations for pay and allowances have increased by 17% in 2014-15. Real increases in salaries are driven by additional recruitment but can also be politically motivated. Whilst salary allocations have risen, the share of the current budget allocated for non-salary spend increased to 10.7% from 4% spend in 2013-14, driven in part by better budgeting and the production of an output-based budget. The non-salary budget includes large allocations for furniture and conditional grants to schools, through PTCs, to address basic resourcing needs. The three largest allocations on the development budget are furniture, free textbooks and girls’ stipends. These comprise over 30% of the budget. Stipends are driven by set per-student rates. These have not changed in several years with the exception of recently introduced top-ups, targeting lower performing districts. Furniture costs are driven by market prices.

Infrastructure
Infrastructure is the second largest component of KESP. The supplier IMC is yet to enter implementation phase. IMC proposes a mix of commercial and community contracting, to drive down costs and draw on local resources where available. IMC estimate this approach could reduce costs by between 94% and 129% compared with government contracting. Construction costs will largely be driven by the market and availability of local suppliers.

Technical assistance
The largest costs of technical assistance are consultant fees, followed by workshop costs. A large share of consultants are locally engaged which helps ensure value for money (VfM). Programme management costs as a share of overall TA costs are reasonable. Recent increases in resourcing are intended to drive up quality management.

VfM performance compared to the original VfM proposition in the business case

Since the last Annual Review, DFID has worked with the TA to develop a VfM framework for KESP. The framework establishes indicators and has begun collecting data to monitor VfM of the programme components, including metrics identified in the business case. A full set of metrics is expected in time for the next Annual Review in August 2015.

KESP targets system reform. The success of influence and reforms in securing institutional change is therefore part of an overall assessment of VfM. There is good evidence that the results and activities framework, supported by TA and driven with the help of strong government and donor oversight, has helped to progress significant reforms. Evidence of how well these reforms have been institutionalised is harder to come by. The review heard several examples of lesson learning, suggesting reforms were being adapted and improved from within government. This included learning from the process of out-sourcing teacher training and improving district access to IMU data after piloting in one district. The introduction of regular District Steering Committees to review the IMU data and district consultations in the most recent budgeting exercise for 2015-16 are positive signals that reforms are extending beyond provincial capacity.

The average spend per child year has been revisited with IMU data from May 2014. It is estimated to have cost the GoKP £94 per child in 2013-14, £67 at primary level and £158 at secondary level. The business case estimated a unit cost for the programme of £52 but found this to be low, with no adjustments made for inflation. Costs are mostly comparable with spend per child in Punjab, primary costing marginally less and secondary costing around £40 more per child. EEF plans to enroll 30,000 students over the next year at a cost of approximately £62 per student. At input level, these unit costs offer good VfM.

Performance on learning outcomes is low with mixed signs of improvement. This suggests the programme is yet to demonstrate VfM from a quality perspective, although the impacts of reforms will admittedly take time to emerge. The 2014 ASER study reported a fall since 2013 in the percentage of children able to read English to the correct level from 6% to 4.6% and a rise in the percentage of children able to read Urdu from 13.4% to 17.9%. It is encouraging that the GoKP has agreed to conduct a DFID-backed, sample-based, learning assessment which will help set baselines to validate learning levels and enable monitoring of progress in the coming years.

The Review identified the girls’ stipends programme as an area where VfM savings might be made. The transaction costs of the current delivery system are high, and an electronic system might help reduce this, although delays in disbursements have reportedly reduced. Analysis would also help with assessing if the recent increase in stipends to two districts is optimal for achieving the programme’s aims. The GoKP has committed to a survey to review these issues.

Scale-up of EEF is expected to improve access for some of the most marginalised. The focus of the vouchers programme is almost entirely on out-of-school children from poor households. EEF is also supporting around 400 girls’ community schools and is aiming to enroll up to 10,000 girls in these schools in the coming year. These are ambitious goals and progress will need to be carefully monitored.

It is still too early in the GoKP’s financial year to judge if SBS has been additional from either a financial or outcomes perspective. Final figures for 2013-14 spend however point to a positive real increase in GoKP allocations to education in 2014-15 of around 10%, net of sector budget support. This is a significant year-on-year real increase. Dialogue around non-salary allocations and assistance to the budget office last year also helped to support a notable increase in the non-salary budget from 4% of current spend in 2013-14 to 10.7% allocation in 2014-15. Assuming budget execution continues on the same positive trajectory, there is a good likelihood that the funding will remain additional and focused on the reform agenda. It will be possible to give a better estimation of this in the next Annual Review in August 2015.

The TA has played an active role in supporting reforms. ASI cited a number of examples where capacity has been built at the provincial level, including in public financial management and strengthening of DCTE. The Review team however noted a number of areas where the VfM of TA provision could be improved, including better forward planning of TA needs and skills, improvements to recruitment processes and increased focus on skills transfer and institutional capacity building.

Assessment of whether the programme continues to represent value for money

Since 2012, KESP has spent £93m of a total combined budget from DFID and DFAT of £245m, of which 90% has been disbursed in the form of budget support. In the six months since August 2014, the programme has completed all outstanding activities against extended milestones in the RAF and, despite some challenges, is now able to highlight some significant achievements at the institutional level that, whilst difficult to quantify, have potential to secure substantial VfM savings.

Programme performance to date has been centred on institutional reforms. With the help of technical assistance, the GoKP has implemented a number of sizeable reforms aimed at improving delivery and efficiencies in the sector. The establishment of the IMU has enabled the collection of real time data on the state of service delivery and has begun to feed into management of the sector, including identifying absenteeism and missing facilities. Improvements to public financial management have included the introduction of output-based budgeting, the establishment of an internal audit cell and increasing involvement of districts in the budgeting process. Improving budget execution rates this year provide initial evidence of the effects of improved planning and financial management. A province-wide rationalisation of teacher posts has led to the issue of 4,817 transfer orders, which for primary alone could lead to a reduction in teacher shortages by an estimated 29% if orders are completed in full. EEF, following a pilot programme, is now planning to enrol up to 30,000 out-of-school children in the coming year and the launch of the ESP provides a solid basis for longer term planning across the sector. There are of course many areas where further efficiency gains can be made, including additional improvements to the use of IMU data in policy making and management and the design of the girls’ stipends programme, but the achievements to date represent a good level of progress in a challenging and low capacity environment.

VfM is less evident yet in improved educational outcomes and is ultimately what the programme will be judged on. Most outcome data for 2014 will only be available in time for the next Annual Review, including the number of children in school supported by the programme. The IMU has however been operational since March and is monitoring a number of indicators. Teacher absenteeism was down to 17% in November (the last full month of IMU data) from 19% in May when the provisional logframe baseline was set. This means that there are approximately 2,375 more teachers attending school on a daily basis. Students’ presence rate however is yet to improve and was recorded at 79% in both May and November 2014. It may be that it takes more time for improvements in the attendance rate to emerge. The rate requires further analysis and triangulation with the EMIS data which is only produced once a year.

Meanwhile, key costs are being monitored and remain broadly in line with budgets. Risk is high and reflects the fragile and conflict-affected environment in which KESP operates. This is recognised and under active management. The development of a VfM, monitoring and evidence framework is improving the availability of data to monitor and assess VfM and now needs integrating as part of regular programme management.

Summary of responses to issues raised in previous Annual Reviews

- Recommendation: Finalise and implement a comprehensive framework for tracking VfM, reporting where possible on a quarterly basis against agreed metrics.
- Action: The VfM framework has been agreed and the first update of metrics was provided in January 2015. The framework will be populated with new data as annual data sets are updated.

- Recommendation: Identify opportunities to improve data and monitoring on the part of both GoKP and KESP
- Action: DFID has continued to engage with the GoKP on improving the access and use of IMU data. In the coming months, the VFM framework is expected to be integrated with other key monitoring and evaluation information and reviewed by ASI and DFID on a quarterly basis.

- Recommendation: Engage in the evaluation design phase to ensure questions of cost effectiveness are adequately addressed.
- Action: Early engagement during an inception workshop in September 2014 on options for the evaluation. Due to various delays in the inception phase, an implementation plan is now due for presentation to DFID in March 2015.

Recommendation:

ASI need to build on the work done to develop the VfM framework and integrate other monitoring data with a view to having easily accessible monitoring information on a regular basis. This could include adopting a dashboard of key information for programme management discussions.

Quality of financial management

Technical Assistance through ASI

Technical assistance requirements are changing due to a number of factors including: 1) the six month RAF to June 2015; and 2) the new ESP clearly outlining ten policy priority areas against which the new RAF will be oriented. These areas have been considered in the contract extension for the forthcoming 20 months. ASI has improved their financial management and forecasting over the review period and will continue to do so. ASI and DFID will continue to improve the financial management by improving planning, determining future needs/ variations in advance and improving communication.

Financial Aid

£30 million has been allocated for Sector Budget Support to the GoKP in UK financial year 2014/15. £21.42 million has been disbursed on the basis of the last Annual Review and a further review of performance in November. Looking forward, an additional £8.58 million is recommended to be disbursed following the Annual Review and the GoKP achieving the outstanding RAF areas. There is currently £30 million forecast for 2015/16 and £12.3 million underspend from earlier years yet to be forecasted.

As outlined in the narrative on Output 1, budget execution has significantly improved over the last few months. The GoKP highlighted a number of large disbursements planned for the coming months, including for girls’ stipends and textbooks, and indicated confidence that strong execution will continue. Better planning was highlighted as a key driver of improved execution. The GoKP launched its portfolio budget statement in December 2014 which provides a clear forward plan for budgeting linked to the previous ESP, but it will be need to relect the revised ESP in next year’s statement.

Auditing:

The GoKP has provided an audit report for 2012/13 with eight audit observations, a number of which are still under process. The audit report of 2013/14 will be due by March 2015. The GoKP has shared the quarterly budget execution reports during the last year for KESP. The Education Directorate has also established an Internal Audit Cell which is now fully staffed and aiming to conduct its first internal audit in the next few months. This is the first fully staffed functional Internal Audit Cell across the GoKP.

Date of last narrative financial report	31-March- 2014
Date of last audited annual statement	31-March- 2014

E: RISK

Overall risk rating: High

Overview of programme risk

KESP remains a high-risk programme relying on sustainable Government reform to improve education in a fragile and conflict-affected province. These reforms are dependent on a reformist political and administrative leadership. Even with high-level political buy-in to reform, there is a risk that this will not translate into action or long-term sustainable change. The recent attack on the army school in Peshawar school underlines the fluid and high-risk operating environment.

The move from the inception phase to implementation of the school construction and rehabilitation component will also see KESP encounter new and increased risks. A further major risk is the remaining timeframe for the contract as there will not be sufficient time to deliver results as stipulated in the original terms of reference.

The short-term focus on results and moving KESP to a more stable trajectory has proved effective but remains high risk for two reasons: 1) there is less time available until the end of the programme to embed immediate well-performing reforms and/or deal with longer-term reforms; and 2) short-term term results bring a few key areas into focus, which may impact on the broader horizon of intended programme outcome.

Overview of programme risk

Access to KP, due to security issues, hampers DFID’s ability to visit and hold regular policy dialogue with Government counterparts and monitor progress supported by the technical assistance team. The KESP team therefore uses alternative methods to manage the programme, including requesting Government counterparts to travel to Islamabad for meetings and commissioning third party verifications. The programme team also works closely with the DFID Provincial Representative and other senior officials to support policy dialogue, as and when needed.

It is recommended that the DFIDP KESP team deepen their direct relationship with E&SED and that priority be given to ensuring regular visits to Peshawar, given that KESP is one of DFID’s five largest programmes.

Security is the most paramount risk. Fiduciary and corruption risks for the education sector are ‘substantial’ according to the FRA 2009 report. These risks are acknowledged and mitigation actions are in place including improving budgeting and execution processes for the current and next fiscal year, improving public financial management (PFM) systems, revising the ESP and establishing internal audit functions. GoKP, ASI and DFID work together to manage these risks and are in process of reviewing and updating the programme risk matrix.

ASI is playing a key role on risk management and has agreed to increase the focus on ‘delivery risk’ going forward.

Outstanding actions from risk assessment

The risk matrix (detailed at Annex 3) is currently being reviewed and will form part of the overall KESP delivery plan. It is recommended that this work should be expedited and the risk matrix be reviewed on a quarterly basis at the regular programme team meetings; and significant changes at the KESP Quarterly Steering Committee.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

KESP has three components:

Financial aid
KESP has spent £72.6 million to date against the proposed up to £123.5 million of financial aid in the form of sector budget support, to support the implementation of the GoKP’s previous ESP from 2012 to 2016. There was an estimated unspent balance of £28 million from last financial year at the start of 2014/15. GoKP has substantially increased its education budget in 2014-15 with an envelope of almost Rs.94 billion. Although the trend this fiscal year is encouraging compared with last three years, achieving 100% spend by 30 June 2015 remains a considerable challenge.

Technical Assistance
The technical assistance contract has been extended during the period the review covers. There was a short-term extension from October 2014 to March 2015. There were some delays in this contracting process which have now been resolved. A proposal to extend the technical assistance from March 2015 until September 2016 is currently going through the approval process. The decision was taken to issue a short term amendment before the longer term amendment in order for the supplier to be able to deliver detailed workplans against the revised RAF and ESP. The team will need to consider carefully how to manage future timelines for the technical assistance if an extension is approved.

Infrastructure component
Progress on the school rehabilitation and construction component continues to be delayed due to the issues concerning the service provider’s (IMC) registration with the Board of Investment (BoI). This has delayed progress from the inception to implementation phase and will have a knock-on effect on the delivery of results as stipulated by the original terms of reference. Implementation was expected to have started in October 2014 IMC is expected to progress from the inception phase to implementation phase soon. This component is now significantly behind schedule. It is unlikely that IMC will meet the anticipated results targets as stipulated in the original TORs within the existing programme. Extending the programme will enable the infrastructure component to be extended which will ensure that the results set out in the original TORs can be achieved.

Evaluation
Oxford Policy Management (OPM) is in the inception phase for the evaluation work. During the time period of the review a stakeholder workshop was held between DFID and OPM. However due to the slow progress of this component, , the inception phase has been extended to March 2015. This will give DFID and OPM time to identify the priorities for the evaluation and set a timeframe going forward.

Performance of partnership(s)

Technical assistance

ASI is working closely with the GoKP, DFID and other stakeholders. It has supported the Government to achieve some good progress on key education reforms over the last six months including IMU, budget execution and planning, completing the voucher pilot, and the establishment of the internal audit cell. Operational-level working relationships between GoKP officials and TA team are improving. Going forward, consistent dialogue with Government in identification of TA focus areas, competitive recruitment of technical consultants, and improved programme management performance will further strengthen the partnership. Within the review period, there has been a marked improvement by ASI regarding programme management of the technical assistance component and it is important that this continues.

The ASI technical team has made progress and has the confidence of the officials but need to ensure a greater core team presence in Peshawar so that they are truly embedded in the Government system; and also re-orientate their technical skills set to support delivery of the new RAF and ESP. ASI and DFID relations need to be more open and candid with an emphasis on the challenges and barriers to progress and solutions; rather than, albeit welcome, good news stories.

Infrastructure component
IMC have performed well during the inception phase despite many hurdles and some initial relationship building challenges. DFID is working closely and supportively with IMC to resolve issues beyond their control which are preventing the move from inception to implementation.

Other donors
DFAT funds KESP through a Development Partnership Agreement and also chairs the KP Education Donor Support Group. The EU is considering releasing funding for the ESP, using the same sector budget support mechanisms and the Joint Review Framework which is currently under development. DFID has good working relations with both partners and meets them on a formal basis every quarter and informally more frequently.

Asset monitoring and control

DFID conducted spot checks of assets of ASI in the last review in August 2014 which was satisfactory. The current review was light touch and did not focus on an asset check. The Annual Review in July/August 2015 will undertake spot checks of assets of ASI, IMC and OPM.

Outstanding actions from risk assessment

The risk matrix is being updated and will be completed in few weeks. (Early March 2015)

G: CONDITIONALITY

Update on partnership principles

DFID support to KESP is classified as Non Budget Support Financial Aid. The published business case states that funding is based on the Government of Pakistan’s commitment to poverty reduction, protection of human rights and strengthening public financial management and accountability, as set out in the UK’s ten year Development Partnership Arrangement (DPA) with Pakistan. DFID Pakistan has reviewed this arrangement periodically since it was agreed in 2006, but not published any formal assessments.

A new Partnership Principles Assessment (PPA) is being negotiated with the Government of Pakistan. This sets out the Government of Pakistan’s commitment to the four Partnership Principles as demonstrated through its policies and actions and will supersede the previous Development Partnership Arrangement. The four Partnership Principles represent a commitment to: reducing poverty and achieving the Millennium Development Goals; respecting human rights and other international obligations; strengthening financial management and accountability; and reducing the risk of funds being misused through weak administration or corruption; and a commitment to strengthening domestic accountability.

Our overall assessment is that the Federal Government of Pakistan is demonstrating a defensible commitment to the four Partnership Principles, particularly given the fragile security and the challenges of the country’s democratic evolution. Pakistan lifted the moratorium on the implementation of the death penalty following the school attack in Peshawar in December 2014. The UK remains opposed to the death penalty in all cases and will continue to raise this as a concern in our dialogue with the government. In the meantime, it would not be fair that the poorest across the country should suffer from a withdrawal or reduction of UK support. A continuing substantive direct partnership is therefore justified.

The most recent public expenditure and financial accountability assessment for Khyber Pakhtunkhwa (KP) was undertaken in 2010, with an update due by June 2015. DFID Pakistan prepared a Fiduciary Risk Assessment on the back of this assessment that rated fiduciary risk in KP as substantial, with a high risk of corruption. The most recent Annual Statement of Progress for KP, currently being completed, finds that the overall risk has not significantly changed. However, there have been continued improvements in budget preparation and budget transparency in KP, specifically related to the publication of the citizens’ budget in fiscal year 2014/15. At the same time, payroll audits in key sectors, including education, have reduced ghost workers on the GoKP payroll and identified system weaknesses that DFID TA teams and the GoKP are working to rectify. Overall, the PFM system in KP can be considered robust, but process heavy. This often delays payments and slows budget execution.

H: MONITORING & EVALUATION

Evidence and evaluation
The contract for the formal evaluation covering both KESP and PESP II was awarded in early 2013 to Oxford Policy Management (OPM). The inception phase was due to end on 31 December 2014 but is currently behind schedule and there are some concerns about implementation capacity.

Given the delay, the ToRs are no longer completely applicable or feasible. This is due to the restructuring of the programme following the KESP refresh and the difficulty of applying rigorous impact evaluation methods to ongoing processes. For example, the ToRs set out plans for an impact evaluation for the stipends programme, but for this to happen as a pure impact evaluation it would mean stopping stipends to some girls who are already receiving them in order to create a control group. This would be difficult for GoKP and potentially harmful to the recipients of the stipends. OPM and DFID had discussions on options for the evaluation going forward at a workshop in September 2014. Due to the reprioritisation of different aspects of the evaluation, the inception phase was extended to the end of March 2015.

There will be a workshop in March 2015 where OPM will present DFID with a new Evaluation Implementation Plan. This will be discussed and a decision made about the best way forward. This will take into account any approval of an overall extension to KESP.

Monitoring progress throughout the review period
The programme is monitored in several ways, internal DFID monitoring processes, monitoring the technical assistance and monitoring and senior level engagement with the GoKP.

DFID’s programme team have established a programme delivery plan in the time period of the review, this is reviewed on a weekly (workplan), monthly (finances) and quarterly (risk matrix) basis. DFID’s programme team have been monitoring the programme closely over the review period to ensure that the programme is delivering against agreed outcomes.

DFID has an agreed schedule of meetings with the TA provider to monitor progress on the programme. There is a fortnightly programme team meeting; there is also a monthly technical team meeting where the monthly report is reviewed and there is the chance for DFID to question the TA team on their deliverables. A Monitoring and Evaluation framework, including the VfM framework has been developed between DFID and ASI. This will be used on a regular basis to monitor progress on several aspects of the programme. This is not yet fully populated, as some data are only available annually, but it will be ready for the next Annual Review.

DFID meets with the GoKP formally on a quarterly basis through the KESP Quarterly Steering Committee. These meetings are attended by GoKP, DFID, other SBS donors (DFAT and EU) and the TA teams. These meetings are a useful way to make sure the programme is on-track and ensure regular formal contact with the GoKP. DFID also meets with the GoKP outside this meeting schedule when the programme demands it, however this is sometimes challenging given DFID’s security constraints in visiting Peshawar. The GoKP has its own internal monitoring processes which include budget execution meetings conducted by the Minister twice a month. DFID also has a Strategic Development Partnership Framework meeting where high-level concerns about progress or the pace of delivery are flagged to the Chief Minister

Annex 1: Results and Activities Framework March 2014- January 2015

Status- KESP Results and Activities Framework- December 2014
Updated	20/02/2015
Results Area	Results	Status of Results	Suggested Activities

1. Government prepares and enables civil servants and teachers to lead and manage the education system more effectively.	Provincial: ESED has the capacity to deliver education reform.	Complete	Fill 90% of officer positions in the provincial Secretariat, ESRU and the EEF

			Deliver management development support and opportunities to provincial civil servants
	District: DEOs will be appointed on merit and supported to succeed in their roles.	Complete	Develop core competencies / job descriptions for DEOs.

			Initiate a training programme for DEOs, including delivery to top five DEOs, based on newly-developed core competencies / job descriptions.

			Plan to evaluate performance of DEOs against core competencies / job descriptions.
			Initiate management development support and opportunities to district civil servants, tailored to their performance level.
			Post all DEOs/ SDEOs on the basis of a merit-based policy.
	School: All head teachers in model high schools are supported to succeed in their roles.	Complete	Initiate a continuous training programme for principals for all model high schools, based on newly-developed core competencies / job descriptions.

2. Government systems generate high quality data, enabling and encouraging civil servants and teachers to make decisions and take action on the basis of good evidence	Provincial: The Independent Monitoring Unit (IMU) is fully operational.	Complete	Ensure the IMU is fully staffed and functional

			Ensure the School Report Card system is ready for roll out.

	District: IMU data are used by district authorities to improve schools.	Complete	Initiate monthly stock takes based on IMU data at District Education Steering Committee meetings.

			DEOs visit at least the ten lowest performing schools in their district each month.
	School: The education complaints hotline is functioning, and communicated to students in all schools.	Complete	Rebrand the corporal punishment hotline and make initial progress towards a clear re-dressal mechanism.

			Publicise the hotline in all schools province-wide.
			Additional Activities

3. Government manages its public finances in education effectively and transparently.	Budgeting: A clear link is established between policy and resources	Complete	Revise the Education Sector Plan.
			Produce output based budget for 2014/15.
			Present Budget Execution Reports to DFID on a quarterly basis

			Additional Activities
	Control: The payroll audit is completed and internal audit cell is functional	Complete	Complete payroll audit and reconciliation in 26 districts; validation underway.

			Ensure Internal Audit Cell is staffed and functional .

			Additional Activities

	Continuous Audit: The PTC Conditional Grants programme is effectively managed using continuous audit	Complete	Provide quarterly progress reports to DFID on actions taken in response to Early Warning Reports.

			Additional Activities

4. Government provides effective teachers and opportunities for students to learn in all its schools.	Teacher Management: Teachers are recruited on the basis of merit and posted on the basis of need.	Complete	Rationalise teacher placement in five districts on the basis of needs assessment. Continue to fill vacant teaching cadre posts on merit.

			Develop job descriptions/core competencies for teaching cadres.

			Review and update existing criteria human resource management at all levels of the school system and initiate work on the development of a comprehensive standards policy

			Pilot hiring support teachers through PTCs in at least two districts.
	Teacher Improvement: Pilot competency test for teachers is established.	Complete	Commission and pilot an in-service competency assessment for teachers.
			Agree and start to implement a policy on DEO monitoring of teacher performance.
			Prepare a framework for teacher professional development

5. Government provides civil servants and teachers with working environments that are fit for purpose	School: Parent Teacher Councils are supported to rehabilitate school infrastructure	In progress	Delivery of training to Parent Teacher Councils in five districts, comprising modules on (i) roles and responsibilities; (ii) management skills; (iii) school improvement plans; (iv) and financial management.

6. Government takes steps to increase access to education for all children of school age, especially girls.	District: ESED takes an evidence-based decision on the future of the stipends programme	Complete	Review findings and use these as the basis of a policy discussion, with conclusions and next steps clearly articulated.

	School: A voucher system for access for out-of-school children to low-cost private schools in designed and pitted	Complete	Pilot voucher scheme in one district.

Results and Activities framework for February to June 2015

	Results (Outcomes)	Intermediate Results (Outputs /Milestones By June 2015)	Indicators	Evidence	Description of Activities
1	Roles and responsibilities of key provincial level institutions reviewed and streamlined	E&SED takes a decision on roles and responsibilities of DCTE and PITE and terms of reference for both institutions	Revised roles and responsibilities of PITE and DCTE agreed	Proposing revised ToR for PITE and DCTE	The roles of DCTE and PITE in certain areas are overlapping, which department is keen to segregate. The TA team has prepared an option paper to examine the current roles of the DCTE and PITE. The next step is to discuss the options presented in the paper and to make a decision about a preferred option (and/or to request more information before making a decision). As soon as a decision will be made, the terms of reference for each institution will be drafted.
2	District Education Offices monitor schools and provide support for education improvement	DEOs and/or the competent authority are supporting schools and taking timely actions to resolve issues identified through IMU data in atleast 5 districts	5 DEOs/ District Education Offices completing actions as agreed every month	Workshop reports; Action tracker; District Steering Committee meeting minutes	Capacity development workshops have been conducted in 5 districts with male and female DEO teams, to impart training on utilization, interpretation and understanding of IMU database. Purpose of the training was to enable the district education staff to plan corrective actions based on IMU data as well as efficient resource utilization. For the next planning stage, 5 more districts (5 male and 5 female DEOs) will be taken up for similar capacity development training. The modality of these trainings is the identification and setting up of simple performance indicators /targets. The TA team will follow up to help DEOs attain these targets and to monitor their achievements. Each District Education office will be supported to track issues and follow up on actions taken through monthly District Steering Committee meetings. District offices will maintain an action tracker which will be updated every month in order to review the status of actions being taken to address issues identified through the IMU data.
3	District Education Offices plan and budget effectively for education improvement	Needs based/ realistic District education plans and budgets prepared in 5 districts	5 district education plans and budgets developed	District education plans and budgets	KESP conducts regular capacity development workshops for District Budget officials which helps them to ascertain their needs and come up with a rational budget. During the current period the TA team will conduct capacity development workshops for District Budget Officials to enhance their capacity in the areas of OBB and Medium Term Budgeting. In these workshops, budgets presented by 2700 Drawing and Disbursing officers (DDOs) in the province is examined and refined to reflect assessment of needs and prioritization of resources, resulting in rational budgeting within the existing resource envelope. Taking this forward, the Department aims to develop District Education Plans and Budgets in atleast 5 districts, reflecting district level priorities and guidelines developed by KESP. District Education Plans will help the Department in strategic planning, rational budgeting and informed decision making. The plan will not only identify key issues confronting the Department at district level but will also elaborate a results chain consisting of outcomes and outputs. 5 Districts (5 male and 5 female DEOs) will be selected in consultation with the Department. Each District Education Plan will be supplemented by an Annual Action Plan, where the emphasis will be on budget utlization and implementation of decisions on IMU reports etc. Audience of these plans would be E&SED, Directorates, Line Departments, Development Partners, PTCs, Academia and Researchers.
4	IMU data is publicly accessible	IMU website operational and shared with potential users	IMU website made public	IMU website/Web Application live and accessible to users	Currently the IMU reports are provided to all districts on monthly/weekly basis for taking corrective actions. IMU website/web Application will be developed to provide live access to IMU reports individually to all DEOs of their district. Similarly public would also have limited access to the IMU web application as decided by the department.
5	Improved teacher recruitment process developed and implemented	Revised recruitment tests developed for primary and secondary school teachers	2 tests developed	Teacher recruitment tests	E&SED currently screens applicants for teaching positions via a test implemented by the National Testing Service (NTS). During this period, we will improve the quality of the test by a) agreeing minimum levels of content knowledge required for teaching at primary and secondary levels (linked to the approved curriculum) and preparing new tests for primary school teachers and secondary school teachers. (Teachers are recruited for middle, secondary and higher secondary grades and we will re-design the test for just one of these.) As part of this process, the E&SED will decide if the NTS should continue with test development or if PEAC should do this, or if another third party (not NTS) should be selected for test development.
6	E&SED provides professional development for teachers, head teachers and principals	Professional development provided to approximately 17,000 teachers and headteachers, and approximately 250 principals in higher secondary schools	17,000 teachers and headteachers trained (m/f, primary/HSS) 250 principals completing all five modules (m/f) Priorities identified and a budget developed for CPD in FY2015-16	Workshop reports/ evaluation; CPD plan and budget	E&SED plans for professional development for teachers in 2014-15 targets primary and HSS school teachers. Some of this professional development support is provided by E&SED (lesson plan training), and some by partners (in English and mathematics). E&SED aims to complete the current programme of professional development by June 2015. Activities to achieve this result include managing professional development by partners (DCTE), conducting professional development workshops (PITE and the DCTE), monitoring implementation of professional development and reporting on progress to E&SED. The Department also plans to provide professional development for principals of HSS schools. GIZ has developed five professional development modules focused on school management for HSS principals and has conducting trainings for one cohort of HSS principals. PITE will scale up this programme with the aim of having all the 355 HSS principals complete thsi training by June 2015. In addition, E&SED will be identifying teacher professional development priorities for 2015-16 during the period of this RAF and preparing a CPD calendar so that budget requirements for the next financial year can be calculated, and the mode of implementation determined.
7	Parent Teacher Councils are supporting schools effectively	Training for 3000 PTCs completed	PTCs trained	Workshop reports/ evaluation	In order to enhance capacity of PTCs, E&SED has prepared a comprehensive capacity development programme for all the members of PTCs to perform their roles and responsibilities properly. In this regard, four training modules are being prepared, which are now standard curriculum of the PTC training approved by E&SED. In the current fiscal year, 3000 PTCs will recieve training . Focus of the activities will remain on planning, effective service delivery and monitoring of the programme. E&SED will work together with service providers to develop district training workplans. Service provider will organize training workshops for the 3000 PTCs. Monitoring of the training will be jointly done by E&SED and TA.
8	Institutionalise an annual sample based assessment of student learning in early grades	Sample student learning assessment for Grade 3 students completed	Student assessment conducted in 340 schools	Assessment report	The E&SED has approved a concept note for a sample based assessment of learning at the start of grade 3. The test is the same test that has been used in Punjab and Sindh in DFID supported programmes and will test learning in three subjects: English, Urdu and mathematics. The test will be conducted in approximately 350 schools and 4500 students. Schools have been selected. The next steps are to decide if the PEAC will plan, conduct and report on the assessment or if E&SED will hire a third party to work with PEAC to conduct the assessment. Once this decision has been made, test administration protocols will be prepared, invigilators will be selected and trained and assessment will be conducted in order to establish a provincial baseline of student learning outcomes by grade 3 in the selected subjects.
9	Government supports children to attend low cost private schools	Education vouchers distributed in 3 additional districts	Children receiving vouchers	Progress report	The EEF launched the Iqra Farogh-e-Taleem Education Voucher Scheme, in 5 areas within the district of Peshawar in August 2014. 790 vouchers were redeemed by children to attend partner private schools of their choice in these areas. The programme will be expanded in 2015 to 3 additional districts in the province. TA support will center on data analysis for area and beneficiary selection, and improving M&E systems for the programme. After a firm conducts an area assessment to finalise areas for expansion and the demand for vouchers, a target for the number of vouchers distributed will be established. Evidence for this work stream will be a progress report that highlights the vouchers distributed, the areas, and the names and basic information of children receiving vouchers.
10	The government increases access to schooling for girls living in underserved areas	600 Girls' Community Schools established	Schools established and functional	EEF progress report/ IMU data	The EEF is currently supporting 194 Girls Community Schools (GCS) in the province. These schools are located in villages where there are no government girls schools present and there is demand for education. The community provides the space for a school, and nominates a female teacher from the community, while the EEF pays the teachers salary. The government is planning to expand the number of GCS in 2015. These schools will be established in under-served localities, and TA will help improve M&E systems for the programme, provide support in using data for site selection, as well as provide reccomendations for teacher training for the programme. It is expected that 600 schools will be established by the end of June 2015.

Annex 2: List of evidence

KESP Annual Review Documentation - February 2015

#	Area	Documentation
1a	Results Area 1 - DEOs	Report on workshop training to DEOs in 5 districts on the IMU and budget preparation
1b	Result Area 1 - DEOs	Training materials used for DMO Orientation (Abbottabad)
2	Results Area 2 - IMU	IMU December report
3	Results Area 3 - Internal Audit	Internal audit 3 day orientation training report
4	Results Area 3 - Budget Execution	Budget Execution Status
5a	Results Area 4 - Teacher Improvement	Report on teacher competency assessment (previously shared)
5b	Results Area 4 - Teacher Improvement	Presentation on pilot teacher competency evaluation
6	Results Area 5 - PTCs	Report on ASDEO PTC training (previously shared)
7	Programme Management	Risk Register (to be shared 28th January)
8	Programme Management	VfM / M&E framework (latest draft to be shared 28th January)
9	Results Area 2 - School Report Card	Meeting minutes with GoKP to finalise format of School report card
10	Results Area 2 - IMU	IMU DEO Action Report (example)
11	Results Area 3 - Conditional Grants	Conditional Grants Final Report
12	Results Area 4- Teacher Management	Entered Teacher transfer orders
13	Results Area 4- Teacher Management	Overview of Teacher Rationalisation Exercise
14	Results Area 4- Teacher Management	School level analysis of teacher surplus / shortage
15	Results Area 4 - Teacher Improvement	Report on a Review of the Textbook Board
16	Results Area 4 - Teacher Improvement	CPD Framework
17	Results Area 4 - Teacher Improvement	Approval of the CPD Framework
18	Results Area 4 - Teacher Improvement	Signed contracts with professional development partners
19a	Results Area 4 - Teacher Improvement	Work plans for lesson plan professional development with primary school HTs (DCTE)
19b	Results Area 4 - Teacher Improvement	Progress report on lesson plan professional development (DCTE)
19c	Results Area 4 - Teacher Improvement	Work plans for lesson plan professional development with primary school HTs PITE)
19d	Results Area 4 - Teacher Improvement	Note from PITE on lesson plan training and HSS principle training
20	Results Area 4 - Curriculum and assessment	Concept note for Grade 3 assessment
21	Results Area 4 - Curriculum and assessment	Approval of concept note for Grade 3 assessment
22	Results Area 4 - Curriculum and assessment	Formatted lesson plans for G6 (Maths, Social Studies, Urdu)
23a	Results Area 4 - Curriculum and assessment	Positive DCTE feedback on lesson plans
23b	Results Area 4 - Curriculum and assessment	DCTE approval of lesson plans ((on file at the DCTE)
24	Results Area 1 - Headteachers	Note from PITE re lesson plan training and HSS principle training (same as 19d)

Annex 3: Khyber Pakhtunkhwa Education Sector Programme (KESP): Risk Assessment
Sr #.	Risk	DFID Risk Owner	Probability	Impact	Mitigation Measures	Residual Risk
	Context
1	Political: Lack of, or reduced political will, due to different priorities or focus on other sectors. Changes of key individuals both at ministerial and bureaucratic levels resulting in shift of focus and policy in education department.	Lead Advisor	M	H	DFID and TA to work closely with the provincial government for their effective buy-in on key decisions related to this programme, and to jointly achieve education and development objectives. DFID to engage TA to focus retention of buy in from the bureaucracy and political leadership to sustain the policy changes in education sector. DFID could engagement with the Chief Minister on institutional reform. DFID to regularly visit Peshawar where possible to build relationships with E&SED	M
2	Conflict: Deteriorating security situation in the country/province Targeting of attacks on schools especially after December 16 2014 school attack in Peshawar DFID not able to travel frequently to Peshawar for monitoring of programme	Conflict Advisor/Lead Advisor	M	H	DFID to closely monitor the security situation DFID to work closely with the E&SED to improve security protocols for schools. DFID to closely monitor security situation and put in place appropriate measures.	M
3	Humanitarian Crisis: Affecting delivery of programme, either for implementing partners to deliver or changing priorities of the programme. Risk of schools being used in disaster situations as camps for IDPs, resulting in children kept out of schools Lack of disaster resilient school infrastructure	Lead Advisor	M	H	DFID to work closely with TA and its stakeholders throughout the duration of the project to monitor the situation and put processes in place to respond where necessary DFID with TA to work with E&SED to monitor the situation closely. DFID to make sure that the TACE component has all the disaster resilience SOPs included in the programme.	M
4	Macroeconomy: Deterioration in macroeconomic conditions with potential impact on fiscal space and other macroeconomic variables including inflation and exchange rates. Reduces availability of public funding for education and/or erodes the purchasing power of DFID financial aid	Lead Advisor	M	H	DFID to closely monitor the economic conditions and overall political economy of Pakistan TA to bear the potential increase in the fee costs due to inflation. Movements in exchange rate will be mitigated through pricing in GBP; while TA will closely monitor the financial and management procedures to deliver the project in time	M
5	Devolution: Local government elections not happening to time which may stall the programme activities to support devolution to the district level Lack of capacity at district level and lack of clarity of roll out of systems. Impact of sub-provincial devolution under the KP Local Government Act on the programme results	Lead Advisor	M	H	Working closely with TA to support devolution and to create a set of clear principles to roll out the systems. Working with TA to build capacity of the district level education department staff. TA and DFID to monitor impact of Local Government Act and elections closely to note key changes in the impact of the programmes.	M
	Partner/delivery
6	Inability to deliver the programme: Partners lack of capacity to deliver, due to security situation or challenge of recruiting high-quality staff to work in Peshawar Low availability of good human resource willing and able to work consistently in KP. Lack of skilled human resource in the field for adequate research and survey Poor performance: related to contractors and sub-contractors	SRO	M	H	TA to develop an extensive security plan with robust protocols in place with DFID, which will extend to all partners and third parties. TA will also regularly monitor the security situation in the country and at project sites for the safety and security of all staff and offices associated with this programme. A will adapt its programme of work as necessary to avoid areas of conflict. Closely monitoring the activities of partners and their deliverables in a timely manner, to avoid lapse in delivery and put in adequate controls to minimise problems. Extensive monitoring mechanism will be in place to tackle poor performance.	M
7	Rising costs: Due to security and access issues extra measures will be taken to implement this project which could be expensive. Rise in cost to operate in KP	SRO	M	L	TA will be required to submit to DFID updated costed work plans at the end of each phase for the subsequent phase. Deviations in cost will be monitored and managed accordingly.	M
8	Lack of engagement with other key players: Uncoordinated response to the Education Sector Plan, leading to slow delivery. Different donor priorities placing competing demands on the GoKP and limiting delivery.	SRO	L	M	DFID to encourage TA to support coordination DFID to work with TA to proactively coordinate with DFAT, EU and other DFID partners to create synergies and put all of the stakeholders under one agenda	L
	Reputational
9	Negative public opinion about the overall KESP programme: public opinion, in Pakistan and/or UK moves decisively against the project’s core objective or DFID’s funding. Negative impact of curriculum changes specifically influenced by political parties	SRO	M	H	TA programme will develop and implement a communication strategy for overall programme including this component focusing both for UK and Pakistan-based audiences. DFID to work with E&SED through TA to monitor negative curriculum policy changes and encourage the E&SED to create a positive narrative	L
	Fiduciary Risk
10	Fraud/ corruption risks: Risk of DFID funds being misappropriated GoKP fails to safeguard DFID support from ineligible areas of expenditure.	SRO	M	H	Clear guidance to partners on appropriate use of DFID funds and support to develop systems and structures to reduce the fraud risk. Third Party Audits to verify DFID expenditure.	M
11	Financial Risks: Poor government budget execution impacts on utilisation of donor funds, increasing exposure to fiduciary risk and/or weakening additionally of funding.	SRO	M	M	DFID to work with government to achieve results areas in order to disburse funds in a timely manner DFID to closely monitor budget execution.	L
12	Financial Risk on infrastructure component: Funds not spent in time, inflation, exchange rates and the independent contractor's capacity to deliver timely progress	SRO	M	M	TACE to keep a close look out on the exchange rates, price in GBP, bear overcosting, planning delivery of work accordingly to minimise falling out of timelines DFID to work with IMC put in place a clear timeline to enable delivery on time.	L