Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Assets to Adolescent Girl’s Programme (SPRING)
Programme Value:		Review Date: 15/12/2016
Programme Code: 203375	Start Date: 17/12/2013	End Date: 31/03/2022

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A	A	A+
Risk Rating	High	High	Major

Summary of progress and lessons learnt since last review

Since the last Annual Review in December 2015, the SPRING central team has been restructured and relocated from Nairobi to London to meet the needs of the programme. This has involved redesigning activities across the programme in order to strengthen support to business and girl impact, as well as the hiring and on-boarding of additional staff to fill in gaps in capacity and resource. It should be noted that relocation has not incurred additional cost, as the team are working within the original fee envelope. Feedback from donors, the Implementing Partner and Evaluation Partner is that this has been the right decision for the programme. It should be recognised that the Implementing Partner delivered this change successfully and to a very short timescale.

 Achievements over the past year include:

Successful delivery of Cohort 1 in East Africa with an End of Cohort event in Kampala in March 2016, and grant disbursements of £1m.

Two outcome milestones have been achieved and one outcome milestone has been exceeded for August 2016.

Effective recruitment and selection of 18 strong, scalable and innovative businesses and social enterprises from Bangladesh, Nepal, and Pakistan between March and June 2016.

Girl landscaping across Bangladesh, Nepal and Pakistan and business landscaping in early 2016 was used to inform SPRING’s selection, and to guide SPRING businesses and wider community in understanding and meeting girls’ needs.

Surpassing the corporate fundraising target, with £266,000 raised against a target of £250,000.

Increased social media influence, reaching over 30,000 people in SPRING target countries through Facebook campaigns alone in support of Cohort 2 outreach.

Conducted several senior partnership and thought leadership forums, and over 30 one-to-one meetings for SPRING’s corporate partnership efforts by June 2016.

Strengthened M&E system and support team to capture SPRING’s contributions to business and adaptations to the programme.

Summary of recommendations for the next year

The SPRING programme is performing to a high standard, meeting or exceeding most of its outcome targets, however the output targets are either being slightly missed, just met or only slightly exceeded. A review of the logframe is taking place in December 2016, which should consider whether adjustments are necessary and whether outputs are still fit for purpose.

The extent to which businesses will continue to target girls beyond their participation in SPRING is not yet clear. It is important that this is recorded and tracked over time. The Implementing Partner will continue to collect KPI data from businesses for 2 years, and will be analysed and reported on by the evaluation partner to see if businesses continue to increase their reach of girls, or if this reduces over time. The evaluation partner should also place a greater focus on digging down into the business case for targeting adolescent girls as part of the Business Performance Evaluation, and following up with businesses post cohort completion to see if the SPRING support continues to guide their approach and business model in the future.

SPRING should revisit the design of their investment support. The programme should make it explicit that not all businesses will received the same level of investment readiness support, and explain what factors and criteria will drive the level of support provided. SPRING should review the current timelines for investment readiness support and consider shifting the most intense support into the Alumni period.

The Implementing Partner and the donor groups should work together to agree a clear governance structure on the dissemination of knowledge products.

The VfM indicators agreed for this Annual Review should be incorporated into the Implementing Partner’s VfM framework and reported against in future annual reviews to ensure they are consistently measured on a year by year basis.

Progress against recommendations from Annual Review December 2015

2015 recommendations	Action
The design of the application, selection and due diligence processes for Cohort 2 should integrate learnings from Cohort 1. The approach to recruitment and selection of Cohort 2 should be finalised by February 2016.	Completed - SPRING has incorporated many lessons from Cohort 1 into the design of Cohort 2. These changes are documented in the Coffey PPE and SPRING annual review 2016.
Complete recruitment of the Implementing Partner’s London based team by January 2016.	Completed
Develop a fundraising plan with clear milestones by March 2016, with an explicit decision point in June 2017 on achievement of fundraising targets for Cohort 4.	Completed - Plan in place and SPRING has exceeded its fundraising target. DFAT contribution has secured funds for Cohort 4.
The Implementing Partner should undertake context analysis, drawing on existing networks and information as well as landscaping visits by February 2016 to ensure that the rollout to South Asian countries is successful.	Completed - Undertook girl landscaping across Bangladesh, Nepal and Pakistan, business landscaping in Feb and Mar 2016 and two research trips across Pakistan in Apr 2016. Insights informed outreach and selection process.
For Output 1 on entrepreneurs increasing the number of girls reached, the Implementing Partner should ensure that the KPI form collects this data reliably, establishing baselines and performance against progress indicators in time for the next AR.	Completed – Implementing Partner implemented a comprehensive M&E system to address this.
The Implementing Partner should provide (1) the checklist and criteria used to assess investor readiness and (2) the criteria to decide whether enterprises are seeking external capital, by December 2015. This is necessary in order to establish a baseline for Cohort 1 and to be able to assess progress for the next AR. The checklist and criteria should be agreed by the donor and independent M&E Partner. For Cohort 2, the Implementing Partner should include investment readiness checkpoints in the grant agreements.	In progress - implemented the investor checklist / Following another recommendation, investor readiness has moved to Boot Camp 2 and beyond. The grant agreements are now focussed primarily on prototype development not investment. Therefore there will likely be only a few companies for whom both investment readiness support and prototype development funds overlap. Where they do, the Implementing Partner would include investor readiness checkpoints in the prototype fund agreements. This will be decided after Boot Camp 2 when the Implementing Partner has put together the ecosystem of support and figured out plans for which businesses they believe they can support to get funding.
The Implementing Partner should revise the design of bootcamp for Cohort 2 – to reflect lessons and feedback from this first year. The grants process and information provided to entrepreneurs should be clear, breaks should be incorporated into the bootcamp schedule (so that it is not two weeks at one time) and customised support to entrepreneurs should be maintained by limiting the number of entrepreneurs to 20 at maximum per cohort.	Completed – Boot camp for Cohort 2 was designed based on feedback from Cohort 1. SPRING received good feedback from businesses participating in Cohort 2 Boot camp 1, meeting almost all the entrepreneurs’ expectations.
The Implementing Partner and M&E Partner should agree criteria on quality, content and relevance for which communications from the programme meet the requirements of the output indicator on communication of evidence by January 2016.	Discussions were held in 2015 concerning measuring the ‘quality, content and relevant’ but this proved challenging as these are fairly subjective. As a result the logframe indicator was changed to “Number of communications products with evidence and or lessons learned produced and disseminated by implementing partner”
The M&E Partner should develop methodology for independently verifying the value of in-kind contributions to the programme by January 2016.	Completed – SPRING has refined what they classify as in-kind contributions and developed a clearer framework which tracks contributions from corporates outside of the programme team. M&E partner is in the process of finishing their assessment on in-kind contributions for far.
The Implementing Partner should propose a set of indicators for monitoring value for money performance consistently over time for future Annual Reviews. These indicators should be agreed with the donor team and M&E Partner by March 2016.	Completed – SPRING worked with Coffey to come up with VfM framework. Following feedback from DFID, SPRING has included indicators that will be reported on at each annual review. SPRING will update their VfM framework to reflect these indicators.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	203375 documents
DevTracker Link to Log frame:	203375 documents

Outline of the programme

The SPRING programme works as a business accelerator. It will identify a mix of early-stage and later-stage businesses with products that can improve the lives of girls and provide support to these businesses to enable them to reach girls at scale. The support provided will include access to mentors, expertise, girl research, funding and peer-to-peer learning to help drive their business models forward. The businesses supported by SPRING will have products that help girls to safely learn, earn, save and invest. SPRING is a five year programme that started in Kenya, Uganda and Rwanda in Cohort 1 and will roll out to six more countries across Africa and Asia in later cohorts.

SPRING is currently going through a contract amendment to include DFAT (Australia) as an additional donor, which will contribute to the delivery of Cohort 4 and enable the programme to expand to Burma.

Expected results

Over five years, the programme aims to support at least 58 entrepreneurs in eight countries (rising to 78 businesses in nine countries with the addition of Cohort 4) and is expected to deliver the following results by 2019:
- Delivery of entrepreneurs’ products and services that enhance the economic outcomes of up to 200,000 girls.
- Improved entrepreneurs’ business performance e.g. new market entry and investment.
- An enhanced strategic evidence base to inform future girl programming and attract donor, government and private sector investment.
- Effective communication and dissemination of evidence gathered.

Contribution to DFID’s Objectives

Economic assets are the building block of economic and social progress. Products and services, in the SPRING context, are assets. An asset can generate income, enhance productivity, facilitate access to capital and credit, and store wealth. It strengthens the owner’s capacity to cope with and respond to shocks by enabling them to diversify income and smooth consumption. Assets can also contribute directly to girls’ economic empowerment by reducing their time-poverty and enabling them to stay in school.

The economic empowerment of girls and women, and their ownership of assets is a strategic priority for DFID. The UK Aid Strategy prioritises the needs of girls and women. DFID’s Strategic Vision for Girls and Women highlights economic empowerment, and especially access to assets. The Economic Development Strategic Frameworks emphasises improved access to markets, finance, property and employment opportunities for girls and women.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

SPRING’s expected outcome is for enterprises to provide market-based solutions (i.e. products and services) that can benefit girls and contribute to their economic empowerment. Under this outcome, the SPRING logframe tracks: (1) the number of enterprises that attract external investment attributable to participation in SPRING; (2) the number of adolescent girls accessing products and services or involved in the business operations, and (3) the number of entrepreneurs who have increased sales from products, services, or business models benefitting girls by 20% or more.

Progress against Outcome Targets is provided below. According to the figures provided by the Implementing Partner (IP) - which were validated by the Evaluation Partner where possible - the indicator targets have been achieved.

Overall output score and description

Indicator(s)	Milestones	Progress
OI1. Number of grantees that attract external investment attributable to participation in SPRING	3	3
OI2. Number of adolescent girls accessing grantee products and services, or involved in the business operations	8,152	10,537
OI3. Number of grantees who have increased sales from products, services, or business models benefitting girls by 20% or more	9	10

Outcome Indicator 1: The target has been met. The KPI forms indicate that SPRING support helped three businesses (Ensibuuko, Sanivation and Totohealth) to raise additional investment, totalling £610,000. Another four businesses raised additional investment, but did not attribute this to SPRING.

It is possible that there was some underreporting in this area by the businesses, as one business highlighted the sensitive nature of the data and a perceived risk that external reporting on investment may be available to their competitors, therefore potentially negatively affecting the investment. The IP plans to address this in Cohort 2 by ensuring confidentiality protocols are clear to businesses.

Outcome Indicator 2: This target has been exceeded. Data from the KPI forms show that businesses managed to reach around 10,500 girl beneficiaries overall. Among the beneficiaries, almost 9,000 are purchasers or end users of the products and about 1,000 are girls in value chains, as shown in Figure 1 below. The number of adolescent girls reached varies a lot across businesses, with only three businesses (BanaPads, Ensibuuko and Toto Health) accounting for more than 8,000 beneficiaries.

Figure 1: Number of adolescent girls accessing grantee products and services, or involved in the business operations
(Source: Business KPI Reporting, June 2016 – June 2017)

Outcome Indicator 3: This target has been exceeded. By July 2016, 10 of the 18 businesses in Cohort 1 managed to increase their sales from products, services, or business models benefitting girls by 20% or more. Of these, seven enterprises grew their sales revenues by more than 100%.

KPI spot checks with one third of businesses were conducted by the Evaluation Partner to confirm this sales figure. During some of these meetings, some businesses indicated that they may not continue with their SPRING product. For example, Ensibuuko will apparently no longer focus on a unique girl-focused saving account. The question of sustainability should be explored further in future cohorts.

Key lessons
- There is an implicit assumption in the Theory of Change (TOC) that a majority of SPRING businesses will be ready to attract and secure investment within the nine-month cohort phase. In reality, many of the businesses in Cohort 1 were in a too-early stage to reach this status within nine months and many were looking for grant funding rather than mainstream investment.
- There is a need to include sustainability indicators that track the incentives for businesses to continue engaging with girls beyond SPRING. The M&E team will focus on this more explicitly as part of the Business Performance Evaluation from Cohort 2 onwards.
- The main finding from the spot check on KPI data was that data could not always be mirrored due to a reliance on paper records that were often located in dispersed locations. The IP has responded to this by ensuring that Country Managers (CMs) are more responsible for conducting quality checks of KPI data before it is submitted. Additionally, later stage Cohort 2 businesses should have fewer issues as a number of them already have advanced methods of capturing and reporting data.

Key actions
- During the TOC workshop in December 2016, it should be considered whether there will be a knock on effect at the outcome and impact level if businesses are not investment ready during the cohort. It should be assessed whether Cohort 2 is likely to present similar or other challenges with regards to investment readiness. It is clear that businesses have been able to gain investments, but these have not been attributed to SPRING.
- CMs will be responsible for collecting data on positive and negative unintended consequences. Conversations with the IP showed that asking businesses to report on negative consequences in writing may elicit fewer and less accurate results. As a result more informal one-to-one conversations with CMs was seen as a more effective methodology for gathering this sensitive information.
- Sustainability indicators will be enhanced in the evaluation framework and these questions will be answered in the Business Performance Evaluation.

Has the logframe been updated since the last review?

No, but a workshop to examine and update the logframe is scheduled for December 2016.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	SPRING grantees reach adolescent girls
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
1.1 Number (% in brackets) of grantees that increase the number of girls reached with products and services or increase the number of girls involved in business operations	14 (80% in C1)	16 (89% in C1)

Key Points

As part of the End of Cohort survey, businesses were asked if SPRING had helped them to increase their reach of adolescent girls. 15 businesses agreed, while two were undecided, and one business did not respond. By June 2016, KPI reporting showed that 16 of the 18 businesses reported having increased their girl reach since baseline, amounting to a total net increase of 9302 girls from their baselines. Four businesses have increased their reach by more than 1000 girls: BanaPads (4980 at baseline, 8586 after Year 1), Ensibuuko (0 at baseline, 3000 after Year 1), Finance Trust Bank (11753 at baseline, 12740 after Year 1) and Toto Health (325 at baseline, 1434 after Year 1).

These figures provide a different view to the absolute reach numbers for Outcome Indicator 2. It is apparent that or some businesses, particularly those without a prior focus on girls, a small absolute increase of 10-50 girls in the value chain required a very significant effort.

This output had its first milestone in August 2016 which is why the impact weighting for the Annual Review has increased from 0 to 30%.

Summary of responses to issues raised in previous annual reviews (where relevant)

After extensive discussion regarding the measurement of girls reached looking only at Base of Pyramid (BoP) girls, it was agreed in the M&E Planning workshop in August 2016 that all girls in SPRING’s age range would count towards the girl reach metrics in the logframe. During these discussions it was agreed that the very poorest girls are unlikely to be a viable target for businesses, and given the lack of clear definition of “BoP”, and the capacity of businesses to measure and track girls, it is not strictly necessary for SPRING’s performance to be measured by BoP girls reached only. The selection of businesses will be constrained to focus on pro-poor products and services, but programme reported results will not be restricted to counting girls at the BoP only. The evaluation team will continue record estimates on the number of girls reached by each business that are considered BoP to ensure the pro-poor aspect of SPRING is captured in impact evaluations.

Recommendations
The extent to which businesses will continue to target girls beyond participation in the programme is not yet clear. It is important that this is recorded and tracked overtime. The IP will continue to collect KPI data from businesses for 2 years, and will be analysed and reported on by the evaluation partner to see if businesses continue to increase their reach of girls, or if this reduces over time. The evaluation partner should also place a greater focus on digging down into the business case for targeting adolescent girls as part of the Business Performance Evaluation, and following up with businesses post cohort completion to see if the SPRING support continues to guide their approach and business model in the future.
Output Title	SPRING grantees improve their investor-readiness
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Number (% in brackets) of grantees who have improved their investment readiness (of those how were looking for mainstream investment	4 (25% in C1)	4 (25%)

Key Points

During the Programme Performance Evaluation (PPE) review, businesses were asked if they felt that SPRING had helped improve their investment readiness, both in the end of cohort survey (completed by all 18 businesses), and in Semi-Structured interviews at the end of the cohort (9 businesses). The majority (10) of businesses reported in the End-of-Cohort Survey that their investment readiness had improved, while 5 were undecided and 2 disagreed.

Interview responses however, suggest that many businesses did not focus on attracting mainstream investment in Cohort 1. This was either because they prioritised grant funding, or because they were still working out business fundamentals (e.g. hiring staff, setting up financial management systems, etc.). For most respondents, improving Investment Readiness meant strengthening business models, operational systems, and basic documentation.

The Implementing Partner helped four businesses become more aware of mainstream investor requirements and improved their investment readiness: Jibu, KadAfrica, Ensibuuko and Bana.

PPE findings show that businesses need to build a solid business before they can begin to improve their investment readiness. The IP have indicated that they will respond to this finding in Cohort 2 by providing this support later in the cohort.

This output had its first milestone in August 2016, which is why the impact weighting for the Annual Review has increased from 0 to 25%.

Recommendations

The Implementing Partner developed an ‘Investment Readiness Checklist’ to track and record the investment readiness of businesses throughout the cohort. This was initially completed following boot camp, and updated throughout the cohort. However, this information was only tracked for those businesses seeking mainstream investment. This meant that when the PPE review was conducted, the evaluation partner was not able to track changes to the investment readiness of all businesses in the Cohort. SPRING should consider if investment readiness can be tracked across the full set of business, rather that only those seeking mainstream investment.

Make it explicit that not all businesses will receive the same level of investment readiness support, and explain what factors and criteria will drive the level of support provided.

Review the current timelines for investment readiness support and consider shifting the most intense support into the Alumni period.

Output Title	Grantees benefit from HCD and other forms of SPRING TA to improve business viability and develop products and services benefiting girls
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 Number of grantees (% in brackets) who report satisfaction with the HCD and other technical assistance provided through SPRING	August 2016: 14 (75% in C1)	18 (100% in C1)
3.2 Number of grantees who use HCD to refine their business model, product or service to meet the needs of target girls.	August 2016: 14 (75%)	16 (89%)

Key Points
A key priority for the Implementing Partner was to maximise their HCD and technical support to businesses. Lesson learning from Cohort 1 was key to redesigning Cohort 2.

Output Indicator 3.1: As part of the PPE review for Cohort 1, the evaluation partner conducted surveys at Boot Camp and end of cohort events with all businesses, and semi-structured interviews with 9 businesses. As part of the End-of-Cohort Survey in March 2016, businesses were asked “How satisfied are you with the support SPRING has provided to your business?” 10 businesses responded ‘Very Satisfied” while the remaining 8 responded “Satisfied”. Many highlighted how much they had appreciated working with fuseproject.

Additionally, the End-of-Cohort Survey asked businesses to rate the statement “The SPRING support met my businesses’ needs” on a Scale of 1 to 5 (with 1 being “strongly disagree” and 5 “strongly agree”). All businesses except for one said that the interventions and changes suggested by SPRING aligned well with their strategic priorities. In the qualitative interviews, entrepreneurs also overwhelmingly confirmed that theirs’ and SPRING’s priorities were aligned.

The evaluation partner conducted a survey with all businesses in Boot Camp 1 for Cohort 2 in September. Although the timing of this survey falls outside of the target timeline for this Annual Review, the findings from this survey provide an early indication of satisfaction from Cohort 2 participants. Overall, most entrepreneurs reported that the Bootcamp had either ‘exceeded’ their expectations (10 entrepreneurs) or met their expectations (6 entrepreneurs). Two responded that the Boot Camp had met ‘some’ of their expectations.

Output Indicator 3.2: The majority of Cohort 1 businesses interviewed were new to HCD at the start of Boot Camp. All businesses reported that they absorbed the HCD training to varying degrees, and with varying degrees of ease.

One business interviewed in Cohort 1 said that SPRING could benefit from having people in the HCD team who have more ‘local knowledge’ and this statement was echoed in the spot checks. SPRING is already planning to involve local moderators more closely in the HCD training and girl research in Cohort 2, as a means to extend the support to all businesses and build more local ownership.[1]
[1] It is planned that these moderators will get to know businesses at Boot Camp and then assist them in preparing and setting up their girl research sessions, taking some of the logistical burden off fuseproject. This will allow moderators and entrepreneurs to be more involved in the preparation of research tools, and to make these as context-specific as they see fit.

In the SPRING End-Of-Cohort Survey, all entrepreneurs reported that they had used HCD principles to refine their product, service, or business model in one way or another. 17 out of 18 businesses reported that they designed a prototype, and 16 said they went on to test it. Only 12 businesses said that they had refined their prototype, which may reflect the fact that designing, testing and refining a prototype is an iterative process that takes some time. Some businesses did not get to the point of refining their prototype during the cohort. In the qualitative interviews, all of the 9 businesses interviewed explained that they changed the way of doing business as a result of learning about HCD and improving different aspects of their business strategy.

Additional evidence provided by SPRING and agreed by Coffey demonstrates that 16 out of 18 businesses used HCD in a meaningful way related to their prototype.

The impact weighting has reduced from 67% to 30% because two other outputs are reporting milestones for the first time in this annual review.

Recommendations

To support businesses further, local moderators should work closely in the HCD training and girls research.

Output Title	Market stimulation for products and services benefitting adolescent girls.
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
4.1 Number of applications received that meet SPRING eligibility criteria (number of total applications in brackets).	August 2016: 275 (430) (cumulative)	223 (325) (cumulative)
4.2 Number of communications products with evidence and or lessons learned produced and disseminated by implementing partner.	August 2016: 7 (cumulative)	8
4.3 Funds raised by SPRING implementing partner through cash and in-kind equivalent contribution	£250,000 (cumulative)	£266,000

Output Indicator 4.1: In Cohort 1 146 businesses out of 245 applications met the SPRING eligibility criteria. Based on lessons learned from Cohort 1, SPRING has made changes to its Cohort 2 outreach to focus on sourcing quality applications. The Implementing Partner (IP) reports that due to more stringent adherence criteria for Cohort 2 (e.g. requiring certain financial and prototype submissions), there have been fewer applications. In Cohort 2 77 businesses out of 80 applications met SPRING criteria, therefore cumulative progress is 223 (325). SPRING argues that while the number of applications for Cohort 2 is lower than for Cohort 1, they have had a stronger, more diverse cohort, with more alignment to SPRING’s mission, and a higher proportion of eligible applicants because of more targeted outreach.

Output Indicator 4.2: SPRING developed three knowledge products in Cohort 1 and a further five in Cohort 2. These include: Bootcamp film, Vanity Fair article, Vanity Fair film, a HCD film, Girls in South Asia and supporting sector insights reports, and three girl landscaping reports for Pakistan, Nepal and Bangladesh. While the majority of these products are publicly available, the work on Girls in South Asia Insights and supporting sector briefs are only available to the donors. The IP has raised concerns that there is a lack of clear governance over when/how knowledge products can be shared externally.

Output Indicator 4.3 the IP has reported that it has exceeded this milestone, raising £266,000 from in-kind support from corporates and professionals, cash donation, and pro-bono contributions. The evaluation partner is responsible for verifying this amount, but has not yet finalised the verification.

The impact weighting for this milestone has reduced from 33% to 15% because two other outputs are reporting milestones for this first time in this annual review. Despite output indicators 4.2 and 4.3 exceeding expectation, 4.1 has been missed therefore this output has received a score of A.

Recommendations

- The indicators for this output could be reviewed during the planned Theory of Change review in December to ensure they are still fit for purpose. For example, the Implementing Partner has used lesson learning from Cohort 1 to better target business. Indicator 4.1 may unduly penalise the IP for achieving a smaller number of quality applications and does not reflect their approach to outreach.
- The IP and the donor group should work together to come up with a clear governance structure on the agreement and dissemination of knowledge products.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

As of 31st October 2016 the programme has spent 46% (£6,185,167) of the total budget. This represents a 24% rise on spending as reported in the last annual review. The increase in spending reflects the increase in programme activities over the last year.
Of the total spending to date, 46% has come from personnel fees (excluding fuseproject). The key cost driver of the programme to date has been project expenses representing 54% of the total spend to date. Of project expenses spend, 88% comes from programme activities, primarily driven by fuseproject costs, grant spending and support to entrepreneurs. The remaining 12% accounts for travel, equipment and operating costs. Travel costs have gone up in the last year due to more expensive flights in Asia (especially regional flights within Asia). Travel costs are expected to remain high in Cohort 3 as regional flights in East Africa have also become more expensive. SPRING has raised this issue with the SRO.
VfM performance compared to the original VfM proposition in the business case

In 2016 SPRING revised its VfM framework in partnership with Coffey to align its work with DFID’s approach to VfM. The VfM framework has a set of indicators under the 3 E’s of VfM (Economy, Efficiency and Effectiveness) to measure progress across the lifetime of the programme. Following feedback during this year’s annual review process, the Implementing Partner has further refined the VfM indicators to ensure they are consistently measured on a year by year basis.

Economy (minimising input cost)

Contributions raised by SPRING through in-kind equivalent contributions (in GBP)
The last annual review provided an estimate on the pro-bono time donated to the programme. Since then, the implementing partner has refined what it classifies as in-kind contributions and developed a clearer framework which tracks contributions from corporates outside of the programme team. As such, the figures reported for this annual review do not include the contributions reported in last year’s annual review. The table below outlines the total cumulative in-kind contribution up until 31st October 2016.
Item Description	Name of Expert	Days / Hours	Normal full cost (GBP)	Cost to SPRING (GBP)	Total in-kind contribution (GBP)
Event space, catering	The Foundation	1	£300	£0.00	£300
Facilitation and organization of corporate event	Charlie Dawson, Partner, The Foundation	3.5	£13,125	£0.00	£13,125
Legal advice on grant management for Cohort 2	Anjan Neupane, Partner, Neupane Law Associates	0.2	£20	£0.00	£20
Hogan Lovells - Pro Bono Legal support	Several senior and junior staff	50	£183,992	£0.00	£183,992
Arachnys license to D3 platform to conduct commercial due diligence on Cohort 2 businesses	David Buxton, CEO Arachnys company	1	£20,000	£0.00	£20,000
Independent senior professionals conducting commercial due diligence on Cohort 2 businesses	Eight professionals from finance, regulatory and legal firms and related backgrounds	80	£32,000	£0.00	£32,000
Hogan Lovells - Pro Bono Legal support - Bootcamp 1 Cohort 2	Associate Lawyer provision of legal support in second week of C2 BC1	6	£17,200	£0.00	£17,200
Videography services; raw footage	Kit Wheldale	12	£5,160	£0.00	£5,160
Facebook outreach ad	Facebook	1	£43	£0.00	£43
Total			£271,840	£0.00	£271,840

Cumulative cost savings (in GBP)

This indicator provides a measure of the total amount of money saved through negotiated savings from time and resources. As of 31st October 2016 we have made a cumulative savings of £40,330 summarised in the table below. These savings are primarily driven by negotiated office rent and website redesign.

Item Description	Normal full cost (GBP)	Cost to SPRING (GBP)	Total negotiated savings (GBP)
Office space and office equipment: first contract for initial 6 months	£25,200	£18,000	£7,200
Office space and office equipment: second contract for 12 months	£62,400	£46,800	£15,600
Marketing and Comms services; project management of procured design agency (Vicky Grinnell-Wright)	£9,000	£4,500	£4,500
Website Design and Development by Agency Mobile	£21,330	£8,500	£12,830
Event space, catering and service from Second Home.	£400	£200	£200

Total	£118,330	£78,000	£40,330

Efficiency (conversion of inputs to outputs)

Percentage (%) of milestone deliverables met on time
To date, the programme has delivered 100% of its milestones on time. This has been achieved despite increased scope of activities as a result of the programme’s redesign in contract amendment 2. These changes include relocation of programme’s operations from Nairobi to London; hiring of a new a core team for London and a South Asia regional management team and delivery of a redesigned cohort experience, including a doubling of boot camps.
Management costs as % of total cost
At inception the benchmark Management/Admin costs as % of total costs was set at 8% and reported at 11% as of 30th September 2015. This was calculated by including all days for Operational and Admin positions, as well as the Operating costs incurred from the start of the project to September 2015. This figure currently stands at 9% as of 30th October 2016.
Cost (in GBP) for regional expenses for programme activity (Boot camp)

This indicator will be reported on in the next Annual Review. The new indicator will provide a measure of cost improvements across cohorts that are comparable. The Implementing Partner is currently closing their Cohort 2 Bootcamp 1 and will provide the benchmark figure for this indicator once the full data is available.

Effectiveness (increasing value)

Costs (in GBP) per business compared with value delivered per business of services
This indicator is measured by comparing the 'market rate' costs of what it would take for a company to commission fuseproject to do a similar level of activity, versus the economy of scale inherent in doing this in a cohort of 18 (or in future, 20) businesses. The Implementing Partner is using a blended fee rate of £1,566 as the benchmark for fuseproject (aligning to global benchmarks for leading design agencies). They estimate the cost per business working independently to be £131,544 if sourced open market, compared against £34,641 through SPRING.
Cost (in GBP) per girl reached
This indicator is measured in terms of the actual number of girls reached against total programme cost. The total number of girl reached by September 2016 is 10,537. The cost per girl reached up to September 2016 is £542.

Assessment of whether the programme continues to represent value for money

From the evidence available as set out above, the programme continues to provide value for money. A fuller value for money assessment will be possible next year as progress across all the indicators above is consistently tracked over time.

Quality of financial management

Palladium maintains a best practice variance tolerance benchmark between forecasting and actuals of 5%. SPRING exceeded the 5% variance once in September 2015 due to unanticipated activities caused by the relocation of project headquarters from Nairobi to London and the subsequent change to personnel.

	Actual	Forecast	Variance	%
Jul-15	£197,874	£191,955	-5,919	-3.08%
Aug-15	£350,073	£341,212	-8,861	-2.60%
Sept-15	£337,228	£317,480	-19,748	-6.22%
Oct-15	£221,053	£222,499	1,446	0.65%
Nov-15	£602,604	£604,018	1,414	0.23%
Dec-15	£161,164	£158,415	-2,749	-1.74%
Jan-16	£85,943	£87,031	1,088	1.25%
Feb-16	£277,262	£287,070	9,808	3.42%
Mar-16	£369,019	£370,639	1,617	0.44%
Apr-16	£527,587	£514,097	-13,490	-2.62%
May-16	£216,587	£216,887	291	0.13%
Jun-16	£120,987	£121,042	55	0.05%

In July, Palladium introduced a new system Enterprise Resource Platform (ERP) as part of their continuous effort to improve the systems supporting the delivery of products. The new ERP will provide a single platform that integrates all their processes for Human Resources, Finance, Operations and other management functions. It will enable Palladium to triangulate management information from different sources, thereby enhancing their ability to provide robust management data, identify errors, expand and optimise record keeping and meet compliance obligations in an increasingly complex environment.
Palladium experienced some delays in the implementation of accounting and timekeeping component of the new system which resulted in delay for the July invoice, and meant they missed their forecast. Since then, Palladium has delivered monthly invoices and forecasts on time and within 2% variance. Furthermore, in discussion with DFID, Palladium now includes a grants line in their monthly forecast to give a more detailed account of our forecasting.

Date of last narrative financial report	30 September 2016
Date of last audited annual statement	31 December 2015

E: RISK (½ page)

Overall risk rating: Major

SPRING is a high risk programme. It has been explicitly designed to test assumptions and build evidence in an area where the evidence base is weak. The evidence on women’s ownership of assets is clear in terms of development benefits, but evidence on girls is not readily available. Moreover, using a private sector development approach to improve girls’ ownership of assets is a novel approach. Rigorous monitoring and evaluation, and continuous focus on research are critical to the success of this initiative, given the experimental nature of programme design and the weak evidence base on interventions that work at scale to increase girls’ access to assets. Risks have been identified at programme delivery, output and outcome level as detailed below. The Implementing Partner has made improvements to risk mitigation.

The SRO is due to update the risk register immediately following this Annual Review to fit with the new DFID risk framework and categories.

Overview of programme risk

Risk	Likelihood	Mitigation
Inefficient use of programme resources, especially staff time, as a result of weak programme management	Low	This risk has been revised to low as the implementing team have restructured the team and recruited a new, stronger team leader.
Activities to directly engage adolescent girls in the programme are not implemented in a safe and appropriate way	Low	Implementing team have a Girls Safeguarding Advisor in place to oversee the implementation of the SPRING girls’ safeguarding policy including a Code of Conduct and a set of minimum standards to ensure that girls are kept safe.
Building of alumni networks, investor networks and human-centred design provision are limited because Implementing Consortium members only resourced till first year. Context Partners team resourced till selection of Cohort 1 and Fuse Project and Investment Director resourced till beginning of Cohort 2.	Low	The objective of the programme restructure has been to address this risk. The programme is now fully resourced to deliver in all 8 countries for a reduced number of enterprises, with fundraising efforts to deliver a Cohort 4 of an additional 20 enterprises. This risk has been revised to low.
Reduction in Resources for Donor Management Team as future of Girl Hub is uncertain	Low	Girl Effect as an independent organisation is providing strategic oversight but with less time-intensive inputs. This is a low risk as the donor team role overall will become less time-intensive in the new phase of the programme.
Delays in implementation - Given the restructure, move to new countries, delivering cohorts 2 and 3 at the same time, and recruitment requirements, there is possibility of delays in implementation of cohort 2	Low	Recruitment of team in London was finalized by January 2016. / Cohort 2 started on time and Cohort 3 is on track
Not enough applicants of sufficient quality, lack of interest from potentially attractive ventures that do not see themselves as playing a role in girls’ economic empowerment	Medium	For Cohort 2, the team undertook pro-active targeting and marketing of the grantees before and during the application process. A weaker than anticipated pipeline from Bangladesh resulted in a lower number of businesses from that country being included in Cohort 2. For Cohorts 3 and 4, a more targeted and effective approach to pipeline development and outreach will mitigate.
Lack of technical assistance funding and mentors for cohort 1	Medium	SPRING is revisiting their mentoring strategy based on feedback from entrepreneurs and mentors on time commitments. They are looking into other approaches such as sector-specific coaches or pro-bono support.
Lack of adequate communication of SPRING at global level reduces effectiveness of entrepreneur outreach	Medium	Develop a clear and measurable strategy to build awareness of SPRING within and beyond specific focus countries. SPRING and donors needs to agree a dissemination plan for knowledge products.
Entrepreneurs are unable to reach girls with low incomes in a commercially viable way and there is limited traction of new-market based approach to reaching girls	High	This risk is important as BoP has been taken out of the measurement. / The evaluation team will continue record estimates on the number of girls reached by each business that are considered BoP to ensure the pro-poor aspect of SPRING is captured in impact evaluations.
Grantee business models are not / commercially viable or attract insufficient investor interest	Medium	Accelerator activities – boot camp, TA, mentors - are targeted at enabling high potential businesses to be investment ready. For some earlier stage businesses, this journey may take longer due to need to build capacity and generation of revenue. Suzanne, the Investment Director will be leading the investment process alongside the Country Managers.
Girls shift away from education because of greater availability of income generating products	Medium	Develop guidelines to target income-generating products in an age-appropriate way. Include this risk and mitigation strategies in questions at selection stage and boot camp stage for entrepreneurs.

Outstanding actions from risk assessment

The Implementing Partner will complete a more targeted and effective approach to pipeline development and outreach for Cohorts 3 and 4.

IP and donors need to agree a dissemination plan for knowledge products.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

SPRING continues to deliver the programme to the planned timeframe.

Performance of partnership (s)

Performance of partnerships continues to be positive and the move of the central team from Nairobi to London has strengthened relationships with DFID.

Asset monitoring and control

SPRING is not an asset intensive programme. The asset register is stored online in the Palladium intranet. All of the documentation was physically moved from Nairobi to London when the office moved and the implementing partner holds both hard and soft copies.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

No funding was dispensed to a government under this programme.

A contract amendment is currently underway to include DFAT as the fourth donor.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Coffey International Development are conducting an independent evaluation of the SPRING accelerator, including a Programme Performance Evaluation (PPE) assessing the effectiveness of SPRING processes and activities; a Business Performance Evaluation (BPE) focusing on how businesses are adapting their business models to incorporate girls and reviewing the business case for targeting girls as a market segment; and an Impact Evaluation (IE) looking at the impact of six SPRING businesses on the lives of the adolescent girls they intended to target with products or services.

The following progress has been made during the annual Review period:
- A PPE report outlining the findings and recommendations from the process review was delivered in May 2016
- PPE findings were presented to DFID staff at a lunch time seminar in September 2016
- Baseline research was completed with one business in Cohort 1, and final baseline data collection is underway for the second business
- KPI data was analysed at the midpoint of Cohort 1 (findings were presented in the PPE report), and at 12 months (Jan – June 2016)
- BPE Research was conducted with three businesses to better understand how their business can meet the needs of end users – final research reports are in progress
- Business Model write ups were prepared for six businesses, which provide a detailed description of the businesses, their intended impact on girls, the support provided by SPRING, challenges faced by the business, and comparisons with similar businesses
- A cross cutting BPE report provided a synthesis of findings from across the six selected businesses in Cohort 1, this is currently being revised and finalised following donor comments and feedback.

Since completing Cohort 1 activities, some changes to the evaluation design were agreed as part of the M&E contract amendment (signed October 2016). The overall Evaluation Framework is currently being refined by the M&E team, and finalised in November 2016.

Monitoring progress throughout the review period

The PPE Review highlighted issues with internal M&E capacity during Cohort 1, including insufficient M&E resources, a lack of clear monitoring framework, some duplication of effort, delays in the collection of the KPI data, insufficient documentation of key activities (e.g. diagnostics), and missed opportunities to produce SPRING knowledge products. The programme quality lacked clear guidelines for the reporting and analysis of KPI indicators, the definition of SPRING beneficiaries, and approaches to assessing whether girls are at the base of the pyramid.

There is a need for better reporting on positive and negative unintended consequences on business performance and on adolescent girls’ empowerment. This ensures there is a full picture of what is happening as a result of SPRING. The IP is looking to collect this data as part of regular updates with the Country Managers and SPRING businesses.

The IP has already taken steps to improving internal M&E capacity, including the recruitment of additional team members focusing on Monitoring and Evaluation.

This annual review was informed by intelligence from documents sent by, and interviews with the implementing partner and evaluation partner.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process