Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Khyber Pakhtunkhwa Education Sector Programme (KESP)
Programme Value: £283.2m		Review Date: August 2015
Programme Code: 202328	Start Date: August 2011	End Date: July 2020

Summary of Programme Performance
Year	2012	2013	2014	2015 (Feb)	2015 (Aug)
Programme Score	C	B	B	A	A
Risk Rating	High	High	High	High	High

Summary of progress and lessons learnt since last review

The last Annual Review of the Khyber Pakhtunkhwa Education Sector Programme (KESP) took place in February 2015 and concluded that the programme now had momentum and serious political buy-in to deliver education reform. That review also took place in the aftermath of the Army Public School attack in Peshawar on 16 December 2014 and recognised the resilience of the Elementary and Secondary Education Department (E&SED) in dealing with the repercussions, including measures to enhance school security and safety across the province, but also continuing to focus on reform.

An interim Results and Activities Framework (RAF) was agreed between DFID and E&SED for the six month period from February to July 2015. The framework provided a set of milestones to assess progress made by the Department during the period up to the start of the new Government of Khyber Paktunkwha (GoKP) Education Sector Plan (ESP) in July. The ESP is Government-owned, realistic, achievable, takes account of existing capacity in the system and is a landmark step within a longer-term vision.

In mid-July 2015, DFID undertook a review to assess progress made by E&SED on the interim results and activities framework (RAF). The review team assessed seven out of ten results areas as ‘complete’ and two results areas as ‘on-track to be completed’. Outstanding action was needed on the remaining results area regarding making data from the Independent Monitoring Unit (IMU) publicly available. On the basis of acheivements in nine results areas, £18.4 million of sector budget support (SBS) was released in August 2015. A summary of progress is provided at Annex A and captured in more detail in a separate Aide Mémoire.

This Annual Review assesses overall progress since February 2015. It builds on the assessment of the interim RAF and also assesses the performance of the technical assistance (TA), school infrastructure, and evaluation components of KESP.

A substantial amount of progress has been made by E&SED over the last six months, despite ongoing security challenges. This progress is evidenced by the positive assessment of the interim RAF and the commitment demonstrated by the Government to improving education in Khyber Pakhtunkhwa (KP). E&SED is clearly in the driving seat of the reform process and success is also visible at the district level where the Department, with TA support, is investing in the capacity of District Education Officers (DEOs) to manage and deliver. This is particularly important as more functions and responsibilities are devolved. Improved budget planning and monitoring have helped to improve the flow of resources to the point of need. Use of information, particularly data from the IMU, is increasing and driving actions to improve the delivery of education. Notable achievements documented in this Annual Review and the RAF review include:
- Improved access to IMU data by DEOs and real time inputting of monitoring data.
- The development of comprehensive district education plans in five districts.
- Improved management by District Education Offices and E&SED including regular meetings of District Steering Committees which are reviewing IMU data and taking decisions based on findings.
- Implementation of a scale-up to the Elementary Education Foundation’s (EEF) voucher programme for out-of-school children with the identification of over 30,000 potential beneficiaries and expansion into six new districts.
- Establishment of over 800 Girls’ Community Schools.
- Completion of a first Grade three learning assessment, intended to assist E&SED in future planning.
- Management and roll-out of teacher training for over 17,000 teachers.
- Revision of roles and responsibilities of the two main teacher training institutions in KP, the Provincial Institute of Teacher Education (PITE) and the Directorate of Curriculum and Teacher Education (DCTE).
- Transparent testing and recruitment of new teachers, through the National Testing Service.
- Strong performance on budget execution this year, including unprecedented 100% execution of the development budget, better incorporation of needs into budget planning, and timely submission of the budget for 2015/16.

Going forward, E&SED needs to maintain the positive momentum achieved over the last year. Potential challenges arising from devolution will need to be carefully managed. Whilst there has been a large amount of activity, equal attention needs to be given to ensuring lessons learnt are fed into future plans and that interventions are having an impact on education outcomes. Quality should be central to all activities, in particular in areas such as training, and the Department will need to ensure sufficient priority is given to equal access for girls as well as boys. This will help ensure equity and that E&SED is able to achieve maximum impact from its efforts.

As the last Annual Review in February noted, it is likely to take several more years and further support on quality in the classroom to demonstrate that cohorts of children are learning more. Achievements to date are positive steps forward and provide encouraging signs of a reform process that is paving the way for an improved education system and better education outcomes.

Over the last six months, Adam Smith International (ASI) have re-orientated their technical assistance team so that it has a greater presence in Peshawar. In May, ASI initiated a refresh of their technical assistance offer to ensure the team had the technical capacity to support delivery of the ESP and the underpinning Joint Review Framework (JRF). This refresh should be concluded by the end of September and it is hoped this will ensure ASI provides E&SED with the right skills set and expertise aligned behind the ESP; as well as the ability to respond flexibly to additional requests from E&SED.

IMC, the service provider for the school infrastructure component, received Board of Investment (BoI) registration in April and moved from inception to implementation phase. Over the last six months, IMC has worked hard to recruit staff, establish District Offices, mobilise resources and identify sub-contractors. Renovation works began on the first higher secondary schools in late June and refurbishment is due to start on phase one of the construction and rehabilitation of primary, middle and secondary schools in the coming months. During the latter stages of the Annual Review, IMC raised concerns with DFID about their assumed average unit cost per classroom. Costs are significantly higher than anticipated which will affect their ability to deliver the original number of classrooms and missing facilities within the scope of work. The detail has yet to be worked through.

This review concludes a period of intense scrutiny for the programme and, on the basis of the progress made over the last year, the review team recommends a return to a normal Annual Review process aligned with assessments of the ESP JRF in July or August each year.

Summary of recommendations for the next year

Sector budget support
1. Review the quality assurance measures for IMU data and ensure monitoring guidelines are comprehensive enough to standardise reporting across monitors. {Immediate action: ASI supporting E&SED}
2. Expedite recommended actions to respond to the findings from the April 2015 DFID Internal Audit Department report on the stipends programme. {Immediate action: DFID, ASI and E&SED}
3. Disseminate findings from the Grade three learning assessment to all key stakeholders, especially teachers, assess the implications of the findings and agree actions to take them forward, including improvements to subsequent assessments. {Immediate action: E&SED/ASI}
4. Introduce a robust monitoring and evaluationsystem to track performance of Girls’ Community Schools and the quality of education provided. {Medium term action: EEF}
5. Ensure IMU data is publicly available on the IMU website before December to improve transparency of information in the sector, and ensure the outstanding results area from the interim RAF is met. {Medium term action: E&SED}
6. Maintain a focus on quality, equity and sustainability across E&SED’s interventions, including better monitoring and adapting as necessary activities such as conditional grants, teacher training and stipends to maximise their impact. Quarterly Steering Committee meetings should be used to take stock of progress. {Medium term action: E&SED with support from ASI}
7. Ensure that the restructuring of PITE and DCTE is carried out effectively and that priority activities from E&SED’s Implementation Plan for strengthening these institutions are taken forward. {Medium term action: E&SED with support from ASI}
8. Support E&SED to ensure quality of teacher training with recommendations to improve the current arrangement of monitoring by DCTE. {Medium term action: ASI}
9. Ensure that teachers have sufficient knowledge of student learning outcomes (SLOs) linked to the curriculum and incorporate key SLOs in teacher lesson plans/guides. {Medium term action: E&SED/ASI}
10. Support E&SED to draw on all evidence available in its planned review of the stipends/cash transfer schemes this year to improve targeting and stream-line delivery. {Medium term action: ASI}
11. Improve accurate identification of potential beneficiaries for the voucher programme and investigate more thoroughly why the redemption rate in the pilot was so low. {Medium term action: ASI}

Technical Assistance
1. Ensure delayed work on the ESP workplan and costing is expedited. {Immediate action: ASI}
2. Regularly communicate workplan priorities to E&SED to ensure they are aligned and expectations are managed. Ensure responses to additional TA requests are jointly considered and agreed, taking into account resourcing implications, availability of expertise and alternative options. {Immediate action: ASI}
3. Regularly communicate developments in the TA refresh to E&SED, so that the Department is fully aware of what support is available and when. {Immediate action: ASI}
4. Ensure appropriate quality assurance measures and processes are in place for E&SED so that IMU data is robust and withstands challenge. {Immediate action: ASI}
5. Finalise the KESP monitoring and evidence framework. This should be a priority for the new ASI monitoring adviser once recruited through the TA refresh process. {Immediate action: ASI}
6. Continue to address delivery challenges early on through open discussion with DFID and E&SED. {Ongoing action: ASI with support from DFID and E&SED}
7. Support E&SED to keep a line of sight at all times to quality, equity and sustainability of interventions, emphasising monitoring of new or expanded interventions and the use of previous assessments, studies and other evidence to inform subsequent activities. {Medium term action: ASI}

IMC
1. Determine and agree the impact of the higher than anticpated unit costs for constructing a classroom on the overall scope of work. {Immediate action: IMC and DFID}
2. Discuss the best mechanism for building in on-site third party verification for IMC construction and put arrangements in place. {Immediate action: DFID and IMC}
3. All parties to work together to strengthen the focus on girls’ schools in phase 2 of construction, taking into account the existing number of girls’ schools and other activities taking place to boost girls’ enrolment. {Medium term action: DFID/IMC/E&SED}
4. DFID to play an active role in facilitating dialogue between IMC and E&SED when issues and challenges arise. {Medium term action: DFID}
5. Encourage E&SED to engage the Communication and Works Department (CWD) in the work of IMC to improve the likelihood of adoption of designs and best practice. {Longer term action: E&SED}
6. Ensure active risk management particularly around the scope of work and unit costs for construction. {Ongoing action: IMC and DFID}

Programme management
1. Revise the KESP logframe to align with the ESP JRF indicators, develop new milestones for the TA and infrastructure activities and consider separate outputs for these components. {Immediate action: DFID}
2. When the impact of the unit cost per classroom on the scope of work is known and agreed, consider a business case addendum and contract amendment for the IMC contract time and any cost extension needed to March 2018. {Medium term action: DFID}
3. Review monthly TA monitoring meetings and reporting formats to ensure these are optimised to support programme performance. {Medium term action: DFID and ASI}

Other
1. Initiate a contract amendment to enable OPM to proceed with the KP system-wide evaluation and scale back the impact evaluation and research components. {Immediate action: DFID}
2. Continue to strengthen DFID’s direct relationship with the Government by keeping open lines of communication; conducting regular monitoring visits to districts accessible by DFID staff; and utilising E&SED staff visits to Islamabad to meet with officials. {Ongoing action: DFID}

A. Introduction and Context

DevTracker Link to Business Case:	Business Case: http://iati.dfid.gov.uk/iati_documents/3745014.odt Addendum to the BC: http://iati.dfid.gov.uk/iati_documents/5064370.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5004175.xlsx

Outline of the programme

KESP aims to support more children to stay in school for longer while learning more. KP’s education indicators are among the poorest in Pakistan, a country which accounts for more than one in ten of the world’s out of school children. Around half of the total 17 million population in KP are illiterate (65% women and 28% men). There are currently 3 million children out of school, of which 75% are girls. The intended impact of KESP is to achieve ‘more educated people in KP, making a positive social and economic contribution’.

Through SBS in partnership with the GoKP and TA support, KESP aims to deliver equitable access to better quality education across the whole province. KESP is structured around four components and the total value is £283.2 million. Through a Development Partnership Agreement with the UK, Australia is also contributing up to £41.3 million.
1. An SBS component provides funds to the GoKP on the basis of progress against the RAF. (Up to £181.2 million (DFID) and £21.3 million (Australia)).
2. TA to the GoKP to support delivery of the RAF and the aims of the new ESP. This is managed through TA provided by ASI. (Up to £42 million (DFID)).
3. A school infrastructure component upgrading facilities in existing public schools to ensure they are fit for purpose. This is managed through TA provided by IMC. (Up to £60 million (DFID) and £20 million (Australia)).
4. TA to inform and evaluate the effectiveness of interventions to date. This is managed through Oxford Policy Management (OPM). (Up to £1.37 million (DFID)).

KESP has faced a number of challenges. The initial DFID design was not sufficiently tailored to the context; funds were initially slow to disburse through Government; there were issues with the quality and delivery of TA; and also procurement delays concerning the infrastructure component. Following the election of the reformist PTI Government in May 2013 led by Imran Khan, the SBS component of KESP was restructured to align more closely with GoKP education reform priorities and assessed through a RAF. The most recent Annual Review in February 2015 scored KESP at ‘A’ for the first time and concluded that there had been significant progress and that the programme was at a stage where capacity was now in place and beginning to deliver. Progress had been made on institutional strengthening, as well as steps that should lead to improved teaching quality in the classroom. This suggested that the delivery chain for enabling children to learn was falling into place and that the reform process was making a difference.
In March 2015, the Secretary of State for DFID approved a time and cost extension to KESP recognising progress made as well as the need for ongoing support. KESP was extended to July 2020, to align the programme with the GoKP new five year ESP. A cost extension of £57.7 million for SBS and £22 million for TA was agreed. During this extension process it was acknowledged that KESP remains a high risk but potentially high return programme.

During the Review period, DFID, on behalf of the other SBS donors (the Australians and EU), led negotiations with the GoKP on a JRF underpinning the five-year ESP. Future SBS disbursements will be made against the achievements of the JRF. This is a welcome shift away from short-term targeting and will enable a deeper level of institutional reform and capacity building over time to help transform the education system.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

In terms of quantitative data on outcomes, student attendance has remained unchanged at 79% from May 2014 to May 2015 with some fluctuation over the year. Boys’ primary (age 6-10) net enrolment rates have increased, from 72% in 2011-12 to 74% in 2012-13, whilst girls’ have remained flat at 59%. New data from the Education Management Information System (EMIS) and the Pakistan Social and Living Standards Measurement (PSLM) survey on enrolment rates was not available for this Review. Likewise, data on trends in learning have not been updated since the February Review. The 2014 ASER study reported a fall since 2013 in the percentage of children able to read English to the correct level from 6% to 4.6% and a rise in the percentage of children able to read Urdu from 13.4% to 17.9%. The new Grade three assessments show average scores of 58% in English, 58% in Maths and 46% in Urdu. These provide a baseline by which future progress can be measured.

It is likely to take several more years before improvements in education outcomes are visible. As highlighted in the Independent Commission for Aid Impact report (2015) on Delivering Impact, achieving lasting impact at scale requires clear, long-term goals and often several programme cycles. It requires gradually putting in place the building blocks, including the right policies, institutions and capacities, in steps appropriate to the context. The limited change so far in enrolment and learning outcomes is not a concern yet but needs to be closely monitored to determine if the programme is indeed having the intended impact on outcomes. The programme achievements to date are creating an enabling environment and delivery chain that can deliver better education outcomes. This momentum will need to be maintained over a longer period to yield results.

Overall output score and description

The programme has largely been successful in delivering against planned outputs for this Review period. The interim RAF has mostly been achieved and E&SED is to be commended for its hard work and focus. On the two results areas assessed as ‘on-track to be completed’, EEF has now distributed most of its vouchers in time for beneficiaries to start school on time but there is some outstanding work to do to ensure that remaining teacher training modules are delivered to all participants. Some sensitivity remains within E&SED about making IMU data publicly available but the Department is relatively confident it can deliver on this. Whilst not part of the RAF, the girls’ stipend programme remains an area of focus. The disbursement of stipends to districts and on to beneficiaries improved last year but still experienced some delay.

Budget execution is another very positive story. Spend as a share of the original budget showed a vast improvement by the end of FY2014-15 compared with FY2013-14. Execution of the development budget in particular increased from 39% in FY2014-15 to 100% in FY2014-15.

Slower progress has been made on setting baselines and targets for key IMU indicators which E&SED can then use to monitor and benchmark performance over time. It is, however, encouraging that these have now been developed and provisionally agreed by the Department. The next step is for this information to feature in discussion and decision-making.

ASI has played an effective role in supporting delivery of the interim RAF as well as several other areas, including capacity building of the relatively newly established Internal Audit Cell and budget monitoring. The Internal Audit Cell recently completed its first audit which focused on the girls’ stipend programme. ASI is still completing a refresh of its TA offer which aims to provide expertise aligned with the ESP and respond flexibly to the Department’s needs. There is outstanding TA work to support the development of a workplan and costing of activities for the ESP.

IMC awarded the contract for the renovation works in a small number of higher secondary schools in late June and refurbishment is due to start on phase one of the construction and rehabilitation of primary, middle and secondary schools in the coming months. Meanwhile progress has been made to mobilise resources and set the necessary ground work for construction to begin.

Overall, this Annual Review concludes that outputs have largely been met. Underpinning many of these outputs is a more important narrative around the impact and quality of interventions which needs to be teased out in subsequent monitoring. There is always a risk that numerical targets can be met at the cost of quality, impacting on the ability to improve learning outcomes. More evidence is needed to judge whether this is a real concern, but there is sufficient scrutiny and lesson learning in areas such as girls stipends to warrant proper reviews and revisions to ongoing initiatives. Follow-up to the recommendations of the DFID Internal Audit Department report on girls stipends is detailed in Section D ‘VfM and financial performance’ under the financial management and SBS heading.

Key lessons

This Review again highlights the value of regular DFID interaction with the GoKP and the need to maintain a direct line of communication to address issues as they arise. Due to security constraints which prevent frequent DFID travel to Peshawar and many other parts of KP, DFID relies heavily on E&SED travelling to Islamabad for meetings. Where and when possible, DFID monitoring visits to districts and schools provide valuable insights into the extent to which education reforms are having an impact lower down the delivery chain. These different channels for direct DFID engagement with Government should continue to be strengthened wherever possible. There are also other DFID-supported programmes, Government of KP departments and Standing Meetings which support the programme and help to address blockages. DFID’s Sub-National Governance programme has a good working relationship with the Finance Department. DFID’s Provincial Representative has excellent networks across Government, and regular donor-GoKP meetings provide further opportunities for engagement with the different Government departments.

This Review also notes the importance of regular and open dialogue. It is healthy and constructive for all parties (DFID, ASI, IMC and E&SED) to tackle challenges and issues as they arise even when, on occasion, this has involved difficult conversations. For example, IMC is now meeting weekly with E&SED in Peshawar to talk through plans, progress and issues.

The regularly changing security dynamic in KP has highlighted the need to balance international staff with suitably senior qualified local staff so that the TA teams (ASI and IMC) can continue to deliver and function effectively, even where constraints to access arise. This requires active management and reporting structures that can support and adapt to the challenges of working in split-site locations.

The recent improvements in the use of IMU data have demonstrated how the availability of good data and information can make a marked difference in the ability of institutions to plan and respond to challenges effectively. Data and robust monitoring should continue to be a focus of the programme going forward.

In previous years, KESP has focused on improving the enabling environment for education reform such as good financial management, budgeting, data, planning and performance management. To some extent, this focus has now begun to become balanced with reforms focused on improving learning and the quality of education. This is a positive step forward and provides evidence that investing first in the enabling environment is an important part of delivering long-term education reform.

Has the logframe been updated since the last review?

Yes. The logframe was updated in May 2015. A further revision is planned following this Annual Review to ensure the logframe is aligned with the ESP JRF indicators and milestones.

## C: DETAILED OUTPUT SCORING

Output Title	Ensuring effective delivery
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Effective district-based planning and budgeting	(1) 5 district needs-based/realistic education plans and budgets developed (RAF 3)	Complete. Plans for 5 districts were developed with budgets attached and approved by E&SED by end June.
	(2) Improved budget execution rates against the original allocations for development and non-salary budgets by end June 2015 as compared to end June 2014	Complete. Provisional budget execution as a percentage of original allocation as of end June 2015 was 99.6% for development budget and 86.3% for the non-salary recurrent budget. As of end June 2014, execution rates were 38.6% for development budget and 56.6% for non-salary recurrent budget.
1.2 IMU data informs planning and management decisions	(1) IMU website made public (RAF 4)	Not met. IMU data website not public, however some IMU data available via the District Performance Monitoring framework website.
	(2) Monthly district stock takes continue to happen with follow-up action based on IMU data by DEOs	Complete. District Steering Committees now established and holding monthly meetings in most districts. Follow-up actions being documented and status reviewed.
	(3) Improvement in results-based school monitoring processes in 5 districts. DEOs/District Education Offices taking timely actions to resolve issues identified through IMU data meeting targets (RAF 2)	Complete. IMU data being used in districts to monitor performance and actions being taken every month. Performance targets identified in 5 district plans.
1.3 Civil servants and teachers have the capacity to lead and manage the education system more effectively	(1) Revised roles and responsibilities (ToR) of PITE and DCTE agreed (RAF 1)	Complete. The E&SED has formally signed off on the ToRs and recommendations approved by the Education Minister.
1.4 Effective technical assistance supporting the Government to deliver	(1) TA completes workplan supporting the Government to achieve RAF indicators	Complete. Workplan of support on RAF indicators completed.
	(2) Completed refresh process that sets out workplan and resourcing going forward agreed with GoKP/ASI and DFID	Partially met. Refresh designed and currently being implemented. Structure needs to be clearly communicated to GoKP. Recruitment for new posts still under way.
	(3) Costed ESP and workplan for the first year based on existing data	Not met. Support on ESP workplan and costings delayed.

Key Points

Effective district-based planning and budgeting: With TA from ASI, District Education Offices in Abbottabad, Lower Dir, Karak, Kohistan and Peshawar developed District Education Plans which were subsequently approved by E&SED. The plans were also shared and discussed with all District Education Officers (DEOs) at a workshop in July. As part of the plans, districts have defined annual targets to align with ESP policy priorities and developed detailed action plans for the year. DEOs from Peshawar and Dir Lower reported that the exercise had been particularly helpful in clearly setting out work priorities and that, as a result, planning for fund releases has started much earlier this financial year, including the preparation and submission of PC-1s and other funding requests. In time and with effective monitoring, the plans could also help identify and inform appropriate staffing needs.

Budgets were prepared as part of a separate exercise which was completed in January. The process involved consultation with districts about their respective needs, particularly for the formation of the non-salary budget. This is an improvement on previous years where district needs were given limited attention in budgeting. The subsequent allocations for FY2015-16 have been attached to the District Education Plans to aid planning. E&SED has agreed that DEOs will review the progress made on their respective plans on a bi-monthly basis and update their work plans accordingly. DEOs have also been asked to include a review framework in the plans on which the performance of DEOs will be assessed by the Directorate. A further five districts aim to complete plans this coming year E&SED could consider extending the number of districts more quickly, providing there is sufficient support in place for implementation and monitoring.

Budget execution as a percentage of the original allocation has vastly improved compared with the previous year. Execution of the development budget in particular is almost unprecedented at 99.6% compared with 38.6% for the same period the previous year. Improved performance is due in a large part to the increased attention given to budget monitoring over the last financial year, with almost bi-monthly budget execution meetings with the Chief Minister and further monitoring meetings within individual districts. Execution has also improved as a result of in-year reallocation of funds within the education sector towards areas more able to spend. This includes a re-allocation to fund the construction of boundary walls following the attack on the Army Public School in Peshawar. During the Review visit to Charsadda district, DEOs reported that it was the first time they had received funding at levels in line with needs and allocations and were able to spend in a timely fashion. Allocations were used in part to resource DEO offices. It is important that the increased allocations made in the FY2015-16 budget for schools and classrooms experience similar levels of execution.

Use of IMU data: Over the last six months, access and use of IMU information has also noticeably improved. District officials now have real-time access to data in an easy-to-use format and training has been given to enable its use and increase understanding. This enables DEOs to quickly take action, where required, often within the month. Monthly steering committee meetings, chaired by the Deputy Commissioner, bring together DEOs and District Monitoring Officers (DMOs) to focus attention on key areas and actions required. In cases of teacher absenteeism there is evidence of teachers’ pay being reduced, disciplinary actions taken or redundancies made. The independence of the data was cited by officials as helping to increase the acceptance of IMU data by teachers and officials. A new electronic “app” was recently introduced (recording GPS locations and visit times) and is improving the transparency of the visit process.

Understandably, there is reluctance around making the IMU data website fully public and the recent interim RAF Review assessed this results area as ‘incomplete’. There are natural concerns that the data, once available, will be partially or mis-represented by different interest groups and that little attention will be given to those areas where the GoKP is making positive headway. Differences between IMU figures and figures collected once a year for the EMIS may also create confusion. Where data has been made public through the Right to Information Act, negative media reports have added to E&SED’s workload in handling responses. This has also raised questions about how the data should be presented so as to avoid misinterpretation and ensure a balanced perspective. The interim RAF Review recognised that this results area may need to be revised to make it realistic and stretching but still achievable. During discussion, E&SED considered that they could publish some key information by December this year but would revert back to DFID with a formal proposal. Despite sensitivities, some IMU information is already available via the District Performance Monitoring Framework website, an initiative led by the Chief Secretary which allows the comparison of key indicators across districts.

Whilst generally perceived as credible, limited assessment exists on the quality of IMU data. Some concerns on the reliability of “functioning facilities” data were voiced and strengthening the monitors’ guidance and criteria may be useful to address this. Lessons learnt from the process of data collection and validation should inform improvements to the new system. Plans to review IMU data alongside EMIS indicators are welcome. E&SED might want to consider strengthening the verification and quality assurance processes for the IMU data to provide additional assurance of data quality.

Revised roles and responsibilities for PITE and DCTE: The reform of the two main provincial teacher training institutions has been a long outstanding issue with duplication between their roles and responsibilities. The ToRs for revised roles and responsibilities were developed and approved by the Education Minister on 15 July 2015.

According to the new TORs, PITE will be responsible for designing and implementing all teacher training activities (including school leaders and education managers). DCTE will continue to be responsible for pre-service teacher training, learning assessment and curriculum. It will also take on the additional responsibility of planning, managing and evaluating professional development of teachers. The TORs were revised and agreed upon after holding several rounds of consultations with E&SED, PITE and DCTE. A draft restructuring strategy has been developed by the ASI TA team and shared with the E&SED. The challenge will be to implement the actual reforms proposed for the restructuring and setting out realistic timelines for achieving these goals. There are likely to be further challenges around reviewing and revising service rules and teachers’ terms and conditions as bringing reforms to both these institutions is a sensitive area. Support from other DFID funded programmes such as Alif Ailaan should be used to create a conducive environment to take forward some of these reforms.

The Department is considering a range of additional areas to strengthen teacher training. These include: the development of a proposal for a separate cadre for the teacher education institutions; linking teacher promotion to completion of professional development programmes as part of a review of service rules, and training teachers right after they are hired.

Effective TA supporting the Government to deliver: The GoKP achieved the RAF targets with technical support from the ASI TA team as noted in various sections of this Review report.

The ASI TA team has established good working relations with Government officials. There are areas where the TA team has been actively involved and is now stepping back where capacity within E&SED is stronger. Examples include monthly district stocktakes of IMU data and fortnightly budget monitoring with the Minister. This is a good sign that the TA team is not just gap filling but building capacity. The TA team has also produced a few studies of Government initiatives which, if taken on board, should help to build the evidence base for E&SED to make future decisions. Recent studies include a review of the girls’ stipend programme and a review of the teacher rationalisation process implemented earlier in the year.

In response to the February Annual Review and E&SED requests, ASI has striven to ensure a greater team presence in Peshawar although this has resulted in some staff choosing to leave the ASI team. Ongoing issues with BoI registration has also resulted in international staff not being granted Non-Objection Certificates (NOCs) to travel to KP. This has impacted on the ASI team and their ability to deliver. ASI is however actively pursuing registration which, if received, may help to improve the situation. With the growing constraints on operating space for civil society and for-profit implementing partners, there are likely to be continuing challenges.

Within the Review period, there has continued to be an improvement by ASI in programme management, notably in cash management and procurement, against a Portfolio Risk and Assurance Programme (PRAP) action plan agreed with DFID. Fortnightly programme management meetings between the DFID and ASI teams help identify issues and follow up actions. ASI have also finalised their Business Process Manual and are in the process of implementing this. The ASI Head of Finance visited Pakistan in August to assess progress and ASI will share a copy of their internal final report with DFID. Strengthening programme management is an ongoing area of work and DFID has agreed with ASI that a follow-up PRAP review to assess progress will be undertaken in late November or December 2015.

In response to feedback received from E&SED during the previous Annual Review and the recommendation to re-orientate the technical skills of the ASI team to support delivery of the ESP, ASI undertook a ‘TA refresh’ process in May. This aimed to:
- Establish a new mission and vision aligned with ESP delivery.
- Develop an implementation approach and plan for Year 1 of the ESP.
- Amend the team structure and budget to support the implementation plan.
- Increase the quality of the TA team and presence in Peshawar.

ASI has also notably moved to open recruitment to fill the positions created by the TA refresh but may need to consider further targeting to fill senior or specialist local posts.

The TA refresh process has taken longer than expected to conclude. Fifteen new posts have been created and the ASI team has been restructured to include delivery leads for ‘Equity’ and ‘Teaching/Learning’ and an overall Team Leader position who is also the delivery lead for ‘Governance and Management’. ASI expects this process to be complete by end September and the new team should be able to offer E&SED greater expertise and flexibility. ASI is also training new and existing staff on core consultancy skill sets. ASI needs to ensure proactive communications with E&SED and DFID to keep both parties up to date and to manage expectations on the TA refresh.

Rolling work-planning with E&SED to underpin the delivery of the first year of the ESP has also taken longer than expected to conclude but should be finalised in the coming weeks. Another outstanding area of support is the development of a work plan and costings for ESP implementation. This work was delayed in part due to weak data. Some ESP activities have already been factored into the FY2015-16 budget allocations or built into the TA workplan. Nevertheless, completing this work is necessary to inform both future budget planning as well as guiding the implementation of the ESP. Again, ASI need to ensure proactive communications with E&SED and DFID to keep both parties up to date, particularly where work needs to be sequenced because of competing priorities.

Summary of responses to issues raised in previous Annual Reviews

The three recommendations from the previous Annual Review together with following action is below:
ESP
- Recommendation: E&SED should develop an action plan for the ESP and focus on preparatory activities in the period leading up to ESP implementation.
- Action: ASI support to the development of an ESP workplan was delayed. Some ESP activities have been factored into the latest budget but there is no work plan currently in place.
Budget execution
- Recommendation: DFID should continue close monitoring of budget execution and undertake regular stocktakes with ASI/GoKP to identify pipeline spend and potential challenges to execution.
- Action: Budget execution has been a standing agenda item in monthly meetings with ASI. Progress was also discussed with the GoKP at the Quarterly Steering Committee and more broadly as part of the Strategic Development Partnership Framework discussions between donors and the Government. ASI monthly reports to DFID were modified to include details on challenges to spend.
IMU
- Recommendation: IMU to undertake a review/stock take/lessons learnt on how the IMU is functioning and what improvements could be made to ensure that this is useful for policy-making, operational planning and decision-making, as well as monitoring and evaluation.
- Action: IMU has made improvements in terms of access and use. No comprehensive review has taken place.

Recommendations:
- ASI needs to ensure regular communication with E&SED and DFID on the ASI TA refresh progress and work plan priorities. ASI should also continue to ensure timely delivery of work including accurate reporting on progress the achievement of the JRF; and developing the ESP work plan and costing which is overdue.
- Building on IMU data access and use improvements, ASI should support E&SED to review the quality assurance measures in place for IMU data and the quality of monitoring guidelines and practices. Strengthened processes should be introduced where needed.
- ASI should help ensure that the restructuring of DCTE and PITE is carried out effectively including priority activities from E&SED’s Implementation Plan to further strengthen these two institutions.
- E&SED should ensure that PITE has the capacity to lead and implement the school-based CPD programme with the support of ASI.

Output Title	Improving teaching and learning
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 % of teachers present at school	(1) Baseline and provisional set of targets for teachers attendance	Complete. Baseline of 79% (May 2014) established and targets approved by the Directorate.
2.2 GoKP actions to improve teacher quality	(1) Revised and improved terms of reference and guidelines for developing teacher recruitment test shared with NTS (RAF 5)	Complete. Revised TORs for teacher recruitment test shared with NTS
	(2) 17,000 teachers and head teachers (m/f, primary/HSS) and 250 principals completing all five modules (m/f) (RAF 6). / Note: RAF indicator revised to completion of 4 modules by July due to delays in holding trainings during local government elections.	Partially met. 17,627 teachers (5,994 female; 11,633 male) received some professional development training including 15,790 primary school teachers (5,384 female; 10.406 male). 1,837 HSS (610 female; 1,227 male) but not all modules are completed. / 20,338 primary school head teachers (7,446 female; 12,892 male) trained on lesson plans. / 135 principals have completed 4 out of 5 modules .
	(3) Priorities identified and a budget developed for CPD in FY2015-16 (RAF 6)	Complete. Budget allocated for CPD in FY 2015-16. Workplan and calendar of activities developed.
2.3 GoKP actions to improve curriculum implementation and student learning assessment	(1) Successful sample student learning assessment for Grade three students completed in 340 schools (RAF 8)	Complete. Assessment undertaken in 329 schools. Only 300 schools were need for an accurate sample size. 340 was designed as an overshoot to ensure the 300 sample size was met for the study. Some concerns exist with bias.

Key points

Percentage of teachers present at schools: Comparisons of the latest IMU data (May 2015) with the agreed baseline (May 2014) shows a slight fall in overall teacher attendance – from 81% to 79%. (Although during this 12 month period attendance fluctuated around 82-83%). More importantly, unauthorised teacher absence fell from 4% to 3% over the same period.

The ASI TA team presented three options to E&SED for setting baselines. E&SED agreed to adopt a fourth option using May 2014 data as the baseline for most indicators. May 2014 data covered 96% of schools and was the most robust data since collection began in March 2014. Provincial and district level targets across five indicators (teacher presence, student presence, non-teaching presence, administrative visits and monitor visits) were formally agreed by Education Secretary in April 2015. Teacher presence baselines were set for each district and for the whole province. The baseline in May 2014 is 81% and the target for 2015 is 84%. As further data becomes available it is good practice to review these targets and clarify the time period. Follow-up is required to ensure the indicators and targets are integrated into E&SED’s stocktakes of IMU data and are fit for purpose.

Teacher recruitment and training: E&SED have started hiring new teachers through a transparent teacher recruitment process, using the services of the National Testing Service (NTS) which administered the teacher recruitment test last year. This should help improve the quality of new teachers being recruited. Over 12,000 teachers were recruited in FY2014-15 using the NTS selection process. An additional 10,000 teachers will be recruited in FY2015-16 to fill the gaps in teaching staff. The Department estimates that it needs 30,000 additional teachers based on existing student enrolment. This is only the second year since 2007 that additional teachers are being hired.

E&SED has clearly defined criteria for teacher recruitment, giving equal weighting to professional qualifications and test scores. The TA team conducted an analysis and concluded that the NTS test was too generic, together with a set of recommendations and guidelines on how to develop a test suited to the Department’s needs. Based on the findings from the report, TORs were developed for NTS to guide the design of a more appropriate test.

Discussions with DEOs revealed that the new system of recruitment through NTS has introduced transparency and expedited the process of recruitment. Grade 17 teaching staff and above are recruited through the Public Service Commission. This is a time-consuming process and can take as long as three years before final selections are made.

The professional development of teachers, including teacher training, is on-track but not yet completed (80-85% of teacher training has been completed). A total of 15,790 primary school teachers and 1,837 teachers from higher secondary schools (a combined total of 17,627) have taken part in professional development programmes. Of these 11,865 teachers (10,415 primary school teachers and 1,450 higer secondary school teachers) have completed the full programme of professional development while the remaining training is underway. PITE and DCTE have also completed lesson plan training for 20,338 primary school head teachers.

Four organisations were contracted to conduct teacher training activities. Differences in training format and the varying quality of trainers were identified as challenges following the outsourcing of teacher training activities. Another issue identified was the weak coordination between DCTE and DEOs which has impacted on attendance and hampered the delivery of training activities. Lessons learnt from implementing training through private sector providers has informed E&SED’s plans for further outsourcing this year.

The Department has a comprehensive plan for continuous professional development (CPD) of teachers. PITE and DCTE were both involved in the process of developing a CPD framework. A GIZ-supported school-based CPD programme for teachers was also piloted in three districts of KP. E&SED has plans to scale this up but it is important that this pilot first demonstrates results and its effectiveness before other districts are included.

This is the second year that a substantial budget was allocated for CPD, previously an area which was largely donor-driven. PKR 800 million was allocated for teacher development in FY2014-15 and a similar amount has been allocated for FY2015-16. There is a teacher training calendar and pre and post-training assessment is also part of the process. English language training is being carried out with British Council assistance.

E&SED needs to prioritise their focus on the quality of training provided. Under the revised roles and responsibilities of the two institutions, training monitoring is within the mandate of DCTE but has been a challenging area to implement and report upon. Moreover, the budget was not sufficient to complete monitoring of all training activities.

Going forward, E&SED plans to develop quality teacher guides in collaboration with the KP Text Book Board. A workshop on quality and standards in education is also being planned. The Department plans to conduct a sample survey of teaching to assess the quality of teachers in government schools. A Human Resource Management Information System providing information on all teaching staff is also planned to help inform future professional development activities.

Curriculum implementation and student learning assessment: E&SED conducted the Grade three learning assessments in April 2015 through the Provincial Education Assessment Cell (PEAC). The assessment was intended to provide a snap-shot of information about student learning to enable remedial action to be taken before children fall too far behind. The intention is to carry out the assessment on an annual basis to identify trends and progress against the ESP.

The ASI TA team designed a sample of 5,000 students from 347 schools across KP. This was an over-sample designed to ensure the minimum level of 300 schools and 4,500 students were selected to meet a 95% level of confidence. 4,966 students took the test in 329 schools. The remaining 18 schools were not covered due to: (1) no children being present on the day; (2) insecurity; and (3) no children reported to be in Grade Three.

Concerns exist around the potential (positive) bias that may be present in the sample design. Initially, it was planned that 15 students should be selected from each school. However, when it appeared that the required sample of 4,500 was unlikely to be met (as Grade Three enrolment in many of the selected schools was lower than 15 students), this was raised to 25 students per school where possible. Thus larger schools are better represented than smaller schools. It is recommended that the raw data is weighted to reduce bias and improve the representativeness of the sample; and that future assessments build on the lessons learnt including from third party validation (TPV).

An independent TPV was carried out in 105 schools. It found that protocols were generally followed, with a few exceptions in a small number of schools. For example, in 15 of the schools, children were observed sharing answers, while in ten schools completed exam papers were not sealed. The TPV makes four recommendations: (1) adopt a consistent approach to the length of time allocated to each test page; (2) continue the use of two invigilators to minimise cheating; (3) remove students not being tested; and (4) provide invigilators with sealing material to ensure completed papers are confidentially stored.

The assessment shows average scores in English (58%), Maths (58%) and Urdu (46%) but this marking scheme counts partially-correct answers as correct. Excluding these partially-correct answers would obviously yield lower scores.

It is vital that the learning information feeds into planning and teacher training activities. Extending assessment to the EEF voucher and Girls’ Community Schools would also help assess the value of these initiatives.

Summary of responses to issues raised in previous Annual Reviews
- Recommendation: Carry out an evaluation of the effectiveness of teacher training and whether it is having an impact on improving learning and incorporate the findings in future teacher training programmes.
- Action: This task is still pending. The ASI TA team should take this work forward (see recommendation below).

Recommendations:

Teacher recruitment and training
- ASI TA team to devise a strategy to monitor and ensure the quality of teacher trainings as the current arrangement of monitoring by DCTE is not sufficient.
- E&SED to continue provision for teacher training, building in improvements based on lessons learnt and results from learning assessments.

Assessment
- E&SED to disseminate the assessment findings to all stakeholders, especially teachers, assess the implications of the findings and consider actions to address these in planned activities and future assessments.
- E&SED to extend the scope of the assessment to include Girls’ Community Schools and low-cost private schools, especially those supported by EEF.

Curriculum
Ensure that teachers have sufficient knowledge of key student learning outcomes (SLOs) linked to the curriculum and incorporate key SLOs in teacher lesson plans/guides.

Output Title	Improving schools
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of schools achieving optimal (40:1) student to teacher ratio (primary, middle, urban and rural, gender)	(1) GoKP agrees baseline and target for number of schools achieving optimal student to teacher ratio	Partially met. Baseline of 10,803 for primary schools only (May 2014). Targets provisionally approved by Directorate but awaiting final Ministerial approval. No baselines set for secondary schools or consideration of disaggregation by gender or rural/urban.
3.2 Number of schools with rehabilitated infrastructure	(1) Training for 3,000 Parent-Teacher Councils (PTCs) completed (RAF 7)	Complete. 12,452 PTCs have completed training in 12 districts.
	(2) TACE: An agreed 6 month rolling work plan with IMC for KP	Complete. Rolling work plan agreed and in place.
	(3) TACE: Complete technical surveys for 375 primary and 36 higher secondary schools	Near complete. Technical surveys completed for 350 primary schools and 37 higher secondary schools.

Key points

Baseline and targets for optimal student to teacher ratio: The Department has undertaken a process to identify and agree primary school student-teacher ratio baselines and set annual province-wide targets up to 2017. These were provisionally approved in July 2015 by the Directorate but final Ministerial or Secretary-level approval is still required and expected in the coming few months. It is important the targets are approved as soon as possible to allow officials time to develop their understanding and focus attention on tracking performance. No baselines were established for secondary schools and this should be considered. Furthermore, it was intended that the data be disaggregated by gender and urban/rural locations and consideration given to establishing targets at this level

IMU data shows the number of primary schools achieving a student teacher ratio of 40:1. This has increased from 10,803 in May 2014 to 12,176 in May 2015. Some progress has also been made on teacher rationalisation. DEOs told the Review team that teacher rationalisation has been a good initiative but unless more teachers are hired, it will be difficult to reduce over-crowding and multi-grade teaching.

Schools with rehabilitated infrastructure: IMC gained BoI registration in April 2015 and formally moved to implementation. IMC have recruited 219 staff (both Punjab and KP), selected sub-contractors, undertaken technical surveys for the first batch of schools and opened district offices in Charsadda and Mardan. These are co-located with E&SED to improve co-ordination, communication and reduce costs. NOCs are being granted for international staff to travel to KP.

The original aim was for IMC to rehabilitate 12,000 new classrooms and provide an equal number of missing facilities. At the request of the GoKP they are also aiming to transform 202 higher secondary schools into model institutions (the original request was for 364 higher secondary schools but this was subsequently revised). IMC also plans to construct two demonstration primary schools on existing school compounds. Minor works were carried out at 28 higher secondary schools during the inception phase with a limited budget of £3,000 per school.

The list of districts higher secondary schools was finalised on 7 July 2015. Criteria from E&SED were incorporated and technical surveys for the second batch of 37 Higher Secondary Schools were completed. Contracts for the ‘standardisation’ of 32 higher secondary schools awarded with contractors now on site. Tendering for the remaining 170 schools is in progress. IMC have reported issues with the initial data provided by E&SED which needed verification due to inaccuracies. The higher secondary schools in the original list from E&SED was also unevenly distributed over all 25 districts of Khyber Pakhtunkhwa. However, to achieve greater efficiency, IMC has agreed to work on all schools in nine districts with the GoKP Communications and Works Department (C&W) focusing on the other districts. The boys to girls school split for the first 73 schools is 70:30. IMC aims to prioritise girls’ students for the remaining 129 schools to ensure an even gender split. The renovation of the 202 higher secondary schools will be complete in June 2016.

Phase one of construction in primary, middle and higher schools has started. IMC are aiming to rehabilitate and construct new classrooms in 350 schools in three districts (Peshawar, Mardan and Charsadda). IMC were given an initial list of 350 schools by E&SED. However, during a detailed infrastructure analysis it was revealed that 42 out of these 350 schools had already received funding from other initiatives for the construction of additional classrooms, boundary walls and toilets; or had rental and land issues. Consequently, E&SED was requested to provide replacements for all of the 42 schools. E&SED eventually provided replacements for 17 schools resulting in the list of 325 instead of 350 schools. This was provided in June and the overall classification is in the table below. It is notable that the boys to girls to co-education ratio markedly declines as the list moves from primary to middle to higher schools.

District	Primary schools			Middle Schools			High Schools			Totals
	Male	Female	Co-Ed	Male	Female	Co-Ed	Male	Female	Co-Ed
Peshawar	54	39	1	4	0	0	1	1	0	100
Mardan	8	46	53	11	0	0	4	3	0	125
Charsadda	23	28	50	14	0	0	10	0	0	125
Totals	85	113	104	29	0	0	15	4	0	350
Percentages	25%	32%	30%	8%	0%	0%	4%	1%	0%	100%

    Source: IMC quarterly report (April – June 2015)

Of the 100 classrooms anticipated to be competed in KP by the end of December; 75 of these are in the first 26 higher secondary scools: eight in Peshawar, six in Mardan, six in Kohat and six in Lower Dir. The remaining 25 classrooms are in 12 primary schools in Phase one districts. Four are in Peshawar, four in Mardan and four in Charsadda.

The pre-qualification of contractors was also completed in June, technical surveys were completed in August and the tendering process is now underway. The timeline for completion is June 2016 with the first classrooms due to be finished in December this year. IMC are using conventional contractors for phase one rather than community contractors due to the need to make up for lost time.

With a fixed budget for capital works, the choice of schools and construction priorities involves trade-offs in coverage and costs. The earlier decision to work in 202 higher secondary schools (not in the original ToR) has implications for the numbers of classrooms that can be built in other schools. IMC estimate that some 30% of the capital works budget will be needed for this. Changing the scope further, for example the extent to which minor repairs and missing facilities are provided for existing infrastructure will also impact on the resources available. These trade-offs will need to be considered carefully when future lists are put together and expectations managed about what is feasible within a fixed budget.
During the latter stages of the Annual Review, IMC raised concerns with DFID about their assumed average unit cost per classroom. Costs are significantly higher than anticipated which will impact on their ability to deliver the original number of classrooms and missing facilities within the scope of work. The detail has yet to be worked through.

IMC faces a range of challenges to timely delivery including: evolving requirements; limited land availability for construction requiring bespoke designs (IMC estimate bespoke designs are needed for between 40% and 60% of schools); inaccessibility of schools during winter and monsoon months; and the prior occupation of schools. Further delays are inevitable and will need to be managed

The current timeline for the IMC contract in KP is the end of March 2016. It was recommended in previous Annual Reviews that this be extended to compensate for both the initial DFID procurement delay and the delay caused by IMC BoI registration. When the impact of the unit cost per classroom on the scope of work is known and agreed, DFID should consider a business case addendum and contract amendment for the IMC contract time and any cost extension needed

The legacy that IMC aim to leave is a sustainable blueprint for classroom design that E&SED can replicate in other schools in KP. IMC are also aiming to ensure that community ownership remains central to classroom rehabilitation in order to break the cycle of build, neglect and rebuild. IMC plan to engage and train PTCs on basic construction supervision and infrastructure maintenance. IMC will not pay the final stage payment to their sub-contractors until the PTCs have formally approved the works. An adapted approach to training for female PTCs may be necessary to address specific issues around monitoring and site access. IMC will provide their training manuals to E&SED so they can be used in other infrastructure projects in KP; and are also encouraging the formation and capacity building of Community Committees for School Infrastructure to widen community involvement and ensure basic monitoring.

While IMC has strong competency to monitor and oversee construction, it is normal for any infrastructure project to include third party on-site verification of construction works. It is recommended that provision be made for this. This will provide an independent monitoring mechanism to assure all parties that quality work is being delivered.

Active risk management is needed by both IMC and DFID. Substantial delivery risks include the unit cost per classroom and the impact this has on the scope of work, schools receiving support for works from multiple suppliers, inaccurate data on school needs and others highlighted above. DFID will need to work closely with E&SED and IMC to ensure these expectations are managed, needs are being met and that the component is equity-focussed and benefiting the poorest.

Summary of responses to issues raised in previous Annual Reviews
- Recommendation: GoKP to ensure that CWD and E&SED take account of IMC data and share their school construction plans to enable informed planning and avoid duplication of effort.
- Action: An initial list of schools for phase one has been agreed. Communication of plans needs to be an ongoing activity.

Recommendations:
- Determine and agree the impact of the higher than anticipated unit costs for constructing a classroom on the overall scope of work.
- When the impact of the unit cost per classroom on the scope of work is known and agreed, consider a business case addendum and contract amendment for the IMC contract time and any cost extension needed to March 2018.
- {DFID and IMC to discuss the best mechanism for building in on-site third party verification for IMC construction and put arrangements in place.
- All parties (DFID, IMC and E&SED) to work together to strengthen the focus on girls’ schools in phase 2 of construction, taking into account the existing number of girls’ schools and other activities taking place to boost girls’ enrolment.
- DFID to play an active role in facilitating dialogue between IMC and E&SED when issues and challenges arise.
- In slower time, E&SED should engage C&W in the work of IMC so as to improve the likelihood of adoption of designs and best practices. IMC to consider preparing a list of assets and asset management policy best practice for E&SED and C&WD at the time of classroom handover.

Output Title	Every child’s right to education
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Transition rate of children in primary school (by gender)	(1) Transition rate baseline agreed	Partially complete. Baseline of 83% (May 2014) and targets provisionally approved by Directorate but require final Ministerial approval. No disaggregation of gender in baselines.
4.2 Economic incentives provided to students, especially girls	(1) Second tranche of stipends released to districts/post office	Complete. Second tranche released to all districts before end of FY 2014-15. Onward disbursement of stipends to beneficiaries completed in some districts and under way in others.
4.3 Number of additional students enrolled in the private sector	(1) Education vouchers distributed in 3 additional districts (RAF 9)	Complete. Distribution of all vouchers in six additional districts almost complete.
	(2) 600 Girls’ Community Schools established and functional (RAF 10)	Complete. 943 schools have been established.

Key points

Baseline for transition rate of children in primary school: Similar to output indicator 3.1, E&SED has undertaken a process by which to identify and agree baselines and set annual provincial targets up to 2017. These were approved by the Directorate in July but final Ministerial approval is outstanding. It is important these are approved as soon as possible to allow officials time to understand the targets and focus attention on tracking performance.

Disaggregation by gender does not appear to have been considered. The last Annual Review highlighted that gender was not being given sufficient attention. The ASI TA team need to press E&SED to include gender-disaggregated data and consider whether gender-specific targets can be set.

This indicator measures the rate at which primary school children progress into secondary school and can therefore only be measured once a year (as data on the previous cohort of children is required). Although 2016 and 2017 targets have been agreed it may be useful to revisit these once more data becomes available.

Stipends: GoKP policy is to provide stipends in two tranches to all girls in Grades Six to Ten attending Government schools. The programme previously suffered from the late release of funds to districts causing delay in stipend disbursement. This year, both tranches were released to all districts before the end of the financial year. The ASI TA team provided support to E&SED and post offices in the preparation of PC-1s; as well as monitoring and coordinating tranche disbursements which helped to speed up the release of funds. The ASI TA team also undertook 29 monitoring visits to six districts. Whilst there appears to have been some overall improvement this year in reducing delays, disbursing in June or later in many cases means households will not receive the second tranche of stipends before the start of the summer holidays. This may impact on the ability of the payment to incentivise enrolment if its main purpose is to reduce the financial constraints to girls attending school.

One of the recommendations from the February Annual Review was that the ASI TA team conduct an impact evaluation of all stipend programmes (KP currently has three). The study, which is being finalised, falls short of an impact assessment due to the lack of an appropriate control group and availability of data. Instead, the focus is on processes and recommendations to improve programme performance. The study nevertheless reiterates the limits of the current programme in effective targeting as well as the limited primary evidence of its impact on school enrolment and attendance. An assumption that targeting is effective is the fact that slightly better-off households choose to send their children to private schools, therefore the girls studying in government schools are, by default, deserving students.

There is also evidence that conditionality requirements are not, in practice, followed. This is mandatory in all but two districts. It is argued that these cannot be enforced due to social pressures and the difficulty in maintaining records. Some districts have developed good standard operating procedures for collecting and managing student information while others are lagging behind.

The study suggests that the current value of the stipends is considered adequate to cover basic expenses and the opportunity costs for girls attending school. However, transportation costs are high and the stipends are not sufficient to cover all related costs. This is borne out by a recent survey by Alif Ailaan that estimated an average annual household expenditure for a child attending a government secondary school of approximately PKR 50,000[1]. For higher grades (nine and ten), a registration and exam fee also have to be paid. An assessment of the appropriate value for a stipend needs to be incorporated into any revision of the programmes.
[1] http://www.alifailaan.pk/notfreeatall

The stipends programme is large and poorly-targeted as it covers all girls studying in Grades Six to Ten in all 25 districts of KP. Monitoring is a challenge and pre-enrolment data is not available to assess the impact on enrolment of girls. IMU monitors the receipt of stipends by asking classrooms of students whether they are receiving stipends, which provides some information but is not robust.

The ESP JRF includes a milestone for FY2015-16 to complete a review of cash transfers, and to agree an approach in the subsequent approach. The newly-established Internal Audit Cell in the Department has also recently conducted an audit of the scheme. It is strongly recommended that E&SED draw on all available evidence when it conducts its review of the programme this year. This is also important for the follow-up on the recommendations of the DFID Internal Audit Report on stipends (see section D).

Vouchers: The voucher scheme of the Elementary Education Foundation (EEF) aims to support out of school children to attend low-cost private schools (LCPS) in areas where there are no government schools.

In 20014-15, EEF launched a pilot in five areas within Peshawar district following which a scale-up was initiated. Around 1,500 vouchers were distributed in the pilot phase. Lessons learnt were incorporated in the scale-up to include six districts and the identification of 30,000 potential beneficiaries. The six additional districts were selected on the basis of the provision of government schools, the numbers of out-of-school children and the proximity of potential beneficiaries to schools.

Semiotics consultants were hired by ASI to identify 30,000 out-of-school children as potential beneficiaries and 231 LCPS as potential partners for the voucher scheme. In its own validation of the survey, EEF highlighted the need to identify additional beneficiaries and conducted a further exercise. Whilst this delayed the process of disbursement of vouchers it ensured sufficient beneficiaries were identified. As of the end of August, 27,481 vouchers had been distributed across all six additional districts. Reasons for non-distribution included: (1) the non-availability of male members of the households during distribution and the reluctance of female members of the households to interact with field staff; (2) the migration of internally displaced people; and (3) changes of address/inability to locate households.  The delay in distribution is expected to have had little impact on students as most vouchers should have reached the beneficiaries before the start of the academic year.

Monitoring the redemption of vouchers over the coming months will be important to assess the success of the scale-up. An initial survey conducted by the ASI TA team on the pilot phase found that the redemption rate of the vouchers disbursed was very low at around 50-55%. A further study revealed that the major causes for low redemption was a lack of awareness of the voucher scheme by beneficiaries, as well as resistance from the community to accept the initiative. The ASI TA team provided recommendations to EEF regarding the provision of uniforms and textbooks; and the development of a school engagement plan. This year vouchers have been increased to cover the costs of uniforms and textbooks, but not transport.

EEF also administered Quality Assurance Tests (QATs) to 236 students who were receiving vouchers in nine partner schools. The aim was to establish a baseline for future beneficiary assessment. The ASI TA team oversaw the tests that were conducted.

GoKP decided not to use Benazir Income Support Programme (BISP) data to identify potential beneficiaries, partly due to concerns around accuracy, data access, and the regularity with which the data are updated. E&SED conducted a household survey in 2005 and plans to start another one soon to identify out of school children which will be completed by December. This is in addition to the national census which is planned to start in March 2016 and which has the potential to establish numbers that are significantly different to those that the GoKP has been working with in recent years. These will provide additional information on the school age population but will not replace the need for regular identification of voucher beneficiaries. In future, EEF is aiming to ensure identification of sufficient beneficiaries by targeting an additional 10% potential beneficiaries to cover for any variation. It also plans to strengthen its capacity and introduce more robust monitoring mechanisms.

Girls’ Community Schools: One of the initiatives of EEF is to establish Girls’ Community Schools to promote access to education for girls from under-served areas. The model is based on a one-room school donated by the community with a teacher identified and selected from within the community. The Government provides teachers’ salaries and free textbooks and teacher resources.

35,412 girls are enrolled in some 940 Girls’ Community Schools established in 25 districts of KP. This is more than the original target. EEF plans to establish a total of 2,000 schools targeting 60,000 girls and aims to contribute to reducing gender disparity in the province. It is too soon to assess the impact of this initiative.

EEF is introducing an monitoring system to track the performance and attendance rates in Girls’ Community Schools as well as the quality of education being provided.

Summary of responses to issues raised in previous Annual Reviews
- Recommendation: The GoKP to consider whether an electronic transfer system is appropriate for the stipends programme.
- Action: The decision rests with E&SED. Following several discussions, the Department’s current view is that introducing such a system would be challenging and is not currently feasible.

Recommendations:

Stipends
- In line with the ESP, E&SED should undertake a more fundamental review of the future of the stipend programmes, drawing on all evidence available, and make clear decisions on steps to improve the impact of the programmes. This should also include a deeper look at options for using BISP data and technology to improve targeting and streamline delivery.
- In the shorter term, E&SED needs to ensure robust monitoring of the disbursement of stipends and document lessons learnt.

Vouchers
- EEF should continue with its plans to strengthen its monitoring system and work with ASI TA to address any issues with redemption early on in the school year.
- ASI TA team to work with EEF to ensure more accurate identification of potential beneficiaries in future surveys.

Girls’ Community Schools
- EEF should introduce a standardised teacher salary disbursement mechanism.
- EEF to introduce a robust monitoring system to track the performance of Girls’ Community Schools and the quality of education provided.
- EEF to provide teacher training for Girls’ Community School teachers.
- EEF, with support from DFID, should explore if the BRAC model for teacher training could be utilised and if there is a role for BRAC more broadly in helping to target areas of KP with low density of both LCPS and government schools.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

Sector budget support (including DFID and DFAT allocations) represents 62% of the overall KESP programme and 3% of E&SED’s budget for 2015/16. It is providing financial support to the GoKP budget for elementary and secondary education. Within this budget, recurrent salaries are the largest cost item representing 71% of total spend in FY2014-15. The allocation for FY2015-16 has increased by 23% on spend in the previous year. The increase reflects in part the sanctioning of an additional 10,000 teaching posts, but also a further increase in salaries. The GoKP budget documents for FY2015-16 describe the rate of increase as alarming and warn of a potential squeeze on non-salary spend. However, the non-salary allocation has also increased by 22% on spend in FY2014-15 and stands at over 9% of the current allocation. The largest cost component in the development budget in FY2015-16 is school infrastructure and renovation. These costs are largely driven by the outcomes of tendering processes. IMC claims that these costs could probably be brought down with better contracting and infrastructure design. Textbooks are another large cost item in the development budget. It cost an estimated PKR 57 (£0.39) per textbook distributed in FY2014-15 with negligible change in unit cost compared with FY2013-14.

Fees and expenses have both increased by over 100% for IMC in the last few months. This is in keeping with the expansion of staff and resources needed for the implementation phase and is expected to continue to increase until the necessary support infrastructure is in place. Capital works rates are currently being finalised with contractors. IMC has raised concerns with DFID that their assumed average unit cost per classroom is higher than anticipated. This will affect their ability to deliver the original number of classrooms and missing facilities within the scope of work and is likely to have a bearing on the overall VfM of the component. In other areas, IMC is demonstrating a conscious effort to manage its costs and secure savings without compromising on quality. One example is the decision to locate district offices where possible within unused E&SED buildings, renovating where necessary to functional standards. This should secure some savings from not having to pay rental of approximately PKR2.7m (£16,981) for an average 18-month period. IMC is also planning bulk purchase for select materials which should also drive down cost.

Fees are easily the largest cost component of the ASI TA contract. Consultant rates fall within agreed bands but should continue to be monitored against overall quality of delivery. Workshop costs make up the largest non-fee component. Per delegate day, these have fallen compared with the previous six months. Used effectively, workshops can be an excellent means of bringing people together to learn, to set performance standards and to create buy-in to the reform agenda. As a large spend item however, these costs should continue to be reviewed against workshop objectives to assess if resources could be better spent through other forms of capacity building. Programme management as a share of total spend has risen over the last period to reflect the effort by ASI to strengthen their programme management function but remains within reasonable limits. Total fees expenditure is expected to rise in the coming months as ASI completes recruitment for its new TA structure.

VfM performance compared to the original VfM proposition in the business case

To address the limited information available from the time of the business case, a set of VfM indicators was developed last year to monitor over the course of the programme. The following provides an assessment against the main efficiency indicators of GoKP spend. The next section looks more broadly at evidence of impact.

Additionality and allocations for non-salary expenditure
These are broad measures of efficient allocation. Assessing trends in GoKP spend on education net of sector budget support indicates whether DFID funding is targeting additional needs in the sector or simply displacing what the GoKP would otherwise be funding. Non-salary spend is typically under-prioritised in education but is necessary to ensure that school inputs such as utilities, furniture and lab equipment needed to complement teaching are available.

There is good evidence of financial additionality. Net of KESP sector budget support, spend on education in FY2014-15 increased by approximately 13% compared with spend in FY2013-14 whilst the FY2015-16 budget allocation predicts a 27% increase over spend in FY2014-15. With inflation currently less than 5%, these represent substantial real increases. The E&SED budget as a share of the total GoKP budget fell marginally from 23.1% in FY2014-15 to FY2015-16 21.4%, but continues to represent a priority spend area for the Government. Non-salary spend increased by 240% between FY2013-14 and FY2014-15 and constituted 9.5% of current spend in FY2014-15. A similar share is allocated for non-salary needs in FY2015-16.

Average unit costs of providing missing facilities under conditional grants
These are based on budget estimates and could be used to compare against IMC cost information, once available. The current average budget for FY2015-16 to build a classroom under conditional grants is PKR 700,000.

Average unit cost of teacher training
Teacher training is resource intensive. E&SED has rolled out a lot of training in FY2014-15 with plans to run more extensive training this coming year. Some training was outsourced for the first time this year, whilst other training was delivered in-house. Unit costs per delegate day for training will be available for comparison once invoicing is complete. These costs will not reflect differences in training, materials and location that affect cost, but given that E&SED is planning further out-sourcing this year, they should provide a starting point for a discussion about cost efficiency. There is a risk that large amounts of resources are going into training with little impact on teaching quality. Building better monitoring into these initiatives and ensuring large numbers are not trained at the expense of quality is a key recommendation of this Review.

Cost per child in school
New enrolment data for FY2014-15 was not available to update this metric. In FY2013-14, the GoKP spent on average £62 per child in primary school and £166 per child in secondary school[2]. Given the low per child spend on education (the UK spends upward of £3,000 per child per year in primary[3]), an upward trend in these amounts in FY2014-15 would be considered a positive outcome, providing the additional resources are being used to improve education services. Unit costs are mostly comparable with spend per child in Punjab, primary costing marginally less and secondary costing around £40 more per child.
[2] Based on EMIS (2013) enrolment figures and FY2013-14 E&SED recurrent spend on primary and secondary functional classifications.
[3] Rough estimate based on IFS 2015 Schools Spending Briefing note and previous right to information responses. Actual spend likely to be higher once all spend across relevant authorities is included.

Assessment of whether the programme continues to represent value for money

KESP currently focusses primarily on institutional reforms and improving systems to deliver better education outcomes. Whilst the resources and reform efforts are yet to demonstrate VfM in terms of improved outcomes, there is growing evidence that at least some of them are on the right trajectory.

The use of IMU data is becoming more institutionalised and is playing a central role in decisions taken at District Steering Committee meetings and district stocktakes with the Chief Secretary and Minister. Whilst it is still early days, and there remain further improvements which could be made to assure the quality of data, there does appear to be a positive trend emerging in some indicators, in particular those areas that officials tend to have more direct influence over such as un-authorised teacher absence. Trends in IMU indicators are shown in the figures below.

E&SED has reported recouping over PKR18m (£113,208) in salary reduction penalties for absent teachers, however more important than these savings is the impact that disciplinary actions seem to be having on teacher presence. Based on the estimated teacher stock of primary and secondary teachers (EMIS 2013), the one percentage point reduction in unauthorised absenteeism equates to approximately 1,190 more teachers present at school. Providing these teachers are teaching, this should have some impact on the numbers of children receiving lessons at a given time. Likewise, assuming for demonstration purposes that the closed schools are all primary schools, then based on an average of 132 children in a primary school and the stock of primary schools (EMIS 2013), the one percentage point reduction in closed schools, means approximately 30,740 more school places are available to children.

There are also areas where improvements in IMU indicators are yet to be seen. There has been no visible improvement in the enrolment attendance gap or in overcoming the challenge of illegal occupation of schools, an area that DEOs cited as especially difficult to handle. Monitoring coverage by district administrative staff has changed little.

The agreement reached on the revised functions of PITE and DCTE, should, if implemented well, have a positive and lasting impact on the management and delivery of teacher training. Anecdotally, revisions to the recruitment test and process is having a positive impact on the quality of teachers entering the system, but again, the impact on learning is still unknown. Encouragingly, the responsible departments are planning further reforms to improve the management and development of teachers.

Efforts to improve budget planning and monitoring have had a clear impact on the utilisation of funds. It is highly unusual for a Department to spend close to 100% of its development budget allocation. Higher utilisation rates not only provide a positive signal about E&SED’s capacity to implement but also encourage staff to actually plan to spend. DEOs that the Review team met with described FY2014-15 as a ‘golden year’ for management, seeing resources reach them for the first time as per budget plans and early enough in the year to actually spend. If this trend continues, there is a growing chance that more resources will be spent on where they’re needed and that education institutions will start to plan more strategically for these resources. This should have a positive impact on the learning environment.

More could be done to improve transparency and ability to track spend down to schools. Non-specific budget classifications and non-reporting of spend beyond a certain level of institution, makes it harder to monitor how exactly resources are being spent and where they are having most impact. Full use should be made of findings from TPVs, monitoring and audits to build up this picture and identify priorities for spend and where further controls are needed. There is great potential for the conditional grants programme, that channels large amounts of resources to PTCs, to improve the provision of missing facilities, but there are substantial risks too to optimum use of resources if the right monitoring and support is not in place. Expenditure tracking exercises might be considered for specific fund flows.

There are other areas highlighted in this Review where the value of benefits from reform efforts is less clear. The management of large amounts of teacher training has been good for building institutional capacity but there is limited evidence at this stage to assess what impact these trainings are having on teaching quality. Likewise, primary evidence is relatively weak on whether the girls’ stipends programme is delivering best value in terms of girls’ enrolment. The rapid expansion of Girls’ Community Schools is extending access but it is too early to know who is benefiting and how well children are learning. Both programmes have a clear focus on improving access to education for girls so it is critical that they are delivering on these objectives.

Overall, the lesson from this Review is that good progress is being made to implement reforms but that there needs to be a continued and clear line of sight to the overall objectives and the quality of interventions if all these efforts are to deliver good VfM.

If the effectiveness of SBS is judged in terms of the reforms that it incentivises, then SBS has performed well over this Review period. SBS is of course not the only driver of this progress but by linking disbursements to progress on the RAF, it has helped to focus activity in specific areas. DFID continues to be the largest development partner in basic education funding in KP. In FY2014-15, DFID’s support constituted approximately 10% of the E&SED budget (including unspent funds rolled over from the previous year). Whilst its support is estimated to make up a smaller 3% share of the budget this year, SBS still creates an opportunity for partnership and dialogue with E&SED.

It is too early to assess the infrastructure component for VfM. IMC’s approach provides confidence that they can deliver infrastructure of good quality, however higher than estimated unit costs could weaken overall VfM. Thoughtful designs and construction techniques demonstrate a clear line of sight to VfM. For example, introducing ‘air wells’ will provide a natural control on temperatures in classrooms across seasons and adoption of a technique known as the ‘Chinese Brick Bond’ is expected to reduce material consumption and cost by 25% without losing structural integrity. IMC is also thinking about opportunities for positive spillovers highlighted under output 3, such as sharing design manuals with E&SED and training PTCs overseeing works funded through other initiatives. If effective, these will enhance the overall VfM of the programme.

TA, by its very nature is harder to assess for VfM. It is clear that the ASI TA support provided to areas such as the IMU, budget execution and revision of roles for DCTE and PITE have contributed to positive changes and opportunities to deliver better value. Evidence of increased capacity in E&SED is also suggestive of TA effectiveness. Some reform areas will demand greater attention to quality if they are to provide VfM and it is hoped that, through the ASI TA refresh, the larger team will help to retain this focus across a number of priority areas. The TA team is also able to provide additional value by growing the evidence base for E&SED’s interventions. If done well and dissemination of findings is managed effectively, then this work can provide a valuable contribution to improving the impact of reforms.

Quality of financial management

Sector budget support

In April 2015, DFID Internal Audit Department reviewed the stipends programme under KESP and assessed it to be high risk. This programme has been running since 2006 and DFID estimates it has contributed £2.3 million through a 30% contribution to E&SED’s stipends programme. Internal Audit recommended that: (1) DFID Pakistan work with the TA team to strengthen the monitoring of the stipends programme and identify where it is possible to put in additional controls; (2) DFID contract a third party validation exercise; (3) DFID discuss with E&SED whether it is possible to implement a system where the beneficiary is linked to money cash transfer forms or whether it is possible to further develop the scheme to include the electronic transfer of funds. On (1), DEOs are assigned the responsibility for monitoring the disbursement of stipends, PO staff are also required to do process monitoring and the TA team district coordinators have been assigned the responsibility to monitor stipends and textbooks. In the new TA work plan going forward, the TA team will document the findings from these monitoring visits. On (2) DFID is currently contracting a third party to undertake the validation exercise which will conclude in the next few weeks. The work will be carried out in mid to late-September to coincide with the start of the school year. On (3) DFID raised this point at the KESP QSC in September with E&SED and the TA team. A further more detailed discussion will take place but it is unlikely that the Department will be able to move to a system of electronic transfers. However, there may be other areas that can be improved.

DFID is also currently undertaking a third party audit of DFID and Australia SBS funds which will report in September. The ASI TA team is providing support to E&SED’s internal audit cell.

Technical Assistance through ASI

Over the previous Annual Review period, ASI improved their financial management and forecasting and have continued to do so. As the TA refresh completes and the work planning is concluded, ASI needs to consider the delays in recruitment of core staff, as well as when surge capacity is needed to deliver, and ensure this is reflected in their financial forecasts.

School infrastructure component (IMC)

The financial management of the programme is structured around (1) advance funding for capital works; and (2) reimbursement for fees and expenses which is subject to a 5% withholding penalty should DFID be dissatisfied with performance. DFID secured prior agreement for the funding arrangement for (1) with HM Treasury in March 2015.

DFID has advanced two sums of funds to IMC for capital works to date in June and July 2015; but IMC have reported delays in payments to sub-contractors due to changing requirements which have impacted on work planning. No advance funding payment was made in August but IMC expect that they will make a request in September. IMC are currently revising their overall forecast substantially down for the next six months in view of their experiences to date of construction in phase one.

Date of last narrative financial report	27/03/2014
Date of last audited annual statement	27/03/2014

E: RISK

Overall risk rating: High

KESP remains a high-risk programme relying on sustainable Government reforms to improve education in a fragile and conflict-affected province. These reforms are dependent on continued political and administrative leadership. With the recent change in the Education Secretary, it is important that high-level momentum for education reform is sustained by the KP Government.

Access to KP, due to security issues, hampers DFID’s ability to visit, build relationships and hold regular policy dialogue with Government counterparts and monitor progress supported by the TA team. DFID visits Peshawar whenever possible and also conducts regular monitoring trips to districts within British High Commission security parameters. DFID is very appreciative of the Department’s willingness to travel to Islamabad for key meetings.

Overview of programme risk

Context
Security and conflict remain one of the primary risks to programme delivery. As described above, political will is also critical. The impact of devolution on delivery also warrants further analysis.

Partner/delivery
The risks to delivery include a lack of buy-in from E&SED at the bureaucratic level to education reform and non-delivery of the various TA components (ASI, IMC and OPM). The availability of sufficient funds to resource delivery is also a risk, particularly as the GoKP faces a potential revenue shortfall this financial year.

Another notable risk to flag is the trade-offs implied by the fixed budget of the infrastructure component managed by IMC. The inclusion of higher secondary schools has significantly decreased the money available for lower, middle and higher schools. IMC has just begun to let contracts to sub-contractors and are negotiating the unit costs. The actual unit costs agreed will clearly affect the number of classrooms to be constructed and pose a significant risk to delivery.

Reputational
DFID’s investment in KESP is substantial (£283.5 million). This represents DFID’s fourth largest investment in Pakistan (by financial size) and also DFID’s fifth largest global bilateral programme. The size exposes DFID to substantial reputational risk if delivery goes off-track.

Fiduciary risk
Fiduciary and corruption risks for the education sector are ‘substantial’ according to the Fiduciary Risk Assessment 2009 report. These risks are acknowledged and mitigating actions are in place including; maintaining budgeting monitoring for the current fiscal year; continuing to improve public financial management systems, and strengthening of internal audit functions.

Outstanding actions from risk assessment

The risk matrix (detailed at Annex B) needs to be reviewed and updated. A more explicit link should also be made to the high-level risks and how they will impact on programme delivery. The risk matrix should be discussed as a standing agenda item (either monthly or quarterly) at the revised KESP monthly technical/monitoring meetings in DFID.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Sector budget support

Taking into account the £18.4 million disbursed in August 2015 against the interim RAF, KESP has disbursed £99.6 million out of the £181.2 million allocated for SBS. A further £1.6 million may be disbursed in December 2015 depending on progress against the outstanding IMU results areas in the interim RAF.

Technical assistance through ASI

The TA contract has been extended multiple times during the period the Review covers. A bridging contract extension was approved until 12 March 2015, below the threshold for ministerial approval, and utilising unspent funds within the existing contract. This interim arrangement was put in place as DFID was waiting to agree with the Government of KP a new multi-year JRF to monitor the ESP. In March 2015, the Secretary of State for DFID agreed a new contract until the end of June 2015 pending the outcome of an audit. A subsequent contract was then agreed from the end of June to the end of September 2016 in line with the original end of KESP and the OJEU terms of reference. Because of KESP’s high risk rating, historical programme management issues and ASI’s corporate stance on hybrid contracts, the contract has remained input-based. DFID is currently in the process of starting a new OJEU process to procure a TA supplier for the extension to KESP.

The uncertainty of the contractual situation has impacted on the ASI TA team as people have been understandably concerned about tenure. The current extension to end September 2016 should give the ASI TA team assurance and continuity to deliver over the year ahead.

Infrastructure component

As highlighted across this Review, progress on the school rehabilitation and construction component has been delayed This will have a knock-on effect on the delivery of results as stipulated by the original ToR as this component is significantly behind schedule. An extension to March 2018 will probably be needed to recoup lost ground.

Evaluation

Oxford Policy Management (OPM) has remained in the inception phase for the evaluation work. This is now substantially delayed. The inception phase was due to end on 31 December 2014 but was extended to March 2015 due to the reprioritisation of different aspects of the evaluation. An inception workshop took place in March 2015 where the supplier’s evaluation implementation plan was discussed and the inception phase extended further to June. There were also delays with submitting the final inception report and ensuring it was of sufficient technical quality. DFID has recently taken the decision to scale back the scope of the evaluation from a system-wide evaluation, impact evaluation and research to just a system-wide evaluation. A contract amendment will be needed before OPM proceed with the KP system wide evaluation. This is an output-based contract with payment linked to the delivery of milestones and a 10% payment set aside for quality deliverables.

Performance of partnerships

Sector budget support

Relations with E&SED have continued to be open since the last Annual Review. The Quarterly Steering Committee continues to be an important forum to bring Government, ASI, IMC, DFID, Australia and the EU together to review progress.

Technical assistance through ASI

ASI has continued to work closely with the Government and supported them to achieve the results indicators in the interim RAF. It is noticeable there is increased capacity and confidence within E&SED indicating that the TA team is building good relationships. The general regard by E&SED for the ASI technical team is positive.

Following on from a Key Supplier Management visit by ASI Senior Management in April which resulted in a change of senior personnel, including the establishment of a new ASI Country Director position, ASI and DFID relations have become more open and candid with an emphasis on the challenges to progress and solutions. There has been some improvement in programme management supported by stronger senior oversight. Both parties agree that the format of the current monthly technical meeting needs to be revised and streamlined. Some lessons could be learnt and replicated in KESP from the monthly Punjab Education Sector Programme (PESP) II ASI/McKinsey/DFID monitoring meeting.

Infrastructure component

IMC continue to perform well despite the hurdles and some initial relationship-building challenges. DFID continues to work openly with IMC to try and resolve challenges to progress.

Evaluation

The DFID partnership with OPM has been open and transparent, particularly regarding timelines for delivery and the quality of personnel appointed by OPM to deliver this component.

Other donors

When KESP started in 2012, a number of donors supported implementation of the previous GoKP Education Sector Plan. Some of these donors (including GIZ, Canada, the Netherlands and Norway) have since moved away from basic education in KP due to falling budgets or prioritisation of other sectors. Currently just DFID, Australia (through a Development Partnership Agreement with DFID) and the EU fund the education sector through SBS.

Both Australia and the EU are standing members of the KESP Quarterly Steering Committee and relations remain good. Australia chairs the KP Education Donor Support Group.

Last year, DFID initiated a process on behalf of the SBS donors (Australia and the EU) to agree a JRF for the ESP against which donors will disburse funds to the GoKP. This was successfully concluded in June.

The EU have subsequently used the JRF and agreed more detailed indicators with E&SED against which they can disburse their SBS funds. The EU are now waiting to conclude negotiations with E&SED on the level and scope of TA offered through their agreement. The EU have consulted with DFID to ensure that this does not conflict with or duplicate the TA package provided through ASI. The time period of the total EU commitment is 2015 to 2018 and the total funds available are EUR 39 million (£27.5 million equivalent).

Asset monitoring and control

The last asset check took place at ASI on 21 August 2015 and no major issues were found. DFID is planning an IMC asset check in the near future once the development of an asset register is complete.

G: CONDITIONALITY

Update on partnership principles

The new Partnership Principles Assessment (PPA) is regularly discussed with the Government of Pakistan. This sets out the Government of Pakistan’s commitment to the four Partnership Principles as demonstrated through its policies and actions and will supersede the previous Development Partnership Arrangement. The four Partnership Principles represent a commitment to: reducing poverty and achieving the Millennium Development Goals; respecting human rights and other international obligations; strengthening financial management and reducing the risk of funds being misused through weak administration or corruption; and a commitment to strengthening domestic accountability.

DFID Pakistan’s overall assessment is that the Federal Government is demonstrating a credible commitment to the four Partnership Principles, particularly given the fragile security and the challenges of the country’s democratic evolution. Pakistan lifted the moratorium on the implementation of the death penalty following the school attack in Peshawar in December 2014. The UK remains opposed to the death penalty in all cases and will continue to raise this as a concern in our dialogue with the government. In the meantime, we judge that it would not be fair that the poorest across the country should suffer from a withdrawal or reduction of UK support. A continuing substantive direct partnership is therefore justified. It should also be noted that there are also growing concerns about the operating space for implementing partners, particularly International Non-Governmental Organisations (INGOs).

With support from KESP technical assistance, the GoKP is costing the ESP and strengthening budget planning, execution and reporting. Technical assistance is also helping to build the Department’s internal audit functions and support stronger financial management at the district level.

H: MONITORING & EVALUATION

Evidence and evaluation

The contract for the formal evaluation covering both KESP and PESP II was awarded in early 2013 to OPM. The inception phase was due to end on 31 December 2014 but then extended to March 2015 due to the reprioritisation of different parts of the evaluation. An inception workshop took place in March 2015 and the inception phase extended further to June.

A range of evidence exists on education in the province, albeit of varying quality. The TA team is in the process of bringing all the evidence together in one place to improve access and consistency of use. The Independent Monitoring Unit has now been collecting monthly data for over a year which has provided a more robust and accessible set of timely data by which to make decisions. Annual EMIS data tells a slightly different story, however these is some discussion that the IMU data is starting to feed into EMIS which may improve its robustness and comparability. 2014-15 EMIS data has yet to be published. (The JRF highlights the need for the Department to examine the use and consistency of these two data sets). Both data sets provide gender disaggregation and it is hoped that gender-specific targets will be set to enable a stronger gender focus.

Monitoring progress throughout the review period

The programme is monitored in several ways, including through internal DFID monitoring processes, monitoring of the TA and infrastructure components as well as monitoring of reform progress and senior-level engagement with the GoKP.

DFID’s programme team reviews its programme delivery plan on a weekly (work plan), monthly (finances) and quarterly (risk matrix) basis. In addition, progress against the RAF is closely monitored in conjunction with ASI. DFID has an agreed schedule of meetings with ASI to monitor progress on the programme. There is a fortnightly programme team meeting as well as a monthly technical team meeting where the monthly TA report is reviewed and provides an opportunity for DFID to discuss issues and review deliverables with the TA team. These arrangements have not changed since the KESP TA refresh.

The monitoring and evidence framework, including the VfM framework, continues to be developed between DFID and ASI, however progress has been slow. It was agreed that the monitoring part of the framework would be finalised in advance of this Annual Review, however this is still not fully populated with data. The intention is for this framework to form the cornerstone of regular monitoring and the definitive picture of progress in the sector at any one point. Extra focus will be required to get to that stage and both the DFID and TA teams should then ensure it forms part of regular monitoring. The VfM indicators have largely been updated with the latest data.

The KESP Quarterly Steering Committee meetings are attended by GoKP, DFID, other SBS donors (DFAT and EU) and the TA teams and allow collective discussion on progress. In addition, Education Working groups have been set up as sub-committees to the Strategic Development Partnership Framework (SDPF) committee, involving donors and the GoKP. These provide platforms to focus on specific issues such as the role of PTCs and curriculum standards. Since October, only one meeting was held (in May 2015) with the next one delayed to September to coincide with the KESP Quarterly Steering Committee.

The GoKP has its own internal monitoring processes which include budget execution meetings conducted by the Minister twice a month and other monitoring meetings to take stock of IMU data and district performance. The KP Apex Committee, which is used to resolve cross-portfolio blockages, and challenges and to co-ordinate with other development partners, and the Strategic Development Partner Forum meetings provide a further opportunity to flag high-level concerns about progress or the pace of delivery with the Chief Minister.

DFID has been meeting with IMC fortnightly to discuss issues and progress. Now that construction has started these meetings will become weekly. IMC have developed a Theory of Change and Monitoring and Evaluation framework (to be finalised in October) which includes the linkages between components as well as definitions and methodologies for key indicators. They have developed a range of monitoring tools, including a construction-specific logframe and user satisfaction surveys. In addition they have developed checklists which will enable PTCs and community groups to monitor progress and quality and then feed into the central monitoring procedures at the district level. IMC and GoKP now have weekly meetings to update each other on issues or potential cross-over in work. This increased communication seems to be improving relationships and understanding of each area’s priorities.

Beneficiary feedback

In addition to meeting with DEOs and DMOs, the Review team visited one girls’ higher secondary school in Charsadda and met with the head teacher, teachers and members of the PTC. Construction work for an additional classroom, funded through a special ‘security measure’ scheme, was taking place at the time of the visit.

The Review team met with the principal and several teachers of the girls’ high school where around 720 students are studying. In response to a question about the general improvements in the education sector, the principal shared that promotions have happened, vacancies are being announced and enrolment has increased. The teachers had received various kinds of training and the feedback was generally positive. The training focused on English language, pedagogy and content knowledge of different subjects and had helped them in their teaching.

The team also met with a few PTC members in the same school where construction of classrooms was going on. The chair of the PTC (previously a head teacher) shared that she just signs whatever the principal asks her to do. It seemed that the principal was in control of the PTC contracting process related to the construction of classrooms including selection of the contractor and purchase of construction material. There was some willingness on the part of the members to be engaged but a lack of training was evident from the conversations the Review team had with them.

The DFID KESP team also visited Mardan on 22 April and met with the DEO, IMU monitors, a primary boys’ school head teacher, the PTC and pupils. The team also visited another boys’ school which had benefited from the minor works carried out by IMC at 28 higher secondary schools during the inception phase. The visit focused on the progress of the IMU; the difference this was making to cutting teacher absenteeism and the positive effect on teacher attendance; the benefits that daily visits by IMU monitors were bringing to schools in terms of increasing accountability; and the actual process of data collection.

Annex A - Summary of July interim Results and Activities Framework Review

Results	Status	Comments
Roles and responsibilities of key provincial level institutions reviewed and streamlined	Complete	The KESP technical assistance team has developed and submitted a proposal for changes to the roles of the Provincial Institute of Teacher Education (PITE) and Department of Curriculum and Teacher Education (DCTE) to the Department for approval. The proposal has been reviewed by the Education Secretary and presented to the Minister on 15th July 2015 where the revised TORs were formally approved.
District Education Officers monitor schools and provide support for education improvement	Complete	Districts taking actions to follow up on, and address issues identified through Independent Monitoring Unit (IMU) data. Training on the use of IMU data has been given and E&SED has introduced standard operating procedures to ensure consistency.
District Education Officers plan and budget effectively for education improvement	Complete	Five pilot District Education Plans (DEPs) were developed by District Education Offices and approved by E&SED. This helped pilot Districts to plan, budget and take forward their work plans in a timely manner. The DEPs were presented to all District Education Officers (DEOs) at a workshop on 10th-12th July.
Independent Monitoring Unit data is operational publicly accessible	In progress	A website has been created but data is not publically available. It is not clear when E&SED will be ready to make IMU data more publically accessible.
Improved teacher recruitment process developed and implemented	Complete	TORs and guidelines developed and shared with the National Testing Service (NTS). This has helped remove political interference in the selection and appointment of teachers.
E&SED provides professional development for teachers, head teachers and principals	On track to be completed	Head Teacher training is well underway. 143 out of 250 Higher Secondary School principals have received training on all four modules, and plans for the remaining schools are still in progress. Teacher training was divided in two phases of five days and three days. 17,627 teachers have started training of which 11,865 teachers have completed training on all modules. The remaining training is expected to be completed in the coming weeks.
Parent Teacher Councils (PTCs) are supporting schools effectively	Complete	11,452 PTCs in 12 districts have been provided training on their basic roles and responsibilities. This has exceeded the original target of 3,000 and E&SED has plans to train PTCs in the remaining 13 districts over the rest of the financial year.
Institutionalise an annual sample based assessment of student learning in early grades	Complete	The assessment was administered to 4,966 children in a total of 329 schools, exceeding the required sample size of 300 schools and 4,500 children
Government supports children to attend low cost private schools	On track to be completed	Initially, the target was to scale up voucher distribution in four districts (including Peshawar). However, distribution has started in six districts and is expected to be completed by the end of the second week of August.
The Government increases access to schooling for girls living in underserved areas	Complete	857 Girls’ Community Schools have been established as of 11th June 2015.

Annex B – KESP Risk Matrix
Sr #.	Risk	DFID Risk Owner	Probability	Impact	Mitigation Measures	Residual Risk
	Context
1	Political: Lack of, or reduced political will, due to different priorities or focus on other sectors. Changes of key individuals both at ministerial and bureaucratic levels resulting in shift of focus and policy in education department.	Lead Adviser	M	H	DFID and TA to work closely with the provincial government for their effective buy-in on key decisions related to this programme, and to jointly achieve education and development objectives. DFID to engage TA to focus retention of buy in from the bureaucracy and political leadership to sustain the policy changes in education sector. DFID could engagement with the Chief Minister on institutional reform. DFID to regularly visit Peshawar where possible to build relationships with E&SED	M
2	Conflict: Deteriorating security situation in the country/province Targeting of attacks on schools especially after December 16 2014 school attack in Peshawar DFID not able to travel frequently to Peshawar for monitoring of programme	Conflict Adviser/Lead Adviser	M	H	DFID to closely monitor the security situation DFID to work closely with the E&SED to improve security protocols for schools. DFID to closely monitor security situation and put in place appropriate measures.	M
3	Humanitarian Crisis: Affecting delivery of programme, either for implementing partners to deliver or changing priorities of the programme. Risk of schools being used in disaster situations as camps for IDPs, resulting in children kept out of schools Lack of disaster resilient school infrastructure	Lead Adviser	M	H	DFID to work closely with TA and its stakeholders throughout the duration of the project to monitor the situation and put processes in place to respond where necessary DFID with TA to work with E&SED to monitor the situation closely. DFID to make sure that the TACE component has all the disaster resilience SOPs included in the programme.	M
4	Macroeconomy: Deterioration in macroeconomic conditions with potential impact on fiscal space and other macroeconomic variables including inflation and exchange rates. Reduces availability of public funding for education and/or erodes the purchasing power of DFID financial aid	Lead Adviser	M	H	DFID to closely monitor the economic conditions and overall political economy of Pakistan TA to bear the potential increase in the fee costs due to inflation. Movements in exchange rate will be mitigated through pricing in GBP; while TA will closely monitor the financial and management procedures to deliver the project in time	M
5	Devolution: Local government elections not happening to time which may stall the programme activities to support devolution to the district level Lack of capacity at district level and lack of clarity of roll out of systems. Impact of sub-provincial devolution under the KP Local Government Act on the programme results	Lead Adviser	M	H	Working closely with TA to support devolution and to create a set of clear principles to roll out the systems. Working with TA to build capacity of the district level education department staff. TA and DFID to monitor impact of Local Government Act and elections closely to note key changes in the impact of the programmes.	M
	Partner/delivery
6	Inability to deliver the programme: Partners lack of capacity to deliver, due to security situation or challenge of recruiting high-quality staff to work in Peshawar Low availability of good human resource willing and able to work consistently in KP. Lack of skilled human resource in the field for adequate research and survey Poor performance: related to contractors and sub-contractors	SRO	M	H	TA to develop an extensive security plan with robust protocols in place with DFID, which will extend to all partners and third parties. TA will also regularly monitor the security situation in the country and at project sites for the safety and security of all staff and offices associated with this programme. A will adapt its programme of work as necessary to avoid areas of conflict. Closely monitoring the activities of partners and their deliverables in a timely manner, to avoid lapse in delivery and put in adequate controls to minimise problems. Extensive monitoring mechanism will be in place to tackle poor performance.	M
7	Rising costs: Due to security and access issues extra measures will be taken to implement this project which could be expensive. Rise in cost to operate in KP	SRO	M	L	TA will be required to submit to DFID updated costed work plans at the end of each phase for the subsequent phase. Deviations in cost will be monitored and managed accordingly.	M
8	Lack of engagement with other key players: Uncoordinated response to the Education Sector Plan, leading to slow delivery. Different donor priorities placing competing demands on the GoKP and limiting delivery.	SRO	L	M	DFID to encourage TA to support coordination DFID to work with TA to proactively coordinate with DFAT, EU and other DFID partners to create synergies and put all of the stakeholders under one agenda	L
	Reputational
9	Negative public opinion about the overall KESP programme: public opinion, in Pakistan and/or UK moves decisively against the project’s core objective or DFID’s funding. Negative impact of curriculum changes specifically influenced by political parties	SRO	M	H	TA programme will develop and implement a communication strategy for overall programme including this component focusing both for UK and Pakistan-based audiences. DFID to work with E&SED through TA to monitor negative curriculum policy changes and encourage the E&SED to create a positive narrative	L
	Fiduciary Risk
10	Fraud/ corruption risks: Risk of DFID funds being misappropriated GoKP fails to safeguard DFID support from ineligible areas of expenditure.	SRO	M	H	Clear guidance to partners on appropriate use of DFID funds and support to develop systems and structures to reduce the fraud risk. Third Party Audits to verify DFID expenditure.	M
11	Financial Risks: Poor government budget execution impacts on utilisation of donor funds, increasing exposure to fiduciary risk and/or weakening additionally of funding.	SRO	M	M	DFID to work with government to achieve results areas in order to disburse funds in a timely manner DFID to closely monitor budget execution.	L
12	Financial Risk on infrastructure component: Funds not spent in time, inflation, exchange rates and the independent contractor's capacity to deliver timely progress	SRO	M	M	TACE to keep a close look out on the exchange rates, price in GBP, bear overcosting, planning delivery of work accordingly to minimise falling out of timelines DFID to work with IMC put in place a clear timeline to enable delivery on time.	L

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for Annual Reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the Annual Review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous Annual Reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process