Project Completion Review - Top Sheet

Review date:	June 2016
Title: Support to the World Health Organisation (WHO): 2011-2016
Programme code: / GB-1-202715			Start date / 12 August 2011	End date: / 31 March 2016
If programme was closed >1 month early please describe in a few words why.			N/A

Summary of programme performance

Year	13/6/12 / Annual Review	13/12/13 / Annual Review	01/01/15 / Annual Review
Programme score	B	A	A
Risk rating	Medium	Medium	Medium

Overall output score following Project Completion Review:

The overall score for the programme is A.

This review recognises: WHO’s continuing unique role in the global health system; the importance of the WHO’s contribution to global health security; and progress on WHO reform since the beginning of this programme in 2011.

To perform more consistently and strongly against its global mandate and deliver results at country level it is imperative that WHO continues to reform, and puts these reforms into practice. Without this, WHO will not contribute fully to the achievement of the Sustainable Development Goals.

Financial Position

Original programme value	£50,000,000
Extensions/ amendments	Addendum: Scale-up: providing an additional £4m spread equally across 2013 and 2014 following achievement of reform targets / Addendum: Bridge-funding: additional £14.5m to cover financial year 15/16 (project originally due for completion in 14/15)
Log-frame revisions (with dates)	Following MAR 2013 (change dated 28/05/14) / Following adoption of Ebola resolution by WHO Executive Board Special Session in January 2015 (change dated 23/03/15)
Total programme spend	£68,500,000

Follow up actions required following closure

A new business case for core voluntary contribution (CVC) funding support to WHO for the period 2016-2020 is being prepared for ministerial consideration and potential approval. This will address lessons learned from this Project Completion Review. The business case will emphasise the continuing priority the UK places on WHO reform and impact and as such will make a significant proportion of future funding conditional on WHO’s progress against its reform objectives and delivery of results.
A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202715/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202715/documents

Outline of programme and what it has achieved

WHO is the lead agency in the international health system. WHO has a unique mandate for the whole of health, which includes setting norms and standards, providing technical assistance where needed, shaping the research agenda and leading the international response to disease outbreaks and health emergencies.

In the original business case for this programme (2011) DFID stated that our core voluntary contribution (CVC) would help WHO fulfil its critical leadership role in global health and development. Namely:

1. Convening for better health, bringing together multiple actors to address key issues.
2. Generating evidence on health trends and determinants, providing internationally recognised evidence to guide action.
3. Providing advice for health and development, building on its reputation for impartial and authoritative advice.
4. Coordinating health security, playing a critical global monitoring and response role.
5. Strengthening health systems and institutions.

This review considers that the UK CVC has made an impact on WHO achieving its programmatic aims and progress on its reform agenda.

This in turn has resulted in a significant contribution to DFID’s strategic objectives. However, as this Project Completion Review (PCR) details, considerable work remains to be done if WHO is to contribute to its full potential and help deliver health results.

This PCR assesses WHO’s performance against four specified outputs, each with its own set of indictors – these are detailed in section C.

In addition, the PCR draws on other available evidence such as: DFID assessments of WHO performance as presented to governing bodies such as the World Health Assembly and Executive Board; our regular informal interactions with WHO throughout the period of this programme; and feedback from other DFID teams engaged in work with WHO – including at country office level.

The logical framework (“log frame”) for this programme described impact in terms of progress towards the Millennium Development Goals (MDGs) 4, 5, 6. Namely:

Maternal mortality
Target: Reduction of 75% by 2015 compared with the 1990 baseline
Result: Mortality rates fell by 44%.

Malaria mortality
Target: Reduction of 75% in the number dying from malaria compared with the 2000 baseline
Result: Mortality rates fell by 60%.

Child mortality
Target: Reduction of 2/3 by 2015 compared with the 1990 baseline
Result: Mortality rates fell by 53%.

The log frame for this programme described outcome in terms of WHO reform. It set the expectation that “WHO makes significant progress on its three reform pillars (Programmatic, Governance and Managerial).”
By its own conclusion (paper A69/4 for the World Health Assembly) WHO has made greatest progress on programmatic reform (100% of expected outputs having reached the implementation stage) but less strong progress on governance (80% of expected outputs having reached the implementation stage) and managerial reform (70% of expected outputs having reached the implementation stage

As this PCR details, DFID’s judgment is that progress on WHO reform has been made – significant progress in places.

However, as DFID assesses WHO reform as it stands today and considers where we want WHO to be in the future, WHO falls short of UK expectations. Further and faster progress is now required. It is also critical that reforms are put into operation with evidence of strong implementation in the organisation that leads to concrete and verifiable results – not least health results at country-level.

WHO must accelerate its reforms focusing on: strengthening accountability between the different levels of WHO’s governance structure; improving its operating model, including human resources, risk management, evaluation and systems for monitoring results and impact at country level; and ensuring that the information management systems are in place for WHO to join the International Aid Transparency Initiative (IATI) later this year.

DFID does recognise that progress on reform is not solely within the hands of WHO. For example, some Member States, that place great importance on regional autonomy, have not fully embraced efforts to improve accountability between the different levels of WHO. Nevertheless, DFID does believe WHO can and should make further progress, with pace, on its reform efforts.

The Ebola outbreak was a highly significant external event that tested WHO’s ability to deliver against its global mandate. The short-comings exposed in the global Ebola response led to a series of high-level reviews of WHO’s role in global health with a focus on health emergencies. This included:

- Reports of the Ebola Interim Assessment Panel (chaired by Dame Barbara Stocking)
- Reports of the Advisory Group on Reform of WHO’s Work in Outbreaks and Emergencies with Health and Humanitarian Consequences (chaired by Dr David Nabarro)
- Review Committee on the Role of the International Health Regulations (2005) in the Ebola Outbreak and Response
- UN Secretary-General’s High Level Panel on Global Response to Health Crises.

These reviews included recommendations related to WHO organisational reform. The WHO Health Emergencies Programme (HEP) has collated these recommendations and categorised them under each major area of the HEP’s work programme. Given the relevance of these recommendations for wider WHO organisational reform, DFID would urge WHO to ensure these recommendations do not become “siloed” within the HEP – they should remain integral to wider organisational reform work.

Since 2011, WHO’s General Programme of Work 2014-19 has been approved by the World Health Assembly as well as programme budgets up to and including the 2016-17 biennium. WHO reports annually to the World Health Assembly on its performance, including on the details of internal and external audit and the range of reform activities – programmatic, governance and managerial.

The business case for DFID’s 2011-2016 core voluntary contribution focused primarily on WHO’s organisational reforms although indicators were incorporated in the log frame that linked to WHO’s emergencies reform (2.3 & 4.3 relating to the Contingencies Fund for Emergencies and the Global Health Workforce respectively). Progress on WHO’s emergencies reform goes hand-in-hand with progress on WHO’s organisational reform.

This PCR identifies a number of recommendations (both for WHO and for DFID) that aim to further support WHO’s reform programme. DFID will monitor WHO’s response to these recommendations as part of our assessment of WHO’s future performance. The recommendations are listed in full below.

Recommendation 1:

DFID should apply the lessons learnt from this programme to the preparation and management of the business case and log frame for DFID’s CVC 2016-2020.

Recommendation 2:

In the upcoming business case for CVC 2016-2020, DFID should construct a new business case section that specifically makes the link to other UK-funded WHO programmes and projects.

Recommendation 3:

In the upcoming business case for CVC 2016-2020, DFID should include a strong element of conditional funding/ payment by results to further incentivise WHO reform. Up to 50% of annual funding.

Recommendation 4:

In the upcoming business case for CVC 2016-2020, DFID should ensure that theory of change principles are rigorously applied and expected impact is tightly aligned with outcomes, outputs and indicators selected.

Recommendation 5:

1. WHO should further strengthen its online reform dashboard, ensuring indicators are “SMART” (specific, measurable, assignable, relevant, time-bound) so that the UK and other member states can hold WHO to account for progress with these reforms;
2. DFID’s business case and log frame for CVC 2016-2020 should use indicators that better reflect progress with effective reporting and monitoring of results and are appropriately specific.

Recommendation 6:

1. WHO should bring together existing tools for measuring country impact, enhancing where necessary, and integrating these into a unified system of reporting and results monitoring (that includes the reform dashboard);
2. WHO should ensure that it has a clear and measurable link between reforms and results, as well as specific outputs and indicators to measure results and impact at county level.

Recommendation 7:

1. WHO should produce and deliver a clear cost-efficiency plan. This plan should identify clear efficiency targets against which DFID and other Member States can hold WHO to account. Such a plan will help WHO demonstrate actual improved efficiency – as opposed to simply reduced corporate expenses.
2. The log frame for CVC 2016-2020 should include comprehensive indicators measuring the degree to which WHO delivers value for money for the UK’s investment.
3. In the preparation of the business case for 2016-2020 CVC, DFID should perform a thorough assessment of WHO’s VFM mechanisms and design log frame indicators that incentivise strong progress by WHO in this area.

Recommendation 8:

1. WHO must further strengthen its audit function with particular attention paid to how effectively audit recommendations when implemented and reinforced throughout the system address underlying risk.
2. WHO should continue to prioritise audit recommendations which have the greatest impact on organisational effectiveness and take forward cross-cutting thematic audits.

Recommendation 9:

1. WHO must ensure its risk management reforms are successfully implemented across all three levels of the organisation. Risk mitigation plans in particular need to be rigorously adhered to.
2. WHO should ensure that all staff understand the agreed “risk appetite” for their work. Staff who work in inherently high-risk situations should feel supported and empowered to act. Risk appetite will differ by WHO office and by the issue in question. WHO has made steps in this respect, such as articulating risk appetite in the Corporate Risk Management Policy. The task now is to ensure this translates to practice on the ground.

Recommendation 10:

WHO should develop its culture of learning and improvement, fully exploiting its ambitious programme of reviews and evaluations.

Recommendation 11:

1. WHO should consider and propose further measures to improve gender equality, including increased parity for higher professional posts across the three levels of the organisation.
2. DFID’s business case for CVC 2016-2020 should use indicators that better reflect progress with WHO’s work to promote gender equality.

Recommendation 12:

DFID should consider indicators for the business case for CVC 2016-2020 that better reflect progress on HR reform; including efficient and effective delivery of the reforms.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The intended outcome of this core voluntary funding 2011-2016, as described in the original business case, was “to help WHO to fulfil its mandate and deliver development results. It will also support the organisation to undertake critical reforms so that it can, in future, make a more effective contribution to health outcomes”.

This PCR details progress made by WHO against specific indicators and targets set (and updated in places) in the original business case for CVC 2011-16. These are considered in detail in Section C.

In places there has been significant progress. For example: WHO successfully adopted a programme budget for 2016-17 that was accompanied by a “SMART” results framework (indicator 1.1); WHO has implemented a new corporate resource mobilisation strategy (indicator 2.1); WHO has made good progress on reducing the number of Direct Financial Contribution (DFC) reports overdue (indicator 3.1); and WHO has made a significant breakthrough in implementing its staff mobility scheme (indicator 4.2).

However, in other places, progress has been weaker and certainly not advanced as far as DFID would have hoped. We urge greater focus here. In particular: WHO’s communication strategy has not yet been implemented at all three levels of the organisation (indicator 1.3); WHO has not done enough to demonstrate the robustness of its efficiency measures (indicator 2.4); WHO has work to do on strengthening its accountability framework in line with good international practice (indicator 3.4); and WHO is still not where it needs to be in terms of having the right people in the right place at the right time (output 4).

Looking beyond outputs and indicators, of key importance, is the extent to which progress on reform has had impact on WHO’s ability to deliver on its mandate and development results. DFID seeks progress on the discrete aspects of WHO reform not because this is an end in itself but because we expect impact in terms of better health. DFID’s judgment on the importance of WHO is clear: the WHO is critical for global health.

The current General Programme of Work (GPW) defines WHO’s high-level strategic vision for 2014–2019 and highlights WHO’s 6 core functions:[1] providing leadership on matters critical to health; shaping the health research agenda; defining norms and standards for health; articulating policy options for health; providing technical support and building capacity to monitor health trends.
[1] General Programme of Work 2014-2019 page 25

WHO will make a critical contribution to SDG 3, which is focused on health, as well as to several other SDGs to which WHO will also contribute. As indicated in WHO’s report ‘From MDG to SDG’, almost all targets included under SDG 3 are addressed in the strategies and global action plans adopted by the World Health Assembly. The importance and expected contribution of WHO only serves to amplify the need for accelerated progress on reform to achieve a level of organisational excellence that can deliver results.

With this in mind, and while recognising the important progress WHO has made to-date, this PCR judges that WHO still has a significant distance to travel on its reform journey if it is to demonstrate tangible improved impact in helping to deliver health results. There is currently no clear link between organisational effectiveness and reform and the improved delivery of health results at country level; nor is there a convincing theory of change that links WHO’s actions and performance with progress on the global health indicators captured in the impact level of the log-frame.

WHO must accelerate its reforms focusing on: strengthening accountability between the different levels of WHO’s governance structure; improving its operating model, including human resources, risk management, evaluation and systems for monitoring results and impact at country level; and ensuring that the information management systems are in place for WHO to join the International Aid Transparency Initiative later this year. It must develop and articulate a causal link to results and a theory of change which clearly outlines WHO’s contribution. Only in this way can Member States and donors to WHO properly hold it to account on performance.

Output Score and Description

The overall score for the programme is A.

This review recognises: WHO’s continuing unique role in the global health system: the importance of the WHO’s contribution to global health security; and progress on WHO reform, including on emergencies reform (albeit triggered in large part by the Ebola outbreak).

However, WHO reform has not advanced far enough. Some of its Member States and parts of WHO itself have not fully embraced the reform agenda. These challenges demonstrate the importance of reform. WHO can and should continue its reform efforts with pace. Without this, WHO will not contribute fully to the achievement of the Sustainable Development Goals.

Lessons and how these have been shared

Lessons learned throughout this programme were documented and disseminated to WHO following each annual review. The overarching lesson from this PCR is that WHO and hence the reform of the WHO is critical to the performance of the organisation but also to the wider global health architecture which it leads and coordinates.

DFID has also learned lessons for its management of our CVC to WHO. In particular, DFID should continue to ensure the business case for CVC 2016-2020 is fully aligned with the multiple other routes by which the UK provides funding to WHO.

DFID should also seek to maximise the influence its CVC brings to bear on WHO reform, in particular by making best use of conditional funding/ payment by results. Finally, DFID must ensure that the future business case and log frame better aligns impact, outcome and outputs. WHO, through its results reporting framework must have a clear link and theory of change from reforms to results delivery at country level.

Specific recommendations to support WHO reform

Recommendation 1:

DFID should apply the lessons learnt from this programme to the preparation and management of the business case and log frame for DFID’s CVC 2016-2020.

Recommendation 2:

In the upcoming business case for CVC 2016-2020, DFID should construct a new business case section that specifically makes the link to other HMG-funded WHO programmes and projects.

Recommendation 3:

In the upcoming business case for CVC 2016-2020, DFID should include a strong element of conditional funding/ payment by results to further incentivise WHO reform. Up to 50% of annual funding.

Recommendation 4:

In the upcoming business case for CVC 2016-2020, DFID should ensure that theory of change principles are rigorously applied and expected impact is tightly aligned with outcomes, outputs and indicators selected.

## C: DETAILED OUTPUT SCORING

Output Title	1. WHO has an effective system for reporting and managing results
Output number per LF		1	Output Score	A
Risk:		Medium/ Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Targets	Progress
1.1 DFID's assessment of quality of WHO's delivery of its results framework	Programme Budget 2016-17 is agreed together with a results framework with SMART indicators, baseline and targets	Output met target.
1.2 DFID's assessment of WHO annual reporting on results	WHO is able to report against all results indicators in Framework together with baselines, results achieved and targets including actions to improve performance	Output met target.
1.3 DFID's assessment of WHO's internal and external communication function at all three-levels of the organisation	Implementation of WHO's communication strategy at all-three levels of the organisation	Output did not meet target.

Key Points

On indicator 1.1: the Programme Budget 2016-2017 adopted at WHA 2015 included a results framework with SMART indicators, baselines and targets. The results chain has outputs, outcomes and impacts (p.8) and the indicators have baselines and targets (p.9).

On indicator 1.2: at WHA69 WHO presented, for the first time, a combined annual report which includes financial statements and performance assessments/results for 2014-2015. This, coupled with the additional information on results available on the webportal increases accountability and transparency. Through this the WHO is able to report against results indicators. At WHA69, the UK welcomed this development and asked that this unified format continue. We would like to see continued progress with
WHO clearly able to report against all results indicators in the future.

On indicator 1.3: According to the DG’s report on reform implementation a communications strategy is being finalised (p.6) so the target has not been met as the new strategy has not yet been implemented. However, the WHO communication strategy has been developed, reviewed and approved by the Global Policy Group (GPG) and the Director General. Completion and roll-out is scheduled for late 2016/ early 2017.

Commentary

WHO has made progress in improving its system for reporting and managing results.

Overall, this PCR concludes that this progress has scored an A .

Of particular note:

WHO has established a system for reporting and managing results - in 2011 WHO did not have an established results framework. Progress needs to continue to develop the effectiveness of this system for example, expanding the use of SMART indicators for all expected outputs.

WHO’s new online webportal provides detail as to where financial contributions come from and how these are spent – this is a strong piece of work on which WHO should be commended. Similarly, WHO’s online “reform dashboard” provides good information as to progress on reform programme objectives. However, the reform dashboard would benefit from further strengthening in particular in providing indicators that have more practical relevance and support the UK and other member states to hold WHO to account for progress with these reforms.

Implementation of a communications strategy was a key lesson from the Ebola outbreak. As the lead international agency for global health it is critical WHO is able to clearly articulate its guidance and expert advice. WHO is in the final stages of finalising and approving its communication strategy but it has not been fully implemented. DFID shall monitor this closely over the coming year.

In terms of the future assessment of results, WHO reform at the global and regional level means little unless it has impact in terms of improved performance where it matters most – on the ground at country level. DFID’s assessment is that WHO’s tracking of whether policies and strategies lead to impact and results in countries is inconsistent and of mixed quality. Assessment of country level impact should be strengthened going forwards.

Specific recommendations to support WHO reform

Recommendation 5:

1. WHO should further strengthen its online reform dashboard, ensuring indicators are “SMART” (specific, measurable, assignable, relevant, time-bound) so that the UK and other member states can hold WHO to account for progress with these reforms;
2. DFID’s business case and log frame for CVC 2016-2020 should use indicators that better reflect progress with effective reporting and monitoring of results and are appropriately specific.

Recommendation 6:

1. WHO should bring together existing tools for measuring country impact, enhancing where necessary, and integrating these into a unified system of reporting and results monitoring (that includes the reform dashboard);
2. WHO should ensure that it has a clear and measurable link between reforms and results, as well as specific outputs and indicators to measure results and impact at county level.

Output Title	2. WHO has in place a budget cycle that enables effective management and demonstration of efficiency savings.
Output number per LF		2	Output Score	A
Risk:		Low/ Minor	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Targets	Progress
2.1 DFID's assessment on progress on Financing Dialogue process and a fully funded budget.	WHO implements its new corporate resource mobilisation strategy, as part of the financing strategy, for Programme Budget 2016-17	Output met target.
2.2 DFID's assessment of progress in developing the Programme Budget 2016-17	The Strategic Budget Space Allocation (SBSA) agreed segments are operationalised in the approved PB 2016-17.	Output met target.
2.3 DFID's assessment of WHO's progress on establishing and operating a contingency fund for public health emergencies	WHO has in place a contingency fund for public health emergencies	Output met target.
2.4 DFID's assessment of the efficiency measures taken by WHO	WHO's progress in achieving 10% reduction in travel costs. WHO reports annually to PBAC on efficiency measures, including a commentary in the results reporting.	Output did not meet target.

Key Points

On indicator 2.1: p.113 of the WHO Programmatic and Financial Report for 2014-2015 states: “the creation of the department of Coordinated Resource Mobilization [has led to] a more focused approach however this needs to be further structured through appropriate standard operational procedures”. WHO did succeed in fully financing its 2014-15 budget. The amount of funding secured at the beginning of the biennium has steadily increased as has the percentage of WHO spend concentrated on its top priorities. A recent UN Secretary General report (A/71/63-E/2016/8) highlighted the WHO Financing Dialogue as a potential model for other UN agencies to follow.
On indicator 2.2: The 69th WHA requested that the DG implement the SBSA model over a period of three to four bienniums, through the ‘Financing of Programme Budget 2016-17: Strategic budget space allocation’ report (p.1). Further the Programme Budget 2016-17 (p.106) states that WHO “will continue to pursue […] a strategic budget space allocation mechanism across the three levels of the Organization”. Evidence presented to DFID by WHO demonstrates that elements of the SBSA have been operationalised prior to the WHA decision – hence this indicator is marked as met.

On indicator 2.3: The DG established the Contingency Fund for Emergencies (CFE) in May 2015. The UK contributes to the fund.

On indicator 2.4: According to the ‘WHO Programmatic and Financial report for 2014-2015’ (p.27) travel constitutes 9% of the organisation’s total expenses. This is a $100million increase from 2012. WHO attributes this to “non-staff” travel costs associated with emergency response. The proportion of travel costs for staff actually decreased from 52% in 2012-13 to 46% in 2014-15.

Commentary

WHO has made progress in establishing a budget cycle that enables effective financial management.

Overall this PCR concludes that this progress has scored an A.

Of particular note:

WHO’s Financing Dialogue is considered to have been a success and contributed to progress in WHO’s stated aim of stable, flexible funding aligned with programme budget. The UN SG judged that the Financing Dialogue has been held up as a potential model for other UN agencies. It will be important that the principles of the Financing Dialogue are adhered to and WHO does not revert to ad hoc programme specific funding (though rare exceptions, for example on emergencies reform, may be considered). Going forward DFID should continue to advocate strongly for WHO to focus its spend on those priority areas agreed by the WHA in the programme budget. DFID should continue to press donors to minimise earmarked funding and endeavour to lead by example in this respect.

The Contingencies Fund for Emergencies (CFE) is operational. According to the ‘Reform of WHO’s work in health emergency management’ report (p.6), as of 18 April 2016 US$6.89 million had been disbursed for five crises. Yet the CFE is vulnerable due to concern over replenishment and the fact that only US$26.9 million in funding and pledges has been found against the $100m target. A secure and sustainable CFE will be a priority for the UK in the coming years.

WHO must continue to proactively demonstrate how it is finding efficiencies in its day-to-day costs. Using travel costs alone as an indicator of efficiency does not lead to an accurate assessment. Travel costs are an inherent part of WHO’s business especially in response to large scale emergencies. Nevertheless, simple steps (e.g. advanced purchase of air travel, travelling economy class to meetings and workshops) will have a major impact. WHO has taken some steps such as controls on travel budgets and increased emphasis on compliance with travel policy across the organisation.

Specific recommendations to support WHO reform

Recommendation 7:

1. WHO should produce and deliver a clear cost-efficiency plan. This plan should identify clear efficiency targets against which DFID and other Member States can hold WHO to account. Such a plan will help WHO demonstrate actual improved efficiency – as opposed to simply reduced corporate expenses.
2. The log frame for CVC 2016-2020 should include comprehensive indicators measuring the degree to which WHO delivers value for money for the UK’s investment.
3. In the preparation of the business case for CVC 2016-2020, DFID should perform a thorough assessment of WHO’s VFM mechanisms and design log frame indicators that incentivise strong progress by WHO in this area.

Output Title	3. WHO has effective financial accountability and oversight systems in place.
Output number per LF		3	Output Score	A
Risk:		Low/ Minor	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Targets	Progress
3.1 DFID's assessment of the improvement in level of country office compliance with corporate procedures	Less than 3% of Direct Financial Contribution (DFC) reports overdue. / Less than 5% of country office imprest accounts have items older than 90 days outstanding.	Output met expectations.
3.2 DFID's assessment of rate of implementation and follow up of audit recommendations	More than 90% of audit recommendations issued are implemented (in-progress or closed), per the 2016 Internal Oversight Service (IOS) Annual Report to the WHA.	Output met expectations.
3.3 DFID's assessment of staff and financial capacity of the IOS	IOS and Evaluation and Learning (EVL) fully staffed.	Output met expectations.
3.4 DFID's assessment of WHO's accountability framework in line with good international practice	Full implementation of statements of internal control by budget centre heads. Compliance, Risk and Ethics (CRE) reports to senior management on and uses corporate risk register.	Output did not meet expectations.

Key Points

On indicator 3.1: Less than 3% of DFC reports are reported as overdue in both the WHO Programmatic and Financial Report for 2014-2015 (p115) and the Report of the PBAC to the Executive Board, Jan 2016 (p8). Although the proportion of country office imprest accounts that have items older than 90 days outstanding is not included in the External Auditor’s Report nor in the Internal Auditor’s Report, the Programmatic and Financial Report does mention that “the biennium has [...] witnessed a high level of reconciliation of imprest accounts” (p115). Additional evidence provided by the WHO indicates that this indicator is exceeded as the number of imprest accounts with items older than 90 days outstanding was less than 2% of the total as of December 2015.

On indicator 3.2: p21 of the Internal Auditor’s Report presents the status of audit recommendations as of both the 9th March 2015 and the 8th March 2016. The reported figures have changed slightly since the last report – the total proportion of ‘Open’ recommendations was used in the previous AR to compare to the milestone. However now, the proportion of ‘Overdue Open’ is recorded; this is 2.5% as of 8th March 2016, and 3.6% if “not yet due” recommendations are excluded. Nevertheless, the log frame target is met.

On indicator 3.3: The Internal Audit Report (A69/51 para 10) indicates that in 2015, the IOS continued to implement plans designed to strengthen its capacity. One Information Technology Auditor and one Data Analyst Auditor joined the Office, respectively, in October and December 2015; an additional Investigator joined at the end of November 2015; and two technical officers from within the Organization were transferred to the Office in January 2016. Vacated posts (resulting from transfer, retirement and promotion of incumbents) have been advertised and selection of candidates is proceeding in order to complete the Office’s team. The Evaluation Report (EB139/9, para 3) indicates that the Evaluation Office recruited a chief evaluation officer, a programme officer and a Junior Professional Officer to strengthen its capacity. The capacity of the Evaluation Office is further strengthened by a roster of prequalified evaluation experts to support the Organization’s evaluation work.

On indicator 3.4: Report on compliance, risk and ethics (Nov, 2015) notes that the risk register was rolled out in two phases: a bottom up phase of risk assessment by heads of budget centres, and a top down phase of validation. CRE reported to the Independent Expert Oversight Advisory Committee on progress on the risk register, including analysis of the top risks. Internal Audit Report (2016) notes that the implementation of Organization-wide risk registers and internal control checklists are still work in progress. The External Auditor’s Report notes that the Internal Control Framework has been issued, and Internal Control Self-Assessment Checklist has been rolled out in all departments at HQ, regional offices and country offices, and scores it as “implemented”.

Commentary

WHO has made progress on ensuring it has effective financial accountability and oversight systems in place. However, significant further improvements are needed. Particular attention should be paid in the future business case to ensure indicators better reflect WHO performance in this area.

Overall, based on the indicators above, this PCR scores WHO’s progress in this area A.

Of particular note regarding improvements required:

The internal auditor, the external auditor and the IEOAC all are of the opinion that control processes and procedures need to be strengthened to mitigate risks and that enforcement of sanctions for continued non-compliance need to be implemented.

The reports of the Internal and External Auditors presented to WHA69 make for uncomfortable reading, noting unsatisfactory or partially satisfactory audits at offices across all levels of the organisation.

WHO has made progress in establishing its dedicated Evaluation Unit but this in itself will not guarantee an organisational culture change to one where organisational learning and improvement is embraced at all three levels of the WHO. DFID will need to continue to press for evaluation recommendations to be integrated into future programme design.

Various reports continue to point to a “culture of non-compliance” within WHO. WHO has taken some positive steps – for example an external whistleblowing hotline has recently been launched. But plenty more remains to be done. DFID will need to continue to stress its zero tolerance of wrongdoing (as it did at WHA69). DFID should put in place a procedure for sampling and studying individual WHO audit reports throughout the year.

Specific recommendations to support WHO reform

Recommendation 8:

WHO must further strengthen its audit function with particular attention paid to how effectively audit recommendations when implemented and reinforced throughout the system address underlying risk. WHO should continue to prioritise audit recommendations which have the greatest impact on organisational effectiveness and take forward cross-cutting thematic audits.

Recommendation 9:

1. WHO must ensure its risk management reforms are successfully implemented across all three levels of the organisation. Risk mitigation plans in particular need to be rigorously adhered to.
2. WHO should ensure that all staff understand the agreed “risk appetite” for their work. Staff who work in inherently high-risk situations should feel supported and empowered to act. Risk appetite will differ by WHO office and by the issue in question. WHO has made steps in this respect, such as articulating risk appetite in the Corporate Risk Management Policy. The task now is to ensure this translates to practice on the ground.

Recommendation 10:

WHO should develop its culture of learning and improvement, fully exploiting its ambitious programme of reviews and evaluations.

Output Title	4. WHO has efficient human resources management systems in place.
Output number per LF		4	Output Score	A
Risk:		Medium/ Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Targets	Progress
4.1 DFID's assessment of WHO's performance management of staff systems.	The new performance management system ePMDS+ is operational at all-three levels of the organisation.	Output did not meet expectation
4.2 DFID's assessment of progress in implementing WHO HR strategy	Mobility scheme enters into force for three years on a voluntary basis.	Output met expectation
4.3 DFID's assessment of WHO Human Resources capability to respond to public health emergencies	Global health workforce in place to be deployed for public health emergencies	Output met expectation

Key Points

On indicator 4.1: External Auditor’s Report to WHA69 (p22) stated that ePMDS is operational. However, the global compliance rate as at 1 April 2016 being 90%. There is still a need to ensure staff adherence to ePMDS+ completions within the required time frame.

On indicator 4.2: HR Report to WHA69: Geographical mobility is being introduced in a phased manner, starting with a three year voluntary phase during 2016 – 2018. The UK strongly welcomed this at WHA69 as a positive step forwards.

On indicator 4.3: The progress report on the development of the WHO Health Emergencies Programme (30th March 2016), as well as the WHA A69/30 paper (para 19) explicitly mentions the Global Health Emergency Workforce. The Global Health Emergency Workforce is in place with emergency medical teams continuing to join the WHO-led quality assurance process with 59 teams from 26 countries now in process. WHO is also strengthening the secretariat of the Global Alert and Response Network, and enhancing its advocacy work, to enhance the capacity of partners in the Response Network to systematically support WHO and Member States in alert detection, risk assessments and rapid response activities. GOARN experts have been deployed since the beginning of 2016 in a number of major outbreak, public health events including Zika, Yellow Fever, Ebola and Cyclone Winston.

Commentary

WHO has made progress in human resources reform.

Overall, this progress is scored an A.

Yet, while this score reflects the specific targets set in the logical framework, this PCR judges that these indicators do not reflect fully the ongoing challenges and further progress required.

Of particular note:

The mobility policy will need to be further embedded if WHO is to better manage its workforce distribution and perform better at having the right people in the right place at the right time. DFID should support WHO’s aspirations to increase the proportion of staff changing duty station across the three levels of the organisation and continue to press for its mandatory adoption in due course.

Gender equity is a key DFID priority and DFID should press to see this reflected in WHO’s organisational make-up. Progress has been made on increasing the number of women in WHO but the increase has been very small recently and DFID should advocate for further progress, especially at the professional and senior levels of the organisation, including Heads of Country Offices.

DFID will need to continue to advocate with WHO to improve its performance management processes although the Secretariat was able to point to sanctions taken against poor performing staff at WHA69. Transparent and timely recruitment and deployment is a further area for attention – WHO is not where it needs to be yet in terms of having the right people in the right place at the right time.

Considerable progress has been made on the Global Health Emergency Workforce. WHO has an internal surge roster that draws on resources across the organisation for deployment within 24 hours.

Specific recommendations to support WHO reform

Recommendation 11:

WHO should consider and propose further measures to improve gender equality, including increased parity for higher professional posts across the three levels of the organisation.

DFID’s business case for CVC 2016-2020 should use indicators that better reflect progress with WHO’s work to promote gender equality.

Recommendation 12:

DFID should consider indicators for the business case fo CVC 2016-2020 that better reflect progress on HR reform; including efficient and effective delivery of the reforms.

D: VALUE FOR MONEY AND FINANCIAL PERFORMANCE

Key cost drivers and performance

WHO’s biggest expenditure is its staff. Between 2012 and 2014, WHO staff costs reduced from 47% to 41% of expenditure. This was due to the discontinuation/ regrading of jobs not aligned with priorities – in line with WHO’s programmatic reforms. Efficiency savings have also been achieved through outsourcing (e.g. $9m saved in this respect on building management support functions at HQ). It is clear however, that savings made by reducing directly-employed staff is off-set by the increasing cost of contractors. DFID will look to WHO for further clarity on this issue. It is not sufficient simply to shift staff costs from one budget to another.

The Director General has made commitments to ensuring further cost savings through efficiencies to be gained with effective procurement of services, rigorous human resource planning and improved management of Direct Financial Contributions (DFC). Yet specific targets are lacking.

However, despite these commitments, WHO does not yet have a published organisation-wide cost-efficiency plan. WHO’s decentralised structure and the lack of efficient systems in place to ensure compliance leads to policies and processes not being implemented consistently across the three levels of WHO. This limits WHO’s value for money culture. It is not clear whether expenditure analysis is actually used in practice to make savings.

WHO has produced a corporate procurement strategy, published in April 2015, which includes a pillar to increase cost-effectiveness and reduce costs. It also identifies enhancing operational capacity by developing systems and staff as a strategic pillar. The strategy aims to make improvements in the effective management of suppliers, supply chain optimisation, and processes and systems. Progress on the implementation plan for this strategy is essential.

Assessment of whether the programme represented value for money, including VFM performance compared to the original VFM proposition in the business case

DFID has performed a number of comprehensive reviews of WHO’s value for money performance.

In 2014, DFID performed a Commercial Expertise Review (CER) on WHO – updated in 2015. The CER noted significant staff reductions in long-term posts, although these savings were somewhat off-set by salary increases for remaining staff. It also noted the savings made by WHO in relocating a large number of its corporate functions from Geneva to Kuala Lumpur – estimated at US$59m per biennium.

The original business case for 2011-2016 core voluntary funding linked measures of VFM to outcomes of the Multilateral Aid Review (MAR). MAR 2011 rated the WHO as adequate value for money. 2013 MAR highlighted weaknesses in this respect: “Targets for savings on administration costs are not stretching and there is little attention to cost saving in developing countries.” Overall however, MAR 2013 rated WHO as having made “reasonable progress” in the area of cost and value consciousness.

With the programme budget increasing in 2016-2017, the WHO is supporting a greater level of activity with a decreasing share of corporate expenditures . However, WHO will benefit from further improvements to enhance value for money. Such improvements will maximise the impact of UK funding but also build other donors’ confidence in WHO and increase the likelihood of investment in its programmes. To properly assess the effectiveness of WHO expenditure, reporting of WHO’s results needs to be more explicit and consistent.

A key challenge for WHO in making efficient programme and investment choices is that approximately 70% of its funding is earmarked to specific programmes or projects. The unpredictable nature of this funding limits WHO’s ability to make long-term smart investments. WHO’s Financing Dialogue has enabled some progress in improving the flexibility and predictability of WHO’s funding but more remains to be done to broaden the donor base. DFID’s CVC sets a positive example in this respect.

The “Process, Costing and Financing” information document relating to the programme budget provides some evidence on the methods used by WHO to make its investment choices. This itself is based on the WHO’s Twelfth General Programme of Work. Budgets are developed through consultations with Member States through a bottom-up process, the governing bodies’ resolutions and past budget lesson learning. Costings are defined through an iterative process involving all three levels of the organisation. Whilst this implies a systematic approach to making investment choices, more evidence is required on the rigour applied to ensuring maximum impact.

Quality of financial management during programme

UK funds were managed through established WHO mechanisms and subject to WHO internal controls, audit and assurance. Reports of the internal and external auditor are presented each year to the World Health Assembly where they can be scrutinised by all member states. WHO’s most recent external audit has an unqualified opinion of WHO’s financial statements.

A key DFID priority for the WHO is its membership of the International Aid Transparency Initiative (IATI). WHO remains committed to achieving membership of IATI by the end of 2016.

Date of last narrative financial report	World Health Assembly May 2016
Date of last audited annual statement	World Health Assembly May 2016

E: RISK

Quality of risk management over the life of the programme

WHO’s approach to risk continues to mature. WHO’s Corporate Risk Management Policy was rolled out in 2014 and is now being implemented.

The internal auditor, the external auditor and the IEOAC all note that WHO’s internal control processes and procedures need to be strengthened to mitigate risks, and that enforcement of sanctions for continued non-compliance need to be implemented. WHO has the right policies in place, but implementation is key to ensure we see progress on compliance.

DFID manages risks associated with this programme through proactive engagement with WHO through dedicated staff based in the UK Mission in Geneva, including engaging with WHO in strengthening their systems for risk mitigation. Going forwards, the management of risk will be a key focus of the upcoming business case for core voluntary funding 2016-2020.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

DFID’s Commercial Expertise Review (CER) of WHO, conducted in 2014 and updated in 2015, assessed WHO’s commercial effectiveness.

The CER identified some strengths in WHO’s approach to procurement and commercial activity. For example, oversight mechanisms in place to try to ensure compliance with regulations and promote good practice. Risk management working groups have been established, and measures underway to strengthen co-ordination and consistency in global purchasing activity. There are flexible arrangements in place for emergencies, to enable rapid responses. There are examples of close and effective working relationships between technical units and procurement.

Yet the CER also identified weaknesses and opportunities for improvement. For example, it noted WHO goods procurement is generally reactive and covers a wide range of mainly low value purchasing. As such, there is scope to improve data management and information sharing, and to ensure the organisation is making full use of business intelligence. The CER also noted that although WHO participates in supplier meetings, including some organised by other agencies, there is scope to expand the level of engagement with suppliers outside of formal bidding processes. This could increase opportunities for two-way feedback and to help develop markets.

Performance of partnership(s)

WHO has a track record of leading partnerships and convening key stakeholders on global health initiatives. WHO hosts a number of health partnerships that the UK participates in. Good examples of partnership working include: the WHO’s role in the Global Polio Eradication Initiative; the WHO’s leadership of a global initiative, involving DFID, UNICEF, UNFPA, UNAIDS, among others, to reduce the total number of core health indicators that countries report on (currently estimated at around 600) by around two-thirds in order to help improve the quality of data available. The WHO-hosted Global Health Workforce Alliance (which is now disbanded and is expected to be replaced by a new network to implement the Global Strategy for Human Resources for Health) is another good example.

However, WHO’s track record has been mixed. DFID’s PCR of the ‘Malaria: Improving the Global Response’ (which includes support to WHO’s Roll Back Malaria Partnership (RBM) programme notes that “Despite the success achieved by RBM, relationships within the partnership have been strained, hosting arrangements with WHO costly and complex with inconsistencies in performance across RBM’s working groups and networks.”

In addition, WHO’s accountability and reporting on results in relation to funds received from partners does need to be improved. This is particularly the case for Gavi and the Global Fund for AIDS, TB and Malaria. Given that the UK is a major funder of both of these global funds it will be monitoring very closely WHO’s performance with funds received from these organisations. Indicators in the log frame for 2016-2020 CVC will reflect this, including progress under the Partners Engagement Framework developed by the Gavi Alliance.

Previous reviews have noted, and it remains the case, that WHO needs to maintain a focus on its comparative advantage, recognising the role other global health actors can play.

Asset disposal and value obtained by DFID

No specific assets are identified as supported by DFID’s core voluntary funding contribution.

G: CONDITIONALITY

Partnership principles assessment

N/A

H: MONITORING & EVALUATION

Evidence and evaluation

Evidence collected throughout the course of the programme through annual reviews and multilateral aid reviews was used to inform DFID’s subsequent engagement and advocacy with the WHO.

DFID has a wealth of materials to draw upon to inform our understanding of WHO’s progress on delivering development results and reforming its organisation. Our active engagement in WHO’s governance structures, including currently, the Executive Board and the Programme Budget and Administration Committee (PBAC) ensure the UK remains abreast of developments. Specifically they allow DFID to study reports of WHO’s internal and external audit, their consolidated financial and programmatic reports and reports on their corporate expenditure.

The WHO Evaluation Office provides an important function and driver for WHO to become an organisation with a culture of learning and improvement. Its recent evaluation of WHO’s country presence in particular provides a valuable basis for further reform and improvement – if recommendations are implemented and shared across all levels of the organisation.

As part of the business case for WHO’s 2016-202 CVC DFID will analyse sources of available evidence for quality, reliability and insight to determine the best mix of evidence to judge WHO performance and the impact of DFID funding.

Monitoring progress throughout the programme

DFID monitors performance through annual reviews of progress which provide a regular formal assessment and through our assessment of papers presented to WHO governing bodies and provides feedback through our interventions as a member these bodies.

DFID also uses multilateral aid reviews to assess progress. MAR Update 2013 noted that reasonable progress had been made by WHO in its reforms, in particular in ensuring a clearer results chain, strengthened financial systems and significant cost savings. However, it also highlighted that more needed to be done to ensure reforms were rolled out to the regional and country levels of WHO.

This review strongly welcomes the creation by WHO of its results framework, with indicators at impact, outcome and output level. WHO’s results framework is aligned with its strategic priorities and provides a framework for strategic monitoring and management of organisational performance.

Nonetheless further improvements can be made. In particular, WHO needs to further develop systems that support complete results reporting against output and outcome indicators each year. WHO should also seek opportunities to maintain a core set of indicators it reports against more regularly throughout the duration of the GPW to provide some continuity in performance monitoring, especially given the long term nature of WHO’s work. The Country Cooperation Strategy is a positive tool that can be further strengthened.

Full use of WHO’s online reform dashboard to report transparently on progress would be welcomed, has been encouraged by the UK at WHA69 and has been committed to by the WHO Secretariat.

Gender

Gender equity and the health and rights of women and girls are front and centre of DFID’s priorities for health. As noted above, WHO has made progress in increasing the number of women on its staff but needs to improve further – particularly for professional and senior levels.

WHO has specific outcome indicators in its General Programme of Work for increasing access to interventions to improve the health of women, newborns, adolescents and children. Also, for reducing violence against women.

However, there have been missed opportunities for progress on women’s sexual and reproduction rights as some Member States slow progress.

As an addition to Recommendation 11 (that WHO should consider and propose further measures to improve gender equality), DFID’s business case for CVC 2016-2020 should use indicators that better reflect progress with WHO’s work to promote gender equality.

ANNEX: Summary sheet from most recent annual review

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: World Health Organisation (WHO) – Voluntary Core Funding 2011-2014
Programme Value: £54 million		Review Date: January 2015
Programme Code: 202715	Start Date: 01/04/2011	End Date: 31/03/2015

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	N/A	B	A	A
Risk Rating	N/A	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

The Ebola virus disease outbreak hit West Africa at an unprecedented scale and has stretched the capacity of the World Health Organisation (WHO) for the past 6-months. The Ebola outbreak has had a significant impact on WHO reform implementation and the pace and delivery of work in other priority programmes. In particular, certain reform initiatives, such as the review of the hosted partnerships, have had to be delayed due to organisational assets being redirected to the Ebola response. This crisis comes in the midst of other persisting and emerging crises in other parts of the world in which WHO is also heavily involved. Sustaining this effort over a significant period is anticipated to have an impact on delivering the programme budget 2014–2015. DFID has been working closely with WHO to strike the right balance between not diverting resources and efforts in WHO away from the immediate response, while ensuring lessons are learned in a timely way to adapt our reform agenda accordingly. We are currently exploring changes in our log frame indicators on the basis of the lessons being learned from the Ebola crisis. However, for the purposes of this Annual Review, the progress assessment is based on pre-Ebola indicators.

The MAR Update in 2013 identified a set of four reform priorities for WHO. These formed the basis for DFID’s recommendations for strengthening WHO’s performance in the 2013 Annual Review. Lessons learned and progress against these recommendations are presented below.

Recommendation 1: To continue to strengthen the delivery and measurement of results in developing countries, and to develop an effective operational plan, which transforms strategic priorities into action and results (contribution to results)

Progress and lessons learned: The WHO adopted a new programme budget for the biennium 2014-15, which provides a clear set of indicators to measure results. This new monitoring framework is a welcomed development and DFID will be monitoring closely how WHO uses it to report on the implementation of the 2014-15 programme budget and for managing organisational performance.

Recommendation 2: To improve the performance management of staff - including overcoming continued reluctance of some staff to embrace change, and to strengthen staff management to ensure a more coherent and positive approach to managing poor performance and encouraging staff development (strategic performance and management)

Progress and lessons learned: The WHO is making good progress to develop policies that will change the performance management culture of the organisation, however, we will monitor closely how these policies are implemented.

Recommendation 3: To ensure that the Financing Dialogue process meets its objectives of predictability, transparency and accountability and that WHO provides greater transparency of how funds are allocated (financial resources management)

Progress and lessons learned: The WHO has made some progress to develop guiding principles for strategic budget space allocation. We will be monitoring closely how these principles are used to develop the 2016-17 programme budget.

Recommendation 4: To continue to look for ways of making savings, using the independent review of administration and management costs as an instrument to streamline administrative systems (cost and value consciousness).

Progress and lessons learned: The WHO is working on streamlining its administration and management costs, and on a proposal for fund these. We will monitor closely how these changes to administration and managements costs will bring new efficiency savings to the organisation.

Summary of recommendations for the next year

While the 2014 Annual Review notes that WHO has made progress across all of its log frame outputs, it makes a number of recommendations for the agency to further strengthen it performance in areas where milestones for 2014 have either been partially met or not met. Specifically, it recommends that WHO:

1. focuses on using its monitoring framework as a tool for managing and improving the overall performance of the organisation. This will require at least annual reporting of progress against indicators on the web portal and actions to improve performance where progress is slow.
2. accelerates progress on developing a corporate resource mobilisation strategy and ensure it is ready for implementation in advance on the 2016-17 Programme Budget;
3. sets-out for each year its policy for efficiency savings and reports on progress made;
4. accelerates progress in rolling-out the corporate risk register at all three-levels of the organisation and ensure its effective use;
5. continues progress to implement its new staff performance management system and wider human resources reforms in the WHO Human Resources Strategy;
6. continues progress to finalise the new mobility policy for staff.