Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	13/12/2016

Title: Animal Health Specialist Advice 2014 - 2016.
Programme Code: 204823	Start Date: 01/08/2014	End Date: 30/09/2016
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2014/15	PCR / 2016
Programme Score	A	A
Risk Rating	L	M

Financial Position

Original Programme Value	£82K
Extensions / amendments	End date extended from 31/07/2015 to 30/09/2016
Log-frame revisions (with dates)	N/A
Total programme spend	£99.5K

Follow up actions required following closure

A new Business Case to be approved to contract a Animal Health and Veterinary Science Specialist for a further 2 years.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	5438166
DevTracker Link to Log frame:	N/A

Outline of programme and what it has achieved

The burgeoning demand for livestock products in the developing world has been driving massive expansion of livestock production systems. Concurrently, increased contact rates between poor people, their livestock and wildlife, climatic factors affecting the distribution of disease and weak regulatory frameworks contributes to significant changes to health risks associated with livestock production in the developing world.

Livestock represents a highly valued and productive asset to poor rural people in delveoping countries. They not only provide food but income from their animals can help them afford many of life’s basic needs such as housing, clothing, education and health.

The DFID Agriculture Research Team supports a number of animal health research programmes which aim to reduce the impact of zoonotic disease on poor communities in developing countries whilst helping to identify and halt the spread of pandemics across the globe.

DFID does not maintain a in-house veterinary specialist. The main reasons for this are a lack of applicants with specialist animal health expertise to the general livelihoods pool, possibly because there is no career path for specialists in this field within DFID as well as a low level of demand accross DFID for specialist animal health advice. The development of animal therapeutics, diagnostics and vaccines is a highly complex and rapidly evolving area of science and maintining the capacity to deliver that specialst advice would involve the development of deep technical skills that would not be deployable across the rest of the organistation. It is for these reasons that DFID decided to source these specialist skills from an external international expert in the international animal health field.

For the past 2 years DFID has drawn on the services of Lifestock Incorporated Ltd for this support. They have provided high quality animal health technical advice in a timely manner. The advice provided has been well grounded in development realities and they very quickly established excellent relationships with all external partners including the Bill and Melinda Gates Foundations.

This programme has helped to contribute to the UK’s commitments to deliver global development objectives of economic growth in developing countries, workling with the private sector and delivery of the UK Governments Animal and Plant Health Strategy. It also complimented the the UK’s international committemnts on hunger.

It has contributed to delivering the RED Operational plan by providing high quality technical expertise in the area of animal health, providing expert views on new evidence which has been generated to explain what works and what doesn’t and working with the private sector to test new and innovative ways of providing the best animal health services in the developing country context.

The duration of the work was initially for a 12 month period, with a 6 month review point and an option to extend. The contract was extended to 25 months following the six month and annual reviews.

We considered Gender Equality Act in the commissioning of this contract to ensure we complied with the Act.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The programme has achieved all it’s objectives.

Major Achievements:

Lifestock Inc. Ltd. has provided a wide range of technical inputs to the Agricultural Research Team between June 2014 and Sept. 2016. (See table below).Some of these have been relatively short duration inputs such as preparation of technical briefs and advice. Other contributions have consisted of longer term engagement on particular projects and programmes.

Breakdown of work from June 2014 to Sept 2016.
Programme	Results
Agresults programme: Brucellosis	Inputs directly resulted in a more appropriate tighter and transparent design of the vaccine competition and helped raise the profile of it. The advice enabled greater value for money for tax payers (by not paying for elements that the private sector already has an incentive for)
Agresults: Newcastle Disease	Oversight of formulation of the Agresults Newcastle Disease Vaccination Business Plan for India from inception to the draft plan being agreed by the steering committee.
Anti-Microbial Resistance	Reviewed the report commissioned BT DFID on Anti-Microbial Resistance and provided technical overview.
Development Impact Bond / For Sleeping Sickness in Ugandan Cattle.	Technical support and advice on was how to mount a successful control for sleeping sickness in Ugandan cattle. His guidance led to materially change the treatment model This allowed DFID to demonstrate value for money.
BBSRC programmer for Combating Infectious Diseases of Livestock for International Development (CIDLID) Review	An independent review of the research work carried out by the projects. The review provided a number of recommendations for ongoing research programmes.
Middle East respiratory syndrome Coronavirus / (MERS-CoV)	Detailed terms of reference for a study on a new zoonotic health threat about camel and human MERS.
BMGF / DFID Collaborative agreement projects	Support enabled DFID staff to improve decision-making and risk analysis linked to technical delivery and to provide the basis for a more effective a challenge to contractors on quality and delivery of work outputs.
Global Alliance for Livestock Veterinary Medicines (GALVmed). / Joint DFID/Bill and Melinda Gates Foundation (BMGF) collaboration	Supported DFID staff with non-specialist backgrounds to maintain a tighter oversight of GALVmed, identifying risks at an early stage and developing mitigation activities. With this support staff have been able to assess the milestones and targets more accurately, and assess the technical feasibility of priorities and therefore ensure good VFM in the proposals for future support.
AAT (Phase 2 business case, monitoring and phase three review)	Specialist inputs enable DFID staff to improve decision-making and risk analysis linked to technical delivery and to provide the basis for a more effective a challenge to contractors on quality and delivery of work outputs.
Annual Reviews (Galvmed, ICIPE, AECF, BMGF collaboration, Agresults)	Provided expert animal health advice for the DFID’s Annual review processes for a number of Research Programmes.
Ad hoc requests
Total

In particular the detailed design of the $30million Brucellosis Vaccine competition and the evaluation of this pilot, required specialist livestock health expertise together with intimate knowledge of the related industry and institutional capability. Livestock Incorporated provided technical support on the detailed specifications for the design of a new brucellosis vaccine, ensuring the AgResults programme was able to position this correctly for the best outcome for small holder farmers in relation to the existing and future capability of the livestock research and pharma industry. These inputs directly resulted in a more appropriate tighter and transparent design of the vaccine competition and helped raise the profile of it. The advice enabled greater value for money for tax payers (by not paying for elements that the private sector already have an incentive for).

The consultant carried out an independent review of the joint BBSRC DFID programme Combating Infectious Diseases of Livestock for International Development (CIDLID). This programme funded a portfolio of livestock disease research projects which had been completed by May 2015. Technical expertise on livestock health and disease was provided to review the research work carried out by the projects and provide an assessment of the quality of the scientific research and evidence developed and the extent to which the programme has met its aims and objectives. The review provided a number of recommendations for ongoing research programmes with BBSRC

Another substantial piece of work was the creation of a Private Sector Development Impact Bond (DIB) for Sleeping Sickness in cattle in Uganda. This would not have been possible without the technical support provided by this programme. The consultant was able to provide extensive technical expertise around the treatment of the disease in cattle and provide guidance on the sampling done to identify the disease. In addition a detailed financial analysis of actual costs involved in this complex programme which allowed us to verify whether the costs of the impact bonds offered by Social Finance offered value for money.

The consultant has also provided technical assessment and support of research projects within the DFID/BMGF Strategic Collaboration Agreement, including Bovine experimental challenge and natural transmission models for bovine tuberculosis and the African Animal Trypanosomiasis Project phase 2, including planning the next 3rd phase of the project on trypanocidal drug development and registration.
The Specialist inputs provided enabled DFID staff to improve decision-making and risk analysis linked to technical delivery and to provide the basis for a more effective a challenge to contractors on quality and delivery of work outputs. The specialist has liaised with BMGF technical staff to ensure that DFID are able to track technical progress of the con-funded projects more effectively and has acted as the first contact point for BMGF specialist of technical questions relating to the project. The has contributed to DFID being able to deliver value for money in these projects.

Technical advice to the Global Alliance for Livestock Veterinary Medicines (GALVmed) supported DFID advisory staff with technical reviews and quality assessments of GALVmed R and D programmes, including liaison with GALVmed and BMGF technical staff and commenting on the technical aspects of the progress reports presented to DFID. He assisted with the development of the Terms of reference for an independent technical review of GALVmed technical performance and capacity and reviewed and quality assured the resulting report commented. On behalf of DFID project management staff he reviewed the proposals from GALVmed for a new phase of joint support by DFID and BMGF, Veterinary Innovations Transforming Animal health and Livelihoods (VITAL).
The advice has helped DFID staff with non-specialist backgrounds, maintain a tighter oversight of GALVmed, identifying risks at an early stage and developing mitigation activities reducing DFIDs overall risk exposure. With this support staff have been able to assess the milestones and targets more accurately, and assess the technicla feasibility of priorities and therefore ensure good VFM in the proposals for future support.

Other smaller, but vital areas of specialist advice provided was assistance with the development of a short-term study on Middle East respiratory syndrome Coronavirus. (MERS-CoV). In response to a request for information on a new zoonotic health threat, DFID commissioned a short–term study to produce an overview of what is known about camel and human MERS and the circulation of MERS-CoV in Sub-Saharan and North Africa so that informed decisions could be made on short term research required to elucidate camel MERS epidemiology. The animal health specialist helped with the preparation of Terms of Reference for a review and needs assessment for this study and provided important QA inputs to the draft report. The final version of the study is in Quest (51041030). The report helped DFID undertake an assessment as to whether longer term research was needed into the risks posed by Middle East Respiratory Syndrome in camel populations.

Output Score and Description

This programme has scored an A.

Lifestock Incorporated Ltd have provided high quality animal health technical advice in a timely manner. The advice provided has been well grounded in development realities and they very quickly established excellent relationships with all external partners including the Bill and Melinda Gates Foundations

Their technical knowledge is highly thought of within the field of animal health and feedback from the BMGF is that they very much appreciate their involvement and technical inputs in the DFID/BMGF joint initiatives.

Lessons and how these have been shared:

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	To provide specialist inputs and advice on aspects on a range of animal health research programmes.
Output number per LF		N/A	Output Score	A
		Minor	Impact weighting (%):	100%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Key points

Livestock Incorporated Ltd has worked to the terms of reference provided and met expectations. They have provided high quality technical advice in a timely manner.

To do this, they established excellent working relationships with a number of DFID technical / programme staff and key external partners. They provided the specialist veterinary support necessary to monitor a number of high profile programmes including the development of Impact Bond for Sleeping Sickness in Cattle - Inception work for a new private sector financing instrument (DIB Inception Programme) and DFID-BMGF Strategic Collaboration on agricultural research: Bovine TB and East Coast Fever.

Access to specialist livestock research expertise has enhanced the capacity and capability of RED’s Agriculture Research team to successfully steer, implement and oversee our animal health research programme portfolio – and has therefore reduce operational risks to the team’s overall portfolio.

Summary responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations for future programmes

DFID do not have Vetinarian Animal Health expertise in-house. It is recommended that DFID look to continue to have access to this specialist expertise to cover the range of animal health research programmes currently held within the Research and Evidence Divisions Agriculture Teams portfolio.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE 2 pages)

Key cost drivers and performance

DFID does not employ a full time member of staff in-house with the type of specialist veterinary and livestock expertise held by Livestock Incorporated Ltd. The main reason for this is that, for the current scope, number and value of DFID programmes in the area of animal health, DFID does not require this level of specialist advice on a full-time basis. The call down requirement was approximately 2 days per week. Employing a full time member of staff to provide advisory support therefore was not a viable or value for money option for DFID.

Effectiveness and efficiency; We employed a call down contract with Livestock Incorporated Ltd which enabled us to draw upon the advice only when needed and allowed us to source the specific expertise and advice we needed rather than using what ever capacity we were able to identify in-house, greatly increasing the utility of the capacity. .

Economy; The cost to DFID of calling down on the independents animal health specialist advice continued to be continues to be competitive when compared to market rates which we tested. The contract was designed in such a way as to ensure there was no obligation for DFID to spend the full contract allocation – the contract value represented a maximum spending limit against which DFID would call down services as required. Livestock Incorporated delivered technical advisory support and services to a very high standard throughout the 2 year programme, often working to very tight deadlines.

VfM performance compared to the original VfM proposition in the business case

The original value for money justification for this 2 year call down contract with Livestock Incorporated Ltd was based on their competitive rates and ability to deliver high quality technical advice and to respond rapidly to DFID’s requirements at very short notice. The contract performed well against expectations, and the fee rates remained fixed for the duration of the contract.

Assessment of whether the programme represented value for money

Yes, this programme represented good value for money. The highly competitive rates were fixed for the duration of the contract; the consultant consistently delivered very high quality work against clearly defined outputs; and all services and outputs were delivered on time. In addition, the contract mechanism allowed DFID to draw on advice on an ‘as needed’ basis, which represented a good fit with DFID’s limited – but critical – requirements for specialist animal health and livestock advisory support as outlined above

Quality of financial management during programme

Financial management was of a very high standard throughout the contract. All invoices were received in a timely manner and forecasting was accurate. The contract was managed by the RED in-house procurement team, who have been satisfied with the financial management.

Livestock Inc. Ltd invoiced DFID on a quarterly basis against actual days worked and travel costs incurred. Time sheets were provided with invoices and details of actual fees and travel expenses were detailed in the attached proforma invoice. The travel expenses were charged as actual expenditure. All travel expenses are reimbursed, against receipts, with DFID scrutinising costs against the anticipated required inputs for each piece of work, and the agreed contractual rates.

Date of last narrative financial report

E: RISK (½ page)

Quality of risk management over the life of the programme

Delivery risk is minor.

Access to specialist livestock research expertise has enhanced the capacity and capability of RED’s Agriculture Research team to successfully steer, implement and oversee our animal health research programme portfolio – and has therefore reduce operational risks to the team’s overall portfolio.

Technical expertise and advice was drawn down on ‘as needed’ basis from a call-down contract with the chosen partner.

Reputational risk is minor.

Drawing on specialist livestock research expertise when needed has enhanced DFID’s capacity and capability in the management of livestock health Research programming, and therefore reduced the potential reputational risk of overseeing specialist programming without the required expertise in-house.

There was a potential reputational risk inherent in contracting specialist expertise from an external partner; however, the Agriculture Research team negotiated competitive rates with the chosen partner and had confidence in the partner’s ability to provide high quality technical advice.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

A rolling workplan was developed and agreed with the consultant throughout the programme. Delivery was tightly monitored and the consultant delivered high quality animal health advice in a timely manner, often at very short notice.

Performance of partnership (s)

N/A

Asset disposal and value obtained by DFID.

No assets were purchased by DFID.

G: CONDITIONALITY (½ page)

Partnership principles assessment

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

N/A

Monitoring progress throughout the programme

The Senior Responsible Owner provided management oversight of this programme working closely with the Agriculture Team Leader and drawing on inputs from advisers, the Senior Research Fellows and other team members as appropriate.

The Deputy Programme Manager was responsible for the monitoring and accounting of expenditure, standard DFID project management procedures for inspecting invoices which demonstrated good Value for Money; and compliance with agreed fees and reimbursable costs. The contract required a low level of management time.

The Senior Responsible Owner, Deputy programme Manager and Team Leader maintained regular contact with the consultant throughout its 2 year lifetime and monitor performance against the key deliverables and received receive and review written programme reports.

A rolling workplan was developed and agreed with the consultant throughout the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Key Points

Access to specialist livestock research expertise has greatly enhanced the capacity and capability of RED’s Agriculture Research team to successfully steer, implement and oversee our Animal Health Research portfolio.
N/A

Recommendations for future programmes

DFID should continue to have the facility to commission high quality Animal Health Expertise to maintain the high level of technical scrutiny of our programmes.

Date of last narrative financial report
Date of last audited annual statement

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process