Annual Review - Summary Sheet

Title: Queen Elizabeth Diamond Jubilee Trust: UK Contribution
Programme Value: Up to £50 million		Review Date: January 2016
Programme Code: 203754	Start Date: 25.11.13	End Date: 30.06.19

Summary of Programme Performance
Year	2013/14	2014/15
Programme Score	A	B
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review
The Queen Elizabeth Diamond Jubilee Trust (the Trust) aims to reduce levels of avoidable blindness in the Commonwealth. The programme is composed of four initiatives. Three tackle main causes of avoidable blindness (blinding trachoma, diabetic retinopathy (DR) and retinopathy of prematurity (ROP)). The fourth supports the other three with fellowships, research and technology development.

This year of the programme has seen a scale up across the 4 initiatives. The core lesson learnt is that laying the critical foundations to engender national engagement has taken considerably longer than envisaged. Hence the service provision targets have not been met. However, all partners are confident that the investment in situational analysis, national and sub national awareness and planning workshops has paved the way for a rapid scale up of service provision.

The trachoma initiative has scaled up significantly and between DFID (this programme and the DFID SAFE (Surgeries, Antibodies, Facial cleanliness and Environmental components) programme) and USAID, the profile and funding for trachoma has never been greater. Nor has the effectiveness of the global response due to the very close collaboration of core global policy and implementation forums and global institutions.

The global trachoma programme is at its zenith. Funding, largely from DFID across the three trachoma programmes - Mapping, DFID SAFE and the Trust - has enabled a massive scale up of access to care which is more evidence based and therefore efficient. Further the success of trachoma’s policy and programming focus and management is influencing the global neglected tropical disease agenda. Within this movement the Trust is respected by a range of partners for brokering partnerships, raising the agenda through a range of strategic forums and websites (including the re-launch of the Trachoma Initiative website on World Sight Day (www.endtrachoma.org)).

The Scientific Advisory Board (SAB) is now well established and met twice this year. The focus has moved from approval of the award of grants to the wide range of implementing partners to monitoring progress on results and approving evaluation proposals.

The Monitoring and Evaluation Strategy has been updated and largely addresses the recommendations made by the Specialist Evaluation and Quality Assurance Service (SEQAS) report (referred to in the 2014 DFID Annual Review) around clarifying evaluation objectives, theory of change, value and legacy. The revised strategy is clearer and has a robust programme level Theory of Change, underpinned by summary theories for each initiative. The Trust has also developed a results summary as a substitute for a formal results framework (given the relatively narrow focus of its work) which provides a good core set of indicators at the outcome and output level that can be aggregated and used for purposes of monitoring and tracking the Trust’s performance over the lifecycle of the programme.

Summary of recommendations from the last AR
- Agree a formal conflicts of interest policy for the SAB and board of trustees. Completed
- Update logframe before March 2015 based on latest data. Completed
- Align DFID and the Trust reporting cycles for future annual reviews. Partially completed but it has proved impossible for all partners to convert reporting to the calendar year which is used for this DFID annual review. For some partners, DFID will use data from the partners’ annual report, plus the % progress towards to next reporting year, to inform the DFID annual review score.
- Develop a more detailed risk matrix that is reviewed quarterly by DFID and the Trust teams. Completed.
- The Trust management team to consider a focus on aggregated results across countries, with performance in any individual country allowed vary by an agreed margin. This would allow flexibility to re-allocate resources if needed and management of delivery risk across the portfolio. The two outcome indicators in the log-frame have been adjusted to capture results from all of the Trust’s avoidable blindness initiatives (see also recommendation below on impact indicators). The Trust has worked to ensure initiatives working in more than one country have comparable top-line indicators. This allows for comparisons between geographies and partners. The trachoma indicators follow guidance from the International Coalition for Trachoma Control (ICTC).
- Clarify branding guidelines at country level, and communication with DFID country offices. Branding policy has been discussed in more detail with DFID with use of the UK aid logo agreed for the recent Time to See Exhibition held at CHOGM in Malta. The Trust must continue to discuss with DFID and acknowledge DFID’s support through use of the UK aid logo in all communications as detailed in the Memorandum of Understanding signed by the Trust and DFID. Relationships with DFID country offices where the trachoma initiative is being scaled up are gradually being established – for example, they are most advanced with DFID Kenya.

Progress against specific outputs recommendations are detailed under Section C.

Key Recommendations for 2016 (output specific ones are presented under the outputs)

- There are two challenges faced in reporting against the calendar year which DFID use for their Annual Review (AR) report. First, many of the milestones set were based on outdated information and affected by circumstances out of the partners’ control. It is very important that all the partners recalibrate milestones as soon as they are aware that is needed. The Trust must then present the changes and justification to DFID for approval. Second, synchronising reporting periods as many partners (including the major one – Sight Savers) have different reporting cycles to the calendar one. DFID understand that partners’ reporting cycles cannot be changed now. Therefore, DFID and the Trust have agreed that for DFID’s AR reporting needs, where partners reporting cycles differ from the calendar year, we will use (i) progress against partners previous report and (ii) % progress in the current reporting year. This is relevant to outputs 1 and 4.
- The Trust to collaborate with the WHO’s Medical Office, Trachoma. Both the Trust and DFID SAFE should collaborate between themselves in offering primary data, potentially co-funding and expertise to WHO to this venture. The Trust and DFID SAFE should collaborate between themselves in offering primary data, co funding and expertise to the studies.
Re-run the cost benefit analysis (CBA) of the programme given the macro results will be less than envisaged in the Business case (and used for the CBA therein), and the availability of more accurate programming costs. This can be done in conjunction with the DFID funded SAFE programme in 2016 and results should support WHO led work on improving the evidence of the cost-effectiveness/economic impact of trachoma control mentioned above.
- The two recommendations above can be done in conjunction with the DFID funded SAFE programme during their mid term reviews (due in 2016).
- Milestone for the Impact indicator: The Trust to consider other milestones (other than Mass Drug Administrations (MDAs) to use a proxy towards achievement of Ultimate Intervention Goals (UIG). The Trust to explore if there is, or could be, a methodology to measure progress towards UIG per country that can be used.
- The Trust to commence strategic deliberations over end of programme sustainability. To ensure each initiative is clear on what its legacy will be: what skills and knowledge and assets will be ensured to partners, what the funding requirements are and possible sources of funding. This should be done in fuller collaboration with the ICTC who has commenced exploring this.
- The Trust to ever improve on providing the evidence that the poor and women are disproportionally being addressed by service provision. Where disaggregation is possible, encourage this (for example by sex). Case studies can be used to illustrate equity dynamics.
- The Trust to continue to discuss the grant payment rescheduling with DFID and to ensure in future that any concerns over expenditure and potential delays in drawing down funds are flagged to DFID at the earliest opportunity.
- To monitor and acknowledge the Trust’s global policy leverage. This can be done by an addition Outcome level indicator: for example “At least two examples of how the Trust has influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes”.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Link
DevTracker Link to Log frame:	Link

Outline of the programme
The Trust was formally established on 6 February 2012 under the chairmanship of the Rt Hon Sir John Major KG CH, former Prime Minister of the United Kingdom. Its purpose, with the contributions it has received, is to create and manage programmes that will bring life-changing benefit to people across the Commonwealth.

DFID will provide up to £50m in match funding to support the Trust’s avoidable blindness programme. International efforts are underway to eliminate the main causes of avoidable blindness worldwide, providing a unique moment to join and help progress the global Vision 2020 initiative.

The avoidable blindness programme comprises four initiatives. First, trachoma management in Africa (£40.1m) and the Pacific (£3.3m). This is managed through a partnership with International Coalition for Trachoma Control (ICTC) who appointed Sightsavers to manage the initiative in 6 African countries working to support the elimination of trachoma in Malawi and Kenya, and significant reductions in the burden of trachoma in Mozambique, Nigeria, Tanzania and Uganda. This is done by the adoption of the WHO SAFE strategy (Surgeries, Antibodies, Facial cleanliness and Environmental components).In the Pacific, the Trust it is working with ICTC and the Fred Hollows Foundation to, support elimination in Fiji, the Solomon Islands, Vanuatu and Kiribati (the Trust also supports work in Australia but not with DFID funds).

Second, addressing diabetic retinopathy (DR). In the Commonwealth, an increase of 60% in DR is predicted over the same period. Diabetes increases the risk of many eye health problems, with DR being the main cause of blindness. The Trust is supporting a partnership between the Public Health Foundation (PHFI) of India and the London School of Hygiene and Tropical Medicine (LSHTM) (£4.2m) to improve prevention, detection and treatment of DR in India. The Trust is also supporting the Caribbean Council for the Blind to reduce rates of DR in the Caribbean (£1.4m), and the Fred Hollows Foundation to reduce rates of DR in the Pacific, Bangladesh and Pakistan (£900k).

Third, addressing retinopathy of prematurity (ROP). The major stream of work is in India through a partnership with Public Health Foundation of India PHFI and LSHTM (£3.5m). The PHFI and the LSHTM are working with federal and state governments to integrate services to prevent, detect and treat ROP within Special New-born Care Units (SNCUs). These units are being rolled out at district level with a target of 1000 units operational in 2017. The initiative covers supporting strategy and guideline development, training, new patient record and management systems and the development and testing of more affordable equipment for ROP diagnosis.

Fourth, strengthening of knowledge, tools and people to improve eye health across the Commonwealth managed by the International Centre for Eye Health (CEHC), hosted by the LSHTM (£7.1m). The Consortium supports fellowships to increase eye care expertise in low income Commonwealth countries, provides a knowledge platform to facilitate learning and information exchange, and a technology programme to develop, validate and rollout low cost eye health diagnostic and management tools.

Results – The 2013 Business Case stated that the trachoma initiative could protect more than 18 million people from blinding trachoma through antibiotic treatment and prevent blindness in a further 405,000 through surgery. As the AR demonstrates, new data on trachoma prevalence has led to a downscale of the coverage needed. It is currently estimated that 7 million will receive antibiotics and 136,000 will receive surgery. Outcome: Increased capacity and access to quality eye health care in targeted areas of the Commonwealth for Trachoma, Diabetic Retinopathy (DR) and Retinopathy of Prematurity (ROP).

Context during the reporting period: The trachoma global agenda has reached its highest ever point. Funding (DFID and USAID in the main) has facilitated a huge expansion of care. The intensive global technical collaboration has ensured a strong focus on SAFE, together with a strong network between implementation partners has ensured effective use of the resources. Critically, drug company Pfizer, donated drugs on a major scale. The trachoma programme’s success holds learning for other neglected tropical diseases. The Trust has a critical role to play in this process.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual OUTCOME and OUTPUT summary assessment

OUTCOME	Baseline	Milestone			Achievement
Number of people whose sight has been protected as a result of programme activities (derived from all the initiatives)	None (new indicator to replace the previous one)	Trachoma (1) 2014-2015: 26,000 people / (2) 2015-2016: 42,129 people / ROP – 360 / DR - n/a / NB: Sightsavers reporting year is April to March			(1 )For April 2014 to March 2015: 24,138 / (2) From April 2015 to September 2015 – i.e. half year 12,539 against the milestone of 42,129 = 30% ROP- 8		B
Number of health professionals trained/retrained and practicing in targeted Commonwealth countries (derived from trachoma initiative and CEHC) / NB: figures are cumulative	None (new indicator to replace the previous one)	(1) 2014-2015:138 / (2) 2015-2016: 195			(1) April 2014 to March 2015: 117 / (2) April 2015 to Sept 2015 – i.e. half year: 148 against milestone of 195		A

Has the logframe been updated since the last review?
Yes, details provided in the logframe’s additional sheet termed ‘Logframe changes’ which presented the chronology of logframe changes agreed between the Trust and DFID. In summary:

Outcomes: In response to the last AR, the indicators have been amended to capture aggregated results from all four initiatives. This was done in consultation with coordinating partners and the Trust’s SAB and allows the Trust management team to look at aggregated results across countries thereby ensuring flexibility to re-allocate resources and manage risk. Agreed with DFID in March 2015.

Outcome Indicator 1
2014 indicator:	Percentage of endemic districts that have achieved criteria for stopping district level Mass Drug Administration (MDA).
Revised indicator:	Number of people whose sight has been protected as a result of programme activities. (This is the sum of all beneficiaries who have received trichiasis surgery for trachoma, and treatment for diabetic retinopathy and retinopathy of prematurity.)

The 2014 indicator on districts that have achieved the criteria on stopping MDA is a useful outcome indicator for the Trachoma Initiative, but it does not apply to the Trust’s other initiatives. The new indicator captures all beneficiaries who have received surgery to treat trachoma, DR or ROP.

Outcome Indicator 2
2014 indicator:	Healthy survival rate without ROP - survival to discharge rates of infants <2000grams in Special New-born Care Units (SCNUs) in quality improvement programme area.
Revised indicator:	Number of health professionals trained/retrained and practicing in targeted Commonwealth countries. (This includes health professionals trained as part of all four initiatives).

The 2014 indicator only applies to the ROP initiative, and is a proxy indicator to show the overall improvement in neonatal care. The new indicator aggregates all the health personnel that receive training (includes, but is not limited to, surgeons performing trachoma surgery, community health workers, nurses in neonatal units, ophthalmologists, and recipients on scholarships and fellowships through the Commonwealth Eye Health Consortium).

Output levels: Four output level indicators have been deliberated on between DFID and the Trust.
Output Indicator 1.1 (agreed and amended in the summer of 2015)
2014 Indicator: Number of people who have had their trichiasis managed.
Revised indicator: Percentage reduction in Trachomatous trichiasis (TT) surgery backlog target.

Improvements in data collection, and results from the DFID-funded Global Trachoma Mapping Project, have led to readjustments of the surgery targets for trachoma elimination. This has particularly been the case in Uganda, where the existing data was out of date, and new data has revised down the number of surgeries required. The objective of the Trachoma Initiative is to eliminate, or significantly reduce the trachoma backlog. Therefore the indicator has been altered to capture the percentage towards progress, rather than absolute figures (although absolute figures of the number of trachoma surgeries will still be captured in the log-frame to give an idea of scale). This will be more useful going forward, as the Trust may expand work into other districts, and the trachoma backlog may increase. Tanzania has joined the Trust’s Trachoma Initiative and has been added to the log-frame.

Output 1.3 and 1.4 - The ICTC is working with partners to identify key indicators for the F and E elements of the SAFE strategy. Once these indicators have been finalised they will be discussed with DFID and used as appropriate for this log-frame.
Output 4.2 - DFID suggested (March 2015) this be changed to "Number of countries receiving support from the Trust to Implement the DR Framework," however, as this indicator would not change over time, the Trust has decided to keep the original indicator – DFID agreed to this during this AR.
Output 4.3 - DFID suggested that "New eye care technologies developed" is a little vague. The Trust agrees, but has decided to keep the indicator and look at establishing more concrete milestones for future years regarding completion of trials, development of hardware and software, and in-country implementation. DFID agreed to this during this AR.

## C: DETAILED OUTPUT SCORING
Output Title	Effective implementation of selected elements of the SAFE (Surgery, Antibiotics, Facial Cleanliness, Environmental Improvements) strategy
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		Yes (changed from low medium)	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone	Achievement	Whether met target and explanation / Given that score is composite of (i) performance against SS’s reporting year April to March 2015 and (ii) mid year progress against April to March 2016.	Score
Number of people who have had their trichiasis managed provided in brackets for context. Figures have been rounded to the nearest 500. / New indicator in 2015/16. Percentage reduction in TT surgery backlog target (introduced in Sightsaver’s 2015/16 reporting year).	April 2014 to March 2015: 26,000 / April 2015 to March 2016: total: 41,500 / Kenya - 54% (12,000) / Malawi - 53% (2,500) / Mozambique - 36% (2,000) / Nigeria - 45% (5,000) / Tanzania - 17% (5,000) / Uganda - 73% (15,000) / April 2015-March 2016: 48%. Half-year target: 24%	For April 2014 to March 2015: Kenya - 24% (9,854) Malawi - 6% (368) Mozambique - 3% (235) Nigeria - 2% (345) Uganda - 35% (13,498) Total - 24,138 against the milestone of - 26,000 / April 2015 to March 2016 total: 12,539 against milestone of 41,500 (30%) / 29% completed so far - so over 50% of annual target met	Marginally under achieved / Not met / Met half year target	B
Number of people treated with antibiotics in endemic target communities in Kenya, Malawi and Pacific Islands. / Figures are for number of treatments each year.	April 2014-March 2015: / Kenya - 2m / Malawi - 5m / Pacific Islands tbc / Total - 6 million / April 2015-Sept 2016: / 7 million	From April 2014 to March 2015: / Kenya - 2.5m / Malawi - 3m / Total – 5.5m / From April 2015 to Sept 2016 / 88,557	Met. 5.5m of 6m = 80% (considered the level needed to be assured a mass distribution is effective) . / Did not meet half year mark - however very probable that progress will accelerate and Sightsavers reporting year 2015/16 milestone will be met).	B
Number of endemic districts where Facial cleanliness is implemented through effective behaviour change programmes	46	From April 2014 to March 2015 / Total 1 against a target of 46 / From April 2015 to Sept 2016 - 0	Under achieved / Did not meet half year mark / (However very probable that progress will accelerate and SS’s reporting year 2015/16 milestone will be met).	B
Number of endemic districts where environmental improvement is implemented	46	From April 2014 to March 2015 / Total 0 against 46 / From April 2015 to Sept 2016 – 0	Under achieved. / Did not meet half year mark. / (However very probable that progress will accelerate and SS’s reporting year 2015/16 milestone will be met).	B

Key Points
Summary: Sightsavers’ reporting year is April to March – thus presently mid way through their second reporting year (2015/16). DFID’s reporting year is a calendar year. Hence, DFID is judging progress by a composite of (i) performance against Sightsavers reporting year April to March 2015 and (ii) mid year progress against April to March 2016.

Progress is mixed. Milestones not met (and thus the overall score is B) but very probable that Sightsavers’ reporting year 2015/16 milestones will be met.

Output 1.1: Mixed progress: milestones for Sighstavers are reporting year 2014/15 (and half way for 2015/16) for the number who had their trichiasis managed have not been met. However, with respect to the new indicator (% reduction of backlog of surgery), 50% of Sightsavers’ 2015/16 milestone has been met. Failure to reach the milestones is due to inaccurate milestone setting because of the reliance on older, less accurate data available at that time. Latterly there have been major improvements in the appreciation of trachoma prevalence – which is proving to be much lower than previously understood and hence fewer surgeries are needed.  Better data is in  large part due to the DFID Global Trachoma Mapping project and improved methodologies used for impact surveys. It is now evident that some countries will reach their universal intervention goals (a reduction in backlog to less than 1/1,000 pop) faster than anticipated.

Progress – mid year – against the new indicator. Note that two of the three countries with the largest burden are making very good progress against their annual milestone. Nigeria’s (a high burden country) progress is problematic.

Country	Yr 2 Percentage Milestone target	Calculated progress using revised 5 yr targets	Number of surgeries to do in Yr 2 to achieve target %
Uganda	73%	45%	6,535
Kenya	54%	39%	6,019
Nigeria	45%	4%	6,430
Tanzania	12.5%	1%	3,149
Mozambique	53%	11%	1,584
Malawi	36%	26%	1,258
Total vs 5 yr target	48%	29%	24,975

The 48% total is calculated using a 5 year total TT surgery target of  127,815 surgeries which are the latest figures emerging due to impact surveys conducted this year.

Output 1.2: mixed: For Sightsavers reporting year 2014/15, 5.5 million of the planned 6 million have been reached. Although the milestone was not reached, 80% coverage is considered the level needed to be assuring a mass distribution is effective. Sightsavers April 20215/2016 milestone is on track to be met. There were challenges managing the Mass Distribution Administration (MDAs) as planned due to production levels of Zithromax by Pfizer. To interrupt transmission of the disease, populations need to receive antibiotics within 12-18 months of their last dose. As the supply-chain problems with Pfizer have now been mitigated, MDAs are expected to be conducted in the second half of Sighstavers reporting year and thus target 1.2 against Sightsavers’ reporting year of April to March 2016 is likely to be met. The Trust and the ICTC have worked with Pfizer to ensure that the MDAs for this programme year will be met. The more significant indicator is the % of endemic districts that are achieving >80% coverage of MDA in the year, rather than the absolute number of antibiotic doses distributed. Thus 1.2 should be amended to reflect this.

Output 1.3 and 1.4: Milestones not met for both Sightsavers reporting year 2014/15 and 2015/16 mid year mark. There has been a particular focus on facial cleanliness and environmental (F&E) improvement components of SAFE, as these are the often neglected elements in SAFE projects. District level intensive cleanliness and environment improvements began in earnest in October but national level preparedness work has been well underway for months. Laying the ground work for interventions has taken considerably longer than anticipated. It is anticipated that Sighstavers 2015/16 milestones will however be met as there is a rapid scale up underway now.
Sightsavers have 19 grants with a wide range of sub-contractors (including Sightsavers country offices).  The initiative scales up SAFE. In some areas the initiative covers all the SAFE components and in some districts only some components of SAFE as it compliments work Sighstavers and other ICTC members are doing with non Trust funded projects in the same areas, hence ensuring maximising resources. As mentioned, the Trust is focusing on the often neglected F&E components.
Sightsavers and ICTC have added value to the global SAFE scale up movement by ensuring “one trachoma programme” in each country by providing strategic oversight, facilitating cooperation across a growing number of (non-Trust funded) projects at country level. Globally they have provided a range of materials and brokered relationships between professionals in the trachoma field. In particular, the initiative is the  largest scale programme driving elimination in some countries and producing critical learning of the “last mile” in control and ensuring experiences and learning are well disseminated, e.g. to the WHO Global Trachoma Scientific Meeting, in November 2015.
Sightsavershas worked closely with WHO (NCD and trachoma units) in profiling and scaling up support to the adoption “preferred” (otherwise called best) practice within SAFE to deliver ever more efficient and quality care.  Sightsavers is also contributing to improved data collection and analysis and will be engaged in the new WHO led Tropical Data initiative – mobile based data collection to work beyond prevalence mapping and into impact surveys and surveillance surveys.
The initiative is building systems: investing in national capacity (132 surgeons and 8,468 case finders trained thus far), training in surveillance and weaving planning into national planning structures and integrating behaviour change into existing programmes such as community led total sanitation and school health programmes.

Africa (ICTC the grantee, Sightsavers are the grant manager)
  1. Annual Participatory Programme Review Meetings took place in each African Country (Jan – March 2015) and each submitted Year Two implementation plans and budgets (April 2015). Tanzania added as 6th country in Africa (April 2015).
  2. 13 districts in Malawi, Mozambique and Uganda have reached trachomatous trichiasis (TT) elimination thresholds earlier than planned and can now be moved to surveillance. The programme is working at a scale not experienced before. Supervision of surgical outreaches at this scale has been a challenge.
  3. Nigeria’s scale up is the poorest. The annual target there (6,430 surgeries) may not be met.
  4. The Unilever supported face washing pilot in Kenya was scaled up through the rest of Turkana, Kenya, from July 2015. School activities were delayed due to teacher strikes but are resuming in the new year.
  5. The Trust and the ICTC secured additional funding: e.g. for surgery in Tanzania from the Conrad N. Hilton Foundation and the END Fund.
  6. Sightsavers’ partnership with the DFID UKAID Match Coordinated Approach to Eye Care provides patients at surgery camps systematic treatment for other eye ailments beyond trachoma, in Kenya, Malawi, Mozambique and Uganda.
  7. Delays in the production of Zithromax by Pfizer have caused some delays in MDAs. This has been tackled with some immediate operational changes, but should not affect long-term plans.
Pacific
Ministries of Health participated in planning workshop (March 2015) and the first nationwide round of MDA completed in Solomon Islands (Sept 2015).

Summary of responses to issues raised in previous annual reviews (where relevant)
  - Logframe targets to be updated by the Trust based on Trachoma Action Plans (TAPs) and agreed with DFID. The targets in the log-frame are updated on an on-going basis as new data becomes available.
  - Sightsavers to report, and the Trust to monitor, the degree to which implementation remains coordinated with national strategies, including potential impact on the provision of other health services (e.g. other eye health programmes). TAPs have been developed with national Ministries of Health. Annual and quarterly review meetings are held with health officials and implementing partners. Sightsaversare also ensuring that the DFID-funded Coordinated Approach to Eye Health does not adversely impact the Trachoma Initiative.
  - Sightsavers to report, and the Trust to monitor, the degree to which FE components are appropriately integrated at country level. F&E proposals have been approved in Kenya, Malawi and Uganda and F&E work is now being implemented by thematic partners.

Recommendations for 2016
Intensify actions to address the poor progress reported in Nigeria .
Output 1 logframe changes
  1. Revise 1.2 to x% of endemic districts achieving >80% coverage of MDA in the year, rather than the absolute number of antibiotic doses distributed.
  2. Revise 1.3 and 1.4 to better reflect the impact of F&E improvements. The Trust and the ICTC are well underway in developing this.
  3. Given Sightsavers’ reporting year is April to March, provide mid-year milestones as well to enable reporting against the DFID reporting year.

Output Title	Increase in the proportion of diabetic patients treated for diabetic retinopathy (DR) in targeted Commonwealth countries
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone / (December 2015)	Achievement	Score
Number of diabetic patients screened for diabetic retinopathy	India - 50,000 / Caribbean - 21,000 / Pacific - Targets identified	India – None. Screening to begin in first states in December 2015, however implementation timelines have since shifted. / Caribbean - 333 (up to Sept 2015) Pacific – 290 (up to Nov 2015)	C
Proportion of screened diabetic patients treated for diabetic retinopathy	India - baseline data collected for chosen states. Targets identified. / Caribbean - 1,000 / Pacific - Targets identified.	India - Situational analyses completed and States selected and targets being developed / Caribbean - 48 (up to Sept 2015) Pacific - Baseline survey completed and being reviewed	B
Number of health professionals trained on prevention, detection and management of diabetic retinopathy	India - States identified	Met as States identified. Working on numbers to be trained	A

Key Points
The output is managed by the Public Health Foundation of India (PHFI with technical support from the LSHTM), and Fred Hollows Foundation. Summary: One of the three milestones met – scored B
Output 2.1 Milestone not met as more foundational work with national authorities was required than anticipated. This has been time intensive – impacting on finalisation of the LF. Milestone targets were not amended to reflect the reality of the intensive nature of establishing partnerships.
In addition, there was a paucity of good data to forecast milestones against. Over this reporting year, experience will enable milestones to be better set.
Output 2.2: Milestone not met. This links to 2.1 as screening needed before treatment provided to those identified as requiring it. Milestone given a B rather than a C, given that although the Caribbean number has not been met, this country’s scale is considerably lower than India’s will be.
Output 2.3: Milestone met. States identified and training numbers being collated and planned for. The training will be for diabetic care physicians and ophthalmologists.
India: The foundational work has taken considerably longer than envisaged. However, the strategic and well planned and delivered foundation work is justified and it is very probable that screening and treatment rates will increase significantly in year 3. Clearly it would have been better if the scope of foundational work was foreseen earlier and screening and treatment levels adjusted.
The initiative commenced in earnest in India in January 2015. It aims to ensure services sites in 10 States by the end of the project.
The strategic advocacy and planning commenced with the Additional Secretary (Health), Ministry of Health and Family Welfare, writing to the Principal Secretaries of Health of 10 State Governments highlighting the need to support integrated district models for prevention of blindness due to DR. The ongoing advocacy work now well underway with 10 State level Ministries of Health: in five States strategic sensitisation work is underway and in two of them tripartite MOUs (PHFI, state government and NGO partners) are in place with 3 more coming on stream. By March 2016 there will be services in 8 States. Care will primarily be provided through non communicable disease (NCD) clinics. The situational analysis report has been disseminated to key stakeholders, is accessible through many websites and presented at a number of conferences. It assessed the service delivery for management of diabetes and treatment of DR in 11 major cities and evaluates 14 leading eye care providers. Six expert groups are now operational: working on programme planning (appraises state proposals), advocacy, communications, data management, monitoring and evaluation, and capacity building for physicians and ophthalmologists (including a specific group developing detection and treatment guidelines).
There are sufficient NGOs working in eye care however there are few working in NCDs. The NGOs will support the training of eye care teams in diabetic care units (in NCD sites), support referrals and monitor the effectiveness of the initiative in strengthening public health care provision. NGOs will not provide services but augment the public sector’s delivery. The private sector is being contracted to train eye care physicians and support the aforementioned guidance and developing technologies.
There were two unplanned but significant additional activities this year. The Trust secured funding from the Helmsley Trust to expand the initiative to Type 1 diabetes. And finally the PHFI has developed a certificate course for GPs in early diagnosis and referral.
Pakistan – Implementation activities are due to begin in January 2016. A representative from FHF Pakistan was unable to visit PHFI in India due to difficulties in securing a visa.
Bangladesh – DR work is starting from a significantly lower level compared to India. The FHF Programme Coordinator visited India with the Trust in October 2015 to share learning with PHFI. The Programme Coordinator was able to subsequently share learning with FHF Pakistan. Data collection for operational research has begun.
Caribbean – (Caribbean Council for the Blind ) Tropical storm Erika in August 2015 caused some delays, especially in Dominica where it delayed the start-up workshop
Pacific – (Fred Hollows Foundation). The first Kiribati Medical graduate returned to Tarawa, Kiribati at the start of 2015 to deliver permanent surgical services to the country for the first time in its history. Supporting the graduate to ensure a strong eye care and DR programme in Kiribati is a priority for FHF New Zealand. Following the opening of the Regional eye Centre in July, there has been a strong increase in the uptake of DR services in Honiara, Solomon Islands.
A theory of change has been developed with input from all DR partners to identify similarities in the projects and form the basis of evaluations.
Summary of responses to issues raised in previous annual reviews (where relevant)
- Based on national consultations and situation analyses undertaken, the Trust and implementing partners should agree geographical focus (India), and logframe baselines and appropriate milestones and targets for DR initiatives by mid-2015. Done: Ten States were selected of which 8 State Governments are demonstrating a willingness to commence engagement and will have services by the end of March 2016. Partners have identified the need for deeper engagement with state Ministries of Health to ensure strong government ownership of the initiative.
- Multi-country implementation and support for the DR Vision 2020 network provide opportunities to measure and compare the effectiveness and value for money of different delivery approaches for different populations across countries, including potential to provide services in more rural settings. Underway: the Trust is facilitating learning across partners within the core countries, between the countries and globally.
- Implementing partners should ensure that mechanisms are in place to monitor and report periodically to the Trust on the socio-economic status of patients accessing DR services. The Trust’s DR Initiative is working primarily within the public system which is the primary point of call for the poor. In India PHFI has pro-actively identified districts with disproportionately poorer people, including tribal communities. The cost of creating a data base has not been done yet – this is needed to inform a decision as to whether it is cost effective to introduce it.

Recommendations for 2016
Output 2 logframe changes: Set the milestones for 2.1 and 2.2 and 2.3.

Output Title	Increase in the number of infants treated for ROP
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone / (December 2015)	Achievement	Score
Number of infants screened for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area	50% of those eligible for screening are screened / = 3,600	Telangana = 175 screened (over 5 months in one SNCU). Screening will start soon in Madhya Pradesh.	B
Proportion of infants treated for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area	(10% of above expected to be treated) = 360 / Obtain baseline rates of ROP requiring treatment from first year of implementation	Telangana = 8 treated (5% of those screened; 2% of the target for the year) / Baseline rates were obtained	B
Number of health professionals trained in screening and treatment of ROP	Baseline data collected for chosen states	Situational analyses completed, baseline data collected, targets set and training begun	A

Key Points
Outputs managed by Public Health Foundation of India PHFI with technical support from the LSHTM.

Summary: One of three milestones met
Output 3.1 and 3.2 Progress mirrors output 2. The foundational work has taken considerably longer than envisaged. Thus whilst the breath of foundational work is impressive and completely necessary, it has resulted in 3.1 and 3.2 not being achieved. Had the extent of foundational work been acknowledged earlier the targets could have been adjusted.
Output 3.3 Met
The output is managed by PHFI with technical assistance provided by the LSHTM and operates in India alone. The initiative address both reducing the risk of sight threatening ROP through improved quality of care, i.e., by reducing sepsis, better oxygen management etc., and reducing the risk of blindness from ROP by screening and prompt treatment of sight threatening ROP.
Currently projects that around 600 screenings will be done by the end of March 2016 with a rapid scale up thereafter. The initiative aims to work in 5 States in 4-5 Medical College and District Hospital SNCUs in each State i.e. 20 SNCUs by the end of the programme. Some States may scale up with non-Trust funds.
Progress at the national level includes: A comprehensive situational analyses in 8 States was conducted to identify the resources available for ROP screening and treatment, to establish suitable health facilities for the ROP Initiative to commence in and to gain political commitment. This informed the prioritisation of the States (albeit the work in 2 States commenced before the end of the situation analysis, at the recommendation of the National ROP Task Force, which is chaired by the Joint Secretary Health for child health). Telangana and Madhya Pradesh are the first partner States.
A national ROP taskforce has been established (3 meetings held to date). A final operational guideline for prevention, management and treatment of ROP has been produced. This links to a new partnership with the RBSK (national child protection scheme addressing the chronic health care needs of the new-born through early intervention centres) to roll out care. A special issue of “Indian Paediatrics” focussing on ROP will be published in early January 2016. The Expert groups (similar to those established for DR) have been established.

Significant advancement made on developing quality of care (QoC) initiative and a range of training tools. This is being led by India’s three leading medical schools.
State level: Telengana State has commenced screening and treatment. Madhya Pradesh will start screening very soon. Both have tripartite MOUs (similar to DR initiative). Three States will join the initiative next year: Orissa, Maharaja and Rajasthan (selected as met the criteria for engagement). Tamil Nadu State will adopt the initiative with its own funding as a result of sensitisation by the Trust. Units within the States are developed to both screen and treat through the intensive QoC interventions. The QoC element of the programme will focus on SNCUs where screening and treatment of ROP is being rolled out by the Trust, as “healthy survival without ROP” is the outcome of this QoC initiative. Data are therefore required on rates of ROP as well as preterm survival.
The initiative focus on public sector (which provides majority of maternity services), and the majority of centres eventually providing services will be rural based and by de-fault will serve the poor. Some components (such as inclusion of ROP into medical training curricula) will have spilt over into private sector maternity services.
PHFI and LSHTM have well established links with policy makers and professional association leaders and the Trust are enabling ever more global networking.
Summary of responses to issues raised in previous annual reviews (where relevant)
- The Trust to agree appropriate logframe milestones with implementing partners for years 2 and 3 (e.g. state selection, completion of situation analyses and agreement on targets).
  States have been agreed. Milestones were added. However, these need to be revisited again in in light of new projections.
- The Trust and ROP implementing partners to agree approach to costing services and estimating cost-effectiveness of ROP programming (drawing on lessons from the DR initiative). The PHFI will design and implement a cost effectiveness study later having established effectiveness first. Nevertheless, addressing cost effectiveness is inbuilt into the initiative: currently the only camera available for screening for ROP costs £60,000. Technology is ever developing – new and cheaper cameras will be validated soon.
- State level situation analyses should include an assessment of which populations groups are utilising SCNUs and are most likely to benefit from ROP investments. The database on families cared for includes a superficial classification of economic status. The cost to adapt the system to ascertain more information will be very high. The Trust is confident the poor will disproportionately benefit, given most SCNUs supported will be at district level.
Recommendations for 2016
Output 3 logframe changes
3.1 Revise down the milestones for the next two years based on programming in Niloufer Hospital, Hyderabad (detailed spreadsheet provided by Prof Gilbert/LSHTM and PHFI).
3.2 Revise down the milestones – as for 3.1.
3.2 Revise down the milestones.

Output Title	Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Yes – was low	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone / (CEHC reporting year June to May (to be amended to calendar year)	Achievement	Whether met target / Score is composite of progress against May (2015) milestones – and progress towards following May (2016) milestone	Score
Number of health care professionals trained and working in eye health in their home country	Total - 28 / MSc students - 3 / Short-term Clinical Fellowships - 10 / Long-term Clinical Fellowships - 15	June 2014 to May 2015 / CEHC advisory board operational: / 12 MSc students in MSC Public Health at LSHTM. / 9 MPH in community eye care at University of Cape Town / Clinical Fellows: Long term 42 appointed (12 commenced) and short terms 36 appointed (12 commenced). / Research training fellowship: 8 PhD fellowship commenced and 2 post-doctoral fellowship underway / Against a target of 10 Short term clinical fellowships / From June 2015 to November 2015 progress / MSc students – 3 Short-term Clinical Fellowships - 13 Long-term Clinical Fellowships – 13 (currently studying) Total - 16 completed, 29 due to complete by end of programme year out of total of 28 for the year	(1)Met / (2)Met	A
Number of countries with domestic institutions that have agreed and implemented national frameworks for DR screening and treatment	6 countries agreeing national DR framework with their NPBCs. National frameworks in place in 2 countries.	(1) June 2014 to May 2015 / Against a target of 10 countries in DR network and 2 countries agree DR framework with their NPBCs. 10 did join the network and one country (Botswana) agreed a framework. / 10 Commonwealth countries joined the Network. National framework agreed in Botswana. / (2)From June 2015 to November 2016 progress / Frameworks have been agreed in Botswana and Zambia, and development is underway in Tanzania. The frameworks are in place in two countries: Botswana and Zambia.	(1) just underachieved / (2) Ontrack mid year mark	A
New eye care technologies developed	Development of technologies and studies underway	June 2014 to May 2015 / Consortium plan developed and proposal approved. / (2) From June 2015 to November 2015 progress Peek studies on usability, DR, malaria retinopathy and school children completed.	Achieved / Achieved	A

Key Point
The output is managed by the CEHC.
Summary: All three milestones met.
Output 4.1: Met milestone as training has really scaled up this year and well on track to meet 2015/16 milestone.
Output 4.2: Met milestone as increasing numbers of countries joining Networks and forming their own frameworks.
Output 4.3: Major scale up in research underway.
- Excellent scale up of training and research support. CEHC’s aim to foster south to south partnership is demonstrating it is feasible, cost effective and fostering real cross commonwealth learning. The training now covers MSc in public health for eye care, MPH in community eye care. Scholarships are awarded. Clinical fellowships have expanded the research fellowship component commenced in September. There has been an enormous demand for the range of training opportunities.
- The selection process is robust and transparent. It pays attention to probability of graduates continuing to serve in the public service.
- The training and research links to the CEHC’s technology programmes is very strong: much of the research underway addresses the implementation of new technology.
- PEEK development is impressive: winning many awards and a new website has been launched.
- There has been a massive scale up in the production of open digital education programmes. The Global Blindness (Vision 2020) training – also funded by Standard Chartered Bank – has had over 1,000 participants – so there is a major appetite for e-education. Testimonials are very positive. The Epidemiology for Eye Care has over 100 institutions engaged and again proving very popular. Three other courses will come on stream soon.
- The DR network complements the Trust’s DR work in Asia as it works in 9 African. It was born out of the LinKs Vision 2020 programme which is now focusing on DR through “twinning” institutions to share knowledge on appropriate care and technology.
- The CEHC were the first partner to develop a comprehensive theory of change (November 2014).

Summary of responses to issues raised in 2014 AR

DR-Net should follow up with members by May 2015 to report on how action plans developed at London workshop have been integrated within national policies at country level. Partially done: a DR Framework has been developed in Botswana and meeting was held with the Ministry of Health in Tanzania, in line with the log-frame targets for the first year of the initiative.

Recommendations for 2016
Output 4 logframe changes.
4.2 milestones to be scaled down given progress to date.

Output Title	A robust, responsive and supportive Trust
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone	Achievement	Score
Annual report and financial accounts clearly detailing use of DFID funding	Compliant accounts and reporting. Clear lines of communication	Unqualified Audit received for FY 2014-15 in October 2015. / 2014-15 Annual Report and Accounts approved by Board of Trustees in November 2015.	A
Proportion of grantees satisfied by implementation and value added by the Trust	Grantee responses to satisfaction survey included in annual reporting to the Trust	Grantees interviewed by DFID for this annual review reported responsive and productive management relationship with the Trust. / Grantee satisfaction recorded as part of six-monthly reports.	A
Development of monitoring indicators and evaluation reports showing capacity building and lessons learned	Nil set	M&E Strategy updated in May 2015 largely addressing the recommendations of DFID’s SEQAS report. / Results indicators agreed with DFID and all major partners. / Evaluation Inception report completed for Commonwealth Eye Health Consortium. / Plans developed for Joint evaluation on trachoma with DFID SAFE programme. / Sharing global learning on addressing trachoma at scale.	A

Key Points
Summary: All three milestones met
- The 2014-15 Annual Report of the Trustees, under the Charities Act 2011 and the Companies Act 2006, was approved by the Board of Trustees and will be published in early 2016 once it has been countersigned by the auditors. It included the Trust’s audited Financial Statements and Accounts which received an unqualified audit.
- One public-facing report has been published to date.
- Grantees and global trachoma partners interviewed by DFID for this annual review reported a continuing responsive and productive management relationship with the Trust.
- The monitoring and evaluation strategy has been updated. The Trust has largely addressed the recommendations made by the SEQAS report (referred to in the 2014 DFID Annual Review) around clarifying evaluation objectives, theory of change, value and legacy. The revised strategy is much clearer and more robust (see also 2015 recommendations below).
Evaluation – the Trust is proactive in developing a joint evaluation with the DFID SAFE programme to evaluate the entire range of DFID funded trachoma work.
- Regular monitoring by the Trust is undertaken through detailed work plans for each partner. Each partner submits six monthly report and monthly updates. Partner’s cycles for reporting vary.
- The Trust has developed a results summary as a substitute for a formal results framework (given the relatively narrow focus of the Trust’s work). This provides a good core set of indicators at the outcome and output level (impact level - see 2016 key recommendations under summary section) that can be aggregated and used for purposes of monitoring and tracking the Trust’s performance over the lifecycle of the programme.
- The Trust’s approach to advocacy is very effective: the Trust has access to very senior officials, Ministers and to strategic forums.
- The Trust global profile is raising – the website is active and other dissemination events include Commonwealth Heads of Government Meeting (CHOGM) and WHO General Assembly.
- The Trust has created platforms for effective lesson learning and networking across a range of relevant professional organisations and between countries (e.g. facilitating Fred Hollows’s officials visiting India).
- The Trust has been influential in unblocking critical strategic bottlenecks. For example, the Trust supported donor efforts to develop a constructive, honest and open dialogue with the International Trachoma Initiative and the Pfizer drug donation programme on the allocation and shipment of Zithromax.  This has been particularly helpful as the past year has seen a significant increase in the demand for Zithromax that has resulted in several logistical challenges for ITI and Pfizer. The commitment from the Trust and other partners to implement SAFE across a number of countries is important in ensuring continued commitment from Pfizer to the drug donation programme and the goal of eliminating blinding trachoma.
- The Trust has now secured the DFID match funding of £50m so is now programming £100millon.
The SAB is shifting its focus to monitoring progress on results and approving evaluation proposals and the Trust has developed a dashboard which, along with the results summary, provides a helpful snapshot of progress for the SAB and the main Board meetings.
The Trust is a critical member of the ICTC Programme Advisory Committee that oversees both the QEDJT programme and the DFID SAFE programme.
Summary of responses to issues raised in the previous annual reviews

- The Trust should ensure as much as possible that logframes for the various initiatives have common indicators to allow the aggregation of results at the outcome level. Done – see above and Logframe section.
- In future Annual Reports, the Trust should align results reporting to these common indicators to demonstrate progress towards achieving programme output and outcomes Partially done – the 2014-15 Annual Report contains results reporting against the indicators but these results are presented in a very narrative format with no summary section highlighting the main programme achievements in an accessible way.
- The Trust should provide in its annual report to DFID a summary of feedback on Trust performance received in routine reporting by suppliers. Done. For each 6-monthly report grantees provide feedback to the Trust on their relationship. This has been reported to DFID.
- The Trust should develop its monitoring and evaluation strategy in line with the recommendations of the SEQAS report to ensure the strategy defines a clear, structured and integrated approach and can be built upon as the programme progresses. DFID will work with the Trust to support the development of a more robust strategy. Done; the feedback from SEQAS has been largely incorporated into the M&E strategy and this has been reviewed by DFID. The M&E strategy will continue to be periodically updated as the initiatives develop. See monitoring and evaluation section.

Recommendations for 2016

- DFID appreciates the Trust’s Annual Report responds to the needs and interests of a wide range of stakeholders. The Trust to consider its presentation of results achieved as part of its Annual Report as per the comments above under responses to previous annual reviews.
- The Trust to develop, as part of the M&E Strategy, more on strategic communications including the Trust’s approach to networking and influencing. The Trust delivers important objectives through its influencing role and should include an appropriate indicator to measure this work; for example the number of countries receiving support to develop eye health policies or x example of policy influence delivered
- The SEQAS report also made recommendations about equity in monitoring processes. The Trust should disaggregate data by gender (at least) as recommended in the report.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The main cost drivers for the programme are: human resource and logistics costs incurred through implementing partners. These vary by initiative and delivery channel (e.g. clinic based services or outreach teams). Pharmaceutical costs for prevention of trachoma are met by the ICTC. Costs for surgical equipment, training materials, and diagnosis of DR and ROP vary by country programme.

VfM performance compared to the original VfM proposition in the business case
At this stage there is insufficient information on operational costs to use to compare to those in the business case.

VfM is well understood amongst the partners. Examples of addressing economy and efficiency include:
- Range of management approaches: criteria for selection of States and districts, robust approaches to contracting (use of standard contracts that allow comparison of unit costs and productivity rates across suppliers);
- Initiatives focused on reducing cost of inputs – PHFI keeping well abreast of new technologies for ROP and engaged in validation of them;
- The roll out of Tropical Data (following the success of Global Trachoma Mapping Project) will provide cost effective data to improve programme decision making and cost saving;
- Improved programming has saved on costs: Kenya no longer needs surgeons for the pre outreach camps for counselling and in Malawi and Uganda have adjusted downwards the number of outreach days needed to get the same result.

Assessment of whether the programme continues to represent VfM
More detailed epidemiological and programme implementation cost data was expected in this annual review however the actual pace of establishing services has been slower than anticipated and hence there is no advance on that stipulated in the last annual review. The last review noted the economic appraisal in the business case adopted different methodologies to assess VFM for each initiative – more detailed epidemiological and service model/cost was available for trachoma programming (found to be highly cost effective in terms on disability adjusted life years (DALYS) averted) and less for both DR and ROP initiatives. The PHFI will do cost effectiveness studies for DR and ROP but not for a couple for years as the programme needs time to bed down and prove it is effective.

There is a case to re-run the cost benefit analysis for the programme’s trachoma initiative given the reduction in overall coverage now forecast compared to those forecast in the business case (see Results – under section A). In addition, there are now more accurate programming costs to work this. This analysis will be of value to WHO in its leadership of CBA related to trachoma elimination.

Equity
All partners across the Initiatives have a poverty focus on selection of service sites which are predominately public sector sites. The trachoma initiative has found that trachoma endemic districts in Kenya have higher than national poverty rates. Both DR and ROP programming will initially have an urban focus, due to the availability of capacity of service sites. DR and ROP partners are addressing how to better appraise the profile of clients but are confident the roll out to rural public sites will disproportionally serve the poor.

The trachoma initiative disaggregated by sex and shows that women and girls represent 71% of trachoma surgery cases.

Quality of financial management
The spend profile of £12m for FY 2015/16 was not completed as forecast. DFID paid the first instalment of £6m in April 2015 and was due to pay the second instalment of £6m in October 2015. However, the Trust was not in a position to draw down this October grant payment because they still have funds left from the April 2015 grant drawdown. Grant payments for the period April to October 2015 were lower than expected due to the fact that most of the programmes reached the end of their first year of implementation and reported to the Trust during this period. This reporting highlighted that there were some underspends and the Trust therefore needed to renegotiate payment schedules with their implementing partners.

The Trust has subsequently commissioned a review of grant spending profile now they have more information about when and how much implementing partners will be spending over the next four years. They have requested that the October 2015 grant payment of £6m be rescheduled to FYs 17/18 & 18/19 with the scheduled payments of £12.7m in FY 16/17 to remain. The Trust must continue to discuss the grant payment rescheduling with DFID and must ensure in future that any concerns over expenditure and potential delays in drawing down funds are flagged to DFID at the earliest opportunity (notification that the October 2015 payment could not be spent by partners during the remainder of the financial year was only sent to DFID in mid-October).

The format of reporting to support each payment request is detailed in the Memorandum of Understanding. This requires the Trust to supply a certified letter with any payment request setting out the detailed actual expenditure to date (committed and spent), a forecast of funds to be disbursed or committed during the next 6 months, a statement supporting new funding raised to which DFID will be viewed as eligible to match and an explanation of the disparity between the forecast commitments and disbursements and funding already held by the Trust.

This reporting requirement was made for the April 2015 payment.

In addition the latest Annual Report will be published in early 2016 once it has been countersigned by the auditors and provides detailed financial reports, including confirmation that there has been no evidence of any financial risk or fraud. The Annual Report also includes the Trust’s audited Financial Statements and Accounts which received an unqualified audit.

Date of last narrative financial report	November 2015
Date of last audited annual statement	November 2015

## E: RISK

Overall risk rating: Medium

Overview of programme risk: This is a complex multi-initiative, multi-country programme, with several implementing partners and multiple sub-contractors.

The Trust has an overall Risk Register which the Executive Team reviews and updates monthly.
The risk register is also reviewed by the Audit Committee at its meetings and the top three risks are reviewed annually by the Trustee Board and included in the verbal report about the activities of the Audit Committee. In addition, the management team ensures that robust internal controls exist and are complied with to mitigate risks to which the Trust is exposed in administering DFID’s contribution.

Each initiative has its own risk register maintained by the implementing partner. The six monthly reports include a section on risk where the implementing partners are required to report on risk and identify new risks which are then assessed, updated and reviewed.

The Trust has Policies on Anti-Fraud and Corruption and the Bribery Act which are issued to all staff and are included in the staff handbook. All grantees are required to have their own policies on this which are included in their grant agreements. For example, the Trust have confirmed that Sightsavers have their own anti-fraud and corruption policy demonstrating that they require their own delivery partners to have their own policies and procedures.

The Trust has conducted a Due Diligence assessment on all grantees. The Trust’s grant contracts require the grantee be responsible for all sub-grantees.

The DFID Business Case and Due Diligence assessment identified a number of high level risk and mitigation actions. Of the initial risks identified four have been completed. The main outstanding risks and mitigation measures across the programme have been incorporated into the Risk Matrix which is reviewed and updated at programme meetings between the Trust and DFID. Some of the key risks from the risk matrix are highlighted in the table below.

Risks: changes and additional mitigation measures

Risk and nature of the risk	Prob/ / Impact	Change over past year	Existing and new mitigation procedures
Insufficient governance by delivery partner impacts on the Trust’s work	Low/high	No changes over the past year	Carry out due diligence on all prospective delivery partners to manage and mitigate risk. Trustees of major delivery partners to be invited to Trust Board meetings on occasions. Monitoring reports and regular meetings with partners will ensure that Trust remain vigilant on the governance of partners.
Fraudulent use of funds overseas by delivery partners	Low/medium	No changes over the past year	Trust enters into grant agreements with all delivery partners. Regular monitoring and robust reporting required from delivery partners. Good relationship management of all grantees by Trust programme team. The right to audit delivery partners is built into the Trust grant terms and conditions. / The Trust will remain vigilant and take appropriate action if fraud is suspected.
Programme fails to deliver expected outcomes or poor quality programmes.	Low/high	Close monitoring and a visit to India by the Trust in October 2015 highlighted a shift in focus for PHFI towards more advocacy to achieve long-term targets	Clear monitoring framework and reporting procedures in place. Trust carries out due diligence on all prospective delivery partners. All programmes will be kept under review and redesigned if necessary.
Programme fails to develop and implement effective exit strategy.	Low/medium	No changes over the past year	Exit strategy to be built in to all programmes from the outset. On-going monitoring and evaluation to be carried out during lifetime of projects.
Programmes underspend or overspend against budget, or work takes significantly longer than expected.	Low/medium	Some aspects of some initiatives have progressed slower than anticipated due to factors beyond their control (drug production) and new data affecting coverage rates required	Internal monitoring and budgetary control. Rolling forecasts of expenditure completed. Very thorough budgets have been prepared and allocated across the programmes. / Where work takes longer than expected, e.g. due to climate, political changes or other issues of context, the Trust will work with delivery partners to review the work plans and will consider options, including extending the length of the programmes.
Delivery partner lacks capacity to deliver programme or over-stretches themselves with other work.	Low/high	No changes over the past year	Trust works closely with delivery partners and carries out thorough due diligence before a grant agreement is signed. If a delivery partner takes on new work, their continued capacity to deliver the Trust’s work will be investigated.
Delivery partner has financial difficulties and requests funding outside the grant agreement to continue operating.	Low/medium	No changes over the past year	Initial due diligence procedures and close working arrangements with and monitoring of delivery partners will ensure that the Trust works with sustainable organisations. If necessary special conditions will be inserted into grant agreements at the outset.
Finance controls fail to pick up internal or external fraud.	Low/high	No changes over the past year	Finance induction for all staff. Dual signatory for all payments. All cheques, cash, credit cards and card readers locked in safe when not in use. Executive team to see management accounts. CEO signs off monthly statement of online banking and the bank reconciliation. Close monitoring and scrutiny by Audit Committee. Audit recommendation that all journal entries are countersigned has been implemented from August 2014.
Funds are used contrary to donor’s wishes and/or objectives.	Low/High	No changes over the past year	Trust has MoUs and agreed contracts with all funders and a tracking and reporting system for all programme spend. Financial control spreadsheet has been created to track and log all programme expenditure.
Staff prove unsuitable for role.	Low/High	No changes over the past year	Stringent recruitment process; six monthly probation period for all staff; regular feedback and 1-2-1s between staff and line managers; HR manual contains detailed capability and disciplinary policy and procedures.
NEW RISKS arise in 2015
Erratic availability of drugs	Low/High		Continue the high level advocacy engagement with Pfizer

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
As detailed above, progress against most milestones has been slower than anticipated. Reports from grantees are delivered in a timely manner to the Trust and to the expected standard of performance and financial reporting.

Performance of partnership (s)
Feedback from central and country level implementing partners, and reports from national symposia, taskforces and launches, suggest that excellent partnerships have been established for each initiatives and within each country. The Trust’s performance is “adding value” at global policy and programme level – as presented under output 5.

Asset monitoring and control
Not applicable.

G: CONDITIONALITY

Update on partnership principles (if relevant): Not applicable.

H: MONITORING & EVALUATION

Evidence and evaluation

Programme monitoring. SEQAS undertook an assessment of the M&E strategy in 2014 and concluded that the current document contains much useful information but would benefit from a clearer and systematic structure to aid clarity about purpose and enable a more systematic and integrated approach to M&E. The M&E strategy was updated in May 2015 and has a robust programme level Theory of Change, underpinned by summary theories for each initiative. Updates on its progress to date and recommendations going forward are detailed under Output 5.

Evaluation plans are well under way. The SAB have oversight of the evaluations. For each of the Trust’s four main avoidable blindness initiatives, the evaluators will produce a mid-term report and a final report.

The Consortium’s evaluation has already been planned and commissioned. The mid-term report will look at the structure of the Consortium and how it is building capacity of eye healthcare. Trachoma and DFID SAFE – SS are leading on developing the ToRs and are liaising with implementing partners to get their input. As the SAFE strategy is well established, the mid-term report will include details on progress made towards elimination and learning generated around data collection. DR and ROP in India – the PHFI is currently working on developing TORs for evaluations of each of these initiatives. Conducting a mid-term evaluation is planned for October 2016. PHFI may commission one joint evaluation or they may commission two separate evaluations depending on which approach seems the most suitable.

DFID Monitoring progress throughout the review period
DFID officials have regular progress meetings with the Trust to discuss progress on the logframe and on financial management issues. In addition, DFID has representation on the SAB which meets twice a year, around March and September.

Annual review process
The desk-based review was carried out by a DFID Senior Health Adviser with inputs from the DFID Programme Manager and Deputy Programme Manager for the Commonwealth, relevant DFID Country Offices, the Trust and some grantees, including the ICTC and WHO.