Business Case and Intervention Summary

Intervention Summary
## Title: Queen Elizabeth Diamond Jubilee Trust contribution

What support will the UK provide?
As committed by the Prime Minister at the Commonwealth Heads of Government Meeting (CHOGM) in 2011, the UK will provide up to £50m in “matched” funding over the lifetime of the Queen Elizabeth Diamond Jubilee Trust, i.e. 2013/14 to 2018/19. The funding we will match will come from a variety of governmental, non-governmental and corporate sources from across the Commonwealth, including the UK, offering a unique opportunity for a diverse, collaborative partnership with global reach.

Why is UK support required?
The Trust has been established to provide a lasting tribute to the Queen and enrich the lives of people in the Commonwealth. The majority of Commonwealth countries are still in need of aid and technical assistance and there is a clear unmet need across a range of health and human development issues. The Trust will primarily focus on avoidable blindness and youth programmes. As set out below, Department for International Development (DFID) support is intended to be channelled through the programmes to tackle avoidable blindness – a significant cause of disability worldwide. Visual impairments affect 285m people worldwide, of whom 39m are blind. There is strong coherence with the Millennium Development Goal (MDG) and emerging post-2015 agenda, and with a range of other DFID work streams. / The Trust is finalising its governance and organisational structures, its strategic direction, its programme goals and its funding. The Trust expects to complete fundraising and start implementing programmes in the last quarter of 2013 and DFID’s disbursements therefore need to start at this point.

What are the expected results?
The trachoma interventions alone could protect more than 18 million people from blinding trachoma through antibiotic treatment, and prevent blindness in a further 405,000 through surgery. The Trust’s interventions are expected to bring about a measurable and sustainable reduction in avoidable blindness (estimated reduction of at least 85,000 disability adjusted life years (DALYs)), reducing disability and enabling wider economic and social benefits. The Trust’s activities as a whole will be pan-Commonwealth, but DFID’s funding will be used in ODA-eligible countries to improve the lives and well-being of poor people, with the potential “pro-poor” impact clearest for trachoma (trachoma prevalence is highest in poor communities and in the most disadvantaged households).[1] There is a real opportunity to eliminate, over the course of the Trust’s lifetime, blinding trachoma in a number of countries, directly contributing to the global goal of eliminating avoidable blindness by 2020. There are also potential co-benefits in the fields of water and sanitation, neglected tropical diseases and sustainable partnerships with governments, non-governmental organisations and the private sector.
[1] Frick KD, Hanson CL, Jacobson GA (2003) Global burden of trachoma and economics of the disease. Am J Trop Med Hyg 69: 1–10.

Business Case

Strategic Case

A. Context and need for a DFID intervention / The Diamond Jubilee Trust was announced at the Commonwealth Heads of Government Meeting in Perth, Australia in 2011 and launched in February 2012 as a way for citizens and Governments across the Commonwealth to create a lasting tribute to the Queen. The aim is to deliver “iconic” projects over a five year span. The Trust is open to donations from individuals, groups, organisations and companies, both inside and outside the Commonwealth. / The Prime Minister announced, also at CHOGM 2011, that the Government would make a multi-million pound contribution to the Trust. DFID is the lead Government department and will make the UK’s contribution as set out in a letter from Andrew Mitchell to Sir John Major, the Chair of the Trust, in December 2011. This is in the form of ‘match funding’ – intending to attract other funding for the Trust’s development work from across the Commonwealth. It is highly likely that the Trust will hit, or exceed, the £50m mark by the last quarter of 2013, through government contributions, corporate donations and partnerships, at which point it intends to stop active fundraising and focus on implementation. / Following the Trust’s establishment, a period of consultation, expert input and reflection on the challenges faced in today’s Commonwealth resulted in a focus on avoidable blindness and youth. Whilst youth development is an important part of DFID’s work and young people are critical in shaping and achieving the development agenda, insufficient detail about the Trust’s plans for their youth programmes was available to commit DFID funding to this part of the trust’s work. This case does analyse the option of funding this work in the appraisal case below, to provide a value for money comparison, but DFID funding will be used only for the avoidable blindness work. The avoidable blindness programmes are informed by the WHO-led VISION 2020 strategy and goals[2], and will focus on trachoma, diabetic retinopathy, retinopathy of prematurity and cross cutting programmes. These areas have been chosen because they: / are (trachoma), or are becoming (DR and ROP), leading causes of blindness in the Commonwealth, according to the best available data (NB “Commonwealth” data as such is not currently available: more complete country-level data, allowing aggregation to Commonwealth level, on causes of blindness will become available from 2014); / together provide a portfolio of interventions benefitting a large number of Commonwealth countries, across all regions of the Commonwealth, which a focus solely on neglected tropical diseases (for example) would not be able to achieve; / offer opportunities to make substantial progress (whether from a relatively low base, or towards the elimination end of the “scale”) over the five year lifetime of the Trust and for the Trust to exit in a way which ensures sustainability (e.g. in contrast to cataract and glaucoma, which although globally more prevalent, cannot be prevented) / Trachoma / Trachoma is the leading cause of avoidable blindness in the world, responsible for 3% of the world’s blindness and considerable disability. It is hyper-endemic in 53 countries[3] and is a significant public health risk in some of the poorest countries in the world. Over 110 million people live in areas where trachoma is confirmed to be endemic[4]. In these areas up to 80 million people have active trachoma, more than 40 million people are in urgent need of treatment, and 4.6 million suffer from blinding and painful trichiasis (the advanced stage of the disease)[5]. It is estimated that 1 million are visually impaired and 0.8 million people blind[6] as a result of trachoma. 80% of the burden is concentrated in 13 African countries plus Pakistan. / A comprehensive, WHO-endorsed package of interventions termed SAFE (Surgery, Antibiotics, Facial cleanliness, Environmental improvements) has been designed to address the different aspects of trachoma for long term, sustainable elimination. In 1998, the World Health Assembly adopted a resolution to eliminate blinding trachoma as a public health problem by 2020[7] that called on Member States to implement the SAFE strategy. In the same year, the Alliance for Global Elimination of Trachoma by 2020 (GET 2020) was formed by the World Health Organisation (WHO). / In January 2012, Ministers announced increased UK assistance for the control of neglected tropical diseases (NTDs). This included a new programme of £50 million to support the control of trachoma, which, despite the availability of antibiotics to treat it and prevent blinding, has received less donor attention than other neglected tropical diseases. In July 2012 DFID approved up to £10.6 million to complete the global mapping of the risk and burden of trachoma,[8] to be completed by March 2015, and the second component of the UK’s support has been recently approved [ref 4049883[9]]: supporting the implementation of activities to prevent, control and treat trachoma in up to 6 high-burden countries in Sub-Saharan Africa (this is referred to as the “DFID SAFE trachoma programme” in this document). This additional proposed investment is explicitly designed to carefully complement that effort, with considerable efforts having been made by both the responsible teams, the Trust and major stakeholders to ensure alignment – for example agreeing the countries/regions where each will operate. More detail on how this will be managed as the programmes move towards implementation is provided below in the Management case. / Diabetic retinopathy (DR) / DR is a major micro vascular complication of diabetes and its prevalence is therefore intimately linked to the global rise in the incidence of diabetes: 347 million people worldwide are now estimated to have diabetes[10]. While accurate figures are difficult to obtain, survey data suggest that 10% of diabetics in middle/low income countries have sight threatening diabetic retinopathy. In 2004, WHO estimated that DR was responsible for 3.9% (1.8 million) of the then 45 million cases of blindness worldwide.[11] This proportion will inevitably grow. A recent review estimates the number of people with DR could grow from 126.6 million in 2010 to 191.0 million by 2030, that DR represents the leading cause of blindness in working-age populations and that DR has been neglected in health-care research and planning in many low-income countries.[12]There is currently no global strategy for tackling DR, and although good control of diabetes and hypertension significantly reduces the risk for DR and there is evidence of the effectiveness of routine DR screening and early treatment, very little is known about the best ways to combat DR in low income settings, and there is no clear research agenda to fill this gap. / There is no doubt that diabetes is a significant concern in Commonwealth countries. According to the International Diabetes Federation[13], in India alone, in 2011, there were estimated to be 62.4 million people with type 2 diabetes, projected to increase to 100 million by 2030. In India, there is growing evidence that diabetes is not confined to the urban wealthy but is increasingly affecting the urban poor[14] and rural communities[15]. DR is also recognised as a growing problem and therefore a priority for VISION 2020 in other parts of South-East Asia e.g. Sri Lanka and Bangladesh. The International Association for Preventable Blindness (IAPB) have just established a global working group on DR. The Trust presented its DR plans to this group in September 2013 and is encouraging collaboration to ensure a clearer set of agreed strategies for DR, including the prevention of diabetes (with input from the International Diabetes Federation). / Retinopathy of prematurity / ROP is a major cause of blindness. It consists of an initial phase of vessel growth retardation followed by a second phase of vessel proliferation. It is caused when preterm infants are given 100% oxygen. Having declined dramatically in the West following awareness of the problem, it has become clear that ROP is on the rise. ROP is a major cause of blindness in children in middle income countries in Latin America, Eastern Europe and the emerging economies of SE Asia (e.g. Vietnam), China and India and is therefore an important part of the VISION 2020 strategy for tackling avoidable blindness, particularly childhood blindness. There are a number of underlying reasons why this is the case: pre-term neonates are increasingly likely to survive and countries are expanding neonatal care, but there is limited knowledge about ROP, insufficient monitoring of oxygen saturation, and lack of ROP screening guidelines. WHO estimate that there are 15 million preterm births a year, and the / expansion of neonatal intensive care will lead to increased survival of preterm babies, putting greater numbers at risk of ROP. The first key milestone for the Trust’s ROP programme will be an expert meeting, in October 2013, bringing together key players from government, the private sector and NGOs to agree a five year plan (for India in the first instance). / Cross cutting programmes / The Trust aims to ensure sustainability and coherence and that the overall package is more than the sum of its parts. It has therefore recognised not only that its work in the areas outlined above needs to be sustainable and contribute to behaviour change and health systems strengthening, but that there should be training, research and technology interventions that feed into the priority disease areas outlined above, whilst also working more broadly to advance the field of avoidable blindness. Initiatives the Trust is examining include: / Fellowship training: short and long term opportunities for ophthalmologists from across the Commonwealth, using a mixture of centres in high and lower income countries, to exchange expertise and develop leaders for avoidable blindness and eye care. / Eye Care Toolbox: multi-functional, smartphone based tool to assess visual function and to perform several important examination tasks. Although of course not all telemedicine interventions are universally found to be effective or cost effective, and challenges remain with implementation and the analysis of benefits and cost effectiveness[16], telemedicine has, for example, been noted to represent the “single most promising technology in the context of rural DR care” (footnote 12).The device and its applications, costing a few hundred pounds instead of hundreds of thousands, can be provided to low income countries at a highly subsidised rate, so that it is available in every clinic. / OpenEyes: This is a collaborative, open source project initiated by Moorfields Eye Hospital to allow the rapid and continuous development of eye patient records (EPR). There may be the potential to lead to improvements in patient care and better outcomes, as well as building up a pool of clinical data that can be used for research and education. / Alignment with DFID’s priorities / Global development agenda and goals / There is good evidence that tackling avoidable blindness would accelerate progress on all the Millennium Development Goals[17]. Goal 1 (eliminate extreme poverty) is expanded upon a little here, whilst Goal 3 (gender) and Goal 7 (improving environmental sustainability) is discussed below in the social and environmental impact sections respectively. There is also good alignment with the direction of travel on the post-2015 development agenda[18], particularly boosting wealth creation. Blindness and poor vision have a tremendous economic impact on households. Up to 90% of blind individuals cannot work[19], exacerbating poverty and leading to greater financial insecurity and lower standards of living. In addition, women and children often have to forego non-wage household work, education or employment to provide caregiving to low vision and blind members of their household. The long-term economic repercussions therefore extend beyond the blind individual. In line with the goal of reducing aid dependency and supporting countries through transition[20] there is therefore an imperative to support countries’ efforts to develop sustainable national strategies. / One of the first estimates[21] of a potential productivity loss across all countries due to trachoma was $2.9 billion per year and considered only the burden caused by visual impairment. However, Frick et al. estimate the sum of annual productivity losses for sufferers and their carers at $5.3bn in 2003 prices[22], which is equivalent to $6.6bn in 2012 prices.[23] This assumed 100% productivity loss from blindness (some analyses had previously assumed 60%) and added a cost of a carer for each blind person. The paper also considered the impact when trichiasis was added and found that the annual lost productivity rises to $8 billion (approximately $9.9 billion in 2012 prices). Estimates by the International Coalition for Trachoma Control (ICTC) suggest that eliminating trachoma in Africa will boost the continent’s gross domestic product (GDP) by 0.2 to 0.4 percentage points, based on previous estimates of the annual productivity loss[24]. / DFID’s approach to disability and health / Non-communicable diseases (NCDs): / DFID’s approach to supporting health outcomes in the poorest countries aims to ensure they are resilient and equipped to address new and emerging challenges. These include emerging diseases and health problems (non-communicable diseases, mental health and a greater focus on trauma), a changing environment (demographic change, urbanisation, climate change, and food availability) and additional systems pressures (drug resistance, migration and disaster risk reduction). The three types of avoidable blindness chosen by the Trust span neglected tropical diseases and emerging challenges associated with changing economic conditions. / In all regions except Africa, NCDs are already the major cause of mortality. Even in African nations, NCDs are rising rapidly and are projected to exceed communicable, maternal, perinatal, and nutritional diseases as the most common causes of death by 2030.[25] NCDs are projected to cost more than US$ 30 trillion (about half of global GDP in 2010)[26]. Many countries will face a double burden in the coming decades as they face climbing morbidity, disability and death from NCDs while they still face preventable mortality from communicable diseases, under nutrition and maternal causes. DFID's current focus aims to support health systems strengthening, health worker capacity and access to essential medicines in order to help countries respond to all their health priorities. Increasing coverage, equity, access and quality within the health system strengthens service provision and community outreach to identify, prioritise and address all evolving health problems including NCDs. The Trust’s proposed approach to diabetic retinopathy is therefore consistent with DFID policy and offers an opportunity to expand DFID’s portfolio on NCDs. / Disability: / More than a billion people in the world live with some form of disability[27]. People with disabilities generally experience poverty more intensely, have lower levels of education, and have fewer opportunities to escape poverty than people without disabilities. Disability is cross cutting across all populations and is arguably the hardest to reach because poor communities may themselves discriminate against people with disabilities. Many face further marginalisation when their disability is compounded by other excluded characteristics, for example gender, ethnicity or age (elderly, children). / DFID has increased its focus on disability during the past year, and the PUSS is a champion[28]. The recent high level panel report asks us to ‘leave no one behind’, regardless of disability, gender, geography, ethnicity, race or any other status. This is therefore a real opportunity to strengthen and give more prominence to DFID’s existing work on disability, which includes the Sightsavers Programme Partnership arrangement[29] and civil society programmes in e.g. Rwanda and India. / Neonatal health / The UK Government has committed to save the lives of 250,000 newborns by 2015[30]. DFID sits on the WHO/UNICEF led steering group for development of Every Newborn – a global action plan to end preventable newborn deaths. Through Every Newborn and related bilateral and multilateral programming DFID is supporting countries to scale up low cost, high impact life-saving interventions for pre-term babies including resuscitation and kangaroo mother care[31]. In countries where these low cost interventions have been implemented at scale there remains a need to establish neonatal intensive care units, to provide care for the small proportion of premature babies who will not survive through low cost interventions alone. For example, through bilateral partnerships, DFID is supporting the development of neonatal intensive care units in India, which has the largest number of preterm births of any country. As set out above, the benefits of neonatal care in terms of lives saved are, however, accompanied by a rise in retinopathy of prematurity, such that there is a compelling case for ensuring that the investment in neonatal care benefits from the most up to date techniques and procedures. The trust’s activities in this area therefore complement DFID’s existing investments. / The Commonwealth / The UK Government is committed to strengthening the Commonwealth. DFID has a clear role to play: the majority of Commonwealth countries are still in need of aid and technical assistance. 14 of the 27 countries on which DFID is focusing its bilateral assistance[32] are Commonwealth members. / Health and human development have been priority areas for Commonwealth governments since 1965, when Ministers first met in Edinburgh for the inaugural Commonwealth Health Ministers Meeting (CHMM) and Commonwealth Medical Conference[33]. In line with the large burden of non-communicable diseases and high prevalence of NCD risk factors in the Commonwealth, Commonwealth Health Ministers adopted the Commonwealth Secretariat Road Map on NCDs in 2010. Advocacy from the Commonwealth is understood to have played a role in the movement towards the 2011 UN high level meeting on NCDs[34], which established NCDs as a development issue[35]. The CHMMs in 2011 and 2012 also both had an NCD focus. / The proposed support to the Trust is therefore the newest part of an overall strategy to strengthen DFID support to the Commonwealth. UNCD is the lead Department within DFID, working to strengthen the effectiveness and impact of the Commonwealth’s work on development[36]. / Partnerships / Trachoma control is already supported by a well-established, international, public-private partnership that includes the WHO, major corporations (e.g. £20m funding from Standard Chartered), NGOs and academic institutions. The Trust’s existence and interest in other areas of blindness provides an opportunity for harnessing a similar coalition on this wider, forward-looking agenda, and the Trust’s engagement with the overarching Vision 2020 agenda and movement will enable it to embed new, developing networks and partnerships in that overarching structure. / The Trust has, in avoidable blindness, identified a major challenge to economic prosperity and a suite of focus areas that bridge the wide range of issues experienced by the Commonwealth. It is offering a unique mix of established intervention, innovation and development plus political will. If we fail to act, we will slow down economic development, and sustain an unnecessarily high burden of avoidable blindness. Failure to invest would miss the once in a lifetime opportunity provided by the Trust’s existence to show leadership and close the funding gap for trachoma to enable the 2020 elimination goal to be reached. It would also be inconsistent with DFID’s wider strategy on the Commonwealth, disability and health.
B. Impact and Outcome that we expect to achieve / The main impact for the avoidable blindness programming is expected to be a significant reduction in avoidable blindness across the Commonwealth. Since DFID funding will be restricted to ODA-eligible countries, the impact expected for this intervention is therefore a significant reduction in avoidable blindness across ODA-eligible countries in the Commonwealth where the trust is operational. At the time of writing, these are anticipated to be Kenya, Malawi, Uganda, Mozambique, Nigeria, Tanzania, Zambia, Fiji, Kiribati, Solomon Islands and Vanuatu (trachoma); India, Pakistan, Bangladesh and Sri Lanka as well as selected countries in the Caribbean and Pacific (DR; India also ROP). The SAFE programme is also likely to be implemented at the same time in Tanzania and Zambia (and a selected number of non-Commonwealth African countries), and the Trust and its partners are clear that they have plans in place to ensure this results in cost efficiency, and greater impact, rather than duplication. / The Trust is pursuing primary and secondary prevention as well as treatment interventions according to the nature of the problem (e.g. the SAFE approach encompasses the full spectrum from environmental interventions for primary prevention to surgery for treatment; whilst e.g. diabetic retinopathy is likely to focus largely on secondary prevention i.e. improved screening). The reduction in disability, illness and lost livelihoods from the prevention and treatment of preventable blindness is expected to lead to improved economic prospects and contribute to a number of other development goals. By supporting this intervention DFID will be contributing to progress against MDG 1 – elimination of extreme poverty as economic prosperity and growth will increase as incidences of avoidable blindness decrease. Given the challenges in attribution and monitoring, these are not explicit goals of DFID’s funding for the Trust. There will also be an impact on MDGs 3 (gender) and 7 (improving environmental sustainability). The prospects for women will improve as the incidence of trachoma falls as women are more likely to be affected by this, as set out in the social development appraisal below. The aim is therefore to ensure gender-disaggregated data wherever possible. The introduction of the SAFE initiative will contribute to improved environmental conditions. / The main outcome for the trachoma programme will be a significant reduction in the incidence of trachoma: DFID currently intends to focus its monitoring of the effectiveness of the implementation of the programme by measuring the number of trachoma endemic Commonwealth countries in Africa reaching elimination targets by achieving their Ultimate Intervention Goals. This outcome will be reviewed to ensure it is an effective indicator of the outcomes achieved across the Trust’s programmes, along with the potential to monitor a DR or ROP-related outcome in parallel. / The overarching goal for the Trust is to enrich the lives and opportunities of people in the Commonwealth. By identifying areas which are neither wholly new territory, nor overcrowded, the Trust has the opportunity to work with established and developing partnerships to maximise the impact from their funding. DFID is expecting to be providing around half of the total funds available to the Trust, and the majority of the ODA-specific funding. Crudely speaking, therefore, more than half of the results achieved by the Trust in ODA-eligible countries through the implementation of the supported initiatives would be attributable to DFID funding. / The Trust is still developing its overarching logical framework and theory of change (see also Appraisal section H, below). A log-frame is attached for the monitoring of the first phase of this work which will be reviewed with each annual review to ensure accurate tracking of results. The mapping activities within the DR and RoP programmes in particular in the first phase of the work will allow efficient allocation of resources to the people and areas in the Commonwealth most in need. The Trust will fund research to evaluate the most effective and sustainable approaches to DR, and bring together key players to identify an effective national strategy for RoP. / Based on assumptions set out below in the appraisal case, it is possible to project that the trachoma interventions could protect more than 18 million people from blinding trachoma through antibiotic treatment, and prevent blindness in a further 405,000 through surgery[37]. Elimination is expected in at least two countries (which countries will become clearer on the basis of further evidence expected imminently from the ICTC). The outcomes for the other areas of work will be established by the end of the first year of the Trust’s activities.
[2] http://www.who.int/mediacentre/factsheets/fs213/en/
[3] Sustaining the drive to overcome the global impact of neglected tropical diseases: second WHO report on neglected tropical diseases, WHO 2013 available at http://www.who.int/neglected_diseases/2012report/en/index.html
[4] Global Atlas of Trachoma, http://www.trachomaatlas.org/
[5] WHO 2010, “Working to overcome the global impact of neglected tropical diseases”, WHO report on neglected tropical diseases, available at http://www.who.int/neglected_diseases/en/ . Trichiasis - the eyelashes turn inward and scrape the cornea. People face the risk of visual impairment or blindness unless treated with antibiotics and a simple surgical procedure.
[6] WHO GET 2020 Alliance. Report of the 2nd scientific meeting on trachoma. Geneva, 25-27 August, 2003 and Burton et al., 2009
[7] Available at http://www.who.int/blindness/causes/WHA51.11/en/index.html, WHA51.11 Global elimination of blinding trachoma
[8] QUEST documents: Business case 3544576; Logframe 3544567.
[9] A more comprehensive analysis of the specific challenges and context of trachoma can therefore be found in that case, rather than being duplicated here.
[10] Danaei, G. et al. (2011) National, regional, and global trends in fasting plasma glucose and diabetes prevalence since 1980: systematic analysis of health examination surveys and epidemiological studies with 370 country-years and 2·7 million participants. Lancet, 378(9785):31-40. doi: 10.1016/S0140-6736(11)60679-X.
[11] Resnikoff S et al. Global magnitude of visual impairment caused by uncorrected refractive errors in 2004. Bull World Health Organ 2008; 86: 63–70.
[12] Zheng Y et al, The worldwide epidemic of diabetic retinopathy. Indian J Ophthalmol. 2012 Sep-Oct; 60(5): 428–431. doi: 10.4103/0301-4738.100542
[13] http://www.idf.org/diabetesatlas/5e/the-global-burden
[14] Deepa, M. et al (2011) Convergence of prevalence rates of diabetes and cardiometabolic risk factors in middle and low income groups in urban India: 10-year follow-up of the Chennai Urban Population Study. Journal of Diabetes Science and Technology, 5, pp. 918 Ind
[15] Chow CK, Raju PK, Raju R, et al. The prevalence and management of diabetes in rural India. Diabetes Care. Jul 2006;29(7):1717-1718. Sridhar, G.R. et al (2010). Time Trends in the Prevalence of Diabetes Mellitus : Ten Year Analysis from Southern India (1994-2004) on 19,072 Subjects with Diabetes. Journal of the Association of Physicians of India, 58, 290-4
[16] Ekeland AG, Bowes A, Flottorp S. Effectiveness of telemedicine: a systematic review of reviews. Int J Med Inform. 2010 Nov;79(11):736-71.
[17] Vision 2020: the Right to Sight. Global Initiative for the elimination of avoidable blindness. Action Plan 2006-2011
[18] A NEW GLOBAL PARTNERSHIP: ERADICATE POVERTY AND TRANSFORM ECONOMIES THROUGH SUSTAINABLE DEVELOPMENT The Report of the High-Level Panel of Eminent Persons on the Post-2015 Development Agenda. 2013 http://www.un.org/sg/management/beyond2015.shtml
[19] http://www.uniteforsight.org/community-eye-health-course/module1
[20] https://www.gov.uk/government/speeches/justine-greening-development-in-transition
[21] 41Frick KD, Basilion EV, Hanson CL, Colchero MA (2003). Estimating the burden and economic impact of trachomatous visual loss. Ophthalmic Epidemiol 10: 121–132.
[22] Frick KD, Basilion EV, Hanson CL, Colchero MA (2003) Estimating the burden and economic impact of trachomatous visual loss. Ophthalmic Epidemiol 10: 121–132. Frick KD, Hanson CL, Jacobson GA (2003) Global burden of trachoma and economics of the disease. Am J Trop Med Hyg 69: 1–10.
[23] Adjusted for inflation using www.usinflationcalcutor.com accessed 02.04.12
[24] “The end insight: 2020 INSight”, International Coalition for Trachoma Control 2011 – see footnote 47.
[25] Global status report on non-communicable diseases 2010, WHO. This discounts the effects of age on mortality. http://www.who.int/nmh/publications/ncd_report2010/en/
[26] Bloom, D.E., et al (2011).The Global Economic Burden of Noncommunicable Diseases. Geneva: World Economic Forum. See http://www.weforum.org/EconomicsOfNCD
[27] WHO/WB World Report on Disability, 2011
[28] http://dfidinsight/other/departments/policyresearchdirectorate/developmentpolicycommittee/pub_035603
[29] http://www.sightsavers.org/our_work/how_we_work/partnership/18685.html
[30] DFID (2010) UK Aid: Changing lives, delivering results
[31] DFID 2010. Choices for women: planned pregnancies, safe births and healthy newborns
[32] UK aid: Changing lives, delivering results 2011
[33] http://www.commonwealthhealth.org/health-in-the-commonwealth/history-of-commonwealth-health-ministers-meetings/
[34] http://www.thecommonwealth.org/news/190698/163083/240420/210911ncds.htm
[35] Political Declaration of the High-level Meeting of the General Assembly on the Prevention and Control of Non-communicable Diseases. A/66/L.1
[36] UNCD’s 2011-2015 Operational Plan
[37] NB these projections are based on the economic appraisal, and will depend on the final selection of countries and appropriate mix of interventions for those countries.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / QEDJT propose a suite of interventions centring around: eliminating blinding trachoma; addressing diabetic retinopathy; addressing the retinopathy of prematurity; Fellowships, research and use of technology against preventable blindness; and young leaders. The Trust will spend up to £105million across these themes. DFID have proposed providing up to £50million towards these objectives (the £50 million figure derives from a pledge made by the Prime Minister). / DFID can approach the proposed package of interventions in one of three ways: by rejecting the intervention package altogether, by funding the entire (ODA-compliant) package with or without weighting our support to one section or another; and thirdly by restricting our funding support to specific aspects of the Trust’s work to ensure focus on the elements with the most positive benefit-cost ratio and best cost effectiveness. / Appraisal raises technical and conceptual difficulties. Some of the areas the trust propose to support are still poorly understood (and the proposed activities will add to a knowledge base from which to tackle them), and the breadth of different interventions proposed means that each intervention needs to have a costs and benefit analysis, and DFID support can be cut across the different interventions in a number of ways depending on the findings. There may also be a case to be made for simply providing the funding to the QEDJT and allowing it to be freely allocated across interventions, depending on the findings of the cost-benefit analysis, and the additional costs imposed by making cumbersome restrictions on funding. / Counterfactual: Reject the approach proposed by QEDJT and undertake no additional work on preventable blindness or youth leadership. Use funds for an unrelated alternative purpose. / DFID has programmes on blindness already, including a new £40million trachoma programme. The counterfactual is therefore to make an impact on preventable blindness under existing programmes and to achieve poverty reduction and development outcomes through other activities. This means: / DFID’s interventions on trachoma will provide roughly 22 million people with antibiotics, and around 455,000 people with surgical procedures to address trachoma[38]. / However, this leaves an estimated gap of 83% in the funding for eliminating blinding trachoma, and there is very little existing support to preventable blindness via either diabetes or the retinopathy of prematurity. So the counterfactual scenario involves unmet needs for support on preventable blindness in the order of 83% of the WHO-determined requirements[39]. Of the 83% funding gap for trachoma, a proportion would be filled by other development partners, such as USAID[40]. The proposed support from DFID would provide 12% (Option 2) and 16% (Option 3) of the remaining funding gap respectively (notwithstanding USAID and other donor funding). / The money would then be reallocated to other DFID priorities. Assuming it would be used for a single health programme, using the range of cost per DALY averted taken from the Quality Assurance Unit (QAU) Annual Report for 2012/13, the counterfactual is an intervention ranging between £171 per DALY averted and £53 per DALY averted. / If we are to support the Trust, therefore, the returns to the intervention must be higher than those of feasible alternatives (as proxied by recent QA’d healthcare projects), or there must be a compelling argument for filling the gap that would exist without intervention, despite the return not reaching this level. / Provide freely-allocable funding across the ODA-compliant activities of the QEDJT. / This option is the least management-intensive for both DFID and the QEDJT. It provides a lump sum for distribution across the various interventions proposed, subject to ODA compliance. This approach will be most cost effective when the gain from focusing on specific elements of the trust’s strategy are less than the effectiveness lost and cost due to the extra administrative burden. Providing support under this option would require that: / Either the returns / net present value of the various interventions are very similar, or the differences are less than the cost of imposing restrictions on funding; and / The returns to the intervention are higher than those of the counterfactual or there is a compelling case to make that intervention is justified for other reasons – such as a lack of credible alternative funding sources. / The costs and benefits associated with this option are examined below. They will be contrasted with both the counterfactual and Option 3, below. / Provide the same value of support (£50m), but restrict funding to a sub-set of activities to maximise the developmental impact and value for money achieved by DFID’s portion of the trust’s spending. / This approach seeks to essentially maximise the net present value or benefit to cost ratio by focusing funding on the highest return segments of the QEDJT programme. It allows greater control of risk, though at the cost of higher information requirements and rigidity of funding arrangements. It makes most sense if: / The returns to the different elements of the intervention are significantly different, and it’s relatively cheap and easy to ring-fence funding; and / There are no reasons to believe that there are significantly diminishing returns to the higher return interventions. / These issues will be addressed in the section on costs and benefits. Note that the appraisal case assumes that all of the funding provided by DFID will be ring-fenced to ODA-eligible activities. This is a reasonable assumption, given the assurances given and measures taken by QEDJT to ensure that this is the case (see section G of the Financial Case).
B. Assessing the strength of the evidence base for each feasible option including delivery routes / In the table below the quality of evidence for each option is rated as either Very Strong, Strong, Medium, Limited (or No Evidence) / Option Evidence rating / 1 Strong / 2 medium / 3 medium / Evidence on the counterfactual (option 1) is medium/strong. – based on quality of Quality Assured Business Cases, knowledge of other DFID funding, and knowledge of other donor interventions (weak link). / Evidence for Options 2 and 3 Medium. We have fairly strong evidence on trachoma; improving, but still patchy evidence on DR and ROP, and currently limited evidence on the fellowship. / For trachoma evidence is fairly strong on all aspects of intervention. For ROP and DR, evidence is strongest on disease burden and costs; weakest on impact and benefits of interventions.
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / The assessment of local capacity would be broadly the same for each option, since the tackling of avoidable blindness requires capacity at national and local levels of the health system. The Trust will not directly implement programmes itself, but rather it will contract delivery partners to deliver programs and services. The Trust is responsible for the allocation of funds to the delivery partners. It will select a limited number of partners from across the Commonwealth to work with under each theme. Capacity to implement avoidable blindness programmes is very variable across the countries where the Trust will work. The overall strategy of the Trust, in line with agreed global strategy for trachoma and best practice for health systems strengthening[41] more generally, is to support national plans. / On DR, globally, the backlog of diabetes has far outstripped the capacity and resources to implement DR eye care. Zheng’s analysis points out that although many low- and middle-income countries (e.g. India and China) have begun to tackle the leading causes of remedial blindness, that is, cataract, the need for DR eye care remains largely unaddressed. Whereas cataracts are treatable with a one-off surgical intervention, DR is often not apparent until it is almost too late (therefore demonstrating the requirement for regular screening programmes) and also requires educational and wider behavioural interventions for successful treatment[42]. The fundamental problem is lack of access to high-quality ophthalmologists, health care resources and facilities. There is no simple solution to build capacity.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / All three intervention options are unlikely to have significant negative impacts on the climate or environment. Opportunities are limited but some are discussed below. / Options 2 and 3 involve direct contributions to the Trust. A draft Partnership and Grant Award Strategy of the Trust shared with DFID recognises the need to embed and spread good environmental practice and look for opportunities for environmental improvement or climate change mitigation and adaptation. Where applicable, monitoring mechanisms to capture this (e.g. within the Trust’s logic model) should be established and capacity built on ensuring these strategy safeguards are implemented. Option 3 may provide more scope to do this for the specific focus areas supported by DFID. / The main link between the Trust’s areas of work and environmental considerations is through the trachoma element. The Environmental component of SAFE aims to reduce transmission of C. trachomatis by promoting better personal and environmental hygiene ( such as construction and use of latrines or other methods of safe disposal of faeces to control trachoma spreading flies and provision of accessible water to allow facial washing). Trachoma is often concentrated in poor areas with limited access to clean water and latrines. Addressing facial cleanliness and environmental improvement activities, while indirect, are important given they / a) depend on water and sanitation services that are impacted by climate variability or condition changes / b) make a contribution to improved environmental conditions. / The actual provision of water and improved sanitation will be carried out by other ministries, partners and stakeholders. The programme approach to environmental change primarily involves advocacy efforts and linkages with WASH (water, sanitation and hygiene) partners as well as education ministries. DFID is increasing its support to WASH programmes through a number of channels, including an expansion of current bilateral programmes. This is in line with efforts to meet MDG 7. Most of these countries are trachoma endemic. / Stopping open defecation and reducing fly breeding is considered an important preventive strategy and part of the global drive for community led total sanitation. Ending open defecation is also an efficient barrier to trachoma transmission.[43] The evidence on improved water supply to control trachoma in endemic settings is mixed, but the plausibility of impact is strong and warrants further research. This is particularly the case in terms of increasing access to water for non-drinking purposes as increasing the quantity of water available for hygiene and/or sanitation would reduce fly numbers by reducing available breeding sites. There is also some evidence that hygiene promotion is effective in preventing active trachoma in endemic settings but sustainable changes in hygiene behaviours may be difficult to achieve. / Ensuring an adequate assessment and risk management strategy is in place by the Trust grant implementing partners will be important. Positive contributions and areas for improvement should also be captured in the evaluations of impact and monitoring via the logical framework[44]. / Activities planned for DR and ROP largely involve training and research and some technology transfer. Some scope exists to limit carbon and environmental footprint in terms of travel, meetings, training sessions held etc., by staff or partners in carrying out these functions. This can be included in the delivery agreements. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 C B
E. If any, what are the likely major impacts on social development? / In line with DFID’s social impact appraisal process this dimension has been considered with relation to effectiveness, impact and inclusion, empowerment and accountability and the “do no harm” principle. / The Trust’s grants procedures and collaboration with expert partners will ensure the proposed interventions are likely to be effective (appropriate, feasible) in the social, cultural and political context, informed by an understanding of likely behavioural change, of social norms, structures and societal change. The Trust will monitor and manage risks to effectiveness as part of its overall risk management strategy, outlined below. This will also avoid, address and mitigate against risks around poverty, inequality, social exclusion and human rights as well as anti-corruption considerations. Its initial work on the DR and ROP strands is designed to help it select the most effective interventions and its initial evaluation should reinforce its understanding and enable it to focus its activities and funding where it will have most impact. / The Trust’s activities as a whole will be pan-Commonwealth, but DFID’s funding will be used in ODA-eligible countries towards the goal of improving the lives and well-being of poor people, with due regard to equality and diversity. The potential impact is clearest for trachoma: trachoma prevalence is highest in poor communities and in the most disadvantaged households.[45] Functional impairment and pain from blindness and loss of vision add to the challenges of poverty and further impact economic opportunities.[46] These people are also often the most difficult to reach, because they are not employed in the formal sector, not enrolled in schools and not accessing healthcare. / Visual impairment can lead to loss of social status, stigmatisation and reclusion from society. In addition, family members who become carers may also be indirectly affected through loss of education and other personal development. School attendance may be affected due to children and grandchildren caring for parents at home, or the occurrence of the acute form of the disease in children in highly endemic settings. / Evidence shows that “trachoma disproportionately affects women and sets young girls, the next generation of women, on a path of perpetual poverty”[47]. The proven sex inequity, with women between 2 and 4 times more likely to be visually impaired from trichiasis than men, and women developing blindness at a rate of 2-3 times that of men, has implications for child nurturing and productivity[48] [49]. The consequences of trichiasis for a woman can be life-changing, reducing her marriage prospects and mobility. The factors that contribute to women suffering to a greater degree may also serve as potential barriers to women accessing health services, including services for trachoma when these are available. Surgery in particular will typically entail both actual expenditures (e.g. to cover travel costs), and opportunity costs and may require up to five days including recuperation. For women, this will mean arranging alternative cover for the domestic responsibilities that they shoulder. / The impact of DR and RoP, i.e. blindness, is impoverishing, and some studies suggest poorer people in these countries are more affected. The picture is complex: e.g. for DR there are competing effects of e.g. lifestyle, health behaviors, and health-care systems. In many low- and middle-income countries, for example, higher socioeconomic groups are more likely to consume western foods and pursue a sedentary lifestyle than their poorer counterparts; these factors may counter the beneficial effects of good diabetes care and glycemic control among the rich.With RoP, where pre-term infants are surviving, the relative lack of access to appropriately trained medical professionals for poorer individuals may increase the risk. / By working alongside national governments to inform and implement national strategies, services and political institutions will be involved from the beginning and therefore accountable to the target population. The Trust is working with a range of stakeholders to gain insights from people’s lives and behaviours and these insights (via case studies) will also be collected during their monitoring and evaluation activities.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / Of the Commonwealth countries, only Sierra Leone and Solomon Islands are currently classified as “fragile” according to the World Bank[50]. The Trust has included in its draft assessment criteria that any delivery partner intending to operate in those states should have a clear plan for how it will do so.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / Counterfactual: Reject the approach proposed by QEDJT and undertake no additional work on preventable blindness or youth leadership. Use funds for an unrelated alternative purpose. / The counterfactual assumes that the full £50 million available would be spent on a single project, partly for simplicity. This is not an unreasonable assumption, as the funding is available as a lump sum, and can be reasonably expected to be deployed to an alternative ‘flagship project’ if this one is deemed non-viable. As a guide as to what kind of returns are available, the expected returns to large projects reporting costs per DALY averted that were quality assured during 2012 are given below: / Project Value Cost Metric / Burma Three MDG Funding £80m $266 (£171) per DALY averted / Malawi Health Services Programme £110m £165 per DALY averted / DRC Humanitarian Pooled Fund £145m Not reported breakeven per DALY / Zimbabwe Sexual and Reproductive Health and HIV Prevention £57m Numerous estimates per DALY averted / Access to Health Care in DRC $214m $83 (£53) per DALY averted / Pakistan Provincial Health and Nutrition Programme £160m £69 per DALY averted / Source: Quality Assurance Unit Annual Report 2012/13 / The current intervention will be deemed unsatisfactory if 1) returns/cost effectiveness of the intervention compares very unfavourably with the above (taking into account qualitative arguments for the present intervention, and the likelihood that costs to multi-country interventions are likely to be systematically higher than country-specific interventions due to some sunk/fixed costs being replicated in a number of countries rather than just one) and 2) any decision not to fund the trust does not result in a significant unmet need that other donors are unlikely to step in to fill. An assessment of whether these conditions are met is made in Section J: Summary Value for Money Statement: the preferred option is 3, i.e. to focus DFID funding on the avoidable blindness programmes. / To complete the counterfactual, therefore, an indication of unmet need is required. Table 1, below makes an attempt at capturing this. / Table 1: Unmet Needs across Trust Priority Areas, assuming no new DFID Funding / Priority Area Unmet Need / Trachoma WHO are pursuing a programme to eliminate trachoma globally. DFID analysis, based on work by the International Coalition for Trachoma Control, suggests the overall funding gap for implementation of trachoma interventions is around £29 million per year; existing DFID programmes under consideration would reduce this by 17%. Of the remaining 83% some proportion would be provided by other DPs (including USAID). Proposed DFID support under this business case would reduce this gap by 12% or 16% depending on the option chosen, notwithstanding the support of other DPs. .[51] / Diabetic Retinopathy In the subcontinent, around 60 million people have Type 2 diabetes in India alone, including in rural areas; and around 10% of these have sight-threatening diabetic retinopathy[52]. DR is also a priority in Sri Lanka’s Vision 2020. Only 8% of Indian ophthalmologists are trained and able to treat DR. We do not know of any current interventions focused on DR. Little is known currently about the best ways to combat DR in low-income and developing settings. No clearly articulated research agenda addressing this is currently known of. / Retinopathy of Prematurity This is an avoidable cause of irreversible (and often total) blindness in children in MICs – of likely increasing (but unknown) incidence, particularly in India. A large number of neonatal care units will have no programme in this at all, as national capacity in India is limited. Improvement of neonatal care is likely to bring other benefits as well. Little is known about either the prevalence or the best ways of combatting RoP in low income and developing settings. No clearly articulated research agenda addressing this is currently known of. / Youth Leadership The youth leadership programme will focus on disadvantaged young people (for example, those affected by violence or disability or those otherwise marginalised). Without further details of the precise nature of the intervention planned, it is difficult to assess unmet need. / Therefore, the counterfactual situation is an alternative project in which cost per DALY may fit in the range expressed above (though with allowance made for differences in multi-country and single-country interventions), and unmet needs in trachoma (significant), diabetic retinopathy (likely to be moderate and of increasing size) and the retinopathy of prematurity (unknown unmet need which is likely to be increasing); and no serious or unknown unmet need in youth leadership. / Provide freely-allocable funding across the ODA-compliant activities of the QEDJT. / This option would involve funding for all of the trust’s activities, to a total of £50 million. It is assumed that the funds would be divided roughly in line with the overall split of funding the trust proposes. The table below summarises: / Trust Activity Proportion of Trust Spending Equivalent DFID contribution / Trachoma 48% £23.8m / Diabetic Retinopathy 19% £9.5m / Retinopathy of Prematurity 5% £2.4m / Cross-cutting issues for preventable blindness, including Fellowship Scheme 10% £4.8m / Youth Leadership 19% £9.5m / With the costs of the intervention set as above, the benefit of the intervention is calculated by the returns expected from each element of the intervention. This requires a slightly complicated approach of valuing the expected returns from each arm of Trust activity. / Trachoma / The appraisal of the cost and benefit of the trust’s actions on trachoma draw heavily on the DFID Business Case for Trachoma: Supporting the Implementation of SAFE. The outcomes, costs and benefits to trachoma interventions presented here are based on assumed distribution of resources based on populations at risk, DALYs in each country under consideration for intervention by the Trust, and the costs of intervention as calculated by the aforementioned Business Case. The precise costs per DALY and DALYs averted will differ from those presented below depending on the specific details of how the final selected bid for undertaking the trachoma intervention proposes to distribute resources according to local capacity and other factors that are not possible to precisely model in this appraisal. The variation may be positive (i.e. better cost per DALY and number of DALYs averted) or negative. The numbers here, however, represent the best a priori estimate of the reach and impact of the intervention given the current state of information. / Best practice in trachoma prevention and treatment as determined by the WHO involves intervention on four dimensions: Surgery (addressing immediate disability burden), Antibiotics (reducing/eliminating the existing reservoir of infection), Facial cleanliness (promoting behaviour change), and Environmental improvements (reducing transmission and eliminating the conditions that encourage the breeding of flies). These interventions constitute the ‘SAFE’ strategy for trachoma elimination. / Estimates for the benefits of the trachoma arm of the intervention assume: / That there is no duplication of effort with existing programmes (i.e. the trust’s activities are well coordinated with those of the DFID SAFE trachoma programme (see Management case section A ). / That the trachoma programmes funded are integrated within the framework of existing SAFE programmes in each country. / That the interventions are a balance across each element of the SAFE strategy. / These assumptions are all reasonable: the trust is already actively engaging with partners (not limited to DFID) to ensure that their efforts are additive and well-coordinated with existing programmes. The precise geographical mapping of activities will be informed by these discussions. The trust has also provided written confirmation to DFID that their focus will be on scaling up existing SAFE interventions, with the aim of providing support in a balanced fashion across the four elements. / Following the DFID SAFE Trachoma Business Case, in line with the assumption that trust trachoma activities would be coordinated with existing SAFE interventions, the following unit costs per element of the trachoma intervention are assumed. These costs take into account a (conservatively) estimated 10% cost savings on the A,F,E arms of the intervention from coordination, justified based on the funding proposal submitted by Sightsavers on behalf of the ICTC, which makes clear that many of the specific interventions planned would be undertaken in coordination with other donors and other WASH (Water, Sanitation and Hygiene) partners in the area[53]. No cost saving is applied to surgery. The table also indicates the number of interventions the funding then translates into, assuming the same balance of funding across SAFE interventions as the DFID SAFE Business Case, based on the existing funding gap for each element of the SAFE strategy (note these are indicative values developed by DFID, rather than reflecting final Trust policy): / Intervention Funding ($) % of funding Unit cost per intervention ($) Number of interventions / Surgery 12,623,520 34% 40.00 315,588 / Antibiotics 13,366,080 36% 0.23 58,113,391 / Facial cleanliness 2,227,680 6% 4,500.00 495 / Environmental improvements 8,910,720 24% 18,000.00 495 / Translating these interventions into benefits is best achieved through the use of Disability Affected Life Years (DALYs), which effectively measure the years of healthy life lost due to a disease. These are measured by WHO[54] and are available for all the countries the Trust is considering intervention in. The benefit of the intervention can then be measured by the number of DALYs it averts and the cost per DALY averted. / The WHO estimate of DALY burden in the ODA-eligible countries in which the trust will operate[55] is currently 320,000. This is very likely to be an underestimate: it includes only confirmed trachoma endemic areas. Suspected areas are currently in the process of being mapped, with DFID support, an activity expected to significantly increase the DALY burden in many DFID priority countries. It also does not account for the pre-visual impairment stage of trachoma, which does have costs for sufferers (including pain, photophobia and sensitivity to dust and smoke) that are likely to affect their lives and earnings potential. / To calculate the DALYs averted through the intervention here, we assume (like the DFID SAFE Business Case) that the facial cleanliness and environmental improvement aspects of the programme ensure that action against trachoma through antibiotics and surgery has long-term, sustainable effects. We also assume that all of the DALYs in each country measured by the WHO accrue over the entire population living in trachoma endemic areas; and that providing treatments covering a certain proportion of these populations avert an equivalent proportion of the DALYs associated with trachoma in each country. This assumption is likely to underestimate the returns to the intervention, as not all those living in endemic areas will suffer from trachoma (so each treatment will in actual fact avert more DALYs than this method assumes), but since no figures on the number of actual sufferers are not available in each country, no better method is available. Making these assumptions, we find that: / The antibiotic aspect of the intervention covers 14.5 million people, assuming four rounds for elimination (the current estimate is 3.38, so assuming 4 is slightly conservative). Calculating DALYs averted from these interventions by taking this number as a proportion of the total population in endemic areas, to calculate the proportion of total DALYs averted yields an estimated 67,126 DALYs averted. / The surgery aspect of the intervention will cover 315,588 surgeries. This translates into 1458 DALYs averted using the same methodology. / The total DALYs averted are therefore 77,111. This translates into a Cost per DALY of £347.02 Valuing these DALYs by using the average income[56] in the countries in which the DALYs are averted yields a value of around $117 million, or £75 million, providing a benefit-cost ratio (BCR) of 3.16. Returns are not discounted because the DALYs themselves have been discounted a 3% per annum; further discounting of the valuation of each DALY would run the risk of double-discounting. Costs are not discounted as the schedule of disbursements made by the trust for trachoma activities is not yet known. This asymmetric discounting approach actually leads to an underestimate of the intervention’s benefit-cost ratio. In fact the returns to this intervention are likely to be even higher: there are secondary benefits to reducing the incidence of trachoma, including the cost (including opportunity cost) of carers, and ability to play a fuller part in community life that are not factored into this calculation. / The foregoing analysis, relying as it does on imperfect data and conceptualisation, includes biases in both directions with regards to the final benefit-cost ratio of the project. These are summarised in the table below: / Source of Bias Direction of Bias / WHO underestimation of DALYs associated with Trachoma (e.g. pre-blindness costs) Leads to underestimation of DALYs averted per treatment and BCR, as well as overestimation of cost per DALY averted. / Secondary benefits of treatment are omitted: due to lack of data we do not estimate the benefits to other family members/carers of those afflicted. Leads to underestimation of economic gains per treatment and thus BCR. / Method of calculating DALYs averted assumes DALYs are spread across the entire population in trachoma endemic areas. Leads to underestimation of DALYs averted per treatment and BCR, as well as overestimation of cost per DALY averted. / Optimism bias – assumption that all completed interventions will be successful Leads to overestimation of DALYs averted in total and BCR, and underestimate of cost per DALY averted. / Incomplete surveying of trachoma-endemic areas. Leads to an underestimate of need (i.e. those living in trachoma endemic areas and at risk of trachoma); but given the method of calculation, neutral effect on BCR. / No discounting of costs due to uncertainty of when funds will be drawn down. Leads to an overestimate of cost per DALY and an underestimate of BCR. Discounting of benefits undertaken through WHO discounting of DALYs. / Each of these biases is essentially a ‘dark figure’, without any basis for adjustment except arbitrarily. So in this appraisal, we do not attempt to make an adjustment to the figures presented above. It is sufficient to note that the net effect is very unlikely to be an overestimate of the BCR presented. It is more likely that the effect is neutral or results in an underestimate of the BCR, as more DALYs averted and uncounted benefits will increase the value of each intervention undertaken, and the estimates of cost of interventions take some account already (within the cost) of completion rates. This in turn means that costs per DALY are also likely to be overestimated in this business case. / Diabetic Retinopathy / This intervention will be focused on India to begin with, and may be extended to Sri Lanka, Bangladesh and Pakistan as work progresses. WHO do not publish specific DALY estimates for Diabetic Retinopathy, but the 2008 Global Burden of Disease report suggests that DALYs associated with Diabetes Mellitus were as high as 2,701,000 in India alone. Adding in the other three countries, the total rises to 3,518,000. Research suggests that 10% of diabetics in middle/low income countries have sight-threatening diabetic retinopathy; and one study suggests that based on 35 population-based studies, 34.6% of diabetics were found to have Diabetic Retinopathy[57]. Even taking a conservative estimate that 5% of this DALY burden is associated with DR yields an estimate of 175,900 DALYs (or 135,050 if restricted to India), a significant burden. Indeed this is little more than half the number of DALYs associated with Trachoma; the funding allocated to this arm of the intervention is less than half of that allocated to trachoma treatment and prevention due to the relative weakness of the evidence base on best practice for intervention, and the need to undertake research and local needs-assessments before a precise intervention strategy is made. Both in the West and in Asian countries that have been surveyed, the likelihood of developing Type 2 Diabetes and the negative effects of doing so (partly related to quality of care and ability to access it) are worse for poor compared to middle-income segments of the population[58]. / Under this option £9.5 million would be allocated to interventions around DR. The nature of these interventions has not yet been established. Research is on-going with the aim of identifying the most effective and efficient means with which to address DR in developing countries. This may involve training of ophthalmologists, funding of different treatment or diagnosis options, research into the link between DR and poverty (an area very poorly understood) and possibly awareness raising. In order to make an informed decision on which intervention(s) to pursue, more research into the topic is required and has been commissioned. Technological solutions for improving screening is often cited, but with few facilities for laser surgery, a more fruitful approach may be to focus on management capacity to improve the quality and regularity of care. / Given this context, a break-even approach to valuation is taken here: we calculate how many DALYs would need to be averted for this aspect of the intervention to represent an acceptable rate of return for DFID. Two cases are presented: the required number of DALYs saved if the intervention is restricted to India and if it covers India, Pakistan, Bangladesh and Sri Lanka, weighted by their share of the total DALY burden associate with Diabetes Mellitus. DALYs are valued according to GNI per capita. / Under scenario 1 (India only): with the full £9.5 million being allocated to India, 4,094 DALYs would have to be averted in order for this subset of funding to break even. To put this in perspective, the intervention would only need to be roughly one-eighth (actually 1/7.52) as cost effective as the trachoma intervention to break even. This translates to requiring the intervention costing less than $2,300 per DALY (£1,500)– a very achievable benchmark, which would also qualify as ‘very cost effective’ using GNI per capita, and ‘cost effective’ using GDP per capita, according to WHO guidelines[59]. / Under scenario 2 (India, Pakistan, Sri Lanka, Bangladesh, funding allocated according to weighted by DALY Burden), 4,557 DALYs would need to be averted for DFID to break even on the intervention. This would require the intervention to be a little less than one seventh as cost effective as the trachoma intervention in order to break even. This translates to a cost of around $2000 per DALY, again, well within the realms of possibility. This would be ‘very cost effective’ for all countries except Pakistan (where it is just beyond the ‘very cost effective’ threshold and thus qualifies as ‘cost effective’). / Given the near-total paucity of information and existing donor programming looking at the problem of DR, and the expertise on this issue available to the trust, this seems acceptable. In particular, not many alternative opportunities to use international expertise on the issue in a developing country context exist. / Retinopathy of Prematurity / This aspect of the trust’s intervention programme will be focused solely on India. This is an area of likely increasing burden to India; but the current scale and distribution are unknown. A relatively small amount of funding has been allocated to this aspect of the trust’s activity. According to the assumed split above, DFID’s contribution would be around £2.4 million. It would most likely focus on improvement of neo-natal care, detection of infants requiring treatment or treatment. Improved neo-natal care in particular will likely have benefits extending well-beyond ROP. / Taking a break-even approach again, this intervention (for India only) would need to avert 1,034 DALYs to break even – equivalent to the programme being, again, around one eighth as effective as the trachoma intervention. The cost per DALY avoided required for breakeven is again around $2300, which as for DR, qualifies as cost effective according to WHO guidelines (since this intervention will focus solely on India, the cost per DALY avoided to achieve the breakeven point is the same as for scenario one under DR, above, since DALYs are here valued by GNI per capita). / Another way of putting this is that given that ROP is a condition that will occur around birth, and using India’s average life expectancy to measure to estimate the number of DALYs avoided per person per effective intervention, the programme would break even if only 15 successful interventions were made due to the DFID funding. Given the small overall value of funding engaged, the lack of alternative interventions currently known, and the trust’s access to world-leading experts in ROP, this represents a small risk; it will also, in the case of either success or failure, generate valuable knowledge through M&E and research. As such, even if it falls short of this number of successful interventions, it may still represent a valuable investment in knowledge on disease burden, treatment and capacity building. / Research suggests that the range of cost-effectiveness per eye treated for ROP is extremely wide[60]. The more expensive scenarios and options in particular may not be justifiable in developing country contexts – so a focus on prevention rather than treatment may be the most effective and least risky approach to take on ROP. / Cross-Cutting Issues for Preventable Blindness / The trust proposes spending on three cross-cutting issues: / Fellowship programme: training to improve ophthalmological care for preventable blindness / Eye care toolbox: a technical diagnostic aid that would vastly increase coverage of diagnostic services / OpenEyes: a software for data management on eye patients. / Each component of this arm of the intervention seeks to address a binding constraint to prevention, diagnosis and treatment of preventable blindness. The training programme seeks to increase the number and distribution of skilled personnel in commonwealth countries, particularly for the treatment of Diabetic Retinopathy and Retinopathy of Prematurity. Training is not limited to individuals, but will also involve use of existing hospital links to create and strengthen systems for screening and management of diabetic retinopathy. / The Eyecare toolbox looks at providing cheaper, more mobile technology to access and diagnose rural and remote patients. The funding from DFID will be used to further develop and test this technology. By one estimate, the cost savings of successful roll-out would be immense: the mobile technology under consideration (PEEKS) produces retinal images at a cost of £1 per image; the best practice, hospital-based, technology producing similar-purpose images (Topcon TRC-50EX) would produce each image at the cost of £2,600. Successful development and roll-out of the mobile technology would therefore both greatly expand coverage of diagnosis, and dramatically reduce its cost. / The third element of this arm of the intervention focuses on patient-recording software (OpenEyes) to replace less efficient paper-based patient information recording, allowing improved patient care and monitoring. The trust seeks to develop the software and implement it in 5 LIC/LMIC countries. This aspect of the cross-cutting interventions is the least compelling. OpenEyes is an online system, developed for needs in the UK, and some evidence has noted that even in the UK, capacity to implement it does not exist in all hospitals, and even where this is the case, usage drops when the speed of use declines[61]. Further research indicates that the capacity to effectively use a web-based system is likely to be extremely low in the countries under consideration. A study in 2010 for South Africa, one of the best-connected and most developed countries in Africa, showed that virtually all staff interviewed across 5 rural healthcare institutions suggested that lack of internet connection was a problem for staff (the exact proportion of staff reporting this problem across the 5 institutions were: 100%, 100%, 83%, 88%, and 73%). Lack of computer equipment was cited by every respondent in four out of five hospitals, and lack of computer skills by more than half in four out of the five[62]. / However, the current suggested plan for roll-out of OpenEyes does take some account of these problems – it suggests a limited roll-out in some locations, with low-cost computers provided, and a system in place that would allow communication with a server as and when internet connections are available. The limited roll-out would be used to assess implementation problems; and the list of countries in which it would be piloted is still to be finalised, allowing for issues of skills and connectivity to be assessed. This does not mitigate the issues identified above fully, but taken as part of a suite of interventions with larger likely benefits, it may be considered, especially if early rollout in a limited number of sites offers the opportunity to scale down the implementation of the programme if problems are significant. It also offers benefits through the possibility of connecting with PEEKS, which may make diagnosis and action on diagnosis faster and more efficient. At present, according to the current proposal, OpenEyes would account for just 16% of the funding for cross-cutting issues; provided an allowance is made for reallocation of funding away from the intervention if pilot phases and process evaluation demonstrate difficulties, a case may be made for financing it on the grounds that in order to protect a small amount of the financing from DFID the additional costs imposed on the Trust of a fairly specific and detailed ring-fencing (as opposed to blanket ring-fencing to exclude only Youth Leadership an entirely different budget line for the Trust) may not be justified. / Costings from the implementing partner (the Eye Health Innovation Consortium) demonstrate that the DFID funding under this option would: / Fully fund 10 people to complete MSc/MPH degrees / Fund 34 1 year clinical fellowships / Fund 24 3 month clinical fellowships / Fund 4 PhDs and 2 post-doctoral fellowships / Provide funding for 4 UK-Africa Diabetic retinopathy partnership networks / Contribute to the development and evaluation of PEEKs, and development and limited roll-out of OpenEyes. / Contribute to the development of open, free and publically accessible learning materials on preventable blindness for remote and electronic learning, available beyond those directly trained. / Funding for training and fellowships includes costs of accommodation and living expenses. The impact of these trainings and better technologies are difficult to ascertain at present – they depend on the specific courses and research undertaken, and which countries the improved skills of students are applied in. Estimates on returns to higher education commonly used (from Psacharopolous and Patrinos’ 2002 study) are not used here: they are unlikely to accurately measure gains to training in medical skills, particularly in places where this may be a binding constraint to improved patient care and health outcomes. However, given the high need for more skilled personnel and better service coverage of remote and rural areas, it seems a reasonable assumption that both training and the implementation of a dramatically more mobile and cheaper diagnostic tool will serve to improve the quality of patient care and speed of diagnosis related to preventable blindness and thus avert DALYs both through better treatment and through earlier detection. / However, consideration must also be made to the risks of attrition from the cohort of trained medical professionals: not all of those will remain in their post in the medium-long terms. A number may use their improved skills to find employment either in private medical facilities or in other countries and there may be attrition for a number of other reasons. The extent to which this is a serious constraint varies by country. At least one study suggests that the proportion of doctors leaving the medical profession altogether tends to be small (though data presented are only from Ghana, and the situation may vary considerably by location), but that the proportion migrating can be much higher[63]. This suggests that careful programme design to ensure some level of ‘capture’ and persistence of benefits should be encouraged, for example prioritising training for staff able to credibly commit to remain in post for at least some multiple or proportion of the length of the training once they return to work, depending on the content, cost and benefits of the course. / Youth Leadership / The information provided on the proposed interventions and split across countries does not allow a clear valuation to be made at this time. This means that the likely outcomes of the intervention in different countries are not yet known - so valuation of this arm of the intervention is not yet possible. / However, while a project briefing produce by ODI for DFID on youth suggests that there are good rationales for supporting youth interventions[64], none of them can be easily valued and it is not clear that the possible interventions are well understood, including for civic engagement (the closest comparison point to youth leadership in the analysis). Other areas for supporting youth, including education and employment may yield more direct results, with better evidence on intervention options and cost effectiveness. / Given that two of the intervention arms under consideration are already assessed using ‘break-even’ criteria, due to the fact that they are not yet possible to value (though there are strong a priori reasons to assume that they can be effectively tackled, due to the expertise and access the trust will achieve through its membership and trachoma intervention), a further, expensive, intervention on youth engagement may generate undue risks to DFID’s investment. The Girl Hub[65] is undertaking interventions and research into similar programmes, so not funding this intervention will still allow DFID funding to be channelled into other interventions, on the basis of more concrete information. It is a more sound approach to take risks in the preventable blindness arm of the intervention, due to the expertise and access this arm is guaranteed to achieve: a good risk mitigation factor. Further risk exposure in the youth intervention may not be advisable – and option 3 provides one way of avoiding this risk. / Provide the same value of support (£50m), but restrict funding to a sub-set of activities to maximise the developmental impact and value for money achieved by DFID’s portion of the trust’s spending. DFID also retains the right to further restrict or reallocate funding should information from monitoring and evaluation demonstrate that value for money (VFM) is not being achieved in any arm of the intervention and can be reallocated to better-performing aspects. / Restricting the funding of the trust by imposing conditions is likely to be costly. As a guide to the likely costs, studies of tied aid have suggested that tying aid (i.e. imposing restrictions on the use of funds) imposes costs on recipients: tied aid has been documented to raise the costs of goods, services and works by 15-30% on average[66]. It is likely, however, that imposing a single funding restriction on DFID contributions to the trust would have a much smaller effect: it would not mandate the use of any specific suppliers, but would simply ensure a focus of DFID funding on avoidable blindness, which is in any case separately conceived and organised to the Youth Leadership intervention. The cost of restrictions to funding based on this single hypothecation is likely to be negligible, therefore. / Furthermore, there are concerns around the £9.5 million which would be allocated to Youth Leadership – which, given the current lack of information on the interventions to be undertaken, and the difficulty of valuing and assessing leadership and civic engagement interventions, may introduce undue risk to DFID’s investment in the Trust. A compromise solution would be to provide unrestricted funding for the four preventable blindness interventions. This would have the additional benefit of ensuring that DFID accesses the full value of the expertise on preventable blindness assembled to inform the trust’s activities. A further right to reallocate or restrict funding during the course of the project, in response to monitoring information provides further insurance against risks of under-performance for DFID, and also provides good incentives to the Trust to ensure even and high-quality implementation across the remaining arms of the intervention. / Under this circumstance, the Trust have shared with DFID the following indicative distribution of DFID funding: / Trust Activity Equivalent DFID contribution / Trachoma £30.6m / Diabetic Retinopathy £12.4m / Retinopathy of Prematurity £3m / Cross-cutting issues for preventable blindness, including Fellowship Scheme £4m / Using the same valuation techniques and rationales used under Option 2, this then provides the following valuations. / Trachoma: The trachoma intervention will now avert 88,180 DALYs, valued at $150.6 million (£92.8 million). This equates to 405,756 surgeries and 18,679,304 courses of antibiotics. The cost per DALY averted and BCR remain unchanged at £347.02 and 3.16 respectively. / Diabetic Retinopathy: The break-even marks remains unchanged: around $2300 for the ‘India only’ option and $2000 for the option addressing India, Pakistan, Bangladesh and Sri Lanka (cost effectiveness thresholds also remain unchanged and the breakeven levels are comfortably within them). However, the number of DALYs to avert increases in both cases: to 5,344 in the India Only option, and to 5,948 in the wider option. These remain a very small proportion of the overall DALYs associated with DR. / Retinopathy of Prematurity: The break-even mark remains unchanged, at $2300, though again, the number of DALYs needed to be averted increases to 1293 (cost effectiveness thresholds also remain unchanged and the breakeven level is comfortably within the thresholds). This is equivalent to 20 successful interventions. / Cross-Cutting issues: Under this funding proposal, DFIDs resources would fund: 8 MSc/MPHs; 30 1 year clinical fellowships; 20 3 month fellowships; 3 PhDs; 1 post-doctoral fellowship; 3 UK-Africa knowledge sharing partnerships on diabetic retinopathy and a proportion of the required funding for developing and testing PEEKs and developing and rolling out OpenEyes. Though these are fewer results than in Option 2, this is because the Trust would in this circumstance focus DFID funding more on trachoma and diabetic retinopathy; costs per result do not change. / This summary demonstrates that for very little cost in break-even requirements and cost-effectiveness, Option 3 eliminates the extra risk to DFID investment associated with the Youth Leadership intervention and provides increased flexibility to maximise VFM. / Conclusion / On the basis that the analysis for Option two argues that there is no way of assessing the value for money or cost effectiveness of the youth intervention aspect of the intervention, Option 3 is chosen for this intervention. It is chosen over Option 2 to minimise risks to DFID funding, given the lack of current knowledge on the youth leadership intervention. It is chosen over the counterfactual because, though the main part of the intervention on avoidable blindness (trachoma) is assessed to have a higher cost per DALY averted than the interventions listed in the counterfactual: / The cost per DALY for trachoma is still highly cost effective. / The cost per DALY for trachoma is likely to be over-estimated for the reasons outlined in the table on page 19. / The interventions on Diabetic Retinopathy and Retinopathy of Prematurity are likely to provide important new information on two poorly understood causes of preventable blindness, and have breakeven levels that are both achievable and cost effective. / This means that DFID money will not be used to fund Youth Leadership interventions. This will remain an issue for the Trust to consider, but in the absence of clear information on what the interventions will be and how they will be assessed (and how they deliver value and might be adjudged cost effective), DFID money should not be used on this aspect of the intervention.
H. Theory of Change for Preferred Option / The Trust have coproduced with their stakeholders a living visual representation of the theory of change for the avoidable blindness programme, i.e. DFID’s preferred option for funding, which it is using to inform discussions with the Board and partners about the development of its programmes (see below). In doing so it aims to represent some of the complexity and interconnectedness of the various interventions it will be supporting. / Not all of the arrows and levels of this representation are robust to testing so a simplified, more linear, representation for the purposes of developing DFID’s log frame and understanding the impact and outcomes associated with this business case (see above) is given below. / A number of assumptions underpin both these representations: / The Trust’s programmes can have a measurable impact on avoidable blindness across the Commonwealth over a 5 year period / Evidence: Medium. The Trust’s entire strategy has now been designed with the guiding principle that all its activities should contribute towards this aim. The trachoma programme is particularly likely to have a measurable impact: measuring the impact in terms of blindness prevented by the DR and RoP programmes will certainly be more challenging in terms of the availability of data. However, the fact that the Trust has quickly mobilised high profile experts to inform their strategies on an on-going basis, across their avoidable blindness programmes, justify the assumption and the rating. Also, elements of their work will directly contribute to improving the evidence base and the ability to obtain good data (e.g. OpenEyes) . / Development and implementation of global/national strategies will create sustainable change across the programmes and help achieve elimination of trachoma/positive change in ROP and DR / Evidence: Medium / Selected technological, training and research initiatives will both reinforce (and advance) the three main parts of the strategy and have wider positive impacts / Evidence: Medium/weak, according to initiatives chosen. There is limited evidence about the relationship between poverty and retinopathy of prematurity and successful strategies in low-income countries, therefore research efforts in these areas are likely to be disproportionately beneficial. The technology initiatives, if chosen and implemented effectively, could substantially increase the pro-poor impact of the Trust’s work: mobile technology, for example, is now being used in some of DFID’s governance, educational and economic projects. The fellowships are aimed at wider trainings and information exchange, rather than professional qualifications that might inadvertently fuel health worker migration. / The countries chosen for intervention are those that enable maximum impact / Evidence: Medium. The countries chosen for the trachoma intervention should be those where there is a high burden and a clear need for assistance: we understand that the Trust will finalise their area and intervention focus by working with partners to ensure there is no duplication and a clear need. It is likely that whilst the other trachoma programme referred to here focuses largely on those where the burden is highest both in terms of proportion and absolute numbers, the Trust extends this to countries where burden in terms of percentage is high but the absolute numbers are lower, i.e. a complementary, demand-led approach. / For ROP and DR, the initial focus country (India) has been chosen both because of high burden, but because there is the infrastructure, at least in some areas, for a proof in principle, and the Trust’s stakeholders have advised the Trust that this will maximise the potential to influence policy regionally given the reputation of India’s eye care professionals. / For ROP and DR, cost-effective strategies can be identified in the initial consultation and planning period which will have an impact over the lifetime of the Trust / Evidence. Medium/weak. Although there is some understanding about screening and treatment, effective primary prevention strategies and real-world evidence about scale-up are lacking. However, the Trust has gathered an eminent advisory panel who are well placed to identify possible ways forward and has considerable good will and political buy-in. / For ROP and DR, learning from initial single-country programmes is scalable and replicable and can be rolled out to other countries according to epidemiological, economic, social, political and institutional similarities / Evidence: medium/weak according to the intervention chosen and robustness of assessment – for example, interventions in high-density populations e.g. in India may be less suitable for rural populations or in populations in small island states in the Pacific and Caribbean. This tension will need to underpin the Trust’s assessment of viable interventions. / For all programmes, the Trust’s inputs will not cause the diversion of funds or resources from other parts of the health system / Evidence: to be reviewed – the Trust is aware of this challenge and will keep monitoring the situation as national strategies and “exit strategies” are drawn up and implemented. / Advocacy will contribute to the achievement of Trust outcomes and reinforce impacts including health system strengthening / Evidence: Medium. There is already evidence that the Trust’s activities and discussions are encouraging positive change elsewhere in the system. For example on DR, the IAPB has set up a working group reflecting the Trust’s interest, WHO and the IAPB have recently restarted work on a tool for assessing capacity gaps at country level, and there has been interest from other areas of the Commonwealth e.g. the Caribbean. The fact that the Trust is high profile, established as a tribute to the Queen, has extensive reach and influence, and a mandate from CHOGM all suggest it can play an influential and high profile role. The evaluation of the Princess Diana Memorial Fund[67], headed by the Trust’s CEO, identified that the Fund was “refreshingly open to learning”, offering some justification for assuming that the Trust will learn from the experiences of the Fund (which also relied on collaboration, influence and advocacy). However, the Trust will need to continue to gather evidence, as noted elsewhere in these assumptions, that their activities, including advocacy, reinforce rather than undermine health system strengthening. / Dissemination of learning and best practice will contribute to the achievement of Trust outcomes and reinforce impacts including health system strengthening / Evidence: Medium. Effective dissemination and uptake is obviously core to health system strengthening efforts: however at this early stage there is limited information about how this part of the Trust’s activities will be organised to ensure effectiveness. / The Trust’s work alongside national governments will result in continuation of programmes under local leadership / Evidence: Medium. The Trust has chosen this approach on the basis of expert advice from its stakeholders. / Finally, the assumption is made throughout that the Trust will retain flexibility, in discussion with DFID and its governance structures, to reapportion funding based on outcomes of research and feasibility studies into DR and ROP to be completed during year one of funding period and agreed approach towards potential national roll out, as well as respond to the outcomes of its initial evaluation (see below). / Given the nature of the Trust and its stage of institutional maturity, there are of course gaps in the evidence underlying the assumptions in this theory of change: in particular, the exact mix and targeting of interventions on the DR and RoP programmes, and the advocacy strategy. These gaps inform the evaluation strategy outlined below (as well as the overall approach taken in this case).
I. What measures can be used to monitor Value for Money for the intervention? / Value for Money in each of the direct arms of the intervention would be demonstrated by maintaining a cost-effective cost per DALY averted throughout the intervention period for each of the three diseases[68]. Calculating this requires measurement of number and cost of completed interventions (surgery, completed antibiotic treatment, etc). / These indicators would allow us to study evolution of the cost per DALY averted each year, and to map this against the incidence of trachoma, DR and ROP against the baseline. Monitoring this information as closely as possible to real time would allow assessments to be made as to the optimal distribution of resources by the Trust. This will be of particular importance in trachoma, where the drive towards elimination may lead to changing unit costs as interventions target harder-to-reach populations. / VFM in impact terms would require that the quantifiable gains (in income and time saved) is greater, in present value terms, than the cost per person treated. However, the ability to generate such information reliably and with causal attribution will depend heavily on the methods of evaluation chosen, and there are trade-offs relating to cost to consider in this decision. / Establishing unambiguous value-for-money thresholds for research and fellowships is less clear-cut. However, for research, a common-sense threshold for VFM can be set, based on DFID’s willingness to pay for new research in a similar field and of a similar design. This depends so closely on the type and kind of research under consideration that it can only really be assessed once research designs are proposed. Even once this is the case, analysing a number of metrics together is likely to be the best approach, as depending on the specific measure under consideration, cost effectiveness can vary significantly even for an individual project[69]. For research, this is likely to focus on the number of citations and reports produced, together with analysis of the costs of research. For Fellowships, the cost per completed course would be the main focus, and it would clearly be helpful if the Trust’s final evaluation (see section D of the Management case) would follow up how many of the fellowship recipients remain in their post e.g. 2 or 5 years after training is completed. / Summary list of proposed metrics: / Trachoma/Diabetic Retinopathy / Retinopathy of Prematurity: / Cost per DALY averted (based on cost per intervention, number of interventions); / Incidence compared to baseline / Research (DR/ROP) / Number of peer reviewed publications, publically available research reports / M&E reports, / citations ; cost analysis and comparisons / Cross-cutting interventions / Cost per competed course at each level (and if possible, proportion of completed course/degree remaining in post 2/5 years after training completion). Metrics for other cross-cutting interventions to be agreed.
J. Summary Value for Money Statement for the preferred option / Option 3 is preferred to option 2. It achieves the same cost per DALY averted / break-even marks as option 1 but eliminates any risks associated with funding Youth Leadership interventions, which are much harder to assess for their value and do not have the same level of unmet need. Benefits from training and development of new technologies are smaller (due to less money being allocated to cross-cutting issues under Option 2), but this can be weighed against a higher proportion of funding being allocated to the most well-understood and least risky intervention, trachoma. / Option 3 is also preferred to option 1, the counterfactual. Though the cost per DALY reported for trachoma is high in comparison to those reported by QAU, the benefit-cost ratio is still very high, and there is also a significant unmet need in the absence of additional DFID funding. The funding proposed under Option 3 will make a significant contribution to the required financing to eliminate trachoma worldwide, and would also make a new contribution to the knowledge base around Diabetic Retinopathy and the Retinopathy of Prematurity. The benefits to the intervention are almost certainly understated by this business case, as the interventions are also likely to have secondary benefits, both to carers, and to the treatment, prevalence and cost of other diseases as training improves health service provision and sanitation and treatment also alleviates other conditions. The training and technological component is also likely to bring benefits to patient care, and most likely not just in the targeted areas of trachoma, diabetic retinopathy and retinopathy of prematurity. / In summary, though there are risks associated with the high level of funding, including to areas with a low knowledge base, since the unmet need in the absence of the intervention is significant; the intervention will provide direct results as well as generate new knowledge on how best to make in-roads to the problems identified; and the project offers an unusual opportunity for exploiting a vast body of experience and expertise in these areas, Option 3 is preferred to the counterfactual of no intervention (and alternative use of funds), with the caveats that funding and results will be closely monitored with the option of a reallocation of DFID resources in the event of monitoring evidence demonstrating a failure to achieve value for money in any arm of the intervention.
[38] DFID, Business Case: Trachoma control: Supporting the implementation of SAFE, (July 2013)
[39] Ibid.
[40] USAID’s support is part of a package to five NTDs together, and as such it is difficult to disaggregate the proportion dedicated to trachoma.
[41] World Health Organization 2007. Everybody’s business: Strengthening health systems to improve health outcomes.WHO’s Framework for Action
[42] http://www.sightsavers.org/in_depth/quality_and_learning/learning/13168_Guidelines%20for%20DR%20Management%20India.pdf
[43] Share consortium. 2011. Evidence Review: WASH and trachoma.
[44] There are indicators in the Trachoma programme logframe that incorporate advocacy and behaviour change activities, specifically outputs 3 and 4, on facial cleanliness and environmental improvement. The mid-term evaluation will assess the projects performance and results against these outputs and their associated activities and recommendations for improvement / revision.
[45] Frick KD, Hanson CL, Jacobson GA (2003) Global burden of trachoma and economics of the disease. Am J Trop Med Hyg 69: 1–10.
[46] Wright HR, Turner A, Taylor HR. 2007. Trachoma and poverty: unnecessary blindness further disadvantages the poorest people in the poorest countries. Clin Exp Optom. 90: 6: 422-428
[47] “Women and trachoma: Achieving Gender Equity in the Implementation of SAFE”, Elfenworks Foundation, The Carter Center, and the Kilimanjaro Centre for Community Ophthalmology, 2009.
[48] Trachoma: Looking forward to global elimination by 2020 (GET 2020), Mariotti P. et al, Am. J. Trop. Med. Hyg., 69 (Suppl 5), 2003, pp. 33–35
[49] Zerihun N (1997), Trachoma in Jimma Zone, South Western Ethiopia, Tropical Medicine & International Health 2.
[50] World Bank, Harmonized List of Fragile Situations FY13
[51] DFID, Business Case: Trachoma control: Supporting the implementation of SAFE, (July 2013)
[52] Zheng, He, and Congdon, The World-Wide Epidemic of Diabetic Retinopathy, Indian Journal of Ophthalmology 2012 Sep-Oct; 60(5): 428–431.
[53] This 10%saving is based on the assumption that whichever bid is accepted will, in a similar fashion, integrate the Trust’s trachoma activities with on-going activities related to antibiotic distribution, behaviour change for facial cleanliness and environmental improvements, The magnitude and type of the saving is calculated following the DFID Trachoma Control project Business Case, which cites Brady MA, Hooper P, Ottesen EA (2006), Projected Benefits from Integrating NTD Programmes in Sub-Saharan Africa, Trends Parasitol 22: 285-291,
[54] Global Burden of Disease 2008 Report.
[55] Kenya, Malawi, Mozambique, Nigeria, Tanzania, Uganda, Zambia and the Pacific Islands(Vanuatu, Kiribati, Solomon Islands, Fiji)
[56] GNI per capita, taken from the World Bank Databank, 08/13
[57] Zheng, He, and Congdon, The World-Wide Epidemic of Diabetic Retinopathy, Indian Journal of Ophthalmology 2012 Sep-Oct; 60(5): 428–431.
[58] Chi-Chen Hsu et. al. (2012), Poverty Increases Type 2 Diabetes Incidence and Inequality of Care Despite Universal Health Coverage, Diabetes Care June 2012. Women are also more at risk, particularly among the poor.
[59] WHO cost effectiveness thresholds consider an intervention to be ‘Very Cost-Effective’ if the cost per DALY is less than GDP per capita; and ‘Cost Effective’ if it is less than 3 times GDP per capita. http://www.who.int/choice/costs/CER_thresholds/en/
[60] Kamholz et. al. (2009), Cost-effectiveness of Early Treatment for Retinopathy of Prematurity, Pediatrics: Official Journal of the American Academy of Pediatrics
[61] E-Health Insider (2012), Open Your Eyes, http://www.ehi.co.uk/insight/analysis/941/open-your-eyes
[62] Ruxwana, Herselman and Conradie (2010), ICT applications as e-health solutions in rural healthcare in the Eastern Cape Province of South Africa, Health Information Management Journal, Vol. 39, No. 1
[63] Dovlo (2005), Wastage in the health workforce: some perspectives from African countries, Human Resources for Health 3:6
[64] Helpdesk Research Report: Youth Unemployment and Livelihoods (2012)
[65] http://www.girleffect.org/about/girl-hub/
[66] Clay, et. al. (2008), Thematic Study: The Developmental Effectiveness of Untied Aid, ODI/OECD
[67] DP Evaluation: A Funder Conundrum, 2012
[68] Using the WHO definition of cost effectiveness as within 3 times GDP per capita.
[69] DFID (2013), Value for Money: Towards a Consistent Approach for DFID (Growth) Research, Growth Research Team, April 2013

Commercial Case

Delivery through a third party entity (multilateral organisation; civil society organisation or support to government)

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The agreement for funding this intervention is as Matched Funding as announced by the Prime Minister at CHOGM 2011. This type of funding is appropriate to try and encourage other partners, donors, etc. to co-fund and so maximise potential for the trust. As indicated above in the Appraisal case, it is appropriate to channel funds through this partner, i.e. the Trust, because they should have the critical mass to make a significant difference over the lifetime of this business case (and the trust itself), over and above existing/planned DFID programmes . / Funds will be released regularly as detailed in a Memorandum of Understanding (MOU) between the Trust and DFID. An MOU is flexible enough to accommodate the “matching” arrangements which have been agreed and the restrictions we would like to place on that. It will set out details of when funds will be released and how much and also what information DFID will require from the Trust prior to the release of the funds e.g. financial statements accounting for previous funds. / It is expected that DFID will release funds on a 6 monthly basis, as set out in the MOU, to minimise overheads and transaction costs but ensure accountability. Exact timing will depend on the rate of implementation over the previous 6 month period and forecast for the following six months. It is not appropriate to pay strictly in arrears given that the Trust requires a certain amount of liquidity to enter into contracts. The Trust has noted the requirement for 6 monthly reporting so that we can see how funds are being allocated, in particular DFID’s funds, which must be spent only on areas which are acceptable as ODA compliant. / The MOU will be linked to the DFID log frame and to the overarching logical framework which the Trust is developing to monitor progress on the programmes.
B. What assurance has been obtained on capability and capacity to deliver? / The Trust will, as set out above, work through partners rather than delivering directly and they are obtaining assurances of the capacity and technical expertise of the organisations they work through to deliver in country. The trust will not issue a “call for proposals” but will seek potential grantees directly following the collaboration described above. Grantees will be selected using the requirements set out in the draft grants procedures: / The organisation: / Is financially healthy and has appropriate capacity to manage the piece of work. / Has appropriate and transparent governance and accountability structures, including how it addresses gender and diversity. / Is collaborative and is committed to sharing learning externally about successes and failures. / The Project or programme: / Clearly fits into one or more of the Trust’s defined funding programmes and policies of what can or cannot be funded, and is focused on one or more appropriate Commonwealth countries. / Is achievable with defined outcomes and a robust monitoring and evaluation plan that can be achieved within five years. / Has a clear exit strategy that will ensure that any benefits will be sustainable, can be communicated easily and will fit into the agendas of long term donors and governments. / Is well planned and has taken into account the needs and views of relevant stakeholders. It must also clearly deal with disadvantage, poverty reduction, gender and diversity. / Appropriate risks have been mapped with plans for mitigation set out. / Has an appropriate budget that represents good value for money. / Builds in partnerships with individuals and agencies which are working in similar or related issues, so that it aligns with efforts in the same region. Appropriate levels of influencing built in and local ownership of long term plans for social change. Added value to the wider field should also be built in. / The procedures also highlight the need for due diligence to be carried out on the grantees. The financial manual sets out requirements for financial management and internal audit. The Trust will also need to continue to take on board the expertise of its advisory panels and stakeholders as it finalises its procedures. / So, for example, in the case of trachoma, where there could in theory be concerns about the rapid scaling up of efforts (with the combination of funding through the trust, separate DFID funding, and USAID funding), the Trust has sought assurances from Sightsavers that there is the capacity to deliver this work and Sightsavers are phasing the work in each country accordingly and have built in very thorough staffing and governance plans. The Trust will be monitoring this very closely and ultimately Sightsavers will have a contractual responsibility to deliver. The Trust is taking the need for robust contract management principles seriously: ultimate responsibility for ensuring contractual arrangements are sound and carefully monitored rests with the CEO. We will underline key expectations on this in the MOU that will underpin this agreement. / DFID has been invited to sit on the expert advisory panel (see below) that has been convened to oversee the first couple of years of the avoidable blindness programmes and will therefore be sighted on on-going monitoring in addition to regular contact and formal annual review processes against a log frame. / The Trust has developed a procurement and purchasing policy and DFID has had sight of this and we note that it contains all the basic principles which we would expect from an organisation such as the Trust. The main requirement for DFID will be that the Trust only procures from delivery partners with a proven track record. / Delivery risks will be monitored and managed as part of overall approach to risk management (see below) through the gathering of monitoring information every 6 months from the delivery partners. This information will be used to assure the trust and the donors that the delivery partners are undertaking the work which has been agreed with them and to raise any concerns on the actual delivery or any other issues which may arise which affect the programme. / CIDA, the Canadian Aid agency, have carried out a due diligence assessment of the Trust and set out areas of identified risk, mainly due to the trust being a new entity with no track record. DFID is building on this assessment and will complete its own due diligence assessment before any payment is released (therefore before the end of calendar year 2013) and mitigate residual risks through the reporting and communication channels established
C. Is there an opportunity to negotiate on anticipated costs? / Not directly, but the Trust is very sensitive to DFID’s emphasis on value for money and the need to spend donated funds wisely. It has emphasised its intention to keep overheads to a minimum, with a target below 10%. Opportunities to reduce costs are maximised by the Trust’s chosen approach of coordinating across different parts of its own programmes (e.g. through the cross-cutting programmes) and with other programmes and existing partners. The Trust’s Finance manual sets out that budget holders must take all steps to ensure goods and services are obtained economically and expeditiously and are of good quality. / We will seek further opportunities to find synergies with existing DFID-funded programmes, e.g. between the Scholarships and Fellowships programme and other higher education initiatives.

Financial Case

A. Who are the recipients of all proposed payments? / DFID will make payments directly to the Trust in the form of Matched Funding to match donations and contributions from other donors to the Trust. DFID reserves the right not to match funding where the source or origin of the Trust’s funding would in our opinion conflict with DFID financial and ethical policies. The Trust will then use the combined funds to engage programme partners to deliver the programmes and projects as set out in their programme strategy.
B. What are the costs to be incurred directly by DFID? / Up to £50m in matched funding. DFID funding will be permitted to be spent only on ODAable programmes and will be ring-fenced by the Trust for this purpose. The expected allocation of DFID funding between programmes is outlined in the appraisal case but is explicitly subject to on-going discussions between DFID and the Trust according to progress in their programming. More discussion about evaluation and overhead costs is set out elsewhere (commercial case section C; management case section D)
C. What are the costs to be incurred by third party organisations? / None, but note that there are other parties to the trust. The Trust will engage partners to deliver programmes and can use DFID funding to finance these activities, so far as these still constitute ODA eligible activities.
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / All funding from the Trust will be through delivery partners, e.g. non-governmental organisations.
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / The funding will be paid from programme resource funds. The provisional payment schedule does set out some further payments beyond the current Spending Review period but these are within the limits set by HMT for approval of spending into the next Spending review period. UNCD will bid for sufficient resources to meet these payments as part of DFID’s resource allocation process.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / We will plan on the basis of 6 monthly payments on the basis of forecast need. This will involve making advance payments but these will be structured to mitigate the risk of advance of need. The first payment will be paid in advance as the trust require this match funding to enable them to begin their programmes. Further payments will be released on provision of reporting detailing how our funds have been expended and confirmation of required funding to enable delivery of programmes within the next 6 month period. The Trust’s financial rules require that funding be in place before they can enter into contracts and commitments. The format of reporting to support each payment request will be detailed in the MOU. This will require the Trust to supply a certified letter with any payment request setting out the detailed actual expenditure to date (committed and spent), a forecast of funds to be disbursed or committed during the next 6 months, a statement supporting new funding raised to which DFID will be viewed as eligible to match and an explanation of the disparity between the forecast commitments and disbursements and funding already held by the Trust. / We will seek assurance from the Trust that their financial and programme management arrangements will enable accurate forecasting. The profile we are using for working purposes – to be set out in the MoU - is currently: / 2013/14: 1 payment of £5m (month to be agreed) / 2014/15: 2 payments of £5m (April and September) / 2015/16: 2 payments of £5m (April and September) / 2016/17: 2 payments of £5m (April and September) / 2017/18: 2 payments of £5m (April and September) / 2018/19: 1 payment of £5m (April) / This payment schedule will be adjusted upwards or downwards based on actual need of the Trust, based on forecast funding requirements. Where it is identified that the proposed payment does not appear justified DFID will seek to consult with the Trust to put in place an amended payment schedule. Alternatively where the proposed payment schedule is insufficient to meet the Trust’s forecast funding requirements for the next 6 months DFID will consult with The Trust and subject to available budgets may amend the payment schedule to increase payments, where required.
G. What is the assessment of financial risk and fraud? / Rating: Medium-High potential impact with a low/medium likelihood: this is not on the basis of concerns about the Trust but because of the fact that the Trust is a new organisation which will operate through multiple partnerships and grants. / Financial risk: / There is a risk of DFID funds being used for non-ODA purposes. The Trust has separate bank accounts for ODA and non-ODA funding. The external audit company, Crowe Clark Whitehill, have been engaged to audit the financial statements of the Trust. As part of their key focus areas they will “specifically consider the extent to which the “match funding” income from DFID has been recognised in the accounts and assess whether this is appropriate give the agreement between the Trust and DFID and any specific assurances received from the UK Government.” / There are risks associated with acting through multiple partners, with multiple layers of accountability. The Audit committee will be largely responsible for assessing risks including financial risks (see section H below). The Board is the main decision-making and accountability structure and will have oversight of risks (see below). As set out in the Trust’s finance procedures manual, the Chief Executive is responsible for ensuring prudent financial management and keeping the Trust’s financial position secure. The Chief Executive was previously head of the Princess Diana Memorial Fund, which had a similar budget (£130m) and did not suffer any financial scandals. / The Trust’s draft grants procedures highlight the following requirements for grantees: / The organisation: / Is financially healthy and has appropriate capacity to manage the piece of work. / Has appropriate and transparent governance and accountability structures, including how it addresses gender and diversity. / Is collaborative and is committed to sharing learning externally about successes and failures. / The Project or programme: / Clearly fits into one or more of the Trust’s defined funding programmes and policies of what can or cannot be funded, and is focused on one or more appropriate Commonwealth countries. / Is achievable with defined outcomes and a robust monitoring and evaluation plan that can be achieved within five years. / Has a clear exit strategy that will ensure that any benefits will be sustainable, can be communicated easily and will fit into the agendas of long term donors and governments. / Is well planned and has taken into account the needs and views of relevant stakeholders. It must also clearly deal with disadvantage, poverty reduction, gender and diversity. / Appropriate risks have been mapped with plans for mitigation set out. / Has an appropriate budget that represents good value for money. / Builds in partnerships with individuals and agencies which are working in similar or related issues, so that it aligns with efforts in the same region. Appropriate levels of influencing are built in and local ownership of long term plans for social change are included. Added value to the wider field should also be built in. / Fraud: / The Trust is a new entity without a previous governance, financial, programme or reporting track record. The theoretical risk this poses will be mitigated through internal expertise and the Trust’s operating procedures, scrutiny from Board and Chair, Commonwealth Advisory Panel, satisfactory 6 monthly financial reporting and regular official level contact. DFID’s funding will be released in instalments, on the provision of 6-monthly financial statements, and the trust will provide audited financial statements on an annual basis, to ensure rapid identification of any irregularities and to minimise the potential loss of funds. / The Trust has set out in its grants procedures the need for the Trust (and partners) to undertake its own due diligence on each potential grantee. This should be covered by the assessment process, including the review of the grant proposal and associated documents (see the section on financial risks above). / Payments to grantees will be recommended every six months, with a bi-annual financial and narrative report being required before the payment is released to reduce the risk of payment in advance of need. More detailed guidance on grant management is still to be drafted by the Trust and will be put to the Board at its meeting in September.
H. How will expenditure be monitored, reported and accounted for? / The Trust’s Finance manual sets out roles, responsibilities and accounting procedures, including the role of the Audit Committee, which consists of five members, two of whom are trustees. The committee is responsible for : / Approving and overseeing the Trust’s annual operating budget. / Ensuring the veracity of all financial statements and management information circulated in or published by the Trust. / Overseeing the quality of management information. / Appointing the external auditor and agreeing their remuneration. / Approving and overseeing the annual Audit plan, bringing audited accounts to the Board for approval and ensuring that resulting recommendations are considered and implemented appropriately. / Considering the need for internal audit activity, identifying appropriate resource; receiving subsequent reports and overseeing implementation of recommendations. / Ensuring adequacy of financial controls and monitoring adherence to delegated authorities. / Overseeing procedures for distribution of funds to agreed beneficiaries/partners to ensure funds reach intended destination and are used for the intended purpose. / Developing, agreeing and overseeing implementation of a treasury policy and, if appropriate, an investment policy to achieve best return within acceptable risk. / Considering risks facing or likely to face the organisation and overseeing management response. This will involve a risk register. / The Trust Risk Register will be reviewed monthly by the Trust’s senior management team and sent to the Audit Committee monthly along with the Trust’s management accounts. The Trustee Board meets quarterly and reviews the top three risks as identified by the Audit Committee. / The Trust’s risk register is based on its operations and high level programme strategy. The Trust will ensure that the organisations/delivery partners that it funds have carried out a full risk analysis of their programmes and projects, before releasing any grant funding. The Trust will monitor its delivery partners’ on-going management of risk as part of its monitoring strategy. / All financial transactions are recorded by the Finance Department. The Trust’s financial year runs from 1st July to 30th June. After the end of the financial year the Trust’s Annual Accounts will be presented to the Board of Trustees. / DFID’s management arrangements (programme and financial) are elaborated further below. The Trust will provide DFID with 6-monthly reports showing how and where our funding has been used. This is discussed in more detail above, setting out support for the planned disbursements. Details of how DFID funding is being used will also be provided in the annual audited accounts and annual report demonstrating progress towards delivery of outputs and outcome indicators set out in the agreed logframe which will be shared with DFID and other donors. The Trust will ensure that the DFID element of total funding and expenditure is clearly distinguishable from that of other donors. The audited accounts will further include a management assertion of the existence and satisfactory performance of procedures and controls to mitigate the major risks to which the Trust is exposed in administering the Contribution. In the unlikely event of a failure to submit annual audited accounts on time, this could in principle lead to future funding being withheld.
I. Are there any accounting considerations arising from the project? / See above: the Trust will ensure that DFID’s contribution is used for ODA eligible activities. Additionally the 6 monthly and annual reporting will provide assurance on how and where DFID funding has been used. There are no implications on DFID’s balance sheet.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The Trust is building up its programme management expertise and capacity for implementing and overseeing its programmes. Partners and grantees are being sought strategically (rather than by open competition, which would be time consuming and transaction-heavy) according to experience, capacity to deliver (see above) and value for money. So for example as Sightsavers is the lead partner on trachoma, the Public Health Foundation of India will be the lead partner for the ROP and DR programmes as it is a very well established organisation which is used to managing donor funds. They will be required to commission specific pieces of work from implementing partners, based on a set of detailed criteria including value for money. / In addition, the Trust expect that running costs will not normally be above 10%, with the exception of the trachoma work in Africa, where the challenges of implementation mean that 17% is expected (this is in line with other donors’ programmes and with the DFID SAFE trachoma programme). / All proposed programme budgets are being thoroughly scrutinised by Trust staff. Programme results will be monitored every six months. If the results are not being achieved, we will work with partners to address this, or ultimately to stop payments if there is not sufficient progress. / From DFID’s side, the intervention will be managed by the A2 Commonwealth Programme Manager with support from a B1 Deputy Programme Manager, both in United Nations and Commonwealth Department (UNCD). The Programme Manager will be first point of contact with the Trust on strategic discussions around work plans, funding decisions etc and will ensure a minimum level of health expertise is brought to bear from UNCD’s perspective. The Deputy Programme Manager (DPM) will be responsible for monitoring project implementation and performance through report against the targets in the log-frame and drafting annual reviews. The DPM will also be responsible for ensuring payments are made accurately to the timescales envisaged and that all necessary financial reports are received on time. The Trust has agreed to monthly catch-ups with the programme team. / In terms of alignment between the Trust’s trachoma activities and DFID’s other major trachoma programme: / the Trust is now a member of the ICTC, as is DFID / the informal communications relied upon to date will be replaced by monthly contact between the two responsible teams both to ensure alignment and to ensure UNCD has access to sufficient health advisory capacity / DFID’s representative on the Trust’s Special Advisory Board will explicitly represent both UNCD and Health Service team perspectives, taking advice widely before attending / Discussions are underway to convene a “funders” trachoma group to include not only the Trust and DFID but also USAID. / Although the donors will not have oversight of the Trust’s work they will receive regular reports on how donations are being used. DFID has, and will continue to, work with other donors to ensure that reporting requirements are applicable and acceptable to all parties to ensure a minimum impact on the Trust team. In turn, the Trust is working with other funders to ensure coherent and streamlined reporting requirements for grantees. / Oversight of the work of the Trust will be carried out by the Board of Trustees, nominated by Buckingham Palace, and this is chaired by Sir John Major. It also includes the Commonwealth Secretary-General and the Governor of the Bank of England. In addition, a Commonwealth Advisory Panel (CAP) will advise and review proposed partners for developing and investing in programmes and projects. This panel comprises of representatives of six Commonwealth countries including Canada, Australia and New Zealand, who are the other main member state donors to the Trust to date. DFID will work with other donors to ensure it keeps up to date with and feeds into the Commonwealth Advisory Panel discussions. / The CAP has been convened by the Commonwealth Secretary General at the request of the Chairman of The Queen Elizabeth Diamond Jubilee Trust and meets every two months. Its purpose is to provide the Chief Executive of the Trust, and through her, the Board of Trustees with counsel on the various activities of the Trust. / This will include: / Identifying opportunities for raising funds for the Trust throughout the Commonwealth / Identifying opportunities for raising awareness about the Trust throughout the Commonwealth / Advising on and reviewing proposed partners for developing programmes and projects / Advising on and reviewing proposed programmes and projects for investment / Day to day management of the Trust is overseen by a Chief Executive working with a small team of around a dozen others. Exact numbers and roles depend of course on the needs of the Trust and are currently shifting from a focus on fundraising to implementation, but are expected over most of the Trust’s lifetime to comprise: four programme staff reporting to a Director of Programmes; three finance, compliance and office staff reporting to a Director of Strategy and Operations; a Director of Policy and a Director of Communications with one assistant. / In recognition of the complexities of the avoidable blindness work, the Trust has also convened an Expert Advisory Panel (now called a Scientific Advisory Board) comprising a number of representatives of academic, diplomatic and partner organisations[70]. The Trust is seeking to expand the membership of the panel slightly to ensure sufficient public health and monitoring and evaluation expertise. DFID has been represented at Deputy Director level since September 2013. The purpose is to provide expert guidance on its strategy and programmes. The Board meets every four months and will initially exist for a period of two years, after which it may be extended for a further three years.
B. What are the risks and how these will be managed? / A complete picture of risks is being built up as the Trust’s programmes develop but the DFID programme team is using this initial risk matrix: / risk impact likelihood mitigation / Financial (including fraud) medium/high low/medium section G, financial case / adverse events in a partner country disrupting and/or requiring change to programming High – possible delays and reduced VFM low Trust mainly operational in stable conditions and will actively monitor risks / Logistical difficulties, difficulties in identifying partners, partners having insufficient capacity. Medium – would reduce VFM medium Trust: Collaborating with existing partners and coalitions able to target programmes according to needs and circumstances of each country. Grant procedures will set out requirements including due diligence, and contracts will be subject to performance monitoring / DFID: Regular dialogue with Trust and other donors represented on Commonwealth Advisory panel; Special Advisory Board membership / Impact mainly limited to middle-income countries and better off in low income countries, for example because of limited transferability of interventions from India to other countries and regions Medium/high: this would not threaten VFM, but would limit the social development impact of the intervention and legacy medium Trust has committed to ensuring learning shared across. DFID engagement on the Special Advisory board and bilaterally / Other assumptions made in the theory of change are not satisfied (section H of the Appraisal case) Low/medium low/medium Flexible approach from the Trust to theory of change and programming as more information, including from evaluation and monitoring, becomes available, should minimise this risk / The Trust’s overall approach to risk management is set out in sections G and H of the Financial case.
C. What conditions apply (for financial aid only)? / No conditions apply.
D. How will progress and results be monitored, measured and evaluated? / DFID has engaged in discussions with the Trust on their monitoring and evaluation strategy, which will be refined throughout the lifetime of the Trust. The strategy is considered to be a “living” document which will be adjusted as the various programmes progress. It will take account of changes in the external context and be used to assess how the projects are progressing and what lessons can be learned. There is an acceptance by the Trust that the strategy needs to improve and we will continue to engage with the Trust on this issue to ensure that it does. A key issue that needs to inform the Trust’s monitoring and evaluation activity is the need to ensure it has data and information about cost-effectiveness. This will both help ensure appropriate prioritisation (and reprioritisation as necessary) of its interventions at the earliest opportunity and on an on-going basis, and inform future projects. / Monitoring / The Trust will collect monitoring information every six months from its grantees and use this to assess progress and to ensure work is being carried out as set out in the grant agreement. Sources of data for monitoring will also include Trust monitoring visit reports and financial reviews of major partners. These will be reviewed and supplemented by information from other sources which will be identified as the programmes progress. Over the lifetime of the programme, it is expected these sources will allow measurement of value for money, such that it can ensure optimal allocation of its funds. For guidance, the appraisal case has set out what can be achieved by similar interventions and the scale of the need that the project is addressing. / Reporting requirements will be set out in the MoU. DFID will monitor progress of the Trust’s work through the log-frame, with progress reviewed and scored annually through the DFID standard Annual Review process. The log-frame will be reviewed at least annually and updated as necessary based on progress to date. The DFID annual review will be based on evidence provided by the Trust through reports based on the outcomes and targets set out in the Trust’s logic model, which the Trust will adjust as necessary as a result of on-going monitoring and evaluation. / Evaluation / This is a significant investment for DFID and at a cost of £50 million requires independent evaluation. This will be done from the project funds and managed by the Trust with DFID’s participation. DFID are working with the Trust to ensure this evaluation meets our and their learning, accountability and decision making needs. Learning needs include the need to test critical assumptions underlying the theory of change. DFID will be able to use the learning to understand whether and how we should support avoidable blindness in the future, particularly diabetic retinopathy and retinopathy of prematurity. / As is clear from the appraisal there are several gaps in the evidence base that planned evaluations will need to address. The most significant of these from DFID’s perspective are: / Level 1: Results / In addition to learning from monitoring, evaluation should generate information on the cost per DALY to allow judgements to be made about the relative VFM of this programme, and of the various interventions. In addition there is a clear need for evaluation to address the evidence gap between the three types of intervention: Trachoma, DP and ROP. The Trust needs to ensure that they fund projects in which learning about the cost effectiveness of different interventions will take place. This means identifying partners who have adequate monitoring and evaluation systems to learn from their interventions and as such they have written these requirements into their draft grants procedures. The final evaluation will in particular need to evaluate the Trust’s legacy and there may be the potential for some evaluation of the impact of the Trust’s work, e.g. by understanding change in beneficiaries’ lives such as income, occupation: we will continue to explore with the Trust whether it is feasible to measure these elements. / Level 2: Organisational Effectiveness / As the business case sets out, securing VFM from this intervention relies as much on the effectiveness of the Trust in bringing parties together and in engaging and influencing stakeholders as it does the actual funds allocated. The Trust needs to learn from their engagement activities and to demonstrate what it is that they add to the funds through their influence and expertise: i.e., what has delivery through the Trust achieved that could not have been achieved by donors working directly with implementing partners (e.g. through advocacy and convening). Evaluating influence can be costly and of limited value. However much can be achieved simply by “projectising” influencing activities and ensuring that alternatives are considered and lessons learned. A decision on whether an evaluation of influencing would be useful can be left to a later date. / Level 3: Engagement / DFID needs to understand the success or otherwise of the match funding arrangement. Evaluation will need to build on the information provided by planned evaluations to understand how the match funding arrangement has added value over the counterfactual, i.e. to what extent DFID funding has attracted “additional” funding. This will require assessment how alternative funds would have been used and their relative effectiveness. / As set out in the Trust’s draft grant procedures, every grant project should have some sort of evaluation component built into it. It is intended that The Trust will commission independent evaluations to report at the mid-term and end of each major programme. The Trust recognises the need to be proportionate and timely. The terms of reference for each evaluation would be drawn up between the Trust and their lead partners, and independent evaluators would be appointed following a commissioning process. The budget the Trust will set aside for this is to be confirmed, but for example for the trachoma programme is foreseen to be around 5% of the total programme. / The Trust will aim to commission the evaluations for each programme during the programme’s first year to ensure there are baseline data and that learning is being captured as the work progresses. In some cases it may be that the lead partner (e.g. Sightsavers) commissions and manages the evaluation: in others the Trust will commission and oversee. Either way, it will be involved throughout to ensure that the evaluations are well managed and properly delivered. The evaluations will be overseen by the Scientific Advisory Board (see Management case section A). There will be an open commissioning process and evaluators’ independence will be part of the specification. / An evaluation steering group will need to be set up to manage the independent evaluations, in addition to a reference or advisory group (which may comprise or build on existing advisory structures). DFID will aim to play an active role in both. / The completed evaluations will be used to inform and prioritise the Trust’s work throughout the period. Senior management will use the information to adjust the Trust’s strategy as appropriate and share key learning points with the Trust Board. The outcome evaluations will be published, as will notes on the implementation of the recommendations. / In addition, UNCD and the Health Services Team will work together to ensure there is an internal review of the success in implementing two complementary trachoma programmes and learning lessons for future collaborative efforts. Terms of reference and process for this review will be agreed in the first year of parallel programming.
Logframe / Quest No of logframe for this intervention: 4180286
[70] Professor Serge Resnikoff, President, International Health and Development; Peter Ackland, CEO, IAPB; Professor Sir Peng Khaw, Moorfields Eye Hospital; Jeanette McKenna, Seeing Is Believing, Standard Chartered Bank; Virander Paul, Deputy High Commissioner for India; Professor Hugh Taylor, University of Melbourne; Keith Mackiggan/Paul Walters, UNCD, DFID; Professor John Dart, Moorfields Eye Hospital; Dr Hannah Faal, Victoria Hospital, The Gambia; Professor Clare Gilbert, London School of Hygiene and Tropical Medicine; Professor GVS Murthy, Director, Indian Institute of Public Health Hyderabad; Dr Anthony Solomon, London School of Hygiene and Tropical Medicine