Type of Review: Annual Review

Project Title: Innovative Metrics and Methods for Cost-Effective Agriculture and Nutrition Programming (IMMANP)

Date started: Approved in March 2013	Date review undertaken: April 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK will provide £7.1m over a 5 year period to stimulate innovation in methods to assess impact in agriculture and human nutrition/health, including the development of novel indicators and metrics. The programme will contribute to the goal of a step change in the generation of high quality evidence linking agriculture and nutrition, which in turn is expected to drive more effective investments by DFID and others. / This support to measuring the impact of agriculture on nutrition is further demonstration of DFID’s global leadership on agriculture and nutrition at a period when this is a high UK priority. It enables us to focus on the delivery of nutritional results through agriculture, an area flagged as important by the UK Prime Minister and the Secretary of State at the Global Hunger Event held in Downing Street in August 2012.
What are the expected results?
The programme aims to contribute to the goal of a step change in the generation of high quality evidence linking agriculture and nutrition. / The outcome from this funding will be to: / Stimulate innovations in robust methodological approaches to impact assessment in agriculture and human nutrition/health, including the development of novel metrics. / The programme is expected to contribute significantly to other existing major initiatives in agriculture, nutrition and health such as CGIAR Agriculture for Nutrition and Health (A4NH) by simulating advances in evaluation methods and metrics. The programme will also act as a facilitator to stimulate the research community to conduct innovative research on methodologies and metrics and share emerging findings. The programme will include a strong capacity building element. This programme would expect to stimulate and contribute to a step-change in evaluation methods and practices in agriculture and nutrition within the research and evaluation community. / Specific deliverables include: / A portfolio of innovative methods and metrics for evaluating the impact of agricultural interventions on nutrition and health outcomes, both qualitative and quantitative; / Peer reviewed publications on metrics and methods in evaluation of agriculture and health research; / Strengthened community of practice, with larger pool of research and evaluation professionals with expertise in this area and greater depth of expertise within the agricultural research and evaluation; / Early career scientists equipped with technical skills and expertise as well as knowledge of application in developing country contexts.

What is the context in which UK support is provided?
Under-nutrition is a major challenge to global human and economic development. It is estimated that almost one billion people globally face hunger and are unable to get enough food to meet their dietary needs. Under-nutrition is associated with one third of all child deaths globally, and 165 million children are stunted. Another one billion people do not get enough vitamins and minerals, which has multiple negative health and development outcomes such as increased morbidity and mortality, and decreased educational achievement. Furthermore, many children are born undernourished because their mothers suffer from poor nutrition during pregnancy. Through this route the burdens of poor health and physical impairment are passed down the generations limiting people’s capability to move out of poverty. / Agriculture is a significant source of livelihoods in many poor countries and, in these settings, is also a major employer of women. There is potential for the agriculture sector to play a critical role in enhancing health and specifically maternal and child health and nutritional status. There is growing interest in this area internationally and the nexus between agriculture and nutrition took leading roles in the 2011 UN General Assembly, and at the Global Hunger Event hosted by the UK Prime Minister in Downing Street in August 2012. / However, policies and systems for agriculture and health are not responding adequately to global nutrition and health needs. Addressing persistent under-nutrition, the growing dietary transition and its serious health effects, the risk of agriculturally-related disease and the links between population health and agricultural productivity requires an integrated approach. / The evidence that agricultural strategies improve the nutrition and health of women and young children derives from a limited number of diverse studies, many of which have methodological limitations. Agriculture certainly holds promise for improving nutrition outcomes, but the evidence base urgently needs to be strengthened with additional methodologically robust research. / This lack of robust evaluation methods and metrics in nutrition sensitive agriculture is a major constraint to developing more effective programmes to address under-nutrition. Initiatives to address this gap will enable DFID to place robust impact evaluation at the heart of DFID’s agriculture and nutrition work. It will encourage and support other organisations to do the same. This in turn will improve our knowledge of how to intervene most effectively to address under-nutrition, and will enhance accountability by allowing the results of nutrition-related investments to be determined and communicated.

## Section A: Detailed Output Scoring

Output 1: Through a competitive procurement process, select a Service Provider to establish a new research programme on Stimulating Innovative Metrics and Methods in Agriculture, Nutrition and Health
Output 1 score and performance description: A Output met expectation
Progress against expected results: / The IMMANP is in its inception phase and there is only one Output for the period under review. / The role of the Service Provider is to establish a new research programme to stimulate innovations in robust methodological approaches to impact assessment in agriculture and human nutrition/health, including the development of novel indicators and metrics. The Service Provider will achieve this by: / Managing a grant fund to support the development of innovative evaluation metrics; / Establishing a network of expertise in this interdisciplinary approach to impact assessment; and / Building capacity and future capability in this area through career fellowships schemes. / The contract for the service provider was competitively procured with Procurement and Commercial Department (PCD), through a two-stage procedure to drive Value for Money through competition. In May 2013 the programme was advertised on the Official Journal of the European Union, and we actively promoted the contract through other sources such as the R4D and DFID external website to maximise coverage. / Two organisations submitted technical and commercial proposals in response to the Invitation to Tender. The award criteria applied to the competition was 70% technical and 30% commercial. The technical criteria focused on: quality, composition, organisation and management of the group/team (35%); and methodology/approach to research (35%). The commercial criteria (30%) focused on: the competitiveness of fee rates; financial planning against key outputs; demonstration of VfM; quality and relevance of key performance indicators; and financial risk management. / The technical proposals were evaluated by a panel comprising of experts from DFID, USAID and the Bill and Melinda Gates Foundation (BMGF). The commercial proposals were evaluated by colleagues in PCD. / Following post-tender negotiations, Ministerial approval to contract the preferred bidder was received in March 2014. We are now in the process of finalising the five year contract, which is due to commence on 1st June 2014. / Recommendations: / Once the contract has been signed an early meeting with the successful bidder should be arranged to discuss the work-plan in detail; / Logframe to be up-dated; / Theory of Change to be finalised. / Impact Weighting (%): 100% / Revised since last Annual Review? Not Applicable / Risk: Low / Revised since last Annual Review? Not Applicable

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / The logframe has still to be finalised and will be up-dated as the programme moves from the inception phase to the implementation phase. / 1.2 Overall Output Score and Description: A Output met expectation. / 1.3 Direct feedback from beneficiaries / Not applicable at this stage.
1.4 Summary of overall progress / A competitive procurement process was undertaken for the selection of the Service Provider for IMMANP. The organisation has not yet been formally announced, as the contract has still to be finalised and signed. The contract is likely to commence on 1st June 2014.
1.5 Key challenges / The skill-sets and expertise in this area of metrics and methods is very limited. In order not to limit the market response for the tender, we stated in the Terms of Reference that the supplier for this contract may also compete for the down-stream research grants. The successful bidder has laid out a robust process with appropriate firewalls to ensure the independence of the selection of proposals and to mitigate any potential for, or perception of, Conflict of Interest. The RED programme team will monitor closely the application of these firewalls to ensure any risk to DFID is effectively managed. The IMMANP steering committee will also play a key role in overseeing selection decisions.
1.6 Annual Outcome Assessment / The expected result this reporting period was the successful procurement of the Service Provider for IMMANP. As outlined above, the programme is on track to achieve this and move forward to the early implementation stage. The first round of grants and fellowships should be awarded towards the end of the next reporting period.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / The contract for the service provider is due to start on 1 June 2014. There has been no spend against the programme to date. DFID will agree a payment plan where payment is released quarterly in arrears on achievement of work-plan milestones. This will ensure a strong focus on delivery throughout the programme. DFID will work with the Service Provider to finalise the implementation work-plan and associated Key Performance Indicators (KPIs). / The financial forecasts will be put in place from June onwards and will be reported in the next annual review. / 2.2 Key cost drivers / Overall costs have been kept to an appropriate level, maximising value for money, by procuring the contract for the service provider competitively. DFID will use the deliverables and milestones in the contract to track delivery of research outputs and outcomes annually. / 2.3 Is the project on-track against original timescale: Yes
3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no evidence emerging that would challenge the design and rationale of the programme at this stage. / 3.2 Where an evaluation is planned what progress has been made? / There will be an independent mid-term review and an end evaluation in the final year of the programme. These reviews are intended to ensure that the programme responds to wider stakeholder interests, including those of developing country stakeholders.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / At the current stage of the programme, the risk of the project not achieving its outputs is low. / The programme has been designed in such a way as to ensure it remains flexible and adaptable to emerging needs. As part of the contracting process, if deliverables and milestones are not being met, payments will be withheld. The mid-term review is intended to ensure that the programme responds to wider stakeholder interests than just those of DFID, including those of developing country stakeholders. / We have built in flexibility to scale up (or scale back) this programme depending on performance and potential impact.
Risk of funds not being used as intended / The overall assessment of financial risk or fraud is considered to be low. Expenditure will be monitored, reported and accounted for in accordance with the terms and conditions of the contract. Payments will be made quarterly and linked to the delivery of results. / 4.4 Climate and Environment Risk / The original assessment that there are low climate and environment risks in this programme remains valid. It does not involve investment in agricultural programmes directly. Instead researchers will add research or evaluation elements to on-going programmes. Developing an additional evaluation component will not impact in any significant way on the climate and environment risks. / However, there will be a climate and environment footprint of the implementing organisations, particularly connected with travel. There will be some climate or environmental impact from this project related to international and local travel and thus carbon emissions. During the post tender negotiations the successful bidder has agreed to decrease the number of face-to-face meetings and going forward will ensure that the carbon footprint of all travel will be monitored and minimised as far as possible.

5. Value for Money
5.1 Performance on VfM measures / Value for Money formed an integral part of the procurement process, with a total of 30% allocated to the assessment of the commercial proposals. PCD were fully involved in the drafting of the TORs and our approach followed best practice through-out. DFID has ensured value for money through both a competitive process and the post-tender clarifications. / The period of this review covers the inception phase of the programme. Therefore, it is not possible to assess performance against all VfM measures mentioned in the business case at this time. / 5.2 Commercial Improvement and Value for Money / Expenditure will be monitored, reported and accounted for in accordance with the terms and conditions of the contract. Payments will be made quarterly and linked to the delivery of results. / There will be an independent mid-term review of the programme after 2.5 years, accompanied by a formal break point in the contract with the service provider. Progression beyond this point is subject to the outcome of this review, strong performance of the service provider and agreement to any revised work plans or budgets. / 5.3 Role of project partners / Not applicable. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? / Not applicable

6. Conditionality
6.1 Update on Partnership Principles (for all programmes) and specific conditions / Not applicable

7. Conclusions and actions
Since IMMANP was approved last year, the programme has progressed as planned. The Service Provider will be in place from 1st June and the programme will move forward to implementation phase.

8. Review Process
The annual review was carried out by the lead adviser and deputy programme manager in April 2014.