Annual Review 2016- Summary Sheet

Title: Strategic Partnerships for Higher Education Innovation and Reform (SPHEIR)
Programme Value: £47m (potential to scale up to £104m)		Review Date: 02 December 2016
Programme Code: 203166	Start Date: 2 December 2014	End Date: 31 March 2025

Summary of Programme Performance
Year	2015	2016
Programme Score	B	A
Risk Rating	M	M

Summary of progress and lessons learnt since last review
This is the second annual review for .Strategic Partnerships for Higher Education Innovation and Reform (SPHEIR). The summary sheet for the previous Annual Review can be found in Annex 1. During the review period, contracting of the Fund Manager (the British Council led consortium that includes PwC and UK Universities International (UUKi) as sub-contractors) was signed on 28 January 2016 and the programme renamed SPHEIR. The Fund Manager (FM) commenced work prior to contract on inception activities on January 1st, in order to enable the programme to move forward as quickly as possible. Overall the inception period was successful in terms of performance and milestones. Key achievements in this period include:
- Selection and contracting of FM consortium
- Establishment of processes and systems needed to manage the fund effectively
- Establishment of governance/strategy systems including an External Advisory Group and a Programme Board
- Selection of two initial partnerships (one focused on Syrian refugees; the other on health workers in Somaliland) and commencement of Grant Stage 1. A possible third partnership has been selected by DFID conditional on its reduction of scale to reduce implementation risk.
- Successful transition of the FM from the formal inception to implementation phase
- Significant outreach and engagement in the UK, Africa and Asia through meetings and events to build awareness of SPHEIR among prospective public and private sector applicants
- Launch of the open call for proposals that will lead to selection of the remaining projects for this phase of SPHEIR

The main lesson learnt concerns communication between the three FM partners. This needs to be frequent and transparent to ensure that SPHEIR fully benefits from the diverse expertise that each brings. The FM has put in place a new structure for work teams that will regularly meet on specific key aspects of SPHEIR (e.g. MEL, Finance & Admin, Outreach and Communications, etc.). All workgroups have cross participation and some workgroups include DFID staff to enhance collaboration.

Summary of recommendations for the next year
For FM
- Significantly improve performance on timely reporting
- Significantly improve the quality of external and intra-consortium communications
- Continue to prioritise private sector engagement to ensure this programme delivers a genuine step-change in the approach to HE support.
- Develop new staffing plan for the implementation phase to ensures that DFID is benefitting from high quality staff who bring the right range of experience and expertise to the task.
- Develop innovative and robust cross-partnership monitoring approach paying particular attention to marginalised groups.
- Present ambitious options to DFID for driving down costs, improving delivery and leveraging additional funding
- Develop Vfm strategy
For DFID
- Procure external evaluator and support FM and evaluator to work closely together
- Ramp up scrutiny of risk as programme moves into implementation phase.

Recommendations and Actions from the 2015 Annual Review
Action	Responsible	Deadline	Status
The fund manager contract contains a number of special conditions agreed through the negotiated process. / These will need careful monitoring and should be transferred into the PHE delivery plan.	DFID Programme Manager (Colin McGinty)	Ongoing from start of contract (From 27 Jan 2016)	Completed
DFID risk matrix updated with new risks emerging from procurement and inception phase	DFID Programme Manager (Colin McGinty)	By end of inception phase (31 Jul 2016)	Completed – see Risk section in this AR.
Prioritise the procurement of the evaluation manager	DFID Programme Manager (Colin McGinty)	Immediately (From 2 Dec 2015)	Not completed – this action was delayed due to staffing constraints but is now being undertaken. Procurement will be complete by April 2017 in time for the selection of the open call partnerships
Agree the strategic plan and workplan as soon as possible once the contract is signed	Fund Manager and DFID Programme Manager (Colin McGinty)	Immediately (From 2 Dec 2015)	Completed
The first task for the Fund Manager will be to provide a revised workplan for inception with key milestones indicating what (and when) input is required from DFID. These should be transferred into the PHE delivery plan.	Fund Manager and DFID Programme Manager (Colin McGinty)	During month 1 of contract (27 Jan – 26 Feb 2016)	Completed
Agreeing VfM metrics during inception phase will be a priority to ensure VfM can be monitored and benefits and savings tracked through the programme	Fund Manager and DFID Programme Manager (Colin McGinty)	By end of inception phase. (31 Jul 2016)	Not completed – following discussions with the FM, DFID has agreed that these metrics should be agreed once partnerships have been selected
Revise the logframe to reflect delays and new timelines and merge with results logframe so there is a single comprehensive framework, agreed by DFID, for the remainder of the programme.	Fund Manager	By end of inception phase. (31 Jul 2016)	Completed – a single logframe has been developed. The indicators for this will be agreed once partnerships have been selected.

Action	Responsible	Deadline
Ensure timely submission of reports continues to feature in new KPIs to incentivise improvements in reporting and task programme board with monitoring performance on timely reporting. / Achieve quality external communications with the aim of developing a reputation for outstanding communications performance. The FM should ensure the programme is using digital and traditional communications channels in an innovative manner to project a compelling and dynamic vision of the potential of HE reform and draw in new players. This should include dynamic in-person events, creative use of infographics and social media in communicating lessons to the HE and development sectors. / Achieve a standard of intra-consortium communications that demonstrates how multi-organisation consortia can add value to fund management for DFID by drawing on the full range of expertise offered by the three consortium members	Fund Manager	January 2017 / Ongoing (review quarterly) / Ongoing (review quarterly)
FM should continue to actively engage the private sector during the open call and within selected partnerships to ensure this programme includes new entrants into the HE systems in targeted countries / A new and streamlined staffing plan for the implementation phase should be agreed which ensures that DFID has confidence that the FM is benefitting from high quality staff who bring the right range of experience and expertise to the task. / The new outreach and communications lead should include utilisation of the EAG where possible to ensure the programme is benefitting from their expertise and extensive networks.	Fund Manager	Ongoing / January 2017 / Ongoing
The FM should aim to set a new standard in how multi-partner programmes can develop consistent and robust monitoring approaches. Objective indicators and standardised tools should be developed which draw on the latest thinking and research (for example on measuring learning outcomes, effective pedagogy, inclusion of marginalised groups etc.). / The FM should pay particular attention to marginalised groups and should set out a strategy for how partnerships will monitor and assess the impact on marginalised groups including women and people with disabilities. / The FM should ensure they provide clear guidance to all partnerships on data sources, tools and roles and responsibilities (between the MEL central team and projects) before the projects start designing their M&E. / The FM should work closely with individual partnerships to ensure they develop fit for purpose MEL strategies which should include ambitious plans for engaging and influencing relevant stakeholders including partner governments and sector bodies. / External evaluator should be procured by April 2017 and DFID should support FM and evaluator to work closely together	Fund Manager	July 2017 / March 2017 / July 2017 2017 / November 2017
FM to present ambitious options to DFID for driving down costs, improving delivery and leveraging additional funding. / Vfm strategy to be developed further to outline how Vfm at partnership level will be scrutinised. This should be agreed as soon as possible to ensure it is incorporated into workplans of the initial partnerships.	Fund Manager	December 2016 / March 2017
FM to simplify risk matrix and classify risk by type / FM to propose potential risks to the external environment and add this as a new category to register. / DFID and FM to ramp up their scrutiny of risk as programme moves into implementation phase. Risk management will be a key feature of quarterly joint FM/DFID meetings. / A system to ensure risks are identified quickly and escalated appropriately should be agreed.	DFID and FM	January 2017 / January 2017 / Ongoing (quarterly) / January 2017
The logframe indicators will be finalised once partnerships have been selected. The FM and DFID should agree ‘process’ indicators which will be used to assess progress at next Annual Review by the end of January 2017. / They should then prioritise finalising other indicators early in grant stage 1 of the open call partnerships and should include collecting baseline data on these indicators as a milestone for next Annual Review.	DFID and FM	January 2017 / November 2017

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203166/ / NB: Business case is not currently published as commercial negotiations are ongoing
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203166/

DFID is ramping up its support for Higher Education in recognition of the crucial role it plays in driving the transition out of aid dependency.

Graduates of Higher Education will play a disproportionate role in future governance and support for HE is an important way in which we can support the emergence of tolerant, critically-thinking leaders of the future. In addition HE can make vital contributions to economic growth providing that it is tailored to achieve this. Crucially, there is a need to ensure HE is developing entrepreneurs who will create more economic opportunities and job-ready graduates with the mix of skills needed to respond to these.

The UK has a particularly world-class HE brand, with four of the top eight universities in the world in the UK, and this makes it well placed to support development of the HE sector globally. Support for research and HE can also build the UK’s credibility and influence which in turn can support UK trade and political engagement in the longer term.

DFID is investing up to £47m in Strategic Partnerships for Higher Education Innovation and Reform (SPHEIR) with two clear aims:
- To improve the quality and relevance, scale and affordability of Higher Education (HE) in DFID focus countries (to make HE more accessible to underrepresented groups, and enable graduates to be active, productive citizens)
- To improve the performance, governance and influence of HE systems and HE institutions in DFID focus countries (so they function effectively and produce knowledge and high quality graduates that has positive effects on inclusive growth and delivery of services)

SPHEIR will support new, high value, partnerships, operating at several levels within the HE system i.e. within a single institution, or across a number of institutions including, for example, quality assurance and funding bodies. The programme will shape and incentivise demand for partnerships to address identified issues in the HE system, including:
- Preparation of HE systems in low income countries for the future, building on learning from other contexts;
- Attracting new types of players within the HE system, such as funding and quality assurance bodies and private sector partners (private providers and employers) to get a dynamic and multi-disciplinary group of experts to focus on solutions to complex issues, such as graduate employability;
- Testing new models of delivery at scale, including online delivery.

The expected results of the interventions are:
- Direct results:
  - Attracting new types of players within the higher education system, such as funding and quality assurance bodies and private sector partners (private providers and employers).
  - Opening up higher education to females and disadvantaged groups.
  - Improving graduate employability.
- Policy and regulatory systems: Supporting partnerships to provide technical advice around data management, standards and transferability of qualifications.
- Evidence: Testing new models of delivery at scale, including online delivery.
- Sharing UK expertise: Promoting a “UK offer” on what works in higher education.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment
When this programme was established, an initial ‘Process Logframe’ was developed to cover the initial contracting and inception period. The stated outcome is “Partnerships in Higher Education programme established and delivering initial activities”. This outcome has been achieved.

The programme logframe has now been drafted with the following outcome statement: “Sustained improvement in HE governance and management, equitable access, teaching, and learner experience and outcomes”. While the partnerships selected to date have not yet initiated activities, the overall strategy and management systems which the FM have put in place provide a high degree of confidence that the outcome will be achieved.

Overall output score and description
The overall output score is A based on the outputs of the ‘Process Logframe’. While there are a few areas where some improvements are needed, overall progress has been good with many examples of the FM significantly improving the chance of programme success.

Key lessons
A number of areas of performance which were particularly positive are outlined below:

- Flexibility: The fund manager demonstrated considerable flexibility in adapting to launch an initial call for proposals in Spring 2016 well in advance of the end of inception target date. DFID requested that one partnership selected through this call should focus on Syrian refugees – and the FM team leader invested a great deal of time gaining understanding of the HE for refugee sector and building links with key actors. This work ensured that a good number of applications from credible organisations were received and that the fund manager had the necessary background knowledge to appraise these.
- HE expertise: The fund manager’s expertise in HE has led to important adaptations to the programme which will increase its likelihood of success. For example, DFID had originally suggested that the FM run a series of calls for proposals throughout the programme. The fund manager carried out analysis of the model partnerships and identified that holding later calls for proposals would mean that projects would not have enough time to achieve results. This is in part due to the general need for long time-frames for capacity building projects – but also due to some particular features of the HE sector – e.g. the need for some projects to wait until the beginning of an academic year to start, the need to gain approval from University Senates and in many cases Ministries and/or national higher education authorities.
- Rigorous grant selection process: DFID has been impressed by the online application system and selection process. The FM ensured that the process was transparent and that applicants were clear on the selection criteria to be used. The process drew on the expertise offered by each consortium partner as well as external experts to inform application scoring and to determine the ‘initial short-list’ of potential partnerships. All partnerships on the initial short-list were subjected to due diligence assessments, DFID and British Council country-office consultations and interviews. The FM then proposed a final short-list of partnerships accompanied by its recommendations, and selection decisions were made by DFID. The FM used the initial call to test out this approach and has made some minor modifications (for example, improving the guidance provided to reviewers to enhance consistency and reduce the time needed to accommodate a larger number of reviewable applications) to revise the on-line application form to enhance usability for wider variety in applications expected for the open call.
- Expertise of consortium partners: Both PwC and UUKi have brought vital inputs to the inception period drawing on their areas of expertise and networks. PwC’s input into both the private sector strategy and the Monitoring, Evaluation and Learning strategy have been exemplary. Similarly, the knowledge of the UK HE sector which has been added by UUKi’s involvement has been outstanding and has significantly increased the likelihood of UK universities developing credible partnership proposals. The British Council’s network of country offices, as well as broader knowledge networks in HE, has been advantageously used to conduct information sessions on the open call and convene successful live and webinar events.

DFID has also identified some areas for improvement in performance as outlined below:
- Intra-consortium communication: There have been some instances of poor communication between consortium members. There is a need to ensure that communication is regular and transparent and that programme delivery is benefiting fully from all the areas of expertise which the different members of the consortium bring.
- External communication: Some areas of external communications have not been of the standard we would expect. In particular, there has been a concern that some oral presentations have not been dynamic and engaging; that new ways of communicating including use of infographics and social media have not been capitalised on adequately; and that guidance and contractual requirements on interactions with the media have not always been followed.
- Timely reporting: Throughout the inception period there have been instances of reports being delivered late.

Key actions

Adjustments in FM team composition and roles have recently been made or are in process that are intended to enhance communication and reporting while also positioning the FM team to provide technical guidance and monitoring to the full portfolio of partnerships that will become operational in the coming review period.

Has the logframe been updated since the last review?
Yes, for the inception phase a simplified ‘Process Logframe’ has been used to assess progress. One of the targets on the process logframe was the development of a draft theory of change (Annex 2) and logframe (Annex 3) for the implementation phase. Because of the variety of partnerships anticipated across the SPHEIR project portfolio, the theory of change and logframe will evolve further and will also be informed by the activities of the independent evaluator currently being sourced by DFID.
.
## C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	Fund manager contracted and delivering effectively against contract requirements
Output number per LF		1	Output Score	A
Risk:		n/a (risk was not assessed in the process logframe)	Impact weighting (%):	35%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
Status of fund manager procurement process	Fund manager contracted	Fund Manager contract signed 28 January 2016	A
Fund manager performance on KPIs	Fund Manager performing adequately and scoring 4 or more against the KPI measurement standards.	Fund manager has scored an average of 4 however it scored 3 on one KPI	A/B

Key Points
FM selection and contracting was completed by the end of January 2016. Inception phase of the programme was started early (in advance of formal contracting) to accelerate activities and fast track some early activities that would have waited for the formal implementation phase – specifically the design, launch and selection of partnerships through an initial call for proposals launched in May 2016 and concluding with selection/recommendations to DFID concurrent with the end of inception in July 2016. The inception period was successfully concluded by the FM and inception report approved by DFID in September 2016. The programme was approved to transition into implementation at that time.

The Fund Manager scored 3 on the KPI ‘Timeliness/quality of reporting’. The FM has acknowledged that this is a key area where improvements are needed and understands that they need to submit documents on time or, where possible, ahead of deadlines or to give DFID good notice, and agree with DFID in advance, where not possible. The Programme Board set up by the consortium to provide strategic oversight to the SPHEIR programme will monitor improvements in this area. All other KPIs scored 4 or above (see Annex 2).

There were some concerns regarding the FM’s communications approach. There were some examples of high quality outputs (e.g. branding guidelines, website, private sector engagement) however there were also areas where communication was not of the quality we would expect. In particular, there were some instances when social media engagement was underutilised and in-person presentation were not as dynamic as we would wish. Internal communications were also problematic at times. It is vital that communications between consortium partners is effective so that DFID gets the full value from all three organisations in the consortium.

Summary of responses to issues raised in previous annual reviews (where relevant)
The strategic plan and workplan were developed and monitored and special conditions were added into the contract and workplan as recommended.

Recommendations
•	Ensure timely submission of reports continues to feature in new KPIs to incentivise improvements in reporting and task programme board with monitoring performance on timely reporting.
•	Achieve quality external communications with the aim of developing a reputation for outstanding communications performance. The FM should ensure the programme is using digital and traditional communications channels in an innovative manner to project a compelling and dynamic vision of the potential of HE reform and draw in new players. This should include dynamic in-person events, creative use of infographics and social media in communicating lessons to the HE and development sectors.
•	Achieve a standard of intra-consortium communications that demonstrates how multi-organisation consortia can add value to fund management for DFID by drawing on the full range of expertise offered by the three consortium members
Output Title	Initial implementation strategy designed and ongoing systems for strategic oversight in place
Output number per LF		2	Output Score	A
Risk:		n/a (risk was not assessed in the process logframe)	Impact weighting (%):	35%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress	Score
Status of inception report	Inception report approved by DFID	Revised Report approved by DFID 7 October 2016	A
Status of the strategic programme plan including an annual work plan	Inception workplan agreed and draft implementation workplan proposed	Draft implementation workplan proposed	A
Status of External Advisory Group (EAG)	EAG formed and have held at least one face to face meeting	EAG formed and first face to face meeting held on 13 July 2016.	A

Key Points
The inception report was completed satisfactorily and on time. DFID appreciated having a clear outline of the programme design and it was useful to have all the strategies and processes collected in one place. There were areas of strong analysis, however, the report was very lengthy and further streamlining of future reports is recommended.

A highlight of the inception report was the private sector strategy which demonstrated innovation and a good understanding of the sector. This was followed through with in-depth engagement with private sector actors in the lead up to the open call. Sustained engagement will be needed to ensure we get the most from private sector involvement. The FM is exploring running a separate ‘innovation window’ which is likely to be particularly attractive to ‘start-up’ companies not operating at the scale necessary for the open call. They will also be examining the make-up of the winning proposals and, if useful, proactively brokering links with private sector actors during Grant stage 1.

The inception workplan was agreed and used to monitor delivery throughout the inception period. The draft workplan for the implementation period has been proposed and will be modified further as part of ongoing discussions related to the contract. In particular, there is a need to reconfigure the FM team to ensure the team has the right mix of skills for the implementation phase.

An External Advisory Group chaired by DFID’s Chief Scientific Advisor and consisting of experts from the HE and private sectors has been formed. In addition to its initial annual meeting, has supported outreach activities in the UK and Africa, as well as in providing comments on the concept note for the current open call. In addition, a Programme Board, chaired by the British Council Director of Education and Society and consisting of senior representatives of each of the consortium partners meets regularly to oversee strategy developments and deal with any emerging risks. The DFID SRO regularly attends the Programme Board meetings and this has helped to ensure close alignment of strategy with DFID priorities.

Recommendations
- FM should continue to actively engage the private sector during the open call and within selected partnerships to ensure this programme includes new entrants into the HE systems in targeted countries
- A new and streamlined staffing plan for the implementation phase should be agreed which ensures that DFID has confidence that the FM is benefitting from high quality staff who bring the right range of experience and expertise to the task.
- The new outreach and communications lead should include utilisation of the EAG where possible to ensure the programme is benefitting from their expertise and extensive networks.
Output Title	Fit for purpose monitoring and evaluation strategy in place
Output number per LF		3	Output Score	A
Risk:		n/a (risk was not assessed in the process logframe)	Impact weighting (%):	30%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress	Score
Status of programme theory of change and logframe	Revised theory of change and logframe co-designed by Fund Manager and DFID (to be further modified based on project selection)	A revised theory of change and logframe has been approved by DFID and can be found in Annex A	A
Status of evaluation plan and procurement	TORs for evaluation quality assured by SEQAS and procurement process for evaluation agreed with PCD	TORs and evaluation criteria have been finalised and procurement will be initiated imminently.	A

Key Points
The provisional Monitoring, Evaluation and Learning (MEL) strategy developed by the FM is exceptionally well thought through. The FM’s approach to how the programme level MEL will inform, and be in-formed, by the respective MEL of each individual partnership is thoughtful and conceptually sound. Some initial testing of this has been done with the initial partnerships and the revised SPHEIR logframe attached to this review reflects input from this engagement. The MEL and evaluation plan will evolve considerably during the next review period as the full portfolio of projects takes shape and the external evaluator starts working. Key priorities will be developing indicators which enable robust comparison of both output progress and Vfm (see also Section D) across partnerships.

Broader evaluation of SPHEIR will be informed by the external evaluator currently being selected by DFID, as well as by the use of “mini impact evaluations” from selected partnerships that the SPHEIR team will be seeking. The external evaluation will combine process evaluation, impact evaluation and linked primary and secondary research projects. This innovative approach will ensure that the evaluation is genuinely delivering useful information that will complement the MEL strategy of the FM.

Summary of responses to issues raised in previous annual reviews (where relevant)
As recommended:
- The process for procurement of the evaluation manager has been initiated
- The process logframe was revised to reflect delays in FM procurement

Recommendations
- The FM should aim to set a new standard in how multi-partner programmes can develop consistent and robust monitoring approaches. Objective indicators and standardised tools should be developed which draw on the latest thinking and research (for example on measuring learning outcomes, effective pedagogy, inclusion of marginalised groups etc.).
- The FM should pay particular attention to marginalised groups and should set out a strategy for how partnerships will monitor and assess the impact on marginalised groups including women and people with disabilities.
- The FM should ensure they provide clear guidance to all partnerships on data sources, tools and roles and responsibilities (between the MEL central team and projects) before the projects start designing their M&E.
- The FM should work closely with individual partnerships to ensure they develop fit for purpose MEL strategies which should include ambitious plans for engaging and influencing relevant stakeholders including partner governments and sector bodies.
- External evaluator should be procured by April 2017 and DFID should support FM and evaluator to work closely together

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
The main costs in the programme are:
- Partnership Funds: 84% of the total budget will be allocated to partnerships
- Fund manager fees and expenses: 16% of the total budget This cost can be further categorised as technical inputs (10% of total budget) and management inputs (6% of total budget)
- Evaluation manager fees and expenses. £2m has been set aside for evaluation.

VfM performance compared to the original VfM proposition in the business case
The business case sets out that VfM will be achieved through the competitive procurement of the FM and competition for and oversight of grants by the FM. The procurement of the FM was more challenging than anticipated due to poor market response. Contract negotiations reduced the cost of the FM’s offer, as well as increased the value of the offer. It is possible that greater market response might have increased DFID’s ability to further drive down costs, but it may not have, or may have resulted in the option of a lower cost FM that would not bring the same combination of experience and sector knowledge. The market response to the open call for proposals is anticipated to be high and thus we are confident that the FM will be able to select proposals which demonstrate maximum value for money.

Assessment of whether the programme continues to represent value for money
The overall cost of the FM is relatively high compared to some other externally managed funds. The FM is delivering a good quality of service and development of the programme is benefitting from expertise which would not be available if the programme was managed in-house. Nevertheless, in consultation with the FM, we are exploring opportunities to achieve better value for money in the future in the following ways:
- Economy/Efficiency: The FM is exploring whether costs can be reduced as part of the reconfiguration of the budget for the implementation phase. One opportunity to reduce costs will be if the overall number of partnerships is lower than originally anticipated.
- Effectiveness: The FM is reviewing the team composition and will propose a reconfigured team which is optimised to deliver the implementation phase.
- Leverage: DFID and the FM are proactively exploring whether other funding could be ‘channelled’ via SPHEIR. Additional funders would benefit from investment in setting up systems and could benefit from significantly reduced overheads.

Quality of financial management
There have been issues with late delivery of reports. The FM reports that this has been due to staff shortages in the programme management team and that these have now been resolved. KPIs for the implementation phase will ensure that timely and accurate financial reporting is incentivised.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous review recommended establishing Vfm metrics. The Vfm strategy has been discussed at length with the FM and we have agreed that having fixed quantitative targets for unit costs may lead to perverse incentives since the costs of achieving certain activities/outcomes will vary hugely by context. Instead, we have agreed that unit costs will be calculated for different partnerships and the FM will scrutinise whether these represent value for money for that context.

Recommendations
- FM to present ambitious options to DFID for driving down costs, improving delivery and leveraging additional funding.
- Vfm strategy to be developed further to outline how Vfm at partnership level will be scrutinised. This should be agreed as soon as possible to ensure it is incorporated into workplans of the initial partnerships.
Date of last narrative financial report	n/a[1]
Date of last audited annual statement	n/a[2]
[1] First annual narrative financial report will be submitted April 2017 and will cover 15 month period
[2] Audited annual statements will be received for future review periods once the partnership funding has been established.

E: RISK (½ page)
Overall risk rating: Moderate
Overview of programme risk
The risk register for this programme has been updated and is included as Annex 5. In addition, the fund manager has produced its own risk matrix and this has been signed off by DFID through the inception report. Both risk registers are living documents which are reviewed regularly by senior staff.

As the programme moves into its implementation phase, DFID and the FM will ramp up their scrutiny of risk. DFID is satisfied that the FM has accurately identified risks and thought carefully about mitigation, however the risk matrix at present is quite complicated and different types of risk are intermixed. We would therefore recommend that the risk matrix is simplified and risks classified into categories (e.g. reputational risks, fiduciary risks, implementation risks etc). An additional category of risks to the external environment (e.g. risks of inciting conflict etc) will be added.

Summary of responses to issues raised in previous annual reviews (where relevant)
As recommended, the risk register has been updated.

Recommendations
- FM to simplify risk matrix and classify risk by type
- FM to propose potential risks to the external environment and add this as a new category to register.
- DFID and FM to ramp up their scrutiny of risk as programme moves into implementation phase. Risk management will be a key feature of quarterly joint FM/DFID meetings. A system to ensure risks are identified quickly and escalated appropriately should be agreed.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
The FM has delivered overall on the milestones and measures agreed. Spot-checks has been carried out on their fees & expense with a slight saving being made. Financial reporting has recently been agreed to move to quarterly reporting. An agreed new timeline and work plan is in place.

Performance of partnership (s)
SPHEIR’s two initial partnerships were selected and commenced Grant Stage 1 during this review period. Both are expected to commence full operation early in the next review period. A third partnership conditionally selected by DFID may also commence full operation early in the next review period. Should it not satisfactorily address the requirements set out to satisfactorily scale down its proposal, the roughly £2 million budget will be reallocated to the open call selection.

The current open call closes in February 2017 and is expected to result in the remainder of the SPHEIR project portfolio becoming operational near the end of the next Annual Review period. The next Annual Review will therefore be reporting on actual performance of partnerships, although some will be close to the end of a full year of operation while others in the early stages.

Asset monitoring and control
Not applicable. The programme has not yet accumulated any assets, Once established spot-checks by DFID and the Fund Manager will be carried out t at 6 monthly intervals. Each of the downstream partners will be required to include this in their ‘Partnership agreement’
G: CONDITIONALITY (½ page)
Update on partnership principles (if relevant)
Not applicable

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
SPHEIR’s broad design was informed by the work of DFID’s higher education task force established in 2012. It considered a range of research and policy evidence associated with higher education reform in developing countries, but was also constrained by the fact that the evidence base for “what works” in HE reform in LICs is in fact quite limited. One of the reasons for this was the significant decline in donor support for higher education in LICs/LMICS prior to and during the MDG period – precisely the situation that prompted DFID to set up the task force.

SPHEIR’s design continues to adapt based on emerging academic literature.[3] Design also draws on practical experience and evidence accrued from specific examples of HE reform, mostly though not exclusively in Africa. This includes:
[3] Relevant publications include World Bank Support for Regional Post-Graduate Education and Research Initiatives and Networks in Sub-Saharan Africa, Mouton and Fine, 2011; The Impact of Tertiary Education on Development, Oketch, McCowan and Schendel, 2014; Higher Education in Africa: A Case and a Model for the Transformation of Higher Education, Clay, 2016; Higher Education for Long-Term Refugees in Dadaab Camps, Kenya, Giles, Gitome, Dryden-Peterson, Dippo, Hyndman, Mensah and Orgocka, 2013; Introduction: Higher Education for Refugees, Dryden-Peterson and Giles, 2011; How to Redesign a College Course Using NCAT's Methodology, National Centre for Academic Transformation, 2014; Tertiary Education and the Sustainable Development Goals: In Search of a Viable Funding Model, Salmi, 2016
- HE initiatives focused on “collaborative” HE (multiple universities in multiple countries involved in delivery of common curricula and standards), such as AERC’s three post-graduate programmes and PASGR’s Master of Research and Public Policy programmes
- Programmes which focussed more on the systems and processes within HE institutions such as DFID’s Strengthening Research and Knowledge Systems programme; the Wellcome Trust’s African Institutions Programme and the World Bank Higher Education Centres of Excellence.

DFID has been impressed by the thought and expertise which has gone into the Monitoring, Evaluation and Learning strategy (see also Output 3 above). There is a risk that such strategies can become ‘tick-box’ exercises but in this case it is clear that the MEL lead has facilitated genuine engagement with the team to develop the strategy. The theory of change, which sits at the heart of the strategy is informed by evidence and experience of the HE sector in developing countries. The logframe flows clearly from this theory of change and will provide an excellent framework for tracking programme progress. The indicators for the logframe are indicative at this stage however the FM and DFID have discussed a strategy for developing these through consultation with partnerships.

Monitoring progress throughout the review period
Since partnerships have not yet been initiated, monitoring has only been of the FM itself. Monitoring has been carried out through written reports and frequent FM meetings. As noted previously, there have been some issues with timely submission of reports. Nevertheless, once submitted, reports have generally been of good quality with the inception report being a particularly useful update on progress and record of processes and systems established. The regular FM have been very useful however as the programme proceeds to implementation the FM and DFID have agreed that there is a need to establish working groups (e.g. on MEL, finance etc) rather than having meetings involving the entire DFID and FM team.

Recommendations
The logframe indicators will be finalised once partnerships have been selected. The FM and DFID should agree ‘process’ indicators which will be used to assess progress at next Annual Review by the end of January 2017. They should then prioritise finalising other indicators early in grant stage 1 of the open call partnerships and should include collecting baseline data on these indicators as a milestone for next Annual Review.

Annex 1: Annual Review 2015 - Summary Sheet
Title: Partnerships in Higher Education (PHE)
Programme Value: £52m (potential to scale up to £104m)		Review Date: 02 December 2015
Programme Code: 203166	Start Date: 02 December 2014	End Date: 31 March 2025

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020	2021	2022
Programme Score	B
Risk Rating	M

Summary of progress and lessons learnt since last review
This is the first annual review for Partnership in Higher Education (PHE). Since business case approval the bulk of the year has been focused on identifying a strong fund manager to provide a combination of high quality technical support to the sector to broker and develop high quality multi-stakeholder partnerships that can bring transformative change to the system, and robust and transparent selection and management of funded partnerships in line with DFID expectations.

An initial international competitive procurement process using OJEU Restricted approach produced a single bid that lacked sufficient ambition and quality to award a contract. DFID subsequently used OJEU’s negotiated tender approach which allowed it to enter into negotiations with this supplier resulting in a significantly improved bid. While the total procurement process has taken longer than anticipated this is largely a result of essentially having to run 2 separate tender processes – the initial failed restricted procedure followed by a negotiated procedure. However, this delay is offset to some degree by the fact that we now have:
- A much improved final bid with stronger accountability mechanisms
- Already resolved/partially resolved some issues that normally form part of inception phase
- Built an initial working relationship with the preferred supplier allowing quicker mobilisation

The uncertainty around both the outcome of the fund manager position and the wider higher education portfolio has meant that the evaluation manager position has only just been internationally tendered meaning there will be a time lag between the fund manager starting and the evaluation manager coming on board. Clearly this is not ideal and some key activities such as the development of the monitoring and evaluation strategy will be affected.

Summary of recommendations for the next year
1. The full list of recommendations for next year are below:
  1. The fund manager contract contains a number of special conditions agreed through the negotiated process. These will need careful monitoring and should be transferred into the PHE delivery plan.
    1. Who: DFID (Colin McGinty) When: Ongoing from start of contract
  2. The first task for the Fund Manager will be to provide a revised workplan for inception with key milestones indicating what (and when) input is required from DFID. These should be transferred into the PHE delivery plan.
    1. Who: Fund manager and DFID (Colin McGinty) When: During month 1 of contract
  3. Prioritise the procurement of the evaluation manager
    1. Who: DFID (Colin McGinty) When: Immediately
  4. Revise logframe to reflect delays and new timelines and merge with results logframe so there is a single comprehensive framework, agreed by DFID, for the remainder of the programme.
    1. Who: Fund manager When: By end of inception phase.
  5. Agree the strategic plan and workplan as soon as possible once the contract is signed
    1. Who: Fund manager and DFID (Colin McGinty) When: Immediately
  6. DFID risk matrix updated with new risks emerging from procurement and inception phase
    1. Who: DFID (Colin McGinty) When: By end of inception phase.
  7. Agreeing VfM metrics during inception phase will be a priority to ensure VfM can be monitored and benefits and savings tracked through the programme
    1. Who: Fund manager and DFID (Colin McGinty) When: By end of inception phase.
Annex 2: Draft Theory of Change

Annex 3: Draft Logframe

Annex 4: KPI scores and comments

- Timeliness/quality of reporting: Score 3: FM needs to submit documents ahead of deadlines and to give DFID good notice, and agree with DFID in advance, where not possible. The Programme Board set up by the consortium to provide strategic oversight to the SPHEIR programme will monitor improvements in this area.
- Risk mitigation: Score 5: The FM submitted a good risk register with the inception report. The big risks around timing were flagged, which demonstrated the FM are thinking ahead to identify potential challenges and escalating them when appropriate.
- Communication: Score 4: Scope for improvement in some areas e.g. adequate meeting minutes
- Continuous improvement (including VfM): Score 4: There are good example of the fund manager achieving VfM but also some areas for improvement including ensuring they achieve maximum VfM in any events and minimising travel/accommodation costs.
- Delivery of results: Score 5: All of the milestones were delivered on time, 2 of 4 ahead of schedule, during a fluid and fast paced inception.
- Consortium management: Score 4: The consortium has had a mixed inception. There are positive examples of the FM benefiting from the diversity of expertise in the consortium but also some examples where poor communication between partners has hampered delivery.
- Programme Management Unit performance on this programme: Score 4: No specific comment
- Wider team performance on this programme: Score 4: The wider team have delivered their objectives, but DFID would like to see more evidence of the wider influence / additional activity to show how they delivered above contractual expectations.

Annex 5: Risk Matrix

RISKS
The risk table below sets out the key high level risks assessed for the 2016 Annual Review. The Risk matrix is a living document which will be reviewed throughout the lifespan of the project. A more detailed risk dashboard at operational level and mapped against the log frame is now in place and operational by the fund manager. A further review of risk will be carried out as the programme moves into the implementation phase (December 2016) .

RISK	MITIGATING ACTIONS	LIKELIHOOD	RESIDUAL RISK	IMPACT
Poor performance of fund manager reduces, hinders or delays programme success	Payments linked to performance through KPIs to incentivise high performance / DFID officials regularly monitor agreed KPIs and associated milestones and targets to manage performance / Iterative delivery approach creates opportunities to review performance, agree new measures and terminate contract if necessary / Contract break points allow sufficient time to select new fund manager if necessary / Financial forecasting is accurate and robust thus ensure VFM is achieved	Moderate	Moderate	Major – The Fund manager & its partnership (Consortium) role is critical to the successful delivery of the programme. / Poor Financial forecasting & budgets will have an impact on project delivery
Insufficient level and quality of demand to meet the extent of the programmes ambition	The iterative delivery approach will help DFID to better understand demand and create opportunities to adapt its response accordingly / The programme provides attractive incentives for a wide range of partners to engage	Moderate	Minor	Moderate
Partnerships involving a range of partners from different sectors take time to establish	Fund manager proactively generates a pipeline of strong partnerships / Fund manager identifies and shares lessons from best practice / Due diligence helps to identify partnership specific risks and establish and manage a partnership level risk matrix / Fund manager provides support to partnerships ensuring they are equipped to deliver	Major	Moderate	Moderate
Partnerships are not sufficiently aligned to DFID, country or regional strategic priorities	Country offices help to identify appropriate partnerships and assess partnership proposals / In country coordination of partnerships and country office engagement by Fund Manager	Minor	Minor	Moderate
Lack of measurability of programme goals making it difficult to hold partnerships to account	Tools for measuring impact of partnerships are developed and communicated clearly to partnerships from the outset / Partnerships supported to produce robust reporting mechanisms that allow for results to be aggregated to fund level wherever possible / Evaluation manager and fund manager design an appropriate monitoring and evaluation strategy, including fund level results logframe / SMART comparable indicators are set, baseline is collected and performance tracked	Moderate / Major?	Moderate	Major – A failure to gather appropriate baseline data and track the right indicators will hinder the future of the programme, minimise capacity to influence governments, HEIs and policy and reduce DFID value for money
Partnerships lack capacity and capability to deliver results	Robust criteria for assessing partnership bids / Due diligence helps to identify partnership risks enabling a more tailored and proportionate management approach / Technical and management support provided by fund manager	Moderate	Minor	Moderate
Results not embedded to last beyond the programme	New approach to partnerships embeds effective processes and practices at several levels of an institution, or group of institutions, so higher likelihood of work continuing beyond lifetime of Partnerships for Higher Education / Multi-partner approach provides greater networking opportunities and helps to share risks around future investment / Dissemination of learning and best practice through DFID (policy team, country offices, HoP, EPE, etc) and the wider sector through DFID and fund manager networks	Moderate	Moderate	Moderate
Partnerships delivering in fragile and conflict affected states and other high risk environments may constrain impact of the programme	The fund manager, DFID and steering committee will ensure the portfolio remains a balanced geographic, thematic and risk profile. / The Fund Manager will manage partnerships proportionately based on risk profile of partnerships (e.g. duration, value, location, etc) established from due diligence checks	Moderate	Minor	Moderate / Major?
Partnerships lack sufficient financial capacity and capability increasing the opportunity for fraud or mismanagement of funds	Due diligence checks will assess financial capacity and capability / Fund manager will provide management support to inexperienced partnerships / Regular programme of spot checks and internal/external audit will be put in place. Report of fraud must be report to DFID	Major	Minor	Severe – Any funds diverted from development activities will reduce the credibility of development funding
Programme results are jeopardised by high percentage of failing projects	Partnership assessment process will consider balance of risk and return for each partnership and ensure risks are identified with appropriate management and mitigating actions in place / Steering committee will have a specific role around considering the level of risk attached to individual partnerships and the balance of risk across the portfolio / Partnerships will be subject to regular monitoring to help identify failing partnerships early, help to support improvement and close them only where necessary	Major	Moderate	Major – If too many partnerships are unable to deliver expected results the programme level results will be significantly impacted
UK higher education institutions may see the payment of full economic costs as an incentive to construct applications that	The fund manager will assess the partnership approach during the selection and determine whether it is appropriate. / The fund manager will also assess budgets during the partnership selection process to ensure all costs are necessary and justified and that the partnership represents good value for money. / Partnership annual reviews will need to demonstrate continued good value for money throughout it’s life.	Moderate / Major?	Minor	Major – Any funds diverted from development activities will reduce the credibility of development funding, DFID and the institutions while reducing programme impact and detracting from potential success stories.
Operation Risk	The Fund Manager will need to ensure Risk management is a key feature of quarterly joint FM/DFID meetings. / FM to simplify risk matrix and classify risk by type / FM to propose potential risks to the external environment and add this as a new category to register.	Minor	Minor	Moderate
Reputational Risk to DFID and partnership	DFID / FM unable to engage with Private Sector (match-funding) / Perceived Conflict of Interest with FM / Consortium and downstream partners	Moderate	Minor	Moderate

New Risk Management (transition from 3 Risk categories recorded in ARIES to 4 Risk categories for AMP)

Individual issue / risk	Definitions
Minor	This is an issue / risk that could have a minor effect on the achievement of one or many of the Department’s strategic objectives, or could have a minor effect on the effectiveness or efficiency of the Department’s activities or processes.
Moderate	This is an issue / risk that could have a moderate effect on the achievement of one or many of the Department’s strategic objectives, or could have a moderate effect on the effectiveness or efficiency of the Department’s activities or processes.
Major	This is an issue / risk that could have a major effect on the achievement of one or many of the Department’s strategic objectives, or could have a major effect on the effectiveness or efficiency of the Department’s activities or processes.
Severe	This is an issue / risk that could severely affect the achievement of one or many of the Department’s strategic objectives, or could severely affect the effectiveness or efficiency of the Department’s activities or processes.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process