## Logframe
PROJECT NAME | UNICEF/DFID "Equity" Programme in Southern Kyrgyzstan April 2012-March 2015
IMPACT | Impact Indicator 1 |  | Baseline (April 2012) | Milestone 1 | Milestone 2 | Target (March 2015) |  | Notes AR 2014
Improved peace and stability and a lessening of ethnic tension in the conflict affected areas of Southern Kyrgyzstan | Number reported incidents of violent and non-violent conflict in Osh, Jalabad and Batken Oblasts (per 1,000 population) | Planned | Osh: 1.39 Batken: 1.17 Jalalabad: 1.03 |  |  | Osh: 1.32 Batken: 1.11 Jalalabad: 0.98 [The above numbers equals a 5% reduction in reported incidents of violent and non-violent conflict in Osh, Jalabad and Batken Oblasts (per 1,000 population)] |  | Baseline data and target amended in AR 2014 - joint UNICEF and DFID decision to include all crimes except traffic crimes.
Achieved
Source
Police Records. Reports of conflict CSO's - International Crisis Group, Saferworld, National Human Rights Protection Centre - "Kylym Shamy Kyrgyzstan".
| Impact Indicator 2 |  | Baseline (April 2012) | Milestone 1 | Milestone 2 | Target (March 2015)
| Percentage of target population expressing that local authorities should support a variety of cultural events with the participation of people with different nationalities in Kyrgyzstan. | Planned | Kyrgyz: 65.5% Uzbeks: 87.5% |  |  | Kyrgyz: 90% Uzbeks: 90% |  | Target for Kyrgyz increased to 90% (up from 75%). Uzbek target to stay the same.
Achieved
Source
UNICEF administered surveys. CSO reports.
| Impact Indicator 3 |  | Baseline (April 2012) | Milestone 1 | Milestone 2 | Target (March 2015)
| Percentage of children in difficult life situations in target areas that have access to social services | Planned | 20% (in 13 municipalities that were targeted in 2012). |  |  | 70% of children in difficult life situations have access to social services (in 33 municipalities targeted by end of project in 2015) |  | Number of target municipalities increased in AR 2014 to 33 (up from 30)
Achieved
Source
Local authority reports developed by social workers. Independent verification by UNICEF.
OUTCOME | Outcome Indicator 1 |  | Baseline (April 2013) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015) | Assumptions
Raised living standards, increased employment opportunities and reduced frustration and alienation among children, youth and families in the Programme target areas | Neonatal mortality in target hospitals (including FGPs / FABs with beds) | Planned | 12.1 | 12.1 | 10% reduction in neonatal mortality in target hospitals | 20% reduction in neonatal mortality in target hospitals | 1.Realistic accurate surveys can be completed in the target. municipalities at reasonable cost. 2. Funds are made available to pay for the improvements.
|  | Achieved |  | 12.1 | 14% reduction 10.2 neonatal mortality rate
Source
Republic medical information center's statistical reports. Independent verification by UNICEF.
| Outcome Indicator 2 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Percentage of youth centre graduates (who have particated in skills enhancement training) employed or continuing their studies whilst active job seekers. | Planned | 5 | 5 | 10 | 20
|  | Achieved | 5 | 5 | 10
Source
UNICEF administrated surveys. CSO reports and analyses.
| Outcome Indicator 3 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Percentage point difference between whole population in target communities and those participating in conflict prevention activities in youth centers who report they don’t wish to see the other ethnicity living in the same areas (disaggregated by Kyrgyz and Uzbek populations) | Planned | 38% of Kyrgyz youth don’t wish to see the other ethnicity living in the respective regions . 0% of Uzbeks don't wish to see Kyrgyz people living in the same area. | Kyrgyz; 17 percentage point difference (based on a small sample) i.e. 21% of Kyrgyz youth don’t wish to see other ethnic minorities living in the respective regions Uzbeks' response to the questions (living with Kyrgyz) were 0% | 10% difference | 10% difference |  | Clarified indicator in AR2014.Previously read: Percentage point difference between whole population in target communities and those participating in conflict prevention activities who report they don’t wish to see the other ethnicity living in the same areas (disaggregated by Kyrgyz and Uzbek populations )
|  | Achieved |  | Baseline established | 11% of Kyrgyz respondents not attending youth centers are negative about Uzbeks living in their region. In comparison only 9% of Kyrgyz respondents attending youth centers responded negatively. The difference is 20% 0% of Uzbek respondents attending youth centers are negative about Kyrgyz living in their region. Amongst Uzbek respondents not attending the youth centers 5% responded negatively.
Source
UNICEF administered surveys. CSO reports and analyses.
| Outcome Indicator 4 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Percentage point difference between whole population in target communities and those participating in conflict prevention activities in youth centers who report they don’t wish to have the other ethnicity as neighbours (disaggregated by Kyrgyz and Uzbek populations). | Planned | 52% of Kyrgyz youth don’t wish Uzbeks as neighbours. Uzbeks' response to the question (living with Kyrgyz) was 0.3% | 33% difference (based on a small sample) i.e. 19% of Kyrgyz don’t wish Uzbeks as neighbours. Uzbeks' response to the question (living with Kyrgyz) was 0% | 10% difference | 10% difference
|  | Achieved |  | Baseline established | 10% of Kyrgyz respondents attending youth centers don't wish to have Uzbeks as their neighbors. In comparison 14% of Kyrgyz respondents not attending the youth centers express the same sentiment. The difference is 40%. 0% of Uzbek respondents attending youth centers don't wish to live with Kyrgyz as neighbors. In comparison 7% of Uzbek respondents not attending youth centers don't wish to have Kyrgyz as their neighbors.
Source
UNICEF administered surveys. CSO reports and analyses.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| £5 million |  | In kind: Tax exemption for UNICEF on VAT and Customs duties; Office and training facilities; Time and expertise of Government officials | UNICEF: $1.7 million from country resources | £6,062,500 or $6.5 million (depending on exchange rates-assumed £1=$1.60 for planning purposes) | 82%
INPUTS (HR) | DFID (FTEs)
Programme Officer: 10%
Governance Adviser: 10%
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2013) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015) | Assumption
Significant increase in child and family welfare among targeted poorest families and communities by increasing access to services. | Proportion of children in the target communities receiving birth certificates. | Planned | 91.5% | 91.5% | 93% | 95% (2,400 children) |  | Removed previous indicator 1.1. Continuing government policy changes to the eligibility requirements for social cash transfers make this indicator untrackable.
|  | Achieved |  | 91.5% | 93% (1,092 children)
Source
UNICEF initiated surveys. CSO reports
| Output Indicator 1.2 |  | Baseline (April 2013) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Number of targeted Community Based Kindergartens established providing equitable and expanded access to preschool education services. | Planned | 0 | 13 (benefitting at least 1,040 children on a yearly basis) . 50% of beneficiaries will be girls | 25 (benefitting at least 2,000 children on a yearly basis). 50% of beneficiaries will be girls | 61 (benefitting at least 4,800 children on a yearly basis) . 50% of beneficiaries will be girls |  | 1.2 Increase target from 55 to 61.
|  | Achieved |  | 13 | 60 (4,972 children annually) 50% of beneficiaries are girls
Source
Registration documents of CBK establishment. Independent UNICEF verification.
| Output Indicator 1.3 |  | Baseline (April 2013) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Number of targeted health facilities with running water in maternity departments. | Planned | 0 | 0 [Assessments completed of rehabilitation needs] | 4 (benefitting at least 9,490 women giving birth on a yearly basis) | 17 (benefitting at least 19,231 women giving birth on a yearly basis)
|  | Achieved |  | 0 [Assessments completed of rehabilitation needs] | 4
Source
Ministry of Health summary report on situation in health sector.
IMPACT WEIGHTING (%) | Output indicator 1.4 |  | Baseline (April 2013) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
30% | Number and proportion of out of school children (OOSC) in target areas enrolled / re-enrolled | Planned | 0 | 0 [Structure introduced i.e. Committees on social issues created and list of OOSC and children at risk of dropping out developed] | 1,000 50% of OOSC enrolled / re-enrolled; | 2,400 50% of OOSC enrolled / re-enrolled;
|  | Achieved |  | 0 [Structure introduced i.e. Committees on social issues created and list of OOSC and children at risk of dropping out developed] | 1089
|  | Source |  |  |  |  | RISK RATING
|  | School enrollment statistics from local education departments. Reports from committees on social issues. |  |  |  |  | Medium
INPUTS (£) | INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 1900000 | In kind-as for the whole Programme | UNICEF: $500,000 or £312,500 | 2212500 | 85.86%
INPUTS (HR) | DFID (FTEs)
The only DFID involvement is in the Programme as a whole. UNICEF will implement the activities under each output.
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (April) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015) | Assumptions
Increased education and training available to youth to improve their employment prospects,reduce their frustrations and enhance inter-ethnic reconciliation | Number and percentage of youths in youth centers attending capacity building initiatives including civic education, income generation and peace-building courses. [At least half of participants in the internship programme should be female] | Planned | number: 13,400 percentage: 50 | number: 13,400 percentage: 50 | number: 14,500 percentage: 80 | number: 40,000 peecentage: 80 | 1. Local Authorities provide suitable buildings to house the Youth Centres. 2. Suitable locally based trainers can be identified. 3. Training equipment and computers are made available in sufficient quantities for the participants in Youth centres. | 2.1 Target increased from: number: 16,000 percentage: 80
|  | Achieved |  | number: 13,400 percentage: 50 | number: 33,789 percentage:75%
Source
Ministry of Youth reports and statistics. UNICEF Programme reports.
| Output Indicator 2.2 |  | Baseline (April) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Percentage of youths participating in internship programme reporting increased skills and professional networks | Planned | n/a | n/a [Intership programme developed] | 50% | At least 200 participants (50% female) At least 70% report increased skills
|  | Achieved |  | Intership programme developed and agreement reached with CSO and other entities on placement of interns. 1st Cohort will participate in the internship programme in the second half of 2013 | 20 participants (52% female) 100% report increased skills and professional networks
IMPACT WEIGHTING (%) |  | Source
25% |  | Surveys administered by UNICEF. UNICEF Programme Reports.
INPUTS (£) | INPUTS (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 600000 | In kind-as Programme as a whole | UNICEF: $400,000 or £250,000 | £850,000 | 70.59%
INPUTS (HR) | DFID (FTEs)
As for Output 1
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015) | Assumptions
Capacity built in local government administrations, local offices of central ministries and health and education facilities to offer efficient and effective services to targeted groups on an ethnically non-discriminatory basis. | Proportion of relevent local government officials (including service providers receiving training in Health, Education and Municipal planning and monitoring) trained and obtained increased capacity [At least half of training participants should be female] | Planned | 0 [4,431 local government officials - including service providers - identified as requiring training as part of the programme] | 39% (1,739 local officials trained) | 60% | 90% | 1. GOK supports the introduction of reforms and the resources for reform is made available. 2. Resource allocations and staff deployments follow the priorities identified in the participatory planning processes.
|  | Achieved |  | 39% | More than 100% (5,380 local officials)
Source
UNDP analyses of the civil service and local government and UNICEF baseline research. UNICEF and independent monitoring reports.
| Output Indicator 3.2 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Number of municipality strategic plans designed in a participatory manner, that are under implemantion (with some key elements under implementation). | Planned | 0 | 6 | 30 | 55
|  | Achieved |  | 6 | 30
IMPACT WEIGHTING (%) |  | Source |  |  |  |  | RISK RATING
20% |  | Existence and content of plans. UNICEF reports on progress in implementing the strategic plans. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | £1,100,000 | In kind as shown under Outcome | UNICEF: $500,000 or £312,500 | £1,412,500 | 77.88%
INPUTS (HR) | DFID (FTEs)
As for Output 1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015) | Assumptions
Mechanisms in place to foster inter-ethnic and inter-community understanding and tolerance and reduce tension. | Number of youths and adolecents in conflict-prone areas of Batken Province who access safe and friendly spaces to interact, raise and address concerns and reconcile differences. | Planned | 0 | 0 | 2,000 (50% female) | 7,500 (50% female) | 1. Funds are available from the Ministry of Education and donors to support the reforms required. 2. Public Institutions led by local authorities and local offices of central ministries support the implementation of reforms. | 4.1 Increased target from 4,500.
|  | Achieved |  | 0 | 5,879 (70% female)
Source
Surveys conducted by UNICEF. CSO reports on youth center participation. Independent UNICEF verification
| Output Indicator4.2 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| % children reporting violence in "schools without violence" target sites | Planned | 83% of children report experiencing/witnessing violence in secondary schools | 5% reduction in 6 targeted schools | 7% reduction in 14 targeted schools | 15% reduction in the 20 targeted schools
|  | Achieved |  | 5% reduction in 6 targeted schools | Survey due in October 2014. Will update indicator then.
Source
UNICEF administered surveys. UNICEF implementation and monitoring reports. Analysis by CSOs.
| Output Indicator 4.3 |  | Baseline (April 2012) | Milestone 1 (April 2013) | Milestone 2 (April 2014) | Target (March 2015)
| Number of peace-ensuring mechanisms introduced (e.g. elderly groups established (OPG)). [At least half of OPG members should be female] | Planned | 0 | 5 | 10 | 30
|  | Achieved |  | 5 | 10
IMPACT WEIGHTING (%) |  | Source |  |  |  |  | RISK RATING
25% |  | Surveys conducted by UNICEF. CSO reports |  |  |  |  | High
INPUTS (£) | INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 1400000 | In kind as shown under Outcomes above | UNICEF:$300,000 or £187,500 | 1587500 | 88.19%
INPUTS (HR) | DFID (FTEs)
As for Output 1

## Results Chain
UNICEF/DFID "Equity" Programme in Southern Kyrgyzstan April 2012-March 2015
OUTPUTS |  |  | OUTCOME | IMPACT
1 | Raised living standards, increased employment opportunities and reduced frustration and alienation among children, youth and families in the Programme target areas | 30% | Raised living standards, increased employment opportunities and reduced frustration and alienation among children, youth and families in the Programme target areas | Improved peace and stability and a lessening of ethnic tension in the conflict affected areas of Southern Kyrgyzstan
2 | Increased education and training available to youth to improve their employment prospects,reduce their frustrations and enhance inter-ethnic reconciliation | 25%
3 | Capacity built in local government administrations, local offices of central ministries and health and education facilities to offer efficient and effective services to targeted groups on an ethnically non-discriminatory basis. | 20%
4 | Mechanisms in place to foster inter-ethnic and inter-community understanding and tolerance and reduce tension. | 25%

## Logframe Summary
UNICEF/DFID "Equity" Programme in Southern Kyrgyzstan April 2012-March 2015
Results Chain |  |  | Indicators | Baseline 2011 | Target 2015 | Source
IMPACT | Improved peace and stability and a lessening of ethnic tension in the conflict affected areas of Southern Kyrgyzstan |  | Number reported incidents of violent and non-violent conflict in Osh, Jalabad and Batken Oblasts (per 1,000 population) | Osh: 1.39 Batken: 1.17 Jalalabad: 1.03 | Osh: 1.32 Batken: 1.11 Jalalabad: 0.98 [The above numbers equals a 5% reduction in reported incidents of violent and non-violent conflict in Osh, Jalabad and Batken Oblasts (per 1,000 population)] | Police Records. Reports of conflict CSO's - International Crisis Group, Saferworld, National Human Rights Protection Centre - "Kylym Shamy Kyrgyzstan".
|  |  | Percentage of target population expressing that local authorities should support a variety of cultural events with the participation of people with different nationalities in Kyrgyzstan. | Kyrgyz: 65.5% Uzbeks: 87.5% | Kyrgyz: 90% Uzbeks: 90% | UNICEF administered surveys. CSO reports.
|  |  | Percentage of children in difficult life situations in target areas that have access to social services | 20% (in 13 municipalities that were targeted in 2012). | 70% of children in difficult life situations have access to social services (in 33 municipalities targeted by end of project in 2015) | Local authority reports developed by social workers. Independent verification by UNICEF.
OUTCOME | Raised living standards, increased employment opportunities and reduced frustration and alienation among children, youth and families in the Programme target areas |  | Neonatal mortality in target hospitals (including FGPs / FABs with beds) | 12.1 | 20% reduction in neonatal mortality in target hospitals | Republic medical information center's statistical reports. Independent verification by UNICEF.
|  |  | Percentage of youth centre graduates (who have particated in skills enhancement training) employed or continuing their studies whilst active job seekers. | 5 | 20 | UNICEF administrated surveys. CSO reports and analyses.
|  |  | Percentage point difference between whole population in target communities and those participating in conflict prevention activities in youth centers who report they don’t wish to see the other ethnicity living in the same areas (disaggregated by Kyrgyz and Uzbek populations) | 38% of Kyrgyz youth don’t wish to see the other ethnicity living in the respective regions . 0% of Uzbeks don't wish to see Kyrgyz people living in the same area. | 10% difference | UNICEF administered surveys. CSO reports and analyses.
|  |  | Percentage point difference between whole population in target communities and those participating in conflict prevention activities in youth centers who report they don’t wish to have the other ethnicity as neighbours (disaggregated by Kyrgyz and Uzbek populations). | 52% of Kyrgyz youth don’t wish Uzbeks as neighbours. Uzbeks' response to the question (living with Kyrgyz) was 0.3% | 10% difference | UNICEF administered surveys. CSO reports and analyses.
OUTPUTS | #REF! | 30% | #REF! | #REF! | #REF! | #REF!
|  |  | Proportion of children in the target communities receiving birth certificates. | 0.915 | 95% (2,400 children) | UNICEF initiated surveys. CSO reports
|  |  | Number of targeted Community Based Kindergartens established providing equitable and expanded access to preschool education services. | 0 | 61 (benefitting at least 4,800 children on a yearly basis) . 50% of beneficiaries will be girls | Registration documents of CBK establishment. Independent UNICEF verification.
|  |  | Number of targeted health facilities with running water in maternity departments. | 0 | 17 (benefitting at least 19,231 women giving birth on a yearly basis) | Ministry of Health summary report on situation in health sector.
| Increased education and training available to youth to improve their employment prospects,reduce their frustrations and enhance inter-ethnic reconciliation | 25% | Number and percentage of youths in youth centers attending capacity building initiatives including civic education, income generation and peace-building courses. [At least half of participants in the internship programme should be female] | number: 13,400 percentage: 50 | number: 40,000 peecentage: 80 | Ministry of Youth reports and statistics. UNICEF Programme reports.
|  |  | Percentage of youths participating in internship programme reporting increased skills and professional networks | n/a | At least 200 participants (50% female) At least 70% report increased skills | Surveys administered by UNICEF. UNICEF Programme Reports.
| Capacity built in local government administrations, local offices of central ministries and health and education facilities to offer efficient and effective services to targeted groups on an ethnically non-discriminatory basis. | 20% | Proportion of relevent local government officials (including service providers receiving training in Health, Education and Municipal planning and monitoring) trained and obtained increased capacity [At least half of training participants should be female] | 0 [4,431 local government officials - including service providers - identified as requiring training as part of the programme] | 90% | UNDP analyses of the civil service and local government and UNICEF baseline research. UNICEF and independent monitoring reports.
|  |  | Number of municipality strategic plans designed in a participatory manner, that are under implemantion (with some key elements under implementation). | 0 | 55 | Existence and content of plans. UNICEF reports on progress in implementing the strategic plans.
| Mechanisms in place to foster inter-ethnic and inter-community understanding and tolerance and reduce tension. | 25% | Number of youths and adolecents in conflict-prone areas of Batken Province who access safe and friendly spaces to interact, raise and address concerns and reconcile differences. | 0 | 7,500 (50% female) | Surveys conducted by UNICEF. CSO reports on youth center participation. Independent UNICEF verification
|  |  | % children reporting violence in "schools without violence" target sites | 83% of children report experiencing/witnessing violence in secondary schools | 15% reduction in the 20 targeted schools | UNICEF administered surveys. UNICEF implementation and monitoring reports. Analysis by CSOs.
|  |  | Number of peace-ensuring mechanisms introduced (e.g. elderly groups established (OPG)). [At least half of OPG members should be female] | 0 | 30 | Surveys conducted by UNICEF. CSO reports
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Annual Review
UNICEF/DFID "Equity" Programme in Southern Kyrgyzstan April 2012-March 2015
Results Chain |  |  | Indicators | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk
|  |  |  | 2012 |  | 2012 |  | 2012 | 2013 |  | 2013 |  | 2013 | 2014 |  | 2014 |  | 2014 | Target 2015 |  | 2015 |  | 2015
IMPACT | Improved peace and stability and a lessening of ethnic tension in the conflict affected areas of Southern Kyrgyzstan |  | Number reported incidents of violent and non-violent conflict in Osh, Jalabad and Batken Oblasts (per 1,000 population) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Percentage of target population expressing that local authorities should support a variety of cultural events with the participation of people with different nationalities in Kyrgyzstan. | [5 empty] | 0 | 0
|  |  | Percentage of children in difficult life situations in target areas that have access to social services | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OUTCOME | Raised living standards, increased employment opportunities and reduced frustration and alienation among children, youth and families in the Programme target areas |  | Neonatal mortality in target hospitals (including FGPs / FABs with beds) | 0 | 0 | n/a | 0% |  | 12.1 | 12.1 | A | 100% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Percentage of youth centre graduates (who have particated in skills enhancement training) employed or continuing their studies whilst active job seekers. | 0 | 0 |  |  |  | 5 | 5 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Percentage point difference between whole population in target communities and those participating in conflict prevention activities in youth centers who report they don’t wish to see the other ethnicity living in the same areas (disaggregated by Kyrgyz and Uzbek populations) | [5 empty] | Kyrgyz; 17 percentage point difference (based on a small sample) i.e. 21% of Kyrgyz youth don’t wish to see other ethnic minorities living in the respective regions Uzbeks' response to the questions (living with Kyrgyz) were 0% | Baseline established
|  |  | Percentage point difference between whole population in target communities and those participating in conflict prevention activities in youth centers who report they don’t wish to have the other ethnicity as neighbours (disaggregated by Kyrgyz and Uzbek populations). | 0 | 0 |  |  |  | 33% difference (based on a small sample) i.e. 19% of Kyrgyz don’t wish Uzbeks as neighbours. Uzbeks' response to the question (living with Kyrgyz) was 0% | Baseline established |  |  |  | 0 | 0 |  |  |  | 0 | 0
OUTPUTS | #REF! | 30% | #REF! | 0 | 0 | n/a | 0% |  | #REF! | #REF! | A | 100% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Proportion of children in the target communities receiving birth certificates. | 0 | 0 |  |  |  | 0.915 | 91.5% |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of targeted Community Based Kindergartens established providing equitable and expanded access to preschool education services. | 0 | 0 |  |  |  | 13 (benefitting at least 1,040 children on a yearly basis) . 50% of beneficiaries will be girls | 13 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of targeted health facilities with running water in maternity departments. | 0 | 0 |  |  |  | 0 [Assessments completed of rehabilitation needs] | 0 [Assessments completed of rehabilitation needs] |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Increased education and training available to youth to improve their employment prospects,reduce their frustrations and enhance inter-ethnic reconciliation | 25% | Number and percentage of youths in youth centers attending capacity building initiatives including civic education, income generation and peace-building courses. [At least half of participants in the internship programme should be female] | 0 | 0 | n/a | 0% |  | number: 13,400 percentage: 50 | number: 13,400 percentage: 50 | A | 100% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Percentage of youths participating in internship programme reporting increased skills and professional networks | 0 | 0 |  |  |  | n/a [Intership programme developed] | Intership programme developed and agreement reached with CSO and other entities on placement of interns. 1st Cohort will participate in the internship programme in the second half of 2013 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Capacity built in local government administrations, local offices of central ministries and health and education facilities to offer efficient and effective services to targeted groups on an ethnically non-discriminatory basis. | 20% | Proportion of relevent local government officials (including service providers receiving training in Health, Education and Municipal planning and monitoring) trained and obtained increased capacity [At least half of training participants should be female] | 0 | 0 | n/a | 0% |  | 39% (1,739 local officials trained) | 0.39 | A | 100% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Number of municipality strategic plans designed in a participatory manner, that are under implemantion (with some key elements under implementation). | 0 | 0 |  |  |  | 6 | 6 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Mechanisms in place to foster inter-ethnic and inter-community understanding and tolerance and reduce tension. | 25% | Number of youths and adolecents in conflict-prone areas of Batken Province who access safe and friendly spaces to interact, raise and address concerns and reconcile differences. | 0 | 0 | n/a | 0% |  | 0 | 0 | A | 100% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | % children reporting violence in "schools without violence" target sites | 0 | 0 |  |  |  | 5% reduction in 6 targeted schools | 5% reduction in 6 targeted schools |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of peace-ensuring mechanisms introduced (e.g. elderly groups established (OPG)). [At least half of OPG members should be female] | 0 | 0 |  |  |  | 5 | 5 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| #REF! | #REF! | #REF! | 0 | 0 | n/a | 0% |  | #REF! | #REF! | A | 100% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
OVERALL OUTPUT SCORE |  | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF!
| Value | Threshold
A++ | 150% | 137.5% | Outputs substantially exceeded expectation
A+ | 125% | 112.5% | Outputs moderately exceeded expectation
A | 100% | 87.5% | Outputs met expectation
B | 75% | 62.5% | Outputs moderately did not meet expectations
C | 50% |  | Outputs substantially did not meet expectations
n/a | 0%
Risk
Low | 1
Medium | 2
High | 3