Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Political Settlements Research Programme (PSRP)
Programme Value: £4,366,612		Review Date: March 2016
Programme Code: 204326	Start Date: 01/04/2014	End Date: 30/03/2019

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A
Risk Rating	Medium	Moderate

Summary of progress and lessons learnt since last review

The Political Settlements Research Programme (PSRP) has now completed its first year. Although a light touch annual review was completed last year, this is the first substantial annual review for the programme.

The PSRP has now successfully concluded its inception period, establish itself with a firm and credible administrative operation, and is on track to meet or surpass by a moderate amount all the milestones set for this early part of the programme. In this short time, the PSRP has already scored some impressive achievements. This includes making a substantial (and recognised) contribution to the United Nation’s 15-year review of UN resolution 1325, on the rights of women. The PSRP has also provided evidence-based support relevant to Syria for the FCO; and has made a significant input to the forthcoming World Bank Development Report 2017.

The programme has suffered only minor setbacks during this first year. These have arisen from external problems, such as the earthquake in Nepal, which has affected research timescales; and the need for special training in Eastern DRC to overcome reticence on the part of interviewees, many of whom had experienced traumatic events.

Summary of recommendations for the next year

The logframe for this programme will need to be revised in particular to reflect better research engagement outputs. This will require a new set of output measures relating to research uptake and stakeholder engagement, and synchronising milestones with future Annual Reviews. (ACTION: DFID to propose new draft by end March 2016; new logframe agreed with PSRP by end June 2016).

The relationship between the PSRP digital strategy and DFID’s new digitalpolicy needs to be clarified. (ACTION: PSRP and DFID, to be concluded by end June 2016).

Edinburgh to test Duty of Care arrangements and ensure they are operating appropriately at all levels within PSRP. PSRP to examine best practice from similar research consortiums eg SLRC, JSRP (ACTION: PSRP to review Duty of Care Arrangements by end of April 2016, subject to conditions in the field).
A. Introduction and Context

DevTracker Link to Business Case:	4429922
DevTracker Link to Log frame:	5350670

Outline of the programme

DFID is providing £4.4m over four years (2015-2019) to fund research into how donors can shape political settlements - the rules that regulate the access of elites to resources and power – to reduce poverty and the risk of conflict.[1] This research programme, in an area which currently has many evidence gaps, will inform the content, choice and targeting of interventions on political settlements by donors, diplomats, and defence actors, especially in fragile and conflict-affected states. This new research will lead to more effective interventions that address conflict risks and promote pro-poor institutions. The Political Settlements Research Programme (PSRP) has now completed its first year, which included a six-month inception period running through to September 2015. This is the first substantial annual review for the programme.
[1] How power is organized in a society and the rules that regulate how elites work together is termed the ‘political settlement’. Additional characteristics of political settlements include a) a broad reflection of the underlying distribution of power between different social groups; b) that they are not static or single events, but continuous bargaining processes over these rules between different elite and non-elite groups; c) that they are expressed through formal and informal institutions which constrain and shape the underlying bargaining processes; and d) exist both at the state and the sub-state level.

This programme focusses on three broad themes:

1. How different types of political settlement emerge, and which actors, institutions, resources, and practices shape them;
2. How political settlements can be improved by internally-driven initiatives, including the impact of gender-inclusive processes and rule of law institutions; and
3. How, and with what interventions, external actors can change political settlements.

This research programme is explicitly comparative (that is, it seeks insights by understanding examples and the differences between them). The programme is using a mix of qualitative and quantitative methods, with a substantial field work component. Currently, work is being focussed on Afghanistan, the Democratic Republic of Congo; East Timor; Ethiopia/Ogaden; Liberia; Nepal; Nigeria; The Philippines; Sierra Leone; Somalia, with comparative work to less fragile settings also drawing on Colombia and Northern Ireland. It has already begun to generate robust evidence with a strong operational focus.

Following a competitive tendering process in 2014-15, the University of Edinburgh was selected to lead the PRSP consortium and implement the programme. The PSRP complements existing RED research programmes, notably the Effective States and Societies Research Consortium (ESID) and the Justice and Security Research Consortium (JSRP).

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The Political Settlements Research Programme (PSRP) is progressing well. Early successes include the take up of PSRP research regarding the role of women in peace settlements by agencies including UN Women (more details are available through this link); and a comprehensive database on political settlements (the ‘PA-X’ database) which has already proven useful to HMG and other stakeholders. In the autumn, the PSRP provided insights to the FCO Syria team which were deemed useful. A DFID field visit to DRC (February 2016) examined PSRP field work and found it to be impressive; a field visit report is provided in Annex 1.

We look forward to greater successes in the years ahead, including more publications and useful research findings, leading to an even greater positive, evidence-based influence on policy makers, as the second half of the programme gets underway.

Overall output score and description

A: Output and performance meets expectations.

Key lessons and actions

The PSRP has attempted to bridge two different bodies of scholarship on political settlements. It has sought to bring together work on peace processes and constitutional issues with theories on elite pacts and inclusive development. It has concluded that, given the number of overlapping definitions of political settlement which already abound, to offer further definitions is unlikely to yield progress. Hence, it will prioritise a set of inquiries which should inform the debate in a more useful way.

The Inception Period (March-August 2015) highlighted the opportunity for the PSRP to build on its stakeholder engagement and research uptake strategies. Given the PSRP’s strong focus on this, the logframe for this programme should now be revised to include a new set of output milestones relating to engagement and uptake (ACTION: DFID to propose new draft by end March 2016; new logframe agreed with PSRP by end June 2016).

The relationship between the PSRP digital strategy and DFID’s new digital policy will need to be clarified. (ACTION: PSRP and DFID, to be concluded by end June 2016).

Edinburgh to test Duty of Care arrangements and ensure they are operating appropriately at all levels within PSRP. PSRP to examine best practice from similar research consortiums (eg SLRC, JSRP). (ACTION: PSRP, by end April 2016, subject to conditions in the field).

Has the logframe been updated since the last review?

The scheduled completion time for Milestone 1.2 (Output indicator 1.2) has been moved back because of a key member of staff taking maternity leave. Further logframe revisions will be made in the coming quarter, which will be substantial.
## C: DETAILED OUTPUT SCORING

Output Title	High quality, relevant, timely and reliable research products on political settlements.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Peer reviewed academic articles, reaching high standards of international excellence	Milestone 1.1 (Dec 2016): / 6 articles published in journals/outlets; / 1 monograph, all with peer review.	On track, and likely to be exceeded by a moderate amount. Eleven months before this milestone is due, one article has been published, with a series of seven others in the final stages prior to publication (see Annex 2 for more details). The PSRP has also produced a wide and comprehensive range of written outputs for its website. This milestone is likely to be exceeded by a moderate amount.
1.2 New datasets capable of supporting ongoing research	Milestone 1.2 (Dec 2016): / Amnesty data base revised; Peace Agreement Access Tool’s data collection advanced on women and international norms; data collection advanced on violence against women projects. (Milestone to be revised further.)	Progress delayed by agreement with DFID. Data collection on women and international norms through the Peace Agreement Access tool has been advanced and the data has been used in some PSRP research products; amnesty database coding is on-time with reference to revised timeline, and an additional output has been delivered the women and peace agreements database. / (The schedule for the amnesty database has been pushed-back by six months due to maternity leave, with DFID’s agreement. Note that the dates of this milestone need to be amended to tie in with annual review process, and the log-frame amended with repsect to the amnesty to reflect the maternity leave delay.)
1.3 Range of research products from research, capable of speaking to different stake-holders	Milestone 1.3 (Dec 2017): / 1 special edition of ‘Accord’ magazine devoted to Political Settlement research; / 10 briefing papers published; / 5 research reports published; / 10 substantial blogposts published. Milestone to be revised.	Milestone likely to be exceeded. Already (January 2016), 7 briefing papers have been published, along with 1 research report and 15 blog entries. A further 3 research reports are in preparation, and the Accord timetable is on track. Given that there remains 23 months, this milestone is likely to be exceeded by a considerable margin.

Key Points

The PSRP is making good progress along all three indicators relating to academic and research outputs. The milestones are 50% met more than eighteen months before they are due. Congratulations are due for their success in achieving high-profile uptake by UN Women of their database of peace agreements (more details here: http://www.politicalsettlements.org/events/pax-unwomen/), and for providing input for the FCO’s work on Syria. There is now a need to plan for the future hosting and curation of the datasets to ensure that they remain available, actively managed, and ‘open access’ beyond the project contract period.

Summary of responses to issues raised in previous annual reviews (where relevant)
There were no significant issues in the last AR as the project was still in the procurement stage.

Recommendations
- The logframe relating to Output 1 will needto be revised, to place greater emphasis on research uptake and synchronise timelines with the annual review cycle.
- Ownership and legacy issues concerning databases and other information assets will need to be clarified. (ACTION: PSRP and DFID, to be concluded by end June 2016).

## C: DETAILED OUTPUT SCORING

Output Title	Enhanced research capacity, particularly in global south
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
2.1 Current partners deliver inception phase with full integration of work- stream projects	Milestone 2.1.1 (Sep 2015): / Current partners deliver inception phase with full integration of work stream projects.	Milestone achieved. The inception phase report was completed to a high standard, and to schedule.
	Milestone 2.1.2 (Dec 2017): / Research products show evidence of cross-learning from and references to each other across organisational outputs. (Milestone to be revised.)	On track. The first research products have already been displayed on the programme website. The programme’s literature database and the website’s ‘virtual learning forum’ have also been developed and made accessible online. Two years ahead of the milestone deadline, satisfactory progress is being made; this milestone will be revised before December 2017.
2.2 Southern-based partners involved in research programme projects with appropriate support	Milestone 2.2 (Dec 2016): / 8 projects involve Southern partners; / 3 capacity-building events; / Southern authors included in at least 4 outputs.(Milestone to be revised.)	On track, and likely to be exceeded by a moderate amount. 9 projects involving Southern partners are already underway; three capacity-building events have already taken place; two publications which include Southern authors are currently being finalised, and two more are being prepared. By December 2016, this milestone is likely to be surpassed by a moderate amount, subject to a quality check of these initiatives, in next year’s Annual Review.
2.3 New research methodologies for complex problems in FCAS tested and disseminated where effective	Milestone 2.3 (Dec 2016): / Social network analysis has begun; Mid-level Social network analysis has begun; / Mid-level analysis has begun; Practice-based labs completed after year one. (Milestone to be revised.)	On track. Social network methodology is being put in place; and mid-level analysis is under development in association with the Peace-Agreements database. Also, an output on database methodology has been accepted for publication in a peer reviewed journal. Practice-based labs are on track to be completed by December 2016. The added-value of these methodologies will need to be confirmed in next year’s Annual Review. Note that this milestone may need to be revisited.

Key Points
Progress is broadly on track at this early stage in this research programme, with no major problems identified. However, future success will depend on further evidence that the programme’s capacity building efforts are bringing demonstrable benefits to southern researchers, and helping generate the global public good of useful research. Note that the recruitment process for a PhD student from a developing country was set back by a lack of high quality applicants. The successful candidate is on maternity leave, and will not begin work until September 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)
There were no significant issues in the last AR as the project was still in the procurement stage.

Recommendations
Milestones relating to this output will need to be revised. The deadline on all milestones may need to be synchronised with future Annual Reviews (ACTION: DFID and PSRP, concluded by June 2016).
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

This is a milestone based contract.expences are paid on a quarterly basis in arrears based on actual costs. DFID retains 5% of each payment the retained amount is then issued the following quarter providing all criterias have been met. Full detals of key cost drivers are set out in section 4 of the contract, which is available on Quest (Quest No 4872330).

VfM performance compared to the original VfM proposition in the business case, and assessment of whether the programme continues to represent value for money

Value for Money in this programme is generated by the production of high-quality, relevant research outputs on political settlements, and the impact on policy interventions based on this research. The programme’s ability to attract additional funding and savings made through reductions in flight costs have enabled the PSRP to produce several research outputs above and beyond the agreed deliverables, as well as facilitating wider stakeholder engagement. Key examples of added value include:

- Funding from UN Women, which enabled PSRP to employ additional coders over the summer to speed up production of the PA-X Database. This funding also facilitated the production of the gender sub-database on peace agreements.
- Facilitating the translation of peace agreements, and adding additional search options to the PA-X Database.
- Increased Stakeholder engagement with PSRP as a result of GJA and University of Edinburgh’s hosting of International IDEA’s conference on constitution making. The conference was hosted by GJA and UoE and funded by International IDEA meaning that no costs were incurred by PSRP for this event, involving high profile participants.
- Flight costs have been reduced compared with the initial forecast, which enabled the use of the funds particularly in additional work and fast-tracking of project 3.1. The active usage of such synergies will continue; the next meeting of the advisory board for example is scheduled in the immediate aftermath of the PSRP summer school, where several members of the board act as speakers. Nahla Valji’s time has been given free of charge (as contemplated in the tender).
- Involving ‘associate researchers’ in the programme, who are working collaboratively on the PA-X analysis in return for access to the data, without their time being costed to the programme.
- Organising a conference on ‘masculinities, violence and (post-) conflict’, in cooperation with INCORE, IRiSS, International Alert, Saferworld, and Conciliation Resources, which supported to a very minimal extent by the programme (enabling RVI involvement), and brought within the programme for clear added value (and has now enabled greater cross-programme fertilization on the gender and masculinities issue).

In light of these impressive cost savings, and innovative use of resources, we are content that this programme continues to represent value for money.

Quality of Financial Management
The overall variance for the first year of the contract was 15%. This is noticeably above our target variance (of 10%), but is not unusual for the first year of a substantial research programme. In future years, the target variance will be 5%.
Invoicing is robust and of good quality, and all relevant backup paperwork has been provided. This contract operates with a 5% retention each quarter. To date, no retentions have been withheld.

The 1st quarter expenditure was 70% of that originally forecast (£170,423). Inevitably there was a considerable amount of process involved with the start-up of a new programme which has reflected in a spend profile lower than predicted. Staff fees incurred during this quarter were 80% of that forecast.

Whilst a number of successful recruitment processes have taken place across the programme, some of the new appointments were not in place until the second quarter. For example, at UoE, there was an unavoidably later start than anticipated for the post-doctoral position, which caused a time lag in the invoices for some staff costs. Expenditure for the Inception Phase (Q1 and Q2) equated to 89% of the original forecast. Whilst it is not uncommon for a programme to recast its forecasted spend, after the Inception Phase it was also very evident during the third quarter that a number of factors were restricting programme spend. Reference has already been made to the Nepal earthquake, but other factors included a rescheduling of activities for the Ogaden study given the restrictive civil and political space in Ethiopia and the Somali region, and the delay in activities on projects 3.2 and 3.3 allowing for key individuals to take maternity leave. These factors supported the rationale to formally recast the budget based upon actual expenditure to date; this revision was submitted to DFID in December 2015.

2nd Quarters expenditure was 107% of the original forecast, which compensated somewhat for Q1’s underspend. Expenditure in Q3 was 74% of the original forecast. See Quest document 5339350 Page 35 for full details of underspend. Expenditure in the final quarter Q4 was 93% of forecast. The variance was due to a slight slippage on undertaking the Nigeria practice lab, some delays in reporting and allowance for the festive break. Overall the project attained an 85% spend against forecast. Going forward the project has been re- forecasted and expenditure for F/Y16/17 is expected to be £1,497,198.

F/Y Spend 15/16

Figures in £	Q1 / (Mar- May)	Q2 / (Jun- Aug)	Q3 / (Sep- Nov)	Q4 / (Dec- Feb)	Total
Forecast	170,423	173,889	387,232	310,476	1,042,020
Actual	119,755	185,891	286,538	288,747	880,931
Variance	(50,668)	12,002	(100,694)	(21,729)	(161,089)

Quest Documents referenced: 5089295, 5190625, 5339350, and 5349672

Date of last narrative financial report	Quest No 5336204
Date of last audited annual statement	N/A Contract

E: RISK

Overall risk rating: Moderate

Overview of programme risk
The programme was originally assessed as a Medium Risk. PSRP members and organisations have continued to implement the risk management activities agreed in the original tender, to ensure that levels of risk in the programme remain at an acceptably low level. In their annual report they focused their risk assessment on four risk categories, two of them related to the outputs laid out in the Logframe, the other two relating to internal factors – governance and management of the programme – and to the external environment. The detailed risk assessment is shown in table 9 (See quest document 5339335).

One particular risk the PSRP wanted to highlight was the security of researchers in fragile and conflict affected states. The Programme has a strong approach to this particular risk. However, they had also highlighted in their original tender that they sought to use the experience of the peacebuilding organisations in the consortium to understand and better address researcher risks in the field. The situation in DRC means that researchers involved in RVI’s research for the programme continue to have to be vigilant. To date a specialised training programme has taken place for researchers in DRC; this is part of a wider research capacity building process (building capacity both in the Global South and North by bringing together good experiences of research in conflict zones). RVI also continues to review questions of researcher safety and together with the Programme Director they have put in place measures relating to location of events, publicity of programme work in the area, and even confidentiality of reporting, to ensure the safety of researchers (see Annex 1 for more on this). Nevertheless, given the importance of this issue, the University of Edinburgh should test their risk mitigation practices, and ensure they are fully embedded throughout their operations worldwide (Action: Edinburgh to test Duty of Care arrangements and ensure they are operating appropriately at all levels within PSRP; PSRP to examine best practice from similar research consortiums (eg SLRC, JSRP) by end April 2016).

Outstanding actions from risk assessment

Although the overall risk of the programme is moderate, the UOE will need to confirm that appropriate duty of care arrangements are in place for field workers.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The project is on track against the planned timeframe.

Inception phase successfully completed (on time). The programme infrastructure is now in place and working well. The consortium partners are working well together, particularly given the geographic logistics. They now have an opportunity to take out-reach, networking, stakeholder engagement, communications and visibility to a new level. For a critical appraisal of the inception phase, see the PSRP inception phase report, part 1, annex 4 (Quest No 5190625)

Project output Year One (on time). All agreed publications for project year one have been delivered – some with slight changes in the delivery format to make use of opportunities to increase impact. Beyond that, one journal paper, one research report, four briefing papers and one conference were delivered above the quantities committed to, and a special issue of a journal with four more guest articles is currently under review prior to publication.

Research uptake. A PSRP research uptake strategy has been developed and implemented; all sub-projects have sub-strategies. Commitments have been fulfilled. The research uptake strategy has already been effective in generating considerable impact on the policy level. Each organisation has rooted its research for the programme firmly within its overall work. For a more detailed account see Parts IV and part V of this report.

Performance of partnership (s)

DFID is represented on the Consortium Advisory Group (CAG), which met for a full day meeting in October. Regular meetings (at least quarterly) are held between DFID and the UoE. Work plans, objectives, performance measures and budgets have been shared and openly discussed with DFID, all to DFID’s satisfaction.

Asset monitoring and control

There are no physical assets associated with this project. The relationship between the PSRP digital strategy and DFID’s digital policy will need to be clarified. (ACTION: PSRP and DFID, to be concluded by end June 2016).

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not relevant.

H: MONITORING & EVALUATION

Evidence and evaluation

The PSRP completed its inception report in September 2015. The report was welcomed by DFID, and approved as a basis for further work.

Monitoring progress throughout the review period
DFID and the Director of the PSRP (Prof. Christine Bell) have formal quarterly meetings to discuss and monitor the overall progress of the programme, as well as special meetings to consider substantial progress markers, including an all-day meeting in October 2015 to consider in detail the Inception Report. This includes tackle individual problems that have arisen, facilitating policy engagement, and noting achievements, in the PSRP programme. This also enables DFID to provide input and direction on the PSRP programme.

This annual review was carried out during February and March 2016 by a team of DFID staff (A Senior Conflict Advisor (A1), a Research Manager (A2) and a Project Manager (B1)). The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners, and reviewing key research and communication outputs. There was also a field visit to the DRC, to inspect and form an opinion on some of the PSRP’s work in country (the field visit report is included in Annex 1). The content and conclusions of this Annual Review have been shared and discussed with Prof. Bell and the University of Edinburgh.
The Annual Review report was been shared with PSRP in March 2016. Recommendations will be followed up at subsequent project meetings.

Quest Documents:
Business case – 4429922
Logical Framework - 4263209
Q1 Technical report – 5089295
Q2 Technical Report - 5190625
Q3 Technical Report - 5339350
Q4 Technical Report - 5349672
PSRP Annual Review - 5339335
Inception Report – 5190625
Contract - 4872330
A sample of PSRP publications was examined for this review. A full list of publications from the reporting period is set out in Annex 2.

ANNEX 1: DRC Field Visit Report, February 2016

Field Trip Report

Visit to the Democratic Republic of the Congo, February 2016, to inspect the work of the Justice and Security Research Programme (JSRP) and Political Settlements Research Programme (PSRP).

Summary of Itinerary:

Monday 22nd February:	Fly out of UK
Tuesday 23rd Feb:	Arrive Kinshasa, DRC; attend JSRP workshop
Wednesday 24th Feb:	Fly to Mouanda, Western DRC; meetings with researchers and key individuals.
Thursday 25th Feb:	More meetings in Mouanda; return to Kinshasa.
Friday 26th Feb:	Meetings with the Rift Valley Institute, consortium member of the Political Settlements Research Programme.

Visit and report by: Iain King, Senior Conflict and Governance Advisor, RED; SRO to the JSRP and PSRP.

Political Settlements Research Programme (PSRP)

The Political Settlements Research Programme’s DRC component is led by the Rift Valley Institute, and managed by Michel Thill. Although the PSRP is only one year old, much of the Rift Valley Institute’s programme of work for the PSRP is front-loaded, and perhaps half has already taken place. Two briefings, one research report and four blogs, several authored or co-written by their Congolese researchers, have already been published, and they are planning on unveiling many of their conclusions at a seminar on stabilisation in Goma in mid-May 2016, at which local DFID representatives will be present.

The Rift Valley Institute are examining the role of armed groups on local security, on the economy, on justice and on customary authority. For this they have mapped 11 armed groups in a previous project, on which the current research builds. They have trained twelve Congolese staff members to conduct research (all are male; they made reasonable efforts to recruit female researchers, but found this was not possible). The outcome of this research drive has already enabled the Rift Valley Institute to draw credible and useful conclusions on the proliferation of small armed groups in DRC; the country’s flawed DDR process; and the interplay of political and conflict actors in different provinces.

The Rift Valley Institute’s research draws heavily on the local knowledge and cultural understanding of their Congolese researchers, although this is buttressed by external checks and academic rigour from the Nairobi headquarters. The Institute are working well, generating useful insights, and had a degree of influence on local outcomes. Their links to some stakeholders could be strengthened, but their use of closed-door meetings with donors and local actors in Kinshasa indicates they already have some sway.

My one point of criticism for the otherwise impressive Rift Valley Institute’s operation in the DRC concerns duty of care arrangements. Probing armed groups for information is an inherently risky activity, and they are doing it in an inherently dangerous environment. Given that context, it is not certain that sufficient duty of care and risk mitigation steps have been taken (to be clear, nor is it clear that appropriate safeguards are NOT in place). The Institute were able to outline a credible approach to duty of care issues based on using informal networks and local knowledge – which is probably the most reliable means of resolving any emergent problems (were one of their researchers to be taken hostage or incapacitated in the field, having the ear of influential community figures is likely to be the most promising approach). The Institute could also report that they have a daily ‘security check-in’ system and that their procedures have satisfied the requirements of ethical research, as determined by Edinburgh University. Further, most of the Instititute’s fieldwork is now complete, having been conducted and concluded in the last four months of 2015. However, I would welcome greater clarity on how the Institute tackles risk, and their plans for responding to any of the incidents or crises which have a reasonable likelihood of occurring.

ANNEX 2: Publications During the Reporting Period

The Political Settlements Research Programme have published and prepared a range of outputs during the reporting period. All their completed evidence products are available on their website (http://www.politicalsettlements.org/research/publications/) and others have already been – or are about to be – published in other media, too.

Journal Articles Published:

‘The resilient state: new regulatory modes in international approaches to state building?’ (Pospisil/Kuehn, in Third World Quarterly, online 5 Jan 16) (http://papers.ssrn.com/sol3/papers.cfm?abstract_id=2727994)	Journal Article, Third World Quarterly
Journal Articles, Publication Pending:
‘The Relationship of Political Settlement Analysis to Peacebuilding from a Feminist Perspective’, (2016), Ní Aoláin, Fionnuala / http://www.globaljusticeacademy.ed.ac.uk/documents/SSRN_FOAN_Feminist_Peacebuilding.pdf	Journal Article, Peacebuilding
What we talk about when we talk about Political Settlements (Bell 2015) (http://www.politicalsettlements.org/files/2015/09/20150901-PSRP-Concepts-Working-Paper-1-1.pdf )	Journal Special Issue in preparation for Global Constitutionalism
‘Bargaining Constitutions: Political Settlements and Constitutional State-Building’ (Bell, 2016)	Journal Article, currently in peer review stage in ‘Global Constitutionalism’.
‘Letting off steam: Interim constitutions as a safety valve to the pressure-cooker of post-conflict transitions?’ (Rodrigues, 2016)	Journal Article, currently in peer review stage in ‘Global Constitutionalism’.
‘The Promise and Limits of Eternity Clauses in Post-Conflict Constitution-Making’ (Suteu, 2016)	Journal Article, currently in peer review stage in ‘Global Constitutionalism’.
‘The alchemists: Courts as democracy-builders in contemporary thought’ (Daly, 2016)	Journal Article, currently in peer review stage in ‘Global Constitutionalism’.
‘Courting Peace: Judicial Review and Peace Jurisprudence’ (Sapiano, 2016)	Journal Article, currently in peer review stage in ‘Global Constitutionalism’.