Management Response / Evaluation Report Title: Performance Evaluation Report of Punjab Education Sector Programme II (PESP II) / Project undertaken by Oxford Policy Management (OPM)

Response to Evaluation Report (Overarching Narrative)
Management Response & Recommendations Action Plan / The performance evaluation of PESP II was divided into three phases: Interim Evaluation Report 1 (IER1), Interim Evaluation Report 2 (IER2) and Final Evaluation Report. BHC provided the management response for the IER1 in March 2019. The IER2 was completed in December 2019 but the team decided to wait until the final evaluation report was completed since at that time PESP II was due to end in March 2020. This management response is against the recommendations provided in final evaluation report. / BHC welcomes this final evaluation report which provides a high-quality analysis of the lessons learned during PESP II and sets out clear recommendations to strengthen future programmes. This report focuses on performance evaluation of all components of PESP II including but not limited to the Sector Budget Support (SBS), Technical Assistance (TA), Roadmap/Stocktake, Punjab Education Foundation (PEF), Special and Inclusive Education, School Infrastructure, Scholarships and Adolescent girls’ education. / The report highlights a number of operational challenges around school infrastructure and policy level challenges around education reforms. BHC agrees to most of the recommendations and conclusions except: / The conclusions with regards to infrastructure spending in the latter part of programme. This comment has been repeated a number of times in the report. “Best buys talk about ‘infrastructure as a stand-alone intervention’. Infrastructure in PESP II is considered a ‘bad buy’ as per the best buys report”. The best buys report was published in 2020 and the decision for re-appropriation of funding was taken in 2018, and therefore could not include the evidence from best buys. The decision was based upon the lack of assurance that IMC would complete work assigned and provide safe schools. Therefore, BHC used alternative means to meet commitments on school construction and rehabilitation. / The conclusions with regards to technical capacity and internal staffing resources for the school construction and rehabilitation components. This comment has been repeated a number of times in the report. For TACE/SCRP the factual position on resources is: SCRP SRO was in place by Jan 2016 (at least) and programme management has never been a gap. Infrastructure Adviser provided inputs at 25% before 2017. Since Jan 2017 there has been full time Infrastructure Adviser. BHC works normally on shared resources but SCRP had full time resources starting from Jan 2017. And since then, there have been no staffing gaps or limited capacity issues in any of the BHC positions. Moreover, none of the reviews /audits determined that the performance of TACE was due to capacity issues. In Nov 2019, BHC decided to have a separate and dedicated BHC team to firefight the specific issue that was triggered following the media attention and the need to retrofit. Thus, we see limited staffing issues as factually incorrect and do not agree with the conclusion. / A clear set of lessons learned provide ample information to help BHC strengthen its thinking for the future portfolio. Most of the information provided in the evaluation report will be helpful for BHC to conduct a strong Project Closure Report. / Most of the recommendations provided for the SED in the first interim evaluation report stand and follow-up is required to implement the action plan agreed. The report also provides useful recommendations to strengthen the policy framework around inclusivity, public private partnerships, ed-tech and early childhood education. / This management response provides an action plan of how BHC and the School Education Department (SED) intend to use the lessons learned and recommendations for future planning and for the remaining course of the programme. / Both BHC and SED accept all recommendations of the final evaluation report. The table below provides a detailed action plan against each recommendation of the report.

Evaluation Report Title: Performance Evaluation of the PESP II
Recommendations / (see recommendation section pp 121-124 of the Final evaluation report of PESP II for more details)	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection / PESP II is ending in March 2022. While some of the recommendations below will be implemented over the remaining period of the programme, we expect that a majority of the recommendations will be implemented over the course of a successor programme in Punjab.
Recommendations to Government of Punjab (GoPB): / Recommendation 1: / Develop an improved policy framework for the education sector that is evidence-based and sets out clearly defined medium-term objectives, and that articulates the actions and (in particular) public spending required to achieve these objectives.	Accepted	The education policy developed by the School Education Department (SED) is in approval process. The policy is based around inculcating four core values of Purpose, Critical Thinking, Creativity and Innovation in not only the students at the classroom level, but all actors associated with the delivery of education. It indicates the resolve of SED to ensure improved access to education through reforms in five key policy areas: (i) student enrolment (ii) student retention (iii) school infrastructure (iv) public-private partnerships and (v) facilitation of all education stakeholders. As outlined in the policy, SED will ensure provision of quality education and improvement in learning outcomes through reforms in four key policy areas: (i) student assessments (ii) alignment of curriculum and textbooks with student learning needs (iii) teacher quality and (iv) conducive learning environments. Furthermore, SED will ensure improved governance in education through reforms in five key policy areas: (i) school financing (ii) community engagement (iii) administrative management and procedures (iv) monitoring and evaluation and (v) evidence-based policy actions. SED is working towards achievement of the above objectives. For example, SED has made considerable progress on provision of quality early childhood education (ECE), improving retention through Insaaf Afternoon School Program, building management capacity through training of delivery managers, and improving teaching quality through continuous professional development of teachers at primary and elementary levels. / The education sector plan (ESP) on the other hand addresses the need to have clear medium-term objectives and actions. The ESP is a costed plan with budgets attached to various activities.
Recommendation 2: / Ensure a strong focus within this policy framework (and in other specific programme actions) on gender, equity, and inclusion to address continuing inequalities in education access and performance. This may include additional data collection and analysis to help improve policy, including on so far relatively neglected issues such as learner preparedness (e.g. the influence of health, nutrition, and the home and social environment on learning prospects).	Accepted	The school education policy stresses the need for ensuring equity and inclusion in access to quality education, with a special focus on children with disabilities and those from marginalised segments of society. The policy also focuses on providing quality education in a safe, inclusive and conducive environment. / In addition to this, a Special Education Policy was approved by the Government of Punjab in 2019. This policy was developed with the support from PESP II TA. The policy address immediate challenges such as access, equity, stigma, discrimination, skills, environment, and poverty faced by people with disabilities. The policy also outlines the role which the Special Education Department (SpED) plays in meeting the needs of those with severe and profound disabilities and the role that the School Education Department (SED) has in integrating children who have mild and moderate disabilities into mainstream schools. / On the data collection front, Programme Monitoring and Information Unit (PMIU) of the School Education Department has added indicators for data collection to include equity. The equity enabled data helps the SED to improve policy decision making. In addition, PMIU has improved its data systems and is strengthening the data collection tools, including collection of data on disabilities. The PESP II TA assisted the department in improving the Annual School Census proforma by adding several new fields which could improve the evidence base for planning and decision-making. / SED has an increasing focus on equity, gender and inclusion. The Insaaf Afternoon School Programme (IASP) is one such initiative of the department where the disadvantaged and marginalized children are provided opportunities to continue their education. / SED has also notified a five-year inclusive education (IE) strategy in 2019. The IE strategy provides a robust implementation framework that will ensure that all marginalised groups of children get equal opportunities to an inclusive and quality education. The strategy also emphases the provision of an enabling environment along with attitudinal and behavioural changes at all levels of education, governance, schools, and communities.

Recommendation 3: / An education evidence and information strategy framework should be developed. This strategy should ensure that all information held by government organisations is, so far as feasible, made available for independent analysis, and that a culture of using evidence systematically to inform government policy decisions is fostered. The strategy should emphasise continuing to strengthen information on education sector performance, especially the quality and coverage of information on learning, including to allow a more detailed understanding of the influence of poverty and social factors on learning achievements.	Accepted	The Education Sector Analysis (ESA) analyses the influence of poverty and socio-economic factors on learning achievements and based on this analysis, the ESP will address how the barriers in this regard will be eliminated through policy and better data collection. / SED will continue to explore opportunities for more comprehensive data collection on learning outcomes and their correlation with socio-economic factors. SED is also in the process of developing an integrated EMIS which will capture all data available in the education system and provide a unified dashboard to inform planning and decision-making processes. In addition, the department has scaled up the School Improvement Framework (SIF) across Punjab. SIF uses data and evidence to inform decision-making at the service delivery level through establishing routines and action management.
Recommendation 4: / Ensure that the quality of PFM for education is improved, in particular with a view to improving the rate of budget execution for the non-salary and development budget, and to ensuring the policy framework to guide spending decisions is clear. The main elements of a PFM reform process should include: / a) development and annual updating of a costed sector plan to provide directions to SED and other education sector organisations. / b) strengthening the budget process through budgeting based on strategic plans, the inclusion of budget demands from lower tiers, and the introduction of appropriate costing mechanisms and challenge functions at SED. / c) SED should also consider piloting school-based budgets in some districts, to allow for greater transparency and better financial management. / d) the Financial Management Cell (FMC) should be re-established in SED to continue the reforms on internal audit, the production of budget execution reports, and general improvements in PFM for education service delivery; and / e) SED and PMIU should play a stronger role in the oversight and coordination of donor-funded programmes, including reporting against a common government-led monitoring framework.	Accepted	The ESP is already a costed plan which provides direction to future budget allocations to all departments under SED. / The new government’s approach is moving from a centralised model to a more district/school level, decentralised approach. This could help in empowering district education officers (DEOs) through better budget execution and implementation of development activities. / SED already provides Non-Salary Budgets (NSB) to schools. The budget varies for each school due to its needs. The NSB is used for hiring of temporary staff, minor repairs, sporting equipment, stationary etc. and now a note has been moved to extend the limits to incorporate civil works in NSB as well. SED feels that all factors of the school-based budget have already incorporated under NSB. / SED is keen to establish a Financial Management Cell (FMC). The purpose of FMC is to strengthen the public financial system in the SED and to encourage a bottom-up approach on budget demands. The process of FMC’s formulation is ongoing and BHC is also working with SED to fast track the process. / PMIU already plays the role of a coordination hub for donors, analysis of data and undertaking stocktake routines. Uniform reporting for all donor funded programmes is not possible due to different requirements of each programme.
Recommendation 5: / Resolve outstanding issues relating to the role of PPPs in education, and the regulatory relationship with private education providers.	Accepted	SED developed the PPP strategy with support from PESP II technical assistance. The strategy identified several PPP options (institutional, programmatic, and funding) providing an array of opportunities for SED to address demand and supply side constraints, low-performing public sector schools, low enrolment, and retention rates. / The current technical assistance (TA) supplier is working with the SED for implementing various aspects outlined as part of the strategy. SED is aiming to translate the strategy into PPP policy. The policy will be a step towards agreeing a regulatory framework to streamline engagement with private sector education providers.
Recommendation 6: / Ensure that teachers in both government and private schools have adequate subject knowledge, use appropriate teaching methods, and are effectively motivated and managed, and develop and track measures of teacher effectiveness.	Accepted	SED has developed the CPD framework for elementary school teachers. In the upcoming months, teacher training material will be developed by Quaid-e-Azam Academy for Education Development (QAED) with the support of TA and teacher training will be undertaken providing avenues for improved quality of teaching and learning in schools. In addition, teachers are being trained by the department on Single National Curriculum (SNC). The SED has also developed an Innovative Teacher Support Package (ITSP) which provides avenues for capacity enhancement of teachers in content knowledge and pedagogical skills. SED is also implementing a Classroom Observation Tool (COT) for school management to improve teacher effectiveness. The tool will help the school management to monitor and provide feedback on teaching and learning practices inside the classroom.
Recommendation 7: / Take forward effective implementation of the Inclusive Education Strategy, Special Education Policy, and Early Childhood Education Policy.	Partially Accepted	Early childhood education (ECE) policy is being implemented by SED and more than 15,000 ECE classrooms are functional in the province. A Special Education policy was already approved by Government of Punjab in 2019 and its implementation is underway by the Special Education Department. Regarding the inclusive education policy, SED will work towards the development of an implementation plan and subsequent actions that are within the mandate of the SED.
Recommendation 8: / Resolve outstanding issues relating to the decentralisation of education sector management, with a strong emphasis on strengthening the management role and capacity, and effective local accountability, of schools and head teachers.	Accepted	SED already has in place a decentralized education governance and management mechanism in the form of District Education Authorities (DEAs). In addition, School Councils (SCs) are functional in all schools of the province and are provided planning and financial autonomy through Non-Salary Budgets (NSB). SED has recently supported the capacity enhancement of education managers at all tiers of the district management. Delivery managers have been trained in various aspects of decentralized planning, management, and facilitating quality service delivery at all levels. More than 3200 district managers have been provided training and receive ongoing mentoring support through the PESP-II TA. SED further plans to align its governance systems in line with the Local Governance Act.
Recommendation 9: / Build on initiatives (such as the ALP and Taleem Ghar) that have been developed in response to the Covid-19 pandemic, with a view to providing more effective online and offline teaching resources and options.	Accepted	PMIU have recently produced model lesson plans to further strengthen the Taleem Ghar initiative. In addition, a survey was also undertaken by the PMIU to seek the perceptions of parents, teachers and other stakeholders regarding the effectiveness and reach of the Taleem Ghar initiative. A PC-1 (project) for Taleem Ghar has also been approved based on which, PMIU will develop digital lesson plans and work towards effective outreach of the initiative.
Recommendation 10: / Ensure sufficient stability and effectiveness in the senior management of key sector organisations.	Accepted	The decisions affecting the stability and effectiveness in the senior management positions at SED are mostly driven by complex political economy factors. SED itself has limited control over these decisions. However, both SED and BHC will continue lobbying with the provincial government for continuity in leadership at SED. Additionally BHC provides support through technical assistance and through working at all levels of the SED.
Recommendations to BHC / Recommendation 1: / Theory of Change and Research / Programmes should be developed around addressing well-defined problems and should be based on a fully articulated theory of change (specifying causal pathways and identifying critical assumptions, including those relating to ownership) that focuses where possible on using well-evidenced ways of supporting transformation through capacity development and policy reform. This theory of change should explicitly articulate the factors that affect the performance of key functions for an effective, learning-oriented education system, and be reflected in a structure of objectives (and logframe) that emphasises these. / Where evidence on what will work best is lacking and initiatives need to be developed and tested, research should be supported and pilot initiatives undertaken based on a rigorous design, and with a clearly specified pathway to scale-up and adoption that is agreed with key stakeholders.	Accepted	PESP II is a large and complex programme designed almost nine years ago to support systems strengthening across a full spectrum of education reform areas. It is a sector reform programme in essence. For programmes of this nature and duration, flexibility and adaptation to emerging needs and context is key to their success. It is also challenging to predict how the reform process will unfold years in advance. So while the programme did articulate a Theory of Change upon inception, the programme continued to evolve in a manner that made it difficult to continuously revisit the ToC. We do however accept that if such an exercise had been carried out intermittently over the course of the programme it could have added value both to programme implementation and its subsequent evaluation. / Lessons learnt from PESP II will be incorporated in the Theory of Change for the successor programme in Punjab which we expect will also remain flexible and adaptive. / There are many successful examples under PESP II where pilots have been carried out, rigorously evaluated, and scaled up on the basis of this evidence. Going forward we will incorporate this approach to evidence-based programming and scale up more strongly across the programme. We will also work with DARE (BHC national education programme on data and research in education) to strengthen the evidence base for context specific programming and policy engagement with the Government of Punjab to ensure scale up of successful interventions.
Recommendation 2: / Technical Assistance / Programmes should use TA that is managed through a clearly structured long-term agreement with GoPb and partner organisations that promotes local ownership and engagement but that also ensures an emphasis on agreed transformational objectives. They should have a strong M&E focus on tracking progress against these objectives, as well as on the effective delivery of specific TA outputs and the quality of relationships with partner organisations, while providing sufficient flexibility to adapt to changing needs, evidence, and context. / TA providers should be selected based on their proven ability to work effectively in the local context and to mobilise both high-quality (in both educational, technical, and ‘soft’ consultancy skills terms) international and local expertise, and to provide effective support both to policy development and implementation.	Accepted / Accepted	We do our utmost to ensure that TA is flexible and responsive to the needs of the government, and more importantly prioritizes areas that are necessary to achieve critical long-term improvements in the system. BHC sets objectives for TA through a robust workplan which is agreed in advance with SED. Finding ways of improving the effectiveness of TA remains a priority for us and we continue to learn and reflect on the best possible approach for the provision of TA. / BHC’s procurement procedures are very robust and allow relevant stakeholders to be part of the bid evaluation process. Over the life of the programme, we have experimented with several different approaches to TA provision. We have found TA to be most effective where there is a nuanced understanding of the local context and where TA providers have the necessary skills to engage with government counterparts building strong relationships of trust based on professional excellence. In this process we have made a serious effort to go beyond established practice, to provide the right kind of expertise needed in a given context. Going forward the team will ensure that GoPb counterparts are fully engaged in the development of TORs and shortlisting of potential TA service providers. The government will also be invited to participate in the selection process for TA. Understanding of the local context, strong M&E, flexibility of work plan and right mix of local and international expertise remain key criteria to select the best available technical assistance provider.
Recommendation 3: / Programme design / The technical focus of support should take account of both international experience and local evidence on what is likely to be effective, as well as taking forward selected promising initiatives from previous support. This is likely to include the following: / a) a strong focus on gender, equity, and inclusion, both in the specific choice of areas of action and in the way that activities are designed and managed; / b) supporting and improving the effectiveness of teachers through an emphasis on improved classroom practice, with appropriate supportive tools, strengthened accountability for performance, and incentives linked to evidence of teaching effectiveness; / c) strengthening school-level management and governance, including for the planning and use of financial and staff resources; / d) supporting community and parental engagement – in particular through sharing information about school performance and learning effectiveness; and / e) building on the successes of PPPs in education (for instance through PEF) to establish sustainably financed and managed models that ensure effective regulation where this is appropriate.	Accepted	These recommendations will be picked up in the design of future programme which would cover the following areas of support: / Support marginalised children, mainly girls and religious minorities, to enrol and stay in school and support girls to read by age 10. Technical assistance under this programme will also focus on strengthening the education system to make it more inclusive. / PESP II developed effective tools and strategies for SED to improve teaching quality, accountability, and teacher performance. These include the continuous professional development strategy and school improvement framework. Implementation of both has already started. The future programme will ensure continued implementation of these interventions making improvements where required. / PESP II initiated the training of the district managers to improve governance and school management. The future programme will evaluate the effectiveness of these trainings and help SED to develop a sustainable plan to continue improving school-level management and governance. / Improvement in data collection, particularly on learning outcomes will remain a priority of the future programmes in Punjab. An improved data system will help SED to share further information specifically on school performance and learning effectiveness with public. / PESP II developed the Public Private Partnership Strategy and Education Technology Policy. This is expected to support SED to engage with the private sector to build sustainable partnerships in future.
Recommendation 4: / Financial Aid / Targeted financial support should be made available to complement the TA provided in order to: (i) fund research and pilot initiatives where appropriate; (ii) selectively provide resources where these can be used to achieve high development impact, especially in conjunction with transformational reforms; and (iii) to help resolve key delivery bottlenecks for improving organisational and system performance. This may in principle be delivered through the government budget or in parallel to it, depending on the specific context and problem being addressed. Funding may also be provided to NGOs and CSOs where there is a clear strategic rationale for this in relation to the theory of change governing the intervention.	Accepted	The combination of results-based financial aid and technical assistance has enabled BHC to work with government to address systemic weaknesses and build institutional capacity in education governance and management, public financial management, and transparency, accountability - achievements that would not have been achieved through technical assistance alone. / The focus of programming going forward will be on capacity and systems building to drive sustainable reforms while retaining some targeted, results-based financial aid to strengthen the education system. Supporting systems change where there is political appetite, as Punjab’s track record attests, is highly cost-effective and an aid ‘mega-buy’. / Any future programme will use financial aid to leverage increased government investment and incentivise the government to implement key reforms. Financial aid will be used to tackle the most challenging and ambitious reforms such as ensuring inclusion and equity within the education system, decentralisation of local government, and taking public private partnerships to scale. Disbursement of financial aid will be conditional on the achievement of results agreed with government, as well as incremental increases in government spend on education.
Recommendation 5: / Focus of the programme / The programme should have a strong emphasis on improving access to, and the use and sharing of, information, including a focus on the use of information by parents and communities, as well as for school management, and on building knowledge through research and communication (for instance through providing funding for research, with clear governance arrangements to ensure what is funded is responsive to both government and civil society needs). / The programme should be actively managed by BHC with a view to developing and implementing a joint vision with government and other stakeholders for key elements of the education sector, and to take account of both opportunities and challenges, including those posed by political change.	Accepted	PESP II has a strong emphasis on the collection, use and sharing of the information. The programme has supported SED to strengthen data collection and information sharing by setting data routines with PMIU. The PMIU monitors all public schools on a monthly basis and this information is publicly accessible through PMIU’s website. In addition to this, PMIU also conducts an Annual School Census (ASC) every year and the report is made available on PMIU website. The information collected regarding teacher and student attendance and the facilities available in public schools is used for planning and decision making at the SED. / PESP II extension phase is also supporting the SED to outline a plan to showcase the reforms introduced to strengthen the education systems in the province, to support girl’s education and to share information related to SED’s initiatives to improve learning. / PESP II is ending in July 2021. The current extension is focused on areas highlighted in the evaluation recommendations and will be laying the groundwork for the successor programme in Punjab. The future programme will be much more aligned with the UK Ministerial priorities, KPIs, Smart Buys for Education, and with the Government of Punjab’s New Deal for education (2018-2023). / BHC’s programming is based on thorough research and we consider recommendations from the evaluation reports of existing programmes while designing new programmes. GoPb including SED and its sub-departments will remain on board and BHC team will hold discussions with all stakeholders to gather information for future programming.
Recommendation E.6 on school infrastructure: / In the upcoming amendment, BHC and IMC should take into account challenges in previous rounds, as well as anticipated delivery risks. / IMC and BHC should assign focal persons with responsibility for relationship management with each other, and with the Government. / Management and governance arrangements within IMC’s Humqadam-SCRP team should be restructured to facilitate rapid decision-making and avoid unnecessary delays.	Accepted	Contract amendment 10 in September 2020 (and subsequent ones) were focused on programme management and delivery priorities, with IMC outlining delivery risks going forward and detailed resource-focused workplans. The contract amendment has been helpful in making accountability and delivery stronger. / Workstream leads (both IMC and BHC) are assigned for working level discussions. IMC’s Team Leader and BHC SRO and Senior Programme Manager have stand-alone calls for relationship management and high-level discussions. BHC and IMC jointly manage relationship with government for collaborative messaging, using PESP II team for support where necessary. a focal person has been identified at Government of Punjab level for coordination purposes. / Decision making has improved on some levels within IMC: quality issues identified by third party inspectors are agreed with field teams with remediation plans, without the need to refer to central office for decisions. Similarly, on technical issues, IMC swiftly coordinates with their engineering experts to address safety challenges and agree remedial works. However, some gaps have persisted in the overall programme management approach due to centralised structures. These issues are also being discussed by PCD through an Action Plan process being undertaken with IMC to address organisational-level issues.
E.6.2 Recommendations to IMC
1. IMC should focus on setting systems which ensure that the planning and design phase of the programme is able to deliver modest yet safe, attractive, accessible, equitable, and durable learning environments that meet local needs	Partly accepted	The current Humqadam-SCRP has already featured (i) wide use of local works contractors under modern FDIC-style Contracts, (ii) a practiced commitment to capacity building of those contractors and local suppliers in the various SCRP construction innovations, and (iii) engagement via both our Engineering and Community Development staff of the School beneficiaries at community, Schools and provincial government levels progressively in the ‘ownership’ dimension of the schools being delivered. IMC agrees that local technical and beneficiary engagement could have been integrated usefully into the earlier stages of Programme planning.
2. The design of facilities should take into account locally available building materials, and skills and techniques among local artisans.	Partly accepted	While this is broadly acknowledged, at the outset of Humqadam there was a strong strategic focus between BHC and IMC on introducing new concepts, practices and materials in school construction, particularly those suited to large volume, accelerated delivery of School construction, influenced by the proven weaknesses and poor sustainability of previous school infrastructure in KP and Punjab. The original IMC design emphasis on innovation (with its inherent risks) in design and execution was then broadly endorsed by BHC.
3. IMC should incorporate robust systems for assessing risks, and continuous monitoring, evaluation, and reporting from the very beginning of the programme. M&E should be undertaken in an open and transparent manner by a multi-disciplinary team.	Partially accepted	IMC has had a risk management system and carried out adaptive actions as required under the programme [NB: things like changing the award strategies, changing the QA systems etc]. A stronger forward looking risk analysis function on part of IMC was an area of weakness, which was flagged at review points. For future programmes, IMC could ensure a stronger methodology and oversight, and adopt a more proactive rather than reactive approaches.
4. IMC should focus on developing a financial management system to secure VFM. For example, a cost database would work as a useful benchmark for monitoring progress on the VFM front.	Partly accepted	Given the ultimate shared BHC / IMC interest in VFM, it is agreed that a more VFM-oriented FMS with an integrated ‘works cost’ database would have been valuable from the outset of SCRP. However, that would necessarily require a more comprehensive VFM strategy and processes that address (e.g.) delivered asset value, life-cycle costs and systematic benchmarking on those fronts also, beyond the focus on only short-term inputs costing and budget management.
5. It is important to consider maintenance arrangements, in particular given the limited NSB funds available for schools53. This is particularly key for IMC schools, where maintenance costs are expected to be higher. One approach to streamline maintenance measures may be to prepare and share standardized documentation pertaining to maintenance arrangements at the time of handover. Similarly, for the R&R component within PSCRP, plans for maintenance of innovative inputs such as the makerspaces, upgradation of IT equipment, must be established.	Accepted	IMC/SCRP has long been committed to providing guidance to Education authorities and schools-linked Community Entities on the Maintenance post-release of schools constructed / enhanced under the Humqadam programme, as a vital part of assisting them to better manage the School assets for an optimal service life. Until recently this advising and guidance was delivered at-site by Engineering and CD staff as part of Handover activities. Now IMC has issued a comprehensive School Maintenance Guide in both English and Urdu to all Humqadam schools’ stakeholders at school, district and provincial government levels on this. With respect to the R&R component within PSCRP (reference innovative inputs such as the makerspaces, upgradation of IT equipment, etc.), NSB available with the schools will be used for future maintenance and the School Councils will ensure the periodic maintenance of the equipment provided under R&R component of PSCRP.
E.6.3 Recommendations to BHC for school infrastructure investments / 1. Targets must be realistically set, taking into account timeframes and available capacities. / 2. School infrastructure interventions require greater planning at the conception/inception stage. The planning stage must recognise the context of the target areas. / 3. Where infrastructure investments form part of wider programmes, adequate resourcing must be ensured from the beginning, with dedicated governance structures, risk mechanisms, and monitoring arrangements. / 4. For infrastructure programmes, arrangements for third-party verification must be established from the very start of the programme’s implementation. Continuity in such arrangements must also be ensured. / 5. The design phase should be informed by environmental and social assessments, / 6. Keeping in view programmes’ size and complexity, a comprehensive theory of change should inform the programme design. In particular, the theory of change must take into consideration the complexity and context of innovations, and push for evidence-based interventions that have been piloted/tested. / 7. A stronger commitment to gender and equity concerns at the inception stage must be supplemented by a similarly strong commitment to these concerns at the implementation stage. / 8. A rigorous monitoring strategy is needed right from the start to allow for a focused and robust follow-up of the targets and to prevent the identification of a bigger shock at the end of the implementation year/period. / 9. Clarity of terms in contracts is essential, particularly where adherence to infrastructure quality and safety standards is concerned. For infrastructure programmes in particular, processes for design approval, handovers, and liability must be clearly laid out. / 10. Innovations must be backed by evidence and/or piloted during the inception stage by the service provider, before moving on to the implementation stage. / 11. Alternatives to infrastructural provision can been sought and established at the inception stage, as opposed to being considered as mitigation efforts. / 12. Adherence to good financial planning and management practices must be a mandatory requirement for all partners. Fiduciary risks can be mitigated through a number of measures, including the involvement of local communities, the maintenance of good baseline information, setting up site supervision, and reporting, monitoring, and verification procedures.	Accepted	Recommendations on target setting and planning for future programmes have been noted. / Contract Amendment 10 locked clear monthly targets against each workstream. The budgets were realigned to match the resources needed to deliver the pending scope of delivery. / Noted for any future intervention design. / A well-resourced team headed by A-1 SRO and Senior Programme Manager including Programme Management and Technical expertise was established to manage the IMC project. Workstream leads (both IMC and BHC) are assigned for working level discussions. / Third Party monitoring and verification was very useful in the delivery of the project’s results. Noted for any future Infrastructure Intervention. / Noted for future programmes / Theory of change remains at the heart of each programme. BHC will ensure that the ToC is more adaptive and flexible for future programmes. / Noted for future programmes. / Monitoring was part of the programme since start. However, the suggestions are noted to further improve it in future programmes. / Contract amendment 10 clearly captured the SOPs for the handover process. / Noted for future programmes. / We will think of alternatives from start in future infrastructure programmes. / Noted for future infrastructure programmes.
E.6.5: Additional recommendations on school infrastructure from supplementary evaluation study
1. It is essential that BHC, Humqadam-SCRP, and TCF determine appropriate mitigation measures in order to address possible risks to programme delivery should handovers be delayed. / 2. It is important to consider maintenance arrangements, in particular given the limited NSB funds available for schools. This is particularly key for IMC schools, where maintenance costs are expected to be higher. One approach to streamline maintenance measures may be to prepare and share standardized documentation pertaining to maintenance arrangements at the time of handover. Similarly, for the R&R component within PSCRP, plans for maintenance of innovative inputs such as the makerspaces, upgradation of IT equipment, must be established. / 3. Uniform reporting mechanisms across suppliers can allow for easier comparative analyses. This pertains to reporting on targets that are common to all three suppliers: classroom construction and per unit costing, per unit technical/operational costs, handovers, and number of quality concerns raised and addressed. / As BHC plans to conduct a Value for Money exercise for the infrastructure component towards the end of the program, important aspects to consider in this exercise include: / 1. The methodology should emphasise the quantification of benefits and the required data gathering and analysis, taking into consideration the availability and quality of existing data. Moreover, qualitative assessment through perception surveys which provide an opportunity to gather experience of the community level stakeholders should also be considered. / 2. A representative minimum sample for each of the three components (IMC, TCF and PMIU) which considers the geographical variation in civil works, choosing sites which have adequate data available, and avoiding sites where construction is still on-going, or schools are non-functional. / 3. The infrastructure experts should be tasked with the evaluation of the primary facilities (classrooms, toilet blocks, furniture) with every facility evaluated against a robust criterion discussed in the grading matrix. / 4. Efficiency assessment must include a review of the life cycle of the facilities. The aspects to be considered to determine this include school design and construction specialisation, material specification, labour quality, hazardous impact and environmental impact. / 5. The exercise should take account of international evidence that the cost effectiveness in relation to achieving improved learning outcomes of spending on school infrastructure is generally low (e.g. it is classified as a “bad buy” in World Bank/BHC 2020) in considering, for instance, whether funds should have been redirected to more cost effective forms of support, given the context following long delays in implementation.	Accepted / Accepted / Partially accepted	Various mitigation strategies have been employed, including extensive monitoring of workplans and support to suppliers on engagement with government to facilitate handovers. / IMC has prepared maintenance guides in Urdu and English which also have details for addressing workmanship defects during the defects liability period (DLP). These guides have been shared with schools to facilitate in maintenance. / All construction components came online at different times under different modalities, and all have had different requirements. Furthermore, the reporting and information requirements have kept evolving over time as delivery got more complex. Some reporting areas remain standard; however, all components differ in terms of logframe targets and reporting areas. / Noted. The detailed VFM analysis considering the recommendations will be available through Project Closure Report after PESP II ends.