## Annual Review

Title: CSSF Economic Stabilisation Project II
Programme Value £ (full life): £2,580,668		Review date: 01/09/2021
Programme Code: 301189	AMP start date: 23/09/2020	AMP end date: 31/03/2022

Summary of Programme Performance
Year	2021
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	N/A – this programme is CSSF
DevTracker Link to results framework:	Given the programme is currently in transition, the results framework will be published in Q3 2021 once changes are complete.

A. SUMMARY AND OVERVIEW

Description of programme

Yemen’s economy remains in crisis, fragmented, and at risk of further deterioration, exacerbating humanitarian need. The depreciation of the Yemeni Rial has dramatically reduced households’ purchasing power whilst the illegal war economy continues to drive the conflict. While the UK’s main political objective for Yemen is to work towards an inclusive peace process and comprehensive nationwide ceasefire, it is important to recognise the intrinsic relationship and critical contribution of economic and stabilisation activities in achieving that goal.

The CSSF Economic Stabilisation Project II contributes directly towards Yemen’s economic stability, which is a key outcome in the development/humanitarian pillar of the UK’s National Security Council Strategy for Yemen. The pillar aims to reduce humanitarian suffering and enhance the protection of civilians and build resilience. The project also contributes towards Campaign Goal 3 of the Yemen Country Business Plan. The Goal aims to promote economic stability by supporting the development of sustainable economic policies that prevent economic collapse, increase resilience, and provide incentives for an inclusive political settlement.

The project builds on the first phase of support in 2019/20 and responds to political developments in Yemen. It aims to complement the UK’s political engagement and commitment on the economic and wider economic stabilisation efforts in Yemen through capacity building of key economic institutions, supporting the collection of reliable national statistics, developing analysis on key economic issues and trends, supporting consultations on economic issues related to the peace process. Due to the conflict having divided the country, the project predominantly operates with institutions in the south of Yemen under the control of the internationally-recognised government. The exception is the component working with the Central Statistical Organisation which is one of the few national institutions which has not fragmented into north and south.

The CSSF Economic Stabilisation Project II was originally approved in August 2020 with a budget of £1,655,817. It has five parts across four partners:

1. Technical assistance to the Central Bank of Yemen (CBY) and the Ministry of Finance (MoF): On the job training and development of operational manuals to support improved public financial management and greater accountability and transparency. The total value of the component is £1 million, and the partner is USAID.
2. Capacity building of the Central Statistical Organisation (CSO): Preserving the capacity of the CSO to compile reliable and more up to date national accounts data. The total value of the component is £150,000 and the partner is the World Bank.
3. Data analysis: A range of detailed thematic and rapid analysis reports on economic issues and the development of the Yemen Economic Tracking Initiative to track key economic issues. The total value of the component is £208,312, and the partner is ACAPS.
4. Convening of Yemeni economic stakeholders: Consultations on economic issues related to the peace process. The total value of the component is £15,484, and the partner is the International Growth Centre (IGC).
5. Strategic Support to the Executive Bureau of the Prime Minister’s Office: Economic advisory support to the Executive Bureau. The total value of the component is £186,331 and the partner is the IGC.
This is the first Annual Review for this programme and examines activities completed from the start of the programme in September 2020 to April 2021.The first phase of the programme ran from 5th November 5th to 31st August 2020

In June 2021, the CSSF Yemen Country Board approved £1.2 million additional funding, and a programme time extension to March 2022. This is being used to fund: further analysis through ACAPS, additional support through USAID to the Central Bank of Yemen, and to extend the support provided to the Executive Bureau.

In light of the above, it should be noted that this Review reflects a programme in transition, evaluating less than 12 months of activities.

Activities undertaken between April 2021 and March 2022 will be examined as part of a full project closure review (PCR) which will evaluate this programme in greater detail.

Summary supporting narrative for the overall score in this review

The overall score awarded for this period of the programme is A. Four out of five outputs were judged to have met their targets and one partially met the targets. This reflects consistent delivery of outputs against expectations across the different programme components.

The UK has been able to provide targeted support to key institutions to develop sustainable economic policies that prevent economic collapse, increase resilience, and provide incentives for an inclusive political settlement.

In addition to the immediate, short-term support provided, International support for the fledgling government has been key and the project has laid the groundwork for supporting institutional resilience while preparing for stabilisation, recovery and longer-term World Band-led reconstruction.

The programme continues to align with, and contribute to, the National Security Council Strategy for Yemen, and CBP Campaign Goal 3 which centres around economic stability, and Campaign Goal 4 regarding institutional resilience and recovery. The programme also aims to mitigate against the portfolio-level risk on macroeconomic instability by enhancing the capacity of key economic institutions.

Key economic risks identified by ACAPS were referenced by the United Nations Humanitarian Country Team and HMG engagements were regularly used to discuss the support provided and secure buy-in from key stakeholders.

Major lessons and recommendations for the year ahead

The recommendations from the Project Closure Review (PCR) of the Economic Stabilisation Project I are included as Annex I, with progress updates.

Lessons:

- Holistic benefits of technical assistance: Multiple components of the programme deliver technical assistance to Yemeni institutions and state bodies. The value of these components extends beyond the technical assistance provided, building important relationships within the institutions themselves and with international bodies, including FCDO. The predecessor programme (Project I) was forced to deliver some technical assistance remotely due to the COVID-19 pandemic – the investment required to maintain the relationships built was stark in comparison to the in-person technical assistance of this project. This programme has found that technical assistance is most successful when provided in person, with experts embedded in the target institutions.
- Embedding Policy and Programming: The analytical work undertaken as part of the Economic Stabilisation project has benefitted from having strong FCDO Yemen ownership. This has facilitated the integration of feedback and collaboration with policy development at key points in compiling the products, thus increasing quality and relevance.
- Benefits of cross-office involvement in CSSF: Coupled with improved understanding, there are benefits to be gained from improved policy and programme cohesion. Bringing these interests together from the concept stage boosts collective ownership, followed by using ongoing feedback to maximise the outputs of each project and thus enhancing overall impact. This was demonstrated by the economic track paper.
- Flexibility and responsiveness: The Yemeni context remains fluid. The programme has demonstrated the ongoing need for flexibility and responsiveness, both in operation and expectation. The ACAPS rapid analysis provided FCDO with a mechanism to better understand, and address in diplomatic engagements, the emerging issues over the review period. While flexibility and understanding around the external constraints faced by the IGC has provided space for valuable relationships to grow.
- Given the challenging operating environment, compounded by the ongoing impacts of COVID-19, FCDO should continue to exercise flexibility to adapt to ensure timings and ambitions are realistic.
Recommendations for the year ahead are:

1. In the next phase of programming, FCDO should reconsider the impact of weighting of outputs given the lower funded components will have the least impact. This is evident in Output 4, which for a value of 5% demonstrated a larger impact by engaging key stakeholders such as OSESGY on the economy.
2. We have requested that partners use standard CSSF report templates to make reporting consistent across the programme’s components. Going forward, FCDO should consider adding a section on VfM so that partners can highlight achievements and lessons. Similarly, partners should be requested to incorporate a gender lens to their reporting, clearly outlining how they are considering and addressing gendered dynamics in their activities. The reporting schedule for all components should also be reviewed to ensure balance between formal and informal updates.
3. FCDO should work with partners and Third Party Monitoring institutions to strengthen monitoring and evaluation tools in order to verify results and capture medium or longer-term outcome level impacts. This is particularly relevant to USAID work where technical assistance is provided to the CBY, as well as to ACAPS’s analysis. FCDO could consider utilising its contracts with Tahseen or ITAD and their Political Access and Influence (PAI) tool to produce in-depth assessments or case studies on these specific components.
4. Linked to the above, FCDO should develop an indicator to monitor and ensure that the policy-programme cohesion demonstrated over the review period is continued. If successful, this could be adapted and used across the FCDO Yemen portfolio.
5. FCDO’s support to USAID’s ELRP should consider more strategic interventions such as prioritising linking CBY reforms with Special Drawing Rights (SDRs), and increasing engagement with IMF’s wider reform agenda and priorities.
6. Given the success of the Economic Stabilisation Project Phase I and this Phase II, FCDO should consider how to deliver more long-term economic programming. Utilisation of CSSF funding to date has had benefits, especially around flexibility, but in order to contribute to sustainable economic recovery FCDO should commit to multi-year economic programming. This links to Recommendation #5 and FCDO taking a more strategic view of interventions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change underpinning the programme is that technical assistance to key economic institutions and analysis of economic issues (outputs) will support improved understanding by FCDO, the Government of Yemen and the Central Bank of issues related to the economy, ensure high quality data on the economy is made available to a range of stakeholders and support improved functionality of economic institutions (outcomes) and this in turn will contribute to economic stability, reduced humanitarian need and a sustainable peace process that gives due consideration to the economic drivers of conflict (impact).

The main assumptions behind the theory of change are that a peace process remains viable and parties to the conflict are engaging on it; the conflict doesn’t escalate to the extent that project activities are no longer possible; the effects of project activities are sustainable over time and there is continuous engagement and coordination with key stakeholders. Over the review period, the UN-led peace process continued to face delays and there have been escalations in both military and economic conflict. However, the ToC assumptions continue to hold and economic deterioration over the review period has strengthened the justification for this programme. There are no changes proposed to the theory of change at this time.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track across the Outputs. The programme Outcomes are partially dependant on external factors, but the programme’s contribution to these is also on track.

Though not specified as a programme Outcome, another avenue through which the programme has been contributing to the Impact of Economic Stability is the utilisation of programme outputs as part of FCDO’s diplomatic engagement. FCDO’s dissemination of analysis carried out by the programme in strategic diplomatic fora has supported other international donors to also contribute to economic stability. This policy-programme cohesion should be continued in the year ahead.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis of outcome and output achievement, the programme continues to represent good value for money and should continue.

This programme is FCDO Yemen’s flagship contribution to Campaign Goal 3 – promote economic stability. It also directly contributes to Campaign Goal 2 – alleviate humanitarian crisis – and Campaign Goal 4 – support institutional resilience.

The Economic Stabilisation programme demonstrates the UK’s continued leadership and determination to end the world’s largest humanitarian crisis through sustainable solutions. It rightly recognises and champions the intrinsic connection between economic stability and humanitarian needs.

C. DETAILED OUTPUT SCORING

Output Title	Capacity building of the Central Bank of Yemen (CBY) and Ministry of Finance (MoF)
Output number:		1	Output Score:	A+
Impact weighting (%):		50%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Expectation
1.1 Assistance provided to CBY to facilitate implementation of Phase 1 action plan recommendations in banking supervision.	Complete	Complete	Met
1.2 Assistance provided to CBY to facilitate implementation of Phase 1 action plan recommendations in anti-money laundering / counter-terrorism financing	Complete	Complete	Met
1.3 Assistance provided to CBY to respond to the contractionary macroeconomic impacts associated with the COVID-19 crisis	Complete	Complete	Met
1.4 Assistance provided to establish a monthly CBY report which presents and analyses information related to major macro-financial performance parameters; including the CBY and commercial banking sector balance sheets, foreign reserve balances, debt indicators, and other relevant macro-financial data.	Complete	Complete	Met
1.5 Assistance provided to the Ministry of Finance in budget preparation and execution.	Complete	Complete	Met
1.6 Assistance provided on foreign exchange management to the CBY	Complete	Complete	Met

Briefly describe the output’s activities, and provide supporting narrative for the score.

This output builds on Phase I of the FCDO’s partnership with USAID and Pragma. FCDO renewed its support to the provision technical assistance to CBY Aden for a second phase, through USAID’s Economic Recovery and Livelihoods Programme (ELRP), starting in September 2020. This output has scored an A+ due to the high quality of deliverables and relationships built. Given this continued positive performance, FCDO will seek to provide a third batch of support.

Ten highly qualified experts with Arabic language skills continue to provide strategic assistance through a combination of on-site mentorship and on-the-job training support provided to CBY and Republic of Yemen Government (ROYG) stakeholders in Aden. Their work is supplemented by off-site or virtual support on related analytical activities. Building on the gap analysis conducted in Phase I, and in line with the key areas listed in the action plan based on the IMF diagnostic, technical assistance during Phase II was successfully delivered on the following six functional areas:

1. Bank Supervision & Risk Management
2. Anti-Money Laundering and Counter Financing of Terrorism (AML/CFT)
3. COVID-19 Response Analysis
4. Monetary Statistics Collation/Reporting
5. Budget Planning and Execution
6. Foreign Exchange Management

Output Indicator 1.1 - Bank Supervision & Risk Management

Technical assistance aimed to address the regulatory, procedural, and organisational restructuring recommendations, were developed to facilitate best-practice policy, procedural, and related analytical framework reforms. Acting on these recommendations, the technical assistance focused on the safety and soundness of the financial regulatory framework and the monitoring and compliance system of the CBY Aden. This included the development of new supervision manuals, implementation plans for a new organizational structure for financial sector supervision, and the delivery of an online training in ‘CAMELS’-compliant supervisory oversight techniques for the Bank’s supervision staff. It also included the development of an action plan advocating for the establishment of an internal control and risk management regulatory framework and oversight system within the Bank Supervision Department (BSD), and at a CBY-wide level.

Output 1.2 - Anti-Money Laundering and Counter Financing of Terrorism (AML/CFT)

The technical assistance aimed to address substantial deficiencies with the AML/CFT regime, to make it more consistent with the Financial Action Task Force (FATF) standards. To do this, ELRP worked with the CBY BSD and the Financial Intelligence Unit (FIU), proposing regulatory amendments to the AML/CFT regime. The CBY management endorsed these amendments, and agreed to advocate the convening of the National AML/CFT Committee as soon as possible to approve them and submit them to President Hadi for promulgation. While the amendments are pending presidential endorsement, the technical assistance continued to address reforms through the issuance of two new AML/CFT circulars, and by developing compliance and AML/CFT inspection manuals, which were formally adopted by the CBY BSD. The latter for example will ensure that banks and financial inspectors comply with the requirements specified in the AML/CFT Law aimed at detecting and preventing money laundering and terrorist financing activities. Furthermore, the technical assistance also helped strengthen the cooperation between the CBY and FIU, through the drafting of a Memorandum of Understanding, which governs the entities’ cooperation on AML/CFT matters.

Output 1.3 – COVID-19 Response Analysis

ELRP, working closely with the CBY, produced an assessment of the impacts of the COVID-19 pandemic on the Yemeni economy, and the monetary and fiscal policy responses initiated by the Yemeni government to address these impacts. The assessment looked in depth at the impacts of COVID-19 on public spending and revenues, and inflation/exchange rate pressures. It included a list of programmatic monetary and fiscal policies in response to these impacts, developed by ELRP’s experts in close collaboration with the CBY and MOF. While further measures are needed, ELRP has already been assisting the CBY to address some of these impacts. E.g., to address the impact of the crisis on inflation and liquidity, ELRP assisted the CBY to design a robust monetary program, to help contain inflation within reasonable limits. The program proved to be highly effective as it helped rationalize the money supply and limit the inflationary pressure caused by monetary emission. Similarly, to address the downward pressure on the exchange rate, which has escalated due to the pandemic, ELRP developed an action plan to assist the CBY in establishing a competitive and transparent Foreign Exchange (FX) allocation system that can promote price discovery and improve market stability.

Output 1.4 – Monetary Statistics Collation/Reporting

Building on work conducted under Phase I, the ELRP team assisted the facilitation of efficient collation and regularized publication of relevant macroeconomic data, which provided a snapshot of macro-financial performance in Yemen. This work has also provided an opportunity for the development of concise policy notes on key macro-financial policy issues of interest to financial sector stakeholders. ELRP specifically helped develop a framework for systematically gathering and collating the relevant macro-financial information. The CBY approved the reporting format for the data, which was entitled the Quarterly Bulletin of Economic and Monetary Developments.

Output 1.5 – Budget Planning and Execution

The technical assistance focused on providing targeted technical assistance to relevant Ministry of Finance (MOF), Ministry of Planning and International Cooperation (MOPIC), and selected line ministry staff on the development of improved budget planning. This included providing support to2021 budget projections; the development of better practice compliance guidelines and manuals, as well as the delivery of training to MOF staff. ELRP has also developed a comprehensive action plan for budget execution reform, which was endorsed by the MOF and the CBY, transitioning the support from planning to execution.

Output 1.6 – Foreign Exchange Management

Based on the gap analysis, the technical assistance focused on rebuilding CBY’s macro-financial regulatory/procedural planning and oversight capacity. In addition to providing detailed guidelines, the technical assistance outlined an action plan to enhance the CBY’s foreign reserve position and its practical foreign exchange management capacity.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.

Value for money across the programme is assessed in Section E.

The quality of deliverables and relationships built through this project constitute good VfM (Effectiveness). Similarly, the broader impact of this work is beneficial to FCDO’s other programmes in Yemen and diplomatic engagements.

This output delivered VfM as FCDO capitalised on USAID’s existing Economic Recovery and Livelihoods Programme (ERLP), saving on procurement and administrative costs. Support to this programme gave the FCDO more bang for buck as it contributed towards a larger impact beyond the amount of its support. It also brought the work of the FCDO and USAID closer together, complementing diplomatic engagement between the US and the UK on Yemen’s economy. Finally, the main cost of this programme, the fee rates of the ten consultants were examined by FCDO’s Procurement and Commercial Department and deemed to be competitive.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output is now complete. Another agreement will be signed imminently with USAID to renew this stream of work. The areas of the action plan to be prioritised with FCDO funding are currently being determined in consultation with USAID, the IMF, the World Bank and the targeted institutions. The logframe will be updated accordingly.

The indicators used in this phase of the programme are binary. In the next iteration, FCDO should seek to agree a qualitative element with USAID/Pragma.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The recommendations from the Project Closure Review (PCR) of the Economic Stabilisation Project I are included as Annex I, with progress updates.

Lessons learned for this output are:

- Due to the COVID-19 pandemic, ELRP experts worked remotely for most of the duration of this phase of the programme, although some spent some time in Aden. This was challenging in terms of the experts’ ability to provide effective on-the-job training to CBY staff, and to ensure they were not working in silos. Therefore, high-level engagement between CBY and USAID/FCDO was critical to overcome these challenges and secure buy-in into the assistance provided, albeit remotely
- More tailored and targeted monitoring and evaluation is required to reflect the medium and longer-term impacts of the technical assistance provided to CBY staff, in the form of guidelines and manuals, and also capacity building training. Current reporting does not reflect how the technical assistance is being embedded and utilised by CBY staff.
- There may be a need to further develop and make clear the terms of reference for the experts embedded in the CBY, as some of the tasks they are performing, and the areas they are addressing fall within the remit and responsibility of other actors, such as the IMF on monetary-related issues.
Recommendations for this output are:

- Future collaborations between the FCDO and USAID should prioritise linking CBY reforms with the Special Drawing Rights (SDRs),
- Increase engagement with IMF’s wider reform agenda and priorities to ensure that ELRP is not creating or exacerbating a parallel currency system.
- FCDO should utilise tailored monitoring and evaluation tools such as the Political Access and Influence (PAI) tool to monitor and measure the impact and added-value of technical assistance to institutions such as the CB. This includes systematising the collection of feedback for these targeted institutions. PAI case studies could for example focus on how technical assistance increases the confidence of the Yemeni public and the international community in these institutions.
- Related to the above, and to increase CBY’s transparency and communications, an update to CBY’s website should be considered in order to reflect the latest statistics, as well as the Quarterly Bulletin of Economic and Monetary Developments (Output 1.4).

Output Title	Restoring capacity of the Central Statistical Organisation
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Expectation
2.1 New base year of the national accounts of Yemen completed following the main concepts and definitions of the 2008 System of National Accounts.	March 2021	Complete	Met
2.2 Supply-use table for the new base year to derive GDP estimates from the production, expenditure and income approaches completed	September 2021	On track	Met
2.3 National accounts series for GDP completed from the base year onwards	September 2021	On track	Met
2.4 Quarterly national accounts series consistent with annual national accounts are completed and disseminated (including seasonal and calendar adjusted series)	September 2021	On track	Met

Briefly describe the output’s activities, and provide supporting narrative for the score.

The Central Statistical Organisation (CSO) is a vital economic institution that remains united and politically neutral. Due to the departure of a large number of managerial and experienced technical staff, the CSO’s capacity has been severely eroded over the past years, while deteriorating security conditions and geographical divisions have significantly reduced the CSO’s ability to collect statistical information to cover all activities and all parts of the country. As a result, since 2014 no official statistics, including but not limited to national accounts (NA) and consumer prices, have been compiled in Yemen, hampering effective monitoring and analysis of Yemen’s socio-economic conditions, including economic impacts of COVID-19 and debt sustainability analysis. In the absence of reliable statistics and up-to-date information, the IMF and World Bank have been unable to update a Debt Sustainability Analysis for Yemen, which was last conducted in 2014. Given the importance of reliable statistics and evidence for the formulation and monitoring of reconstruction and development plans in the future, it is crucial to rebuild and preserve the CSO’s capacity to compile reliable NA indicators.

2.1: Rebasing of National Accounts Series entails replacing the old base year used for compiling the constant price estimates to a new, more recent base year. This allows for comparisons with more recent prices in the economy and increases the relevance of the information.
Completed in March 2021. The World Bank developed a good understanding of Yemeni NA, data sources and compilation methodology, updated the methodology with CSO to better suit the context, provided training on NA compilation, and reached a consensus with the CSO to change the NA base year from 2000 to 2012 (the year with the best data quality and quantity across sectors).
2.2: Supply use tables provide an overview of the availability of goods and services (supply) and the destination (use) of the production, among the different sectors of economic activity.
On track. This extensive area of work is nearing completion. The World Bank and CSO have completed data collection, discussed and developed a deep understanding of the data, built the supply use tables and quality assured. Capacity building of CSO is ongoing, to ensure staff can use the tools once this project is complete.
2.3 & 2.4: National accounts systems are used to measure the economic activity of a country. They include measurements pertaining to output, expenditure and income activities in the economy.
On track. Completion of this work area would be above and beyond the CSO’s pre-war operation; the main focus is capacity-building CSO to be able to complete quarterly NA series. The methodology has been built and staff are being trained on this and how to clean/QA the relevant data. Dissemination routes are under discussion, such as publishing on the CSO website.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Value for money across the programme is assessed in Section E.

The quality of deliverables and relationships built through this project constitute good VfM (Effectiveness). Similarly, the broader impact of this work is beneficial to FCDO’s other programmes in Yemen and diplomatic engagements.

Economy: The FCDO and World Bank teams negotiated a lower allocation of overheads for this project, compared to the organisational standard rate. This reduced the project cost and increased the percentage of funding going to direct activities.

Effectiveness: Reliable and up-to-date information is crucial for the formulation and monitoring of development plans. Therefore other FCDO programmes will benefit from this project’s outputs, through improved evidence for decision-making and planning.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made over the course of the Review period to March 2021.

During the second phase (April 2021 – September 2021), the World Bank will help modernise the CSO’s approach to data collection. Indicators and progress on these items will be evaluated in full in the PCR.

Although not a planned change, there is a risk that the deteriorating context may affect completion of indicator 2.4. If the conflict and fragmentation prevent quarterly data from being collected, then the CSO will be unable to complete and generate quarterly series. Indicator 2.4 may require adjustment to reflect.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons:
Informal reporting and partnership communication is particularly important.
Recommendations
FCDO should proactively engage with other institutions considering funding technical assistance to the CSO to ensure the sustainability of this project’s outputs and discourage fragmentation. FCDO should leverage its relationships to encourage other institutions to consider the most appropriate timing for further technical assistance (e.g., immediate term, or recovery/reconstruction period). Future technical assistance could address related information areas, such as external debt or public finances, that will improve the quality and overall statistical capacity in Yemen.

Output Title	Analysis of key economic trends and risks and economic data made available
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Expectations
3.1 Number of quality and timely thematic products delivered	2	2	Met
3.2 Number of quality and timely rapid analysis support products delivered	2	2	Met
3.3 Number of joint analysis meetings to disseminate findings from the research	2	1	Partially Met
3.4 Number for reports translated to Arabic	4 (on demand)	3	Partially Met
3.5 Web-based economic database and interactive dashboard developed	Complete	Complete	Met
3.6 Daily monitoring and tracking of economic trends and risks based on the analysis framework developed in phase I	Complete	Complete	Met

Briefly describe the output’s activities, and provide supporting narrative for the score.
Building on Phase I, the purpose of this output is to provide a platform, which tracks key economic trends, developments and risks in Arabic and English to support economic policy making for Yemen; and to make these accessible through an online interactive dashboard.

Outputs 3.1 - 3.6

The project delivered an online user-friendly and accessible tool, which effectively presents qualitative and quantitative analysis on the economic and political situation in Yemen. The dashboard attracted strong interest from economic actors, and more than 3,400 users visited the dashboard’s landing page by 31st March 2021.

The project also delivered the following pieces of analysis:
- Thematic analysis, split into two phases, focusing on remittances. While phase 1 focused on the impact of COVID-19 on remittances into Yemen, phase II encompassed a broader focus on remittances, both regionally and internationally. The analysis was presented to the Quad’s Technical Advisory Committee (TAC), generating a lot of interest among its members. The discussion with the TAC focused on how the findings of the analysis could be taken forward to develop policy recommendations. TAC members made verbal commitments to provide feedback to the FCDO, which will be incorporated as part of the next stage review process.
- Rapid analysis, which mapped out scenarios for reduced external financial support in Yemen, for the benefit of the FCDO’s internal planning and analysis.
- Rapid analysis was also conducted on options for Saudi fuel provision.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.

Value for money across the programme is assessed in Section E.

This output delivered VfM in various aspects. ACAPS and Mercy Corps saved the set-up costs of the online dashboard by utilising an existing agreement with Amazon Web Services to host it at no additional cost to the FCDO. The dashboard also builds on existing, established analysis capacity already available within ACAPS and Mercy Corps. This helped keep cost down by sharing costs including office rent, management and support staff across a broader base, which freed up funding to focus directly on delivering analysis products.

Furthermore, ACAPS collaborated with another FCDO partner organisation, utilising their broader organisational access to data sources in order to enhance the rigour and coverage of their analysis.

Finally, the impact this project has had on HMG’s and other relevant stakeholders’ effort far exceeded the amount of funding provided by FCDO. The analysis contributed to a broader discussion on how to strengthen monitoring and contingency planning for economic risks in Yemen. Key economic risks identified by ACAPS were referenced by the UN Humanitarian Country Team, and in HMG engagements to review support and generate buy-in among key stakeholders.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The number of rapid analysis products and joint analysis workshops were revised down due to the reduced project timeframe.

Looking forward, an extension has been signed and logframe indicators are being finalised. Progress against these will be reviewed in the PCR.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The recommendations from the Project Closure Review of the Economic Stabilisation Project I are included as Annex I, with progress updates.

Lessons:
The project team agreed to gradually build and develop the online dashboard, starting with simple architecture, and progressing towards adding more features in agreement with the FCDO’s technical and management team. This approach helped the project team effectively resource and plan their work.
Engaging as many regional economic specialists as possible at the beginning would have enriched the preliminary analysis produced during Phase I of this project. Doing so for the thematic analysis on remittances for example helped contextualise Yemen’s remittance dynamics with broader regional dynamics leading to nuanced recommendations, thus extending the analysis’s reach.
Recommendations:
The project should include the number of people, or number of organisations represented, at the joint analysis sessions to gauge the level of interest among the international community.

Output Title	Online convening of Yemen economic stakeholders
Output number:		4	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Expectations
4.1 Number of consultations and accompanying reports on topics agreed with FCDO Yemen	3	3	Met
4.2 Number of consultation findings reports presented to the OSE	3	3	Met

Briefly describe the output’s activities, and provide supporting narrative for the score.

The output focuses on a number of consultations held by the International Growth Centre (ICG) to support economic advisors mediate between the conflict parties on key economic priorities; raise public awareness; and guide interventions of international actors supporting the peace process.

Outputs 4.1 – 4.2

Between November 2020 and March 2021, the IGC held consultation sessions with Yemeni and international stakeholders regarding three main topics (in chronological order):
Public sector salaries in Yemen: towards building confidence in the peace process
  - The consultations provided valuable insights into the history of public sector salaries prior to the conflict, including 2014 data on the number and breakdown of public servants, wages bill, and budget implications. It also provided insights into the evolution of the payment of salaries since 2015, and lessons learned from various attempts to address the salaries crisis so far.
- Fuel imports to Hodeidah: towards building confidence in the peace process
  - The consultations provided valuable insights into the evolution of the fuel import process to Hodeidah during the conflict, including data on volume of imports. The discussions also provided insights into the technical and political challenges that faced the UN-brokered temporary mechanism for fuel imports to Hodeidah, and suggestions for addressing them.
- Options for an economic track of the Yemen peace process
  - The consultations identified the rationale and merit of establishing an economic track of the Yemen peace process, detailed the potential framework that would underpin such track, and highlighted the risks and necessary enabling conditions to establish such track.
IGC produced three reports on the topics above, and all of them were shared and discussed with the Office of the Special Envoy of the Secretary General of Yemen ( OSESGY). OSESGY welcomed the engagement with the IGC and valued the work. The third report/consultations came as a direct request from OSESGY. Reports were also shared with international organisations and multilateral development banks involved in Yemen. All reports were translated to Arabic.

One of the key challenges was that Ansar Allah distanced themselves from the peace process after their designation as a terrorist organisation by the Trump Administration. This impeded their engagement in the consultations, hence understanding of their views and/or influencing their positions.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.

Value for money across the programme is assessed in Section E.

This output delivered VfM as FCDO maximised a small amount of funding to successfully engage and bring together key economic actors on critical economic priorities. Due to unforeseen delays and the COVID-19 pandemic, the budget was also reduced to match a change in some activities’ format.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Due to the COVID-19 pandemic, planned in-person training in Jordan of Yemeni economic advisors on peace processes were cancelled. The training was revised into online consultations with parties to the conflict, and independent economic experts. The number of consultations was also reduced from four to three due to delays in scheduling them beyond IGC’s control.

This component has ended.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Lesson:
In order to deliver effective consultations, more time and effort and resources needed to be committed than originally planned. IGC encountered delays beyond their control scheduling the consultations, but also engaging with partners and local and international stakeholders proved to be a lengthy process.
Recommendation:
- For holistic cohesion, FCDO should ensure that any future work in this area is based on: an economic track, recommendations to OSESGY from this component, and additional analysis as required.
- The strategic impact of any future work in this area should be reflected through a higher component weighting.

Output Title	Assistance provided to the Executive Bureau to support the development of key policy reform priorities for the Government of Yemen.
Output number:		5	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Expectations
5.1 Electricity sector reforms: / a. identification of interventions that could improve service and reduce costs / b. number of policy papers developed / c. number of workshops held with key stakeholders	a) Complete / b) 1 / c) 1	a) Complete / b) 1 / c) 4	Met
5.2 Macroeconomic stabilisation: / a. identification of interventions to control inflation, stabilise the currency, and coordinate monetary, fiscal and trade policies / b. number of policy papers developed / c. number of workshops held with key stakeholders	a) Complete / b) 1 / c) 1	a) In progress / b) 0 (1 briefing paper) / c) 0	Partially unmet
5.3 Private sector support: / a. identification of urgent priorities including the feasibility of and best approaches to implement PPP projects, potential tools and approaches to de-risk private sector investments, and identifying priority sectors for investments / b. number of policy papers developed / c. number of workshops held with key stakeholders	a) Complete / b) 1 / c) 1	a) In progress / b) In progress / c) 0	Partially unmet
5.4 Support to prioritisation of key policy reforms: / a. advice on best approach to prioritise reforms identified by the government / b. number of policy papers developed / c. number of workshops held with key stakeholders	a) Complete / b) 1 / c) 1	a) In progress / b) In progress / c) 0	Partially unmet
5.5 Number of strategic conversations between senior GoY leaders and relevant IGC experts, including under 5.4c	3	1	Partially unmet
5.6 Number of embedded technical specialists	3	3	Met

Briefly describe the output’s activities, and provide supporting narrative for the score.

The UK is the Executive Bureau’s primary partner. FCDO provided the founding £3 million contribution to the World Bank trust fund that oversaw the establishment of the Executive Bureau, as part of efforts to take forward the Mutual Accountability Framework to track economic and policy reforms. Following the Executive Bureau’s recalibration in 2019, the FCDO provided further funding to hire policy experts on consultancy contracts to deliver priority projects. FCDO’s continued funding under this Output is supporting much needed reforms on food prices, electricity and the private sector with the following objectives:

- To improve the policy and regulatory frameworks of the electricity sector with a focus on creating an enabling environment for investing in renewable energy technologies.
- To minimise food insecurity through evidence-based policies. Identify factors that significantly drive prices and formulate recommendations to address these. Mapping of actors involved in the supply chain.
- To support the provision of basic services by promoting private sector investment in service delivery.

There are three embedded technical specialists in position, with plans to expand to a fourth during the next extension of this component. Additional advisory expertise is available from IGC, Oxford and LSE, and a pool of former ministers and central bankers.

This component faced delays over the review period, which has led to under-achievement against 4/6 indicators. IGC’s communication regarding the challenges was not as proactive as desired, meaning mitigating measures or changes could not be enacted. However, it is recognised that many of the challenges stemmed from external factors, and the component has built very valuable relationships over the review period. The FCDO has received positive feedback from the Managing Director of the Executive Bureau on the quality and importance of the support provided. Therefore, this component has scored B and should be continued. A no-cost extension has been agreed to allow the component to complete its existing milestones.

5.1 Electricity Sector Reform

An initial policy paper has been drafted and submitted to the Executive Bureau. The paper was shared with the Prime Minister, Ministry of Energy, World Bank, and other key stakeholders. Findings were presented to the Prime Minister and Minister of Energy at an in-depth meeting, with several areas identified for further analysis. Findings were also presented to technical-level staff at the Public Electricity Cooperation. The Executive Bureau is seeking to schedule a session for findings to be presented to international donors, with the aim of engaging on findings and encouraging coordinated support to the government’s agenda in the energy sector.

5.2 Macroeconomic Stabilisation

Initial analysis of challenges and potential interventions has been completed and used to prepare a briefing note for macroeconomic experts. This will inform a roundtable discussion with the Executive Bureau and the Supreme Economic Council. However, this meeting is yet to take place and scheduling is outwith the control of IGC.

5.3 Private Sector Support

An initial policy paper is under development, taking stock of the existing state of Yemen’s telecommunications sector, analysing challenges and undertaking initial identification of potential interventions. Expert involvement is required to progress further. Identifying the right expert and connecting with telecommunications companies for input are proving challenging. Little work has been done in contexts similar to Yemen on this topic, and competing priorities mean the Executive Bureau has not had the capacity to support connecting with the telecommunications companies. FCDO should explore if some expert support could be sourced via the technical cadres.

5.4 Support to Reform Prioritisation

A draft policy paper has been developed, drawing from recommendations from the Fragility Commission and other country experiences. This is undergoing amendment and quality assurance, particularly from senior State Fragility initiative staff.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Value for money across the programme is assessed in Section E.

Economy: IGC’s daily rates were benchmarked against FCDO’s framework of economic consultants and found to offer good VfM.

Effectiveness: By funding positions within the Executive Bureau, the FCDO complements and maximises the impact of GoY’s own funding. The programme allows for targeted support to Yemen’s nascent reform agenda while helping accelerate delivery of short-term priorities that benefit Yemen’s humanitarian, economic and stability agenda. Supporting a key state institution through this project also offers insights and relationships which benefit FCDO’s broader portfolio and policymaking.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This component has suffered challenges, as described above, resulting in an underspend as of March 2021. A no-cost extension to August 2021 has been agreed to utilise the unspent funds and complete the agreed outputs.

Based on the needs, progress and relationships built, it is planned that this component will be extended further and funding increased to the end of February 2022. The logframe is therefore in transition and updated indicators will be reported against in the PCR.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons:
The original timeframe for this component’s workplan was 4 months – this was too ambitious. Lessons have been learned regarding the time necessary to recruit consultants, and to present policy recommendations at Supreme Economic/Energy Council meetings as scheduling is outwith IGC control.
Recommendations
- IGC should be more proactive in discussing progress, challenges and financial management with FCDO, and FCDO should require more regular written and financial updates.
- The next extension of this component should plan for activities to end in February 2022 rather than March 2022. This way, if there is another underspend it will be known with enough time to reprogramme and utilise the funds before the end of the financial year.

D: RISK

Overview of risk management

The risk rating for this programme is major. HMG does not have direct access Yemen and so programming is managed remotely. Programme partners have specifically been selected for their robust expertise and undergo thorough due diligence as necessary. Partners maintain project risk registers and escalate relevant risks or changes to FCDO. The programme team maintain a programme-level register and feed key risks into the full portfolio-level risk register. This is co-ordinated by the FCDO risk specialist as part of the overall ODA spend risk management strategy for Yemen.

Ongoing assessments by HMG policy, political and regional teams have highlighted the role of the economy is central to incentivising and maintaining peace. However, stabilisation and economic programmes are high risk from a conflict sensitivity perspective. Continued monitoring of the effects of the programme, with the support of FCDO Yemen’s Conflict Adviser, and collaboration with the IMF will continue to be essential to mitigate the high risks.

Risk Category	FCDO Yemen Appetite	Programme Appetite
Reputational	Eager	Eager
Financial & Fiduciary	Financial – Cautious / Fiduciary – Eager	Financial – Cautious / Fiduciary – Cautious
Safeguarding	Receptive	Receptive
Policy & Programme Delivery	Eager	Eager
Strategy & Context	Eager	Receptive
Public Service Delivery & Operations	Cautious	Cautious
People	Cautious	Cautious

Given the UK’s sustained public commitment to economic recovery and reform in Yemen, and the volatile context meaning reform agenda can be deprioritised with little warning, Reputational and Delivery risks are the highest categories for this programme. FCDO and programme partners take continual mitigating action by investing significant time into stakeholder relationships – especially with the relevant institutions receiving support and other international donors contributing to the economic file. This mitigation strategy has been successful to date, and has facilitated the diplomatic and policy successes described under the Lessons/Recommendations section.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Project Management Performance

Overall, Partners’ project management performance has been good as most delivered on their targets. Some partnership agreements include limited formal narrative and financial reporting, relying heavily on a comprehensive completion report. However, Partners have generally performed well in providing regular informal reporting via fortnightly or monthly progress meetings. This has allowed FCDO to remain appraised of project progress, mostly receive advance notification of emerging threats/issues, and manage changes required due to COVID-19 and/or the wider context. Furthermore, partners such as USAID/Pragma and ACAPS successfully incorporated the recommendations made during Phase I of their activities (Nov 2019 – Aug 2020) into Phase II, which increased the impact of their work.

Financial and Commercial Performance

As above, Partners’ financial and commercial performance has generally been good, albeit predominantly reliant upon informal reporting during the course of implementation. Financial reports submitted have been of suitable quality and Partners have remained open to queries as needed. USAID and World Bank agreements operate on the basis of payment in advance, which has made financial management easier. ACAPS final variance was just £4, reflecting sound financial management. IGC faced some financial management challenges during the review period, predominantly driven by external factors beyond the project’s control. Underspend was not communicated as promptly as desired – the project has been granted a no-cost extension with greater frequency of reporting required moving forward (see Output 5).

Value for Money

FCDO uses the ‘4 Es’ framework (economy, efficiency, effectiveness and equity) to ensure that its funding maximises impact. With a relatively small budget (compared to humanitarian programming) the programme helped further HMG’s economic stabilisation objectives and represents good VfM within the overall FCDO Yemen context and programme portfolio. The programme continued to unpack costs, and work with FCDO’s Procurement and Commercial Department to ensure individual rates and expenses are competitive.

Economy:
- Utilising USAID’s existing programme with Pragma provided the Economic Stabilisation project with a ready-made intervention without the costs associated with an open procurement process, with USAID undertaking the administrative costs. Support for this programme allowed the UK to demonstrate added value, and to claim attribution for the benefits of the whole project whilst only providing a portion of the funding.
- As the main cost of the project with USAID, the fee rates of the ten consultants were examined by FCDO’s Procurement and Commercial Department and deemed to be competitive.
- Similarly, IGS’s rates were benchmarked against FCDO’s Procurement and Commercial Department economic consultancy framework and found to be competitive.
- ACAPS and Mercy Corps saved the set-up costs of the online dashboard by utilising an existing agreement with Amazon Web Services to host it at no additional cost to the FCDO.
Efficiency:
ACAPS’s dashboard builds on existing, established analysis capacity already available within ACAPS and Mercy Corps. This helped keep cost down by sharing costs including office rent, management and support staff across a broader base, which freed up funding to focus directly on delivering analysis products.
Effectiveness:
- FCDO’s support to USAID’s ERLP gave the FCDO more bang for buck as it contributed towards a larger impact beyond the amount of its support. It also brought the work of the FCO and USAID closer together, complementing diplomatic engagement between the US and the UK on Yemen’s economy
- ACAPS collaborated with other FCDO partner organisations, utilising their broader organisational access to data sources in order to enhance the rigour and coverage of their analysis.
- The impact ACAPS’s activities have had on HMG’s and other relevant stakeholders’ efforts far exceeded the amount of funding provided by FCDO. The analysis contributed to a broader discussion on how to strengthen monitoring and contingency planning for economic risks in Yemen. Key economic risks identified by ACAPS were referenced by the UN Humanitarian Country Team (HCT), and in HMG engagements to generate buy-in among key stakeholders.
- FCDO maximised a small amount of funding to successfully engage and bring together key economic actors, including OSESGY on critical economic priorities.

Equity:
- IGC’s work on the economic considerations of the peace process sought to bring greater breadth and inclusion to the Track I peace process.
- ACAPS track and promote gender equality in staffing and hiring. Currently 57% of Yemen Analysis Hub staff and 50% of their Yemen Management team are women. This ensures a greater range of experience and perspectives inform the analyses.

USAID – Capacity building of the Central Bank of Yemen and Ministry of Finance (Output 1)
Date of last narrative financial report	Narrative report: 27/04/2021 / Financial report: 08/09/2021	Date of last audited annual statement	N/A – within first year

World Bank – Restoring capacity of the Central Statistical Organisation (Output 2)
Date of last narrative financial report	N/A – final report only	Date of last audited annual statement	N/A – within first year

ACAPS – Analysis of key economic trends and risks and economic data made available (Output 3)
Date of last narrative financial report	Narrative report: 31/05/2021 / Financial report: 31/05/2021	Date of last audited annual statement	N/A – within first year

International Growth Centre – Online convening of Yemen economic stakeholders (Output 4) AND Assistance provided to the Executive Bureau to support the development of key policy reform priorities for the Government of Yemen (Output 5)
Date of last narrative financial report	Narrative report: 12/07/2021 / Financial report: 23/08/2021	Date of last audited annual statement	N/A – within first year

Annex I – Economic Stabilisation Project I PCR Recommendations and Progress

Area	Recommendation	Progress to date
Commercial & Financial Performance	In the next phase of programming, FCDO should work with FCDO’s Procurement and Commercial Department where possible to ensure consultants’ fee rates and expenses are competitive.	Ongoing – see VfM examples regarding USAID and IGC rates.
Output 1 (USAID)	For the CBY component, the project successfully adapted to COVID-19 with the final stage successfully implemented remotely, largely due to the implementing partner’s close relationship with CBY. The next phase will most likely be delivered remotely. Regular engagement with CBY should continue to ensure strong coordination and buy-in continues and the quality of the Technical Assistance (technical assistance) is not affected.	Ongoing – FCDO and partners USAID and Pragma continue to engage with CBY and MoF as well as other relevant actors in support of the technical assistance provided to the CBY. In-person technical assistance is being delivered, with COVID-19 and safety considerations.
Output 1 (USAID)	Future technical assistance should be expanded to the GoY Ministry of Finance to support budget execution policies.	Complete.
Donor Coordination	FCDO should coordinate with other donors in the successor programme who are considering interventions to support the economy.	Ongoing – FCDO is a leading member of the TAC, continuing to engage with and promote coordination amongst donors on the economy. The US, World Bank, IMF and KSA remain key partners.
Output 3 (ACAPS)	ACAPS should engage data specialists to further develop the economic trends platform in the next phase of programming.	Complete
Output 3 (ACAPS)	ACAPS reports have been utilised and referenced by a number of different actors. Between 1,000 to 3,000 visits are recorded per month on the ACAPS Yemen Analysis Hub website. In the next phase of programming, FCDO should measure the number of times programme-funded reports are downloaded to gauge the usefulness and impact of the analysis. Economic analysis products should also be translated into Arabic to extend the reach of the analysis and its accessibility for stakeholders in the region.	Complete.
New components	FCDO should explore future programming options to support the private sector directly to address key macroeconomic challenges, financial sustainability and job creation.	FCDO is pursuing this recommendation outwith this programme.