## Annual Review

Title: Humanitarian Assistance and Resilience in South Sudan (HARISS)
Programme Value £ (full life): 2020 programme value: £92m (calendar year). Overall programme value £787m (cost and time extension approved February 2021)		Review date: August 2021
Programme Code: 204019	AMP start date: 13/03/2015	AMP end date: May 2023 (cost and time extension approved February 2021)

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020
Overall Output Score	A+	A	A	A+	A	A
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5207793.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/5327724.xlsx

Since the last Annual Review, the humanitarian situation in South Sudan has remained dire, with worsening levels of violence against civilians, catastrophic flooding, and deepening food insecurity. In 2020, the impacts of the COVID-19 pandemic exacerbated the humanitarian needs of a highly vulnerable population. This review finds that despite this extremely challenging context, the HARISS programme has made the necessary adaptations to ensure the continued delivery of critical services at scale. Alongside this, good progress has been made in the implementation of resilience programming that promotes sustainable recovery, as well as activities that contribute to an enabling environment that optimises operational response and access.

This review covers the period of January to December 2020. Due to the complexity of HARISS as a programme, the standard FCDO annual review process has been adapted to reflect its portfolio nature.

A. SUMMARY AND OVERVIEW

Context
The humanitarian context in South Sudan is characterised by protracted conflict, displacement, poor governance, persistently high inflation, a lack of infrastructure and basic services. By the end of 2020, there were an estimated 8.3 million people in need of humanitarian assistance in South Sudan, compared with 7.5 million at the same time in 2019. 1.7 million people were internally displaced and another 2.3 million were refugees in the region.
[note] https://www.humanitarianresponse.info/en/operations/south-sudan/infographic/south-sudan-humanitarian-snapshot-june-2021
[note] https://displacement.iom.int/reports/south-sudan-—-mobility-tracking-round-10-initial-findings?close=true

A significant deterioration in the food security and nutrition situation, driven by cumulative and compounding shocks including a second consecutive year of devastating flooding, rising sub-national inter-communal conflicts, a weakening economy, and a breakdown of social structures, resulted in famine-like conditions in some areas of the country. Humanitarian presence was severely limited in some areas for months due to violence and insecurity, hampering a meaningful response. According to the latest Integrated Phase Classification (IPC) data published in December 2020, between October and November 6.3m people (53% of the population) faced high levels of acute food insecurity. This is expected to increase in 2021 as the lean season is projected to be the worst ever on record.
[note] The 6 most food insecure areas include Pibor, Akobo, Aweil South, Tonj East, Tonj North and Tonj South
[note] http://www.ipcinfo.org/ipcinfo-website/alerts-archive/issue-31/en/

The first COVID-19 case was confirmed in South Sudan in early April and though the caseload was relatively low throughout 2020, the impacts have been significant, including the disruption to supply chains and reduced market functionality. Movement restrictions have also limited humanitarian movements and aid delivery.
[note] In South Sudan, between April 2020 and June 2021 there have been approximately 10,700 confirmed cases of COVID-19 with 115 deaths. However, testing capacity is low and actual cases are likely much higher: https://covid19.who.int/region/afro/country/ss/

Despite the deterioration in the humanitarian context, there was not a significant and timely enough scale up across the humanitarian response. The South Sudan Humanitarian Fund (SSHF – a country-based pooled fund supported by multiple donors) allocated $7.6m for COVID-19 related activities and there was also a COVID-19 addendum to the Humanitarian Response Plan (HRP). Funding to the 2020 HRP totalled $1.23bn (64.7% of the 1.9bn requested), with significant gaps in the health, protection, shelter / non-food item (NFI) and water, sanitation, and hygiene (WASH) sectors. The UK contribution to the HRP was approximately 7.2% of total funding, making the UK the second largest humanitarian donor (this is consistent with previous years).
[note] The HRP is prepared for a protracted or sudden onset emergency that requires international humanitarian assistance. The plan articulates the shared vision of how to respond to the assessed and expressed needs of the affected population. 2020 HRP: South Sudan Humanitarian Response Plan 2020 - COVID-19 Addendum (June 2020) - South Sudan | ReliefWeb
[note] https://fts.unocha.org/appeals/865/summary

In September 2020 the UK Foreign Secretary appointed Nick Dyer as the UK Special Envoy for Famine Prevention and Humanitarian Affairs. South Sudan was identified as a key concern and a priority country for humanitarian action by the envoy, as a result of the deteriorating food security situation and increasing level of humanitarian need. The British Embassy in Juba engaged with the envoy on both diplomatic and programmatic efforts to address the scale of the humanitarian challenge in South Sudan. HARISS was the primary programmatic vehicle for scale ups in the UK’s response to increasing need in South Sudan.

Description of programme
HARISS is a large-scale, multi-year humanitarian programme (£787 million budget 2014/15 – 2022/23) providing humanitarian assistance and resilience building activities across four components with 12 partners. During the 2020 calendar year, HARISS spend was £92m.
[note] In recognition of the dire humanitarian situation, a third cost extension of up to £100m (extended until May 2023) was approved in February 2021
[note] HARISS is delivered through 4 UN partners (UNICEF, WFP (including UNHAS and Logistics Cluster), FAO, IOM), 5 NGO partners (GOAL-led consortium, IMC, Medair, HI and REACH), the ICRC, a pooled fund partner (SSHF) and a commercially-contracted monitoring and learning provider (ELFSS, run by IMC Worldwide). In addition, HARISS supports technical secondments to the UN lead clusters (Standby Partners). The Oxfam component was closed in 2019
[note] This figure represents spend per the 2020 calendar year. The FCDO financial year runs from April – March. With the exception of the 2019 Annual Review, the previous Annual Reviews have recorded the FCDO financial year figure. The HARISS calendar year breaks down as follows: £91m in 2015, £112m in 2016, £118m in 2017, £119m in 2018 and £119m in 2019. Overall spend up until the end of December 2020 totalled £650m

HARISS invests in:
- Life-saving humanitarian assistance to reduce the vulnerability of people through: (i) the provision of food assistance and emergency livelihoods support, nutrition, water, sanitation and hygiene (WASH), health, shelter and emergency non-food items (NFIs), camp management; (ii) making the humanitarian coordination system more effective and accountable.
- Resilience-building to help vulnerable populations prepare for, cope better with and recover from conflict, economic and weather-related shocks that cause humanitarian disasters and stresses. The resilience approach focuses on supporting food security and livelihoods, protection and reducing violence against women and girls, emergency preparedness and response and building the capacity of national NGOs.
- Monitoring, evaluation, accountability, and learning (MEAL) to enable verification, learning and adaptation.
- Internal Risk Facility (IRF), a contingency budget line which enables rapid response to shocks and unforeseen needs across the country.
  [note] In 2019, £1,000,000 was allocated through the IRF, including £400,000 to UNICEF for COVID-19 WASH activities in Wau, £250,000 for Standby Partnerships positions to support the COVID-19 response and £350,000 to support urgent gaps to a number of HARISS NGOs in December 2020

HARISS comprises a wide range of partners, including UN agencies with their own multiple downstream partners (DPs) – including both international and national NGOs (INGOs and NNGOs respectively). HARISS also directly funds INGOs, most of whom in turn have their own downstream NNGOs. The HARISS portfolio also includes the International Committee of the Red Cross (ICRC) and the SSHF.

HARISS was designed to shift from providing short-term assistance to meet immediate needs, to a more flexible, longer-term approach aimed at increasing the resilience of conflict affected people. As HARISS has evolved, it has aimed to integrate both the World Humanitarian Summit Grand Bargain (2017) commitments as well as the UK Humanitarian Reform (2017) priorities in a number of ways:
[note] The Grand Bargain (Official website) | IASC (interagencystandingcommittee.org)
[note] UK government’s Humanitarian Reform Policy - GOV.UK (www.gov.uk)

- Piloting cash-based approaches where feasible.
- Strengthening Accountability to Affected Populations (AAP) by encouraging HARISS partners to build two-way communication approaches with beneficiaries.
- Supporting local and national responders through financing to national NGOs as downstream partners, including through the South Sudan Humanitarian Fund (SSHF) (in 2020, 33% of the SSHF funding went directly to national NGOs.)
  [note] South Sudan Humanitarian Fund 2020 Annual Report

Due to COVID-19, 2020 was an even more challenging year for programme delivery. From March 2020 in-country presence of UK staff was severely limited due to COVID-19 and quarantine requirements and restrictions on movement, severely hampered the ability of partners to deliver and directly monitor programmes (more detail is outlined under the pillars in section C). This risk was partially mitigated through the third-party monitoring (TPM) contract, which adopted remote monitoring techniques during this period. The easing of restrictions in October enabled a full complement of UK staff to return, as well as improved access by partners towards the end of the year and the resumption of in-person monitoring visits. This was still against the backdrop of a deteriorating security situation more generally, in a year which saw increased risks of violence against aid workers.

There was a visit by the FCDO Minister for Africa and the UK Special Envoy for Famine Prevention and Humanitarian Affairs to South Sudan in October, where the UK delegation visited Pibor, one of the six worst affected counties, facing famine-like conditions. This provided an opportunity to assess the response and advocate for strengthened UN leadership and Government of South Sudan accountability. The UK also announced an uplift in funding as part of its commitment to reduce extreme hunger and help mitigate the ongoing risk of famine in the country.

Summary supporting narrative for the overall score in this review
HARISS covers a range of humanitarian sectors and supports both life-saving emergency operations as well as interventions that aim to build resilience to shocks. The performance of each HARISS partner was scored individually against their log frame. Partner level performance was technically reviewed by FCDO advisers looking at their contribution across the different pillars of the HARISS programme. These scores were then grouped by sector and aggregated into pillars (see below). Overall, at a pillar level the programme scores an A which reflects both over and under performance by partners. Nonetheless, this is an impressive achievement given the challenges of the operating context.
[note] Pillars are weighted according to the budget allocated by HARISS to the particular sectors
[note] FCDO has a standard approach for scoring performance in its Annual Reviews: A++ is over 137.5%, A+ is 112.5-137.5%, A is 87.5-112.5%, B is 62.5-87.5%, C is under 62.5%
Pillar	Emergency Food Assistance	Nutrition	WASH	Health	Shelter/NFIs and Camp Management	Food Security and Livelihoods	Protection and GBV	MEAL	Enabling Environment
Weight	30%	14%	7%	7%	6%	11%	10%	1%	14%
Score	A	A	A	A	A	A	A	A	A

Major lessons and recommendations for the year ahead
Recommendations from the 2020 review incorporate those from the 2019 review that continue to have relevance and require action. Where necessary, these have been revised to account for changes in context. A limited number of sub-recommendations have also been included under each pillar.

Emergency Food Assistance	Targeting remains a systemic challenge, particularly for WFP and its downstream partners. FCDO and HARISS partners should continue to discuss targeting approaches, focusing on findings and recommendations from the Evidence and Learning Facility for South Sudan (ELFSS) Synthesis Study on Determining Needs and Beneficiary Targeting, May 2020 and ensuring resources are directed to the most vulnerable. / FCDO and implementing partners should make all efforts to support the 2021 IPC analysis process to ensure it is i) achieved through consensus and is ii) a technically sound, evidence-based process.
Nutrition	UNICEF’s multi-sectoral nutrition programming in 2020 was an important step in laying the groundwork for further integration of services with WASH and Health interventions. UNICEF should continue to build on the success of this approach, including the development of more ambitious multisectoral indicators, and clear linkages with activities implemented by UNICEF and other partners for the same community.
WASH	The FCDO should consider prioritising funding to the IOM WASH pipeline. / FCDO should engage and support the roll out of the WASH Severity Classification assessment and analysis (a multi-agency approach coordinated by REACH and the WASH cluster, similar to the IPC process for food security) for South Sudan, which the UK is providing some funding to from centrally managed programming.
Health	Strengthen linkages between the health, nutrition and WASH sectors, and seek out better synergy between health services funded through HARISS, the Health Pooled Fund (HPF) and the World Bank/UNICEF to ensure complementarity and to support the sustainability of investments in strengthening health systems and addressing malnutrition. / Advisory leads within the British Embassy Juba Humanitarian and Human Development Cluster should prioritise discussions on this issue, in order to feed into discussions on HPF 3 and future humanitarian programming.
Shelter / NFIs	FCDO, working closely with IOM and the humanitarian community, should identify opportunities to support advocacy on ensuring returns are voluntary, safe, and dignified. FCDO should work across the international community to ensure that existing guidelines are being correctly followed and risks relating to upcoming census and elections are managed. Any concerns should be raised at the highest levels to the Humanitarian Country Team, the UNHCR Country Representative, and the relevant Government of South Sudan ministries.
FSL	FCDO should seek to look across its investments in HARISS and the Building Resilience Through Asset Creation and Enhancement (BRACE II) programme with a view to determining the most efficient and effective models for strengthening resilience (in particular cash modalities) in South Sudan, identifying good practice from both FAO and GOAL.
Protection	Substantial progress has been made in 2020 to strengthen inclusion across HARISS partners. For maximum impact and sustainability, HARISS partners should engage and empower Organisations of Persons with Disabilities to ensure they have the resources and skills to represent and advocate for their members with the wider humanitarian response.
MEAL	As the contract finished in May 2021, ELFSS and FCDO should undertake an exercise to ensure key lessons are captured from the ELFSS contract, drawing on the synthesis studies and the issues that are consistently captured in the TPMs. In particular, future design should consider a feedback loop mechanism and continued M&E of community perception of humanitarian programming and emphasis of conflict sensitivity risk analysis, including regular conflict trend analysis to inform planning and risk mitigations. FCDO should draw on conflict advisers to support this process and ensure conflict sensitivity analysis and mitigations meet FCDO standards. / FCDO to revisit its internal monitoring processes now that field visits are more feasible than last year, and prioritise partners / projects given the current gap in Third Party Monitoring services
Enabling Environment	The Logistics Cluster should continue to work with partners to improve prepositioning of stocks during the dry season and to further capitalise on efforts to use cheaper road and river transport, reducing the reliance on air freight. / The UK should develop a strategic approach to the Standby Partnership Mechanism, working with UN partners to identify and address capability gaps crucial to response delivery
VfM	FCDO to consider the impact of its budget cuts on programming, including VfM. To strengthen analysis, FCDO, working with HARISS partners, should review VfM tools (in particular VfM matrices) to enable better reporting on effectiveness and equity. / Exchange rate volatility has always been identified as one of the key risks which should be monitored and addressed across the HARISS programme. The FCDO should work with partners to advocate for a more coordinated approach through the Cash Working Group.
Risk	HARISS continues to operate at a major risk level with regular escalation of risks that challenge agreed tolerance levels. / The UK continues to coordinate with donors and the wider humanitarian community to collectively respond to issues that affect programme delivery and the deteriorating level of safety and security for humanitarian workers in South Sudan.
[note] This recommendation was implemented during the 21/22 prioritisation work
[note] See example: https://www.reachresourcecentre.info/theme/wash/cycle/34986/#cycle-34986
[note] HPF is a programme delivered by multiple donors, including the UK, in partnership with the Government of South Sudan’s Ministry of Health, which provides access to quality basic health services
[note] This is the UK’s flagship resilience and international climate finance project in South Sudan, which aims to increase the capacity of vulnerable households to cope with climate shocks and stresses, improve their food security and build better community relationships
[note] The Standby Partnership (SBP) network is comprised of a range of partners that come together to provide specialist support to UN agencies during humanitarian emergencies by seconding experts into UN agencies
[note] The Cash Working Group brings together approximately 200 partners operating in South Sudan to promote the utilization of cash and vouchers as a modality for humanitarian assistance

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Theory of change impact statement:
Save lives, avert suffering, maintain dignity, and reinforce coping capacities of those affected by conflict, disasters, shocks, and conflicts in South Sudan.

Theory of change outcome indicators:
- Reduced vulnerability of people in need.
- Improved capacity of the most vulnerable populations to withstand, adapt to, and recover from conflict, disasters, and shocks.
- Improved quality of impact of measurement of humanitarian action
Overall, the theory of change is still relevant and many of the assumptions underpinning it have not changed. For instance, peace remains fragile, the UN-led Strategic Response Plan (SRP) continues to prioritise humanitarian assistance and flexibility within the programme allows for adjustments, based on evolving national and local contexts.
The original HARISS business case outlined the intention to shift from the provision of immediate humanitarian needs to resilience building activities over the lifetime of the programme. This was on the basis that enduring political and economic stability would create the conditions in which sustainable outcomes would result. On the contrary, the majority of interventions in 2020 prioritised life-saving activities in response to the worsening humanitarian situation noted above. HARISS partners have performed well, flexing to meet changing needs across the year.

Describe where the programme is on or off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to meet expected outcomes and impact targets. HARISS has demonstrated in 2020 that it is able to meet ever increasing humanitarian needs, whilst also contributing to strengthening the resilience of people in more stable areas. In particular, the flexibility that has been built into the programme across both its range of partners and sectors has been crucial to enable the programme to adapt to the challenges posed by the COVID-19 pandemic and increasing need across South Sudan’s 10 states. In 2021, partners will need to incorporate key learning from these adaptations to mainstream COVID-19 prevention and response activities into wider multi-sectoral interventions. This will be extremely challenging as the humanitarian system faces significant funding shortfalls, including from the UK humanitarian budget in South Sudan.
[note] The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions. The UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. This will result in significant changes to the programme in 2021

Portfolio performance and cross-cutting issues
The COVID-19 pandemic necessitated that partners made significant adjustments to programming to align with global and national guidance. Across the portfolio, some activities were suspended (e.g. some types of nutrition surveys and some physical gatherings) and there were delays in the procurement of supplies, meanwhile some activities were adapted (e.g. counselling groups were reduced to 10 people and distributions also limited the number of people at any given time). Movement restrictions also meant that many key partner staff were outside of the country and those in Juba were often unable to reach field locations. Inevitably, this led to less oversight of programmes, with partners providing technical support and building capacity of frontline staff remotely. Generally, the majority of partners kept delivery plans on track, albeit with slightly lower than expected outputs in some areas. As a result, the FCDO agreed revisions to milestone targets in some partner log frames.

Some HARISS partners were also able to utilise additional funding in 2020, including:
[note] In parallel, some HARISS partners were required to make savings to programming which totalled £2.8m across the portfolio. This followed an internal FCDO prioritisation exercise as a result of the impact of COVID-19 on the 2020 budget. This was separate to funding decisions made ahead in FY 21/22
- £8m uplift from the FCDO Crisis Reserve: allocated to WFP, UNICEF, ICRC and IOM in September 2020 to support the food and nutrition crisis.
  [note] The purpose of the ODA Crisis Reserve is to provide fast and flexible funding for crises, including either rapid onsets or spikes in an existing, or protracted crisis. This is a central contingency reserve which is allocated throughout the year
- £6m uplift from the FCDO Crisis Reserve: allocated to WFP, FAO and IOM in December 2020 to support early recovery from floods.

While this review is disaggregated by sector, many partners employ multi-sectoral approaches or work together to deliver results across sectors; collaboration and cooperation has been an increased feature between HARISS partners. This includes the WFP-led Integrated Rapid Response Mechanisms (WFP, UNICEF, and FAO), inter-operability between IOM and WFP, and WFP and Medair’s Scope-CODA biometric work. Further strengthening of integration between sectors and across partners will continue to be a priority for FCDO in 2021 and lead to better outcomes for beneficiaries.

Cross cutting issues
HARISS has continued to integrate humanitarian reforms and Grand Bargain (GB) priorities, particularly ensuring accountability to affected populations (AAP) is integrated across the programme. The key measure of progress used by partners is the number of feedback tools and channels. While progress has been made there is scope for improvement. The primary route for assessing the success of integrating AAP is through the TPM function, which has functioned well with a constructive and collaborative relationship between partners and ELFSS researchers.

In addition, REACH’s AAP workstream has made significant progress towards filling key information gaps regarding community perceptions in the humanitarian response in South Sudan. A substantial achievement was the addition of AAP monitoring indicators in the 2021 HRP. Going forward, REACH will capitalise on the opportunities created this year to allow for more granular analysis of AAP issues related to central themes and locations prioritised by the response, as well as for strategic engagement with key actors to ensure REACH’s AAP research enhances a community-centred approach in humanitarian programming.

The use of cash for humanitarian response has continued to be prioritised by HARISS across a range of partners (WFP, FAO, GOAL, IMC, and IOM), in addition to its use as a means of strengthening community resilience. The FCDO is active in the Cash Working Group and have continued to advocate for the use of cash where appropriate.

Addressing inclusion and gender across the HARISS portfolio has continued in 2020. The HI approach offers a well-rounded and complementary package of interventions ranging from direct support to beneficiaries through to coordination, advocacy, and improved capacity of other HARISS partners. HI has continued to support HARISS partners’ efforts to embed inclusive practices within their project cycle, with UNICEF, IOM, WFP and IMC all benefitting from practical measures including disaggregated data collection. Across HARISS, most partners routinely disaggregate data by gender, and the disaggregation of data by disability is also increasing. There has been a continued focus across the portfolio on promoting women’s participation in programming as well as ensuring that humanitarian assistance meets the specific needs of women (such as through the work of IMC) and people with disabilities (particularly from HI, ICRC and IOM).

Nonetheless, the needs assessments and beneficiary targeting that underpins programming continues to raise many challenges; this has been identified as an issue by beneficiaries and frontline staff during TPM. FCDO and partners should therefore renew efforts to consider how to identify and reach those are who are not ‘socially connected’. Central to this will be the use of robust evidence and systems that interact with local dynamics.

The capacity of NNGOs is key to a successful, effective and sustainable humanitarian response in South Sudan. The Grand Bargain committed the humanitarian system to providing more support and funding to local responders, including a commitment to provide 25% of overall global funding to these organisations. NNGOs are crucial DPs of nearly all HARISS partners, but the UK does not provide any direct funding to these organisations. However, the SSHF consistently provides NNGOs with significant amounts of direct funding, with 33% of funding in 2020 directly awarded. This is well above the global target and high compared to the majority of other pooled funds. The SSHF is a key mechanism for the UK to deliver on its localisation commitments.

2020 saw a significant escalation of the levels of violence, with an estimated 57% increase in the number of violent incidents recorded as compared to 2019 (ACLED). Most violence resulted from conflict between community-based armed groups, mainly driven by competition of local resources, cycles of revenge, and sometimes fuelled by national elites. Deadly attacks on humanitarian workers are sadly far too common. High levels of conflict frequently restrict access for humanitarian operations, requiring activities to pause or be delivered through alternative means. The UK works with HARISS partners to monitor local conflict trends and respond when they impact operations. This requires conflict sensitivity to be at the core of HARISS’ interventions and FCDO utilise various expert sources, including the Conflict Sensitivity Resource Facility and UK conflict advisers. It is also why protection interventions are a major priority for HARISS, as detailed in the output scoring later in the review.

A key part of HARISS’ delivery is the accompanying policy and advocacy work delivered by HMG in South Sudan. The UK regularly deploys diplomatic influence with a range of partners to advance policy priorities and address challenges that impact the delivery of effective humanitarian assistance. The UK Famine Initiative announced by the Foreign Secretary in September 2020, drove extensive UK engagement on the issues of food security and access and protection. As a leading member of the Humanitarian Donor Group (HDG), the UK works with other donors to coordinate donor policy and engagement to drive effectiveness and value for money across the system. In 2020 this included responding to numerous instances of interference in humanitarian assistance. This involved the development of an in-country donor principles paper that coordinated a collective response to particularly serious incidents, such as that in Renk which is discussed under the risk section of this review. Our engagement with the UN also aligns to the wider UN reform agenda, where the UK has been consistently lobbied to not only improve coordination within the humanitarian system but for a step-change in coordination between the humanitarian system and wider UN mission and peacekeeping operations. This has involved cross-HMG collaboration to engage key actors in South Sudan and in New York, including at the UN Security Council where South Sudan is regularly discussed.

The UK also engages the Government of South Sudan (GoSS) at all levels given their accountability for the safety and security of their citizens as well as humanitarian workers. This engagement occurs at the highest political levels in Juba as well as officials and political figures at the local level. This local level engagement is often the key to unblocking specific delivery issues and was hindered due to travel restrictions in 2020 but is a priority for 2021. The UK also works very closely with the UN both in South Sudan and New York to unblock specific issues and facilitate effective delivery of humanitarian assistance across the country.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
This review concludes that the programme should continue as HARISS provides an appropriate response to the context in South Sudan and is able to respond flexibly to the changing context. The programme represents value for money and demonstrates consistent achievement against milestone targets. The work of HARISS is also key to the delivery of the British Embassy Juba Country Plan and supports wider UK objectives in country.

## C: DETAILED SCORING

Headline results from the HARISS programme are presented below. These are combined results from all HARISS partners. While each HARISS partner has been reviewed, scored and assessed against individual targets, the figures in the table below are an estimate of the overall reach of the HARISS programme in 2020. Each result presented is attributable to FCDO funding and adjusted for any double counting of beneficiaries. Attribution was estimated based on FCDO’s funding share to partners. For example, FCDO provided 5%, 14% and 15% of the total funding to ICRC, SSHF & WFP respectively - and only this proportion of the result observed has been recorded in the review. Double counting adjustments were made in situations when there was a likelihood that a person received the same intervention from more than one implementing partner. In this situation, the highest reported result for the intervention in question has been presented in the table below.

No.	Indicator	Result
1	Number of people reached with food assistance	270,000
2	Number of people reached with cash assistance (conditional)	24,000
3	Number of people reached with cash transfer (unconditional)	679,000
4	Number of children (6-59 months), women, adolescents treated with severe or moderate acute malnutrition	44,000
5	Number of beneficiaries supported through blanket supplementary and/or therapeutic supplementary feeding programmes	86,000
6	Number of beneficiaries with improved access to clean water and/or sanitation.	1,375,000
7	Number of vaccinated against preventable diseases	22,000
8	Number of people whose health needs were met (curative, preventive and vaccination) by SSHF funding	126,000
9	Number of people provided with shelter and/or non-food items (NFI)	102,000
10	Number of vulnerable households (HH) supported with emergency livelihoods kits (seeds & tools, fishing kits)	15,000
11	Number of vulnerable households supported to strengthen their resilience to shocks	20,000
12	Number of women, men, boys and girls reached with information on GBV, rights and services available	337,000
13	Number of livestock vaccinated & treated	224,000
14	Number of protection services delivered	70,000
15	Number of people benefitting from awareness sessions on disability (partner staff)	475
16	Number of aid workers per month enabled to access remote project sites	4,000
17	Number of people trained on GBV prevention & response	1,000

Pillar	Emergency Food Assistance		Pillar Score		A
Risk:		Severe		Impact weighting (%):		30%
Risk revised since last AR?		N		Impact weighting % revised since last AR?		Y

Emergency food assistance accounted for 30% of HARISS funding in 2020. This output captures food assistance delivered both in-kind and for cash-based transfers and vouchers to food-insecure individuals and households. The tables below show partner pillar scores and headline partner results which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
GOAL	Food insecure households’ access to humanitarian cash transfers to meet their immediate needs	3%	A
WFP	Food, nutritional products, non-food items, cash transfers and vouchers distributed in sufficient quantity and quality and in a timely manner to targeted beneficiaries	89%	A
WFP	Development and implementation of a consultative framework to adapt food assistance modalities to contexts and needs, and enable timely shifts to various modalities	5%	A
ICRC	Distribution of food commodities	3%	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of people reached with food assistance	WFP / ICRC	318,472 / 15,000	251,448 / 18,163
Number of people reached with cash assistance (conditional)	WFP / GOAL	697,837 / 24,000	679,441 / 23,922

Overall Situation
People’s overall food security deteriorated through 2020. The number of people facing crisis-level acute food insecurity (IPC Phase 3) or worse, increased to 6.5 million people in the period May-July. South Sudan remains one of the most food-insecure coun­tries in the world due to a number of factors, including conflict and intercommunal violence, flooding and popula­tion displacement, which have disrupted trade, markets and food production activities. More than half of the population faced crisis or above levels of acute food insecurity in 2020 and the situation into 2021 has only worsened at the time of writing.
[note] South Sudan Humanitarian Fund 2020 Annual Report

Partner Performance
WFP responds to the food security crisis in South Sudan through a number of activities, including General Food Distributions (GFD) (both conditional and unconditional), Cash Based Transfers (CBT) and the Rapid Response Mechanism (RRM).

In 2020, through GFD, WFP assisted 251,448 unique beneficiaries against the planned 318,472 target. WFP performed very well, despite the impacts of COVID-19 and security challenges which meant that the target was not achieved. Commodities purchased consisted of the standard food basket for general food distributions, including sorghum / maize, yellow split peas, oil and iodized salt, as well as fortified nutritious foods for the prevention and treatment of acute malnutrition. The Integrated Rapid Response Mechanism (IRRM) also continued to be a vital component of South Sudan WFP’s Emergency Response, reaching people in hard-to-reach areas due to insecurity and logistical challenges.
[note] The COVID-19 pandemic compounded the economic crisis, with prices for most food items having increased, as a result of travel and transport restriction. This threatened to exacerbate the already acute food insecurity and disrupt the livelihoods of the most vulnerable
[note] National, subnational and localised violence severely constrains humanitarian access, particularly in hard-to-reach areas. WFP report that humanitarian access improved slightly over the second half of 2020, partly due to the decrease in the cycle of violence emanating from cattle raids and revenge killings (hugely attributed to the onset of the rainy season). Such insecurity also risks the safety and security of humanitarian actors and beneficiaries and results in humanitarian assets being destroyed and supplies looted
[note] Through the IRRM, WFP coordinated with partners including UNICEF and FAO to provide complementary services such as nutrition, livelihoods, water and sanitation (WASH) and health services, and occasionally seeds and tools, alongside food assistance interventions

During the reporting period, WFP developed remote monitoring guidelines in alignment to the COVID-19 context while ensuring continuity of monitoring activities for learning and accountability purposes. During the first half of 2020, the monitoring coverage of food assistance activities increased from 24% to 41% compared to the same period in 2019. This increase was due to capacity building training conducted for focal points based at field offices and timely surge support from the country office.

In the latter half of the year, WFP conducted the first phase of Post Distribution Monitoring (PDM) whereby 1,062 beneficiaries were contacted remotely. Overall results show a significant improvement among the GFD beneficiary households, with a 64% reduction in the percentage of households with poor food consumption. This is despite the difficulties faced by households because of the pandemic that largely affected food availability in the markets as well as prices and their livelihoods. Despite this, households also reported increased use of coping mechanisms due to the impact of the pandemic. This is reflected in the key observations from Third Party Monitoring (TPM), which noted that the sharing of food supplies was common and increased due to COVID-19. This often resulted in supplies not lasting for the intended period. In addition, the TPM demonstrated that the selling of food supplies was common in areas where beneficiaries would have to walk for long distances, to either cover transport costs or to reduce their load.

Alongside GFD and the RRM, WFP distributed cash-based transfers to 679,441 people amounting to USD $11.6m (FCDO attributable figure). CBTs are used where markets have adequate supplies and can respond to increased demand, as ascertained by supply chain and Vulnerable Analysis and Mapping VAM assessments. The amount of cash/voucher transfer is adjusted periodically based on the price levels so that beneficiaries can get the same amount of food from the market as they would get from WFP’s in-kind assistance.

GOAL also successfully implemented cash programming to meet the immediate needs of food insecure households, achieving the target of 4,000 households (24,000 people). In 2020, there was a shift from unconditional to conditional cash transfers, which supported communities to set up flood dikes while receiving cash that enabled them to purchase essential food stuff. The rationale was that this would build communities’ resilience and mitigate the impacts of shocks, and GOAL reported reduced impacts from flooding in some areas as a result. However, this shift from unconditional to conditional cash was initially resisted by both beneficiaries and local authorities, due to the new requirements that beneficiaries must complete certain work norms. It was only through constant engagement with community leadership and beneficiaries that this was subsequently resolved, and conditional cash transfers continued without problems. In addition, TPM in both Melut and Rubkona highlighted perceptions that cash transfers were too low and only lasted a week, helping beneficiaries to purchase immediate needs.

ICRC supported the emergency distributions of food and household essentials to communities displaced by violence and/or affected by the heavy floods, particularly those living in areas not covered by other organizations.

Gender and Inclusion
WFP has a formal framework to guide how it adapts food assistance modalities to local contexts, including where shifts towards more conditional and targeted modalities may be possible. It has a prioritisation matrix which considers food security, markets, and livelihoods indicators; this was updated with new IPC results released in December 2020 and Food Security and Nutrition Monitoring (FSNMS) data to ensure that areas with greatest needs were prioritized.

In 2020, WFP increased the capacity of UN agencies and partners to register, analyse and manage digital beneficiary data to strengthen accountability and support planning and coordination for assistance provision to the most vulnerable through the SCOPE system. By doing so, this enabled 31,000 people to receive humanitarian assistance. So far, WFP has biometrically registered over 3.7 million people in South Sudan, in collaboration with NGO partners and including the first successful interagency data migration with IOM as part of the data sharing agreement between WFP and IOM. This provides increasing reassurance that the most acute needs are being met.
[note] SCOPE is a digital system used to manage the identities and entitlements of beneficiaries

Although WFP takes into account the conflict history and broad vulnerability criteria in targeting at County level, communication between WFP and the NGOs carrying out the work on the ground can be further improved. This will strengthen vulnerability targeting at the field level by engaging communities as well as improving accountability for downstream partners. This includes the revision of WFP’s communication strategies with NGO partners about targeting, selection criteria, caseload and registration processes. This issue was explored in further detail in the ELFSS Synthesis Report on Targeting beneficiaries and Determining ‘vulnerable'.

Recommendations
- Targeting remains a systemic challenge, particularly for WFP and its downstream partners. FCDO and HARISS partners should continue to discuss targeting approaches, focusing on findings and recommendations from the Evidence and Learning Facility for South Sudan (ELFSS) Synthesis Study on Determining Needs and Beneficiary Targeting, May 2020 and ensuring resources are directed to the most vulnerable.
- FCDO and implementing partners should make all efforts to support the 2021 IPC analysis process to ensure it is i) achieved through consensus and is ii) a technically sound, evidence-based process.

Pillar	Nutrition	Pillar Score	A
Risk:	Major	Impact weighting (%):	14%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

HARISS funding for nutrition activities accounted for 14% of the total budget and activities broadly fell into two categories:
- Prevention of acute malnutrition comprising messaging on infant and young child feeding (IYCF) and blanket supplementary feeding programme (BSFP).
- Management of acute malnutrition comprising outpatient therapeutic programmes (OTP) for severe acute malnutrition (SAM) and targeted supplementary feeding programmes (TSFP).

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
WFP	Messaging and counselling on specialised nutritious foods and infant and young child feeding (IYCF) practices implemented effectively	10%	A
UNICEF	Girls and boys under age five, adolescent and women have increased access to quality preventative nutrition, health and WASH services	36%	B
UNICEF	Girls and boys under age five have increased and more equitable access to better quality nutrition services for early detection and treatment of severe acute malnutrition	36%	A
SSHF	Support to nutrition services	8%	A
Medair	Children with severe acute malnutrition have increased access to quality preventative and curative nutrition services	9%	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of children (6-59 months), women, adolescents treated with severe or moderate acute malnutrition	UNICEF / SSHF / Medair	44,080 / N/A / 8,636	43,696 / 13,763 / 7,363
Beneficiaries supported through blanket supplementary feeding programmes (BSFP)	WFP	58,713	37,678
Beneficiaries supported through therapeutic supplementary feeding programmes (TSFP)	WFP	104,684	86,095

Overall Situation
By the end of the year, 1.4 million children under age 5 were estimat­ed to suffer from acute malnutrition. This represents the highest caseload of children with acute malnutrition reported since December 2013 and marks an increase from 1.3 million children reported at the beginning of the 2020. A high prevalence of diseases and poor quality and diversity of food elevated levels of food insecurity (IPC Phase 3 and above), and poor access to health and nutrition services continued to drive up malnutrition rates.
[note] South Sudan Humanitarian Fund 2020 Annual Report

Partner Performance
The vast majority of FCDO’s funding to UNICEF in 2020 supported a multisectoral nutrition programme with two main components of prevention and treatment of acute malnutrition. In an effort to improve delivery, UNICEF shifted to a more integrated approach across nutrition, WASH and health. Under this pillar, UNICEF’s performance has been mixed.

UNICEF exceeded its target for the number of community nutrition volunteers (CNVs) trained on counselling in nutrition, health and WASH (868 against target of 800) and the number of pregnant and lactating women (PLWs) and caregivers who received key messages and were counselled on nutrition, health and WASH (349,674 against target of 332,000). Information on the symptoms and prevention of COVID-19 were integrated into the training sessions, with sanitation and handwashing also among the key messages provided in the context of the COVID-19 outbreak. Husbands, grandmothers, and in-laws were also included in the counselling as they strongly influence whether mothers and caregivers can adopt and sustain optimal practices. UNICEF also achieved the target for the number of children treated in the Greater Upper Nile (GUN) region (43,696), with children reached through both static nutrition sites as well as through the Integrated Rapid Response Mechanism (IRRM).

Key challenges for UNICEF in 2020 have related to procurement delays, with most of UNICEF’s supply chains (apart from Ready to Use Therapeutic Food (RUTF)) severely disrupted due to COVID-19. Production delays, shipment delays and backlog at customs all resulted in the halting of key activities that rely on large scale procurements. For instance, UNICEF had not delivered any of the insecticide treated nets (ITNs) (318,000) and only a small number of the expected WASH kits (33,800 out of 318,000) had been delivered to SAM and MAM children. By the end of 2020, supplies had arrived in-country and were in the process of being dispatched to nutrition partners, ahead of final distribution to beneficiaries by June 2021. Indicator milestones were subsequently amended to reflect the context.
[note] UNICEF had to change its supplier in India to an alternative supplier based in Germany. In addition, there was a shipping lead time of 9-10 weeks.
[note] Lockdown in June affected suppliers manufacturing capacity and transport delays due to COVID-19 testing and certification of truck driver during transportation from Uganda to Juba also had an impact

The COVID-19 pandemic also presented challenges to Medair’s nutrition programming, which meant that it had to restructure services and train staff to ensure that interventions were aligned with national and global protocols (see risk and challenges below). Nonetheless, Medair performed well and most outputs achieved within <5% of what was planned. In Leer, Renk and Aweil, Medair operate a number of nutrition sites, providing outpatient and supplementary feeding services. On 31 December, nutrition services in Aweil were handed over to another partner. In Renk, Medair suspended all nutrition services in October due to insecurity (see more detail under the risk section). In addition, Medair’s emergency team conducted three rapid assessments in three counties resulting in implementation of two interventions in Jonglei County, one in Ayod and one in Pibor. In Ayod, the team implemented an emergency multi-sectorial response which targeted 10 nutrition sites, though this was disrupted due to flooding and the team had to be evacuated in August. In Pibor, the emergency team handed over the Stabilisation Centre where they provided inpatient treatment of complicated SAM patients to a static team who will develop a longer-duration programme over 2021 with continued UK support.
[note] Such scenarios are factored into the HARISS risk register, with accompanying mitigation actions. In some cases, partners may need to reprioritise resources should areas become inaccessible.

WFP also performed well under this pillar. Between July and December 2020, 96% of targeted caregivers received the three key messages through WFP-supported messaging and counselling, exceeding the target of 90%. However, the number of children and caregivers reached through WFP-supported messaging and counselling at the facility level was reduced due to COVID-19 and the resulting change in admission criteria. WFP and partners did ensure that community outreach through community nutrition volunteers was increased, and key messages around COVID-19 prevention and mitigation incorporated.

With support from the SSHF, the nutrition cluster supported activities including treatment of children with severe acute malnutrition and nutrition counselling on maternal, infant, and young child nutrition targeting mothers/ caregivers.

Gender and Inclusion
UNICEF works with partners to ensure active participation of women and girls during social mobilisation. During implementation, women and girls’ empowerment is supported through participation in community activities, training, and provision of MIYCN education opportunities for adolescent girls and women.
While the programme does not restrict employment of community health and nutrition workers and CNVs to women only, preference is given to women as they are proven to be more effective in influencing behaviour change through mother-to-mother support groups.

Following IASC guidelines, UNICEF also works closely with the Government and implementing partners to engage women and children with disabilities to ensure equitable distribution of services. UNICEF ensures that children with disabilities are screened for malnutrition and treated based on the admission criteria; there is a referral mechanism to identify cases of malnutrition among children with disabilities and to refer them to treatment sites to avail health and nutrition services. CNVs and mother-to-mother support groups are also oriented to pay special attention to physically disabled women and children to ensure their access to nutrition and health counselling services.

Risks and Challenges
Due to the COVID-19 pandemic, nutrition sites suspended the use of weight for height (WFH) as an admission criterion and instead adopted the simplified mid-upper arm circumference (MUAC) protocol. Since many children in South Sudan are diagnosed with acute malnutrition by WFH alone and some partners reported a shortage of MUAC tapes, the roll out of this new methodology has not been successful in all locations. This has been picked up through TPM, as well as the perception among caretakers and staff that the switch in the admission criteria has meant that some of the children could not be admitted who otherwise would have been. Compared to 2019, both WFP and UNICEF have reported lower admission rates in 2020, with some partners attributing this to the change in admission methodology. Further work is needed to understand the impact of COVID-19 restrictions on admissions, however, UNICEF has played a critical role in the nutrition cluster to encourage partners to adapt this new criterion and adjust to the challenges presented when such a significant change is rolled out.  In addition to the MUAC protocol, all household SMART surveys and exhaustive MUAC assessments were put on hold in-line with national and global pandemic guidelines to prevent the spread of COVID-19.
[note] This reflected updated policy from the Global Nutrition Cluster in response to COVID-19

Recommendations
UNICEF’s multi-sectoral nutrition programming in 2020 was an important step in laying the groundwork for further integration of services with WASH and Health interventions. UNICEF should continue to build on the success of this approach, including the development of more ambitious multisectoral indicators, and clear linkages with activities implemented by UNICEF and other partners for the same community.
.
Sub-recommendation
Most of UNICEF’s supply chains (apart from RUTF) were severely disrupted by COVID-19. UNICEF should consider revisiting its procurement pipeline to prevent this issue happening should supply chains continue to be impacted.

Pillar	WASH (Water, Sanitation and Hygiene)	Pillar Score	A
Risk:	Major	Impact weighting (%):	7%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

WASH funding accounts for 7% of the HARISS budget. In 2020, HARISS supported WASH interventions through UNICEF, Medair, IOM, SSHF and ICRC. These included:
- Drilling and rehabilitation of water sources (boreholes and wells) and establishing or restoration of surface water treatment systems.
- Rehabilitation and construction of sanitation facilities within communities and in institutions.
- Promotion of improved hygiene practices through hygiene messaging.
- Distribution of WASH non-food items like jerry cans and water treatment tablets.

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
Medair	Timely access to safe water, sanitation, and improved hygiene practices is provided to vulnerable populations in acute and chronic emergency situations	27%	A
UNICEF	Vulnerable populations (female and male) in Protection of Civilians (PoC) have access to WASH humanitarian lifesaving services at minimum sphere standards.	18%	B
IOM	IDPs in PoCs and adjacent collective sites have access to appropriate WASH services, including sufficient and safe water for domestic use, soap to meet hygienic needs, and dignified, safe, clean, and functional excreta disposal facilities	9%	A
IOM	Displaced populations, IDPs, and host communities in hard-to-reach areas have access to WASH services through rapid WASH Emergency Preparedness and Response (EPnR) Missions	8%	A
IOM	At-risk communities have access to additional infrastructure that supports regular hand washing behaviour	8%	A+
IOM	At-risk communities have strengthened awareness of COVID-19 WASH-related preventative measures	8%	A+
ICRC	Improved access to water, hygiene and sanitation facilities	8%	A
SSHF	Support to WASH services	15%	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of beneficiaries with improved access to clean water and/or sanitation.	IOM / SSHF / Medair / UNICEF / ICRC	N/A / 42,000 / 142,491 / 111,000 / 14,260	1,534,951 / 70,000 / 174,666 / 111,237 / 22,019

Overall Situation
50% of the population in South Sudan lacks access to safe water and only 10% of the population has access to improved sanitation. Flooding in 2020 affected an estimated 856,000 people, with flood-induced displacements further limiting people’s access to WASH infrastructure and services.
[note] https://www.unicef.org/southsudan

Partner Performance
IOM performed well in 2020, providing WASH support in Protection of Civilians site (PoCs) (Bentiu, Malakal and Wau), emergency WASH outside of PoCs, and managing the WASH core pipeline. Bentiu and Wau have now been de-designated as PoC sites and transitioned to IDP camps, but IOM continues to operate in those locations.
[note] The PoC sites were established at existing UNMISS bases as a result of the 2013 conflict, providing protection to those at risk of immediate physical harm. UNMISS provides physical protection at these sites with policing undertaken by UNPOL. PoC sites differ from previous ‘safe havens’ in other contexts such as Iraq or Rwanda as they were not pre-planned and were co-located at existing bases

In PoCs (or former PoCs), IOM provided on average 18 litres of water per person per day (LPPD) to 79,696 people, exceeding the minimum Sphere standard for water provision. While below the target of 90,143, IOM attributed this to the decrease in the total population in the PoCs due to 10,447 people either returning home or relocating. IOM also continued to maintain five boreholes, as well an emergency one, across the PoCs and conducted daily free residual chlorine (FRC) tests in order to ensure safe water. A total of eleven solar pump systems continued to operate across PoC sites. Initial findings from the Knowledge, Attitudes and Practices (KAP) survey in December 2020, undertaken by IOM, report above average usage of latrines, marking an improvement from last year. However, the ratio of number of people per latrine in Bentiu stood at 29:1 which is higher than the sphere standard of 20:1. IOM clarified that this was due to ongoing issues of congested sanitation corridors which they are working to address.
[note] The Sphere standards are a set of principles and minimum humanitarian standards in four technical areas of humanitarian response, including WASH. The minimum standard for water provision is 15 litres per person per day
[note] Designed by IOM to help define and refine IOM’s Risk Communications and Community Engagement (RCCE) strategy in areas where IOM had planned to build C-19 WASH-related infrastructure https://reliefweb.int/sites/reliefweb.int/files/resources/KAP_finalreport_endline_DEC.pdf

With the outbreak of COVID-19, FCDO provided IOM with an additional £800,000 to support key WASH and pipeline activities in response to the pandemic. It is for this reason that a much higher number of people have been reached with WASH activities in contrast to previous years (1,534,951).  In total, four handwashing facilities (two in Wau; two in Juba), also physically verified by the TPM team, and 14 handwashing stations (all in Juba) were built and remained operational, in addition to direct COVID-19 related hygiene promotion. Beneficiaries interviewed through TPM appeared to have a basic understanding of how COVID-19 spreads, identifying some of the symptoms and what they should do if they experienced them, although capacity to act can be an issue – the KAP found that 98% of households had received COVID-19 messaging, but only 55% were implementing, highlighting a clear gap between knowledge and practice. Finally, TPM findings challenged IOM’s exit/sustainability plans regarding the maintenance of the washing stations.

Through the WASH Emergency Preparedness and Response Missions (EPnR) in host communities and hard to reach areas, IOM met and moderately exceeded expectations across all indicators. As part of a £1.5m scale up in September 2020, further WASH and NFI support to flood-affected populations was implemented in priority IPC 4 and 5 areas to reduce the risk of famine. This included improved access to safe water and hygiene promotion and repair and maintenance of dikes.

In 2020, FCDO’s support to UNICEF under this pillar targeted the displaced people in Bentiu, where beneficiaries were provided with safe water through the operation and maintenance of surface water treatment systems in vulnerable host communities in Rubkona and mechanised boreholes in the PoC. The sanitation output targeted the residents of the PoCs in Juba and Bentiu, where beneficiaries were provided with safe sanitation through rehabilitation as well as the construction of emergency latrines. Following consultation between FCDO and UNICEF, the output targets for both indicators were revised as other funding was secured by downstream partners for the planned activities. Additionally, the number of residents decreased for the sector in which UNICEF/FCDO continued to provide water and sanitation services.

It should be noted that targets for this component have been consistently revised downwards in both FY 19/20 and 20/21 (see risk and challenges section below). This is the principal reason for the score of B in this output, despite the revised targets being met, which contributed to the decision that FCDO will not continue its support to UNICEF for WASH standalone frontline delivery or pipeline in 2021.

Medair continued implementing institutional and community WASH activities in Renk until October (activities were then suspended due to escalating tensions), Aweil Centre, Leer and ERT locations. In the third quarter of 2020, the rain intensified and forced Medair to halt interventions in some locations in Aweil and Leer. Despite the challenges, the WASH sector achieved all the milestones against this output. COVID-19 restrictions hindered the ERT’s ability to respond to emergencies, nonetheless they conducted rapid WASH needs assessments alongside other sectors in eight locations and completed interventions in Akobo East, Palouny, Lekuangole (flood response), Pibor AA Site, Nimule, Lekuangole (inter-communal violence emergency response), Hai Baraka and Gondokoro Island.

In cooperation with local authorities, ICRC repaired or constructed latrines and water systems. It also supported the COVID-19 response by setting up handwashing stations in health facilities and places of detention, and donating soap, face masks, and other supplies. Through the SSHF, the cluster prioritized households’ access to safe WASH, including household water treatment and handwashing facilities.

Gender and Inclusion
IOM utilizes a strong community-based approach within its WASH programming, which included promoting the participation of women in activities. IOM incorporated GBV mainstreaming activities within WASH operations in the PoC sites and EPnR missions, including GBV safety audits at water points and sanitation facilities. Latrine and bathing facilities at the Bentiu and Malakal PoCs, are separately and equally allocated to men and women, and marked by colours and signs. Meanwhile, both UNICEF and Medair ensure that gender-specific facilities are constructed when appropriate.

Risks and Challenges
Management of the WASH pipeline has been an issue of ongoing concern in South Sudan. There are two WASH pipelines: one run by UNICEF, and the second run by IOM. Whilst international cargo handling has been very challenging during 2020 due to the pandemic (as outlined under the nutrition pillar), the UNICEF WASH pipeline suffered significant delays while the IOM pipeline remaining relatively stable.

Recommendations
- The FCDO should consider prioritising funding to the IOM WASH pipeline.
  [note] This recommendation was implemented during the 21/22 prioritisation work
- FCDO should engage and support the roll out of the WASH Severity Classification assessment and analysis (a multi-agency approach coordinated by REACH and the WASH cluster, similar to the IPC process for food security) for South Sudan, which the UK is providing some funding to from centrally managed programming.
  [note] See example: https://www.reachresourcecentre.info/theme/wash/cycle/34986/#cycle-34986

Pillar	Health	Pillar Score	A
Risk:	Major	Impact weighting (%):	7%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Health accounted for 7% of HARISS funding in 2020. Health interventions supported under HARISS included:
- Disease outbreak prevention and response.
- Primary health care especially maternal and child health including integrated management of childhood illnesses.
- Expanded programme of immunisation.
- Trauma treatment and rehabilitation, particularly of war wounded.

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
Medair	Increased access to quality preventative and curative health services for emergency affected populations	27%	A+
UNICEF	Vulnerable populations (female and male) in humanitarian situation have access to health services.	18%	A
SSHF	Support to health services	27%	A
ICRC	Improved access to health and provision of surgical care	11%	A
IOM	Displaced populations in PoCs have access to life-saving primary health-care services, including Expanded Program on Immunization and Sexual and Reproductive Health, including HIV/AIDS counselling and testing	9%	A+
IOM	Life-saving primary health care services are provided to displaced populations through static and mobile clinics outside of PoCs and deployment of Health Rapid Response Teams	8%	B

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of people vaccinated against preventable diseases	Medair	26,148	22,096
Number of people whose health needs were met (curative, preventive and vaccination) by SSHF funding	SSHF	98,000	126,000

Overall Situation
Prolonged conflict and limited investment in the health-care system continue to adversely affect health infrastructure and basic service delivery. Of approximately 2,300 Government of South Sudan health facilities in South Sudan, more than 1,300 are assessed to be non-functional, with some 57% of the functioning sites supported by humanitarian and development actors.
[note] South Sudan Humanitarian Fund 2020 Annual Report
[note] The UK supports eight states through the Health Pooled Fund to deliver primary health care services

Partner Performance
In 2020, Medair implemented chronic emergency response health activities in Renk, Aweil and Leer and acute emergency interventions across South Sudan through its Emergency Response Team (ERT), reaching 107,514 people overall against the target of 98,434. It either achieved all output indicator targets or was easily within a 10% deviation.

Across its static locations, Medair has continued to contribute to improved access and quality of essential health services and has invested in promoting key public health practices through Care Group networks, and capacity building of local health staff and rehabilitation of health facilities. In Leer, it has also expanded its mental health and psychosocial support. In Aweil, Medair provided its last year of support where 16 locations were supported with integration of a complementary package of health services. Most services were handed over to the Ministry of Health in this location. Meanwhile, health services in Renk were significantly impacted as a result of the escalating tensions with local groups labelling themselves as ‘youth’, which led Medair to postpone all activities in October 2020, leaving an extremely vulnerable population unsupported. There have since been reports of women who delivered children along the roadside as delivery services were not functioning and several infant and maternal deaths.
[note] Care Group Networks consist of trained women volunteers who regularly visit women and their families in the community to promote good health, hygiene and nutrition

Many of the ERT interventions supported the COVID-19 outbreak. This included the training of health workers in Nimule (a priority location as a major entry point from Uganda) and assessing of health facilities in and around Juba on their COVID-19 prevention and preparedness. This was complemented with a joint WASH and health risk communication and community engagement (RCCE) intervention, through which health and hygiene promoters shared messages on COVID-19 prevention, recognition, and response. A success of the ERT has been the design and implementation of a remote case management intervention for support of patients with mild and moderate COVID-19 in home isolation, addressing key gaps while protecting health staff. The MoH and WHO welcomed the initiative that has played a key role in the response in Juba. The ERT was also able to carry out a reactive measles vaccination campaign in Pibor in November and December, as well as vaccinations undertaken in the static locations. It also conducted three primary healthcare interventions in 2020, including in Pibor where it responded to high levels of morbidity from malaria and water-borne diseases.

A key challenge for the ERT in 2020 has been related to movement restrictions because of the COVID-19 pandemic which has meant a lot of the responses this year have been in and around Juba. This started to change in the latter part of the year (including the ERT response in Pibor mentioned above, which is now in the process of transitioning to a static location). It is important that the ERT can reach areas most in need and not unnecessarily hampered by restrictions and other bureaucratic impediments.

In 2020, FCDO’s contribution to UNICEF under the health pillar was smaller in contrast to previous years. The primary focus of activities was on the installation of cold chain equipment to enhance the capacity of the MoH to ensure safe storage and uninterrupted supply of vaccines across the country. The cold chain equipment was to be prioritised in the health facilities which had their equipment damaged following the 2019 floods. 180 cold boxes and 600 vaccine carriers were received in September 2020 and were distributed to respond to measles outbreaks in Pibor, the yellow fever campaign in Kajokeji and the ongoing polio outbreak response. Passive cold chain equipment (designed for vaccine storage with ice packs without the need for electricity) was provided to the state vaccine stores in Bor, Pochala, Old Fangak, Akobo and Nyirol. The delivery of solar direct drive refrigerators was delayed due to procurement issues, caused by competing demands globally and longer lead times resulting from the impact of COVID-19 on the global supply chain. This was expected to be completed in early 2021.

IOM continued to provide life-saving primary health care services through static, mobile and Rapid Response Teams (RRT) within the PoCs. 587,843 consultations were provided and clinical quality assessments from the reporting period showed 100% of patients were treated as per the protocol and recommended the use of the health care services to other community members. IOM continued to reach displaced populations outside PoCs; 21 health facilities (13 of which were mobile) were supported for primary health care and routine immunization, whilst 19 RRT were deployed for primary health care responses. COVID-19 related restrictions and flooding limited the number of people accessing health services in RRT sites thus the outreach was not as frequent as planned, resulting in an under achieved target.

Gender and Inclusion
Medair ensures that health and nutrition services and hygiene promotion were conducted including a house-to-house model where possible to reach the elderly, people with physical disabilities, women who are in late-stage pregnancy or who have recently given birth, or women and girls unable to travel long distances due to the burden of domestic labour.

Risks and Challenges
COVID-19 posed the main challenge during 2020, requiring a crucial adjustment in programming to protect beneficiaries and staff while enabling access to essential health services. Health staff received training and many clinics were redesigned with screening and triage areas, isolation areas for suspected cases, additional handwashing facilities and provision of personal protective equipment (PPE) and social distancing measures. However, the focus on COVID-19 has severely disrupted the capacity of partners and the wider health system on the monitoring, surveillance, and treatment of other communicable diseases, which was already severely stretched prior to the pandemic. Successive Ebola outbreaks in neighbouring Democratic Republic of the Congo posed a risk for South Sudan during the first half of 2020. Although the risk was not realised and no Ebola cases were confirmed in South Sudan, in future there may be similar risks given the recurrent nature of recent outbreaks.

Recommendations
- Strengthen linkages between the health, nutrition and WASH sectors, and seek out better synergy between health services funded through HARISS, the Health Pooled Fund (HPF) and the World Bank/UNICEF to ensure complementarity and to support the sustainability of investments in strengthening health systems and addressing malnutrition.
- Advisory leads within the British Embassy Juba Humanitarian and Human Development Cluster should prioritise discussions on this issue, in order to feed into discussions on HPF 3 and future humanitarian programming.

Sub-recommendation
Due to COVID-19 movement restrictions, a lot of the ERT responses this year have been in and around Juba. Medair should seek to broaden the geographic scope of the ERT as soon as COVID-19 conditions allow and reorientate this component to react to lifesaving interventions.

Pillar	Shelter/NFIs and Camp Management	Pillar Score	A
Risk:	Moderate	Impact weighting (%):	6%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Overall, Shelter/Non-Food Items (S-NFIs) and Camp Coordination and Camp Management (CCCM) amounted to 6% of HARISS’s overall budget. HARISS partners that work in this sector included IOM (S-NFI and CCCM), Medair (S-NFI), and SSHF (S-NFI and CCCM). The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
IOM	Displaced populations in PoCs reside in safe and dignified sites in accordance with defined international standards through Camp Coordination and Camp Management activities	10%	A
IOM	Newly arrived IDPs and those facing shelter issues in PoC and Collective Centres in Wau supported with life-saving shelter and life-sustaining NFIs	10%	C
IOM	Displaced populations in hard-to-reach areas – including areas of return and camp-like settings – supported in governance, site care and maintenance, protection mainstreaming and inclusion through CCCM mobile responses	8%	A+
IOM	Survival and self-sufficiency of crises and flood affected populations is supported through timely and quality provision of S-NFI services	8%	A+
IOM	Relevant authorities are better capacitated to manage HLP issues in an ethical and transparent manner and communities have strengthened capacities and resources to resolve HLP issues	8%	A
IOM	Coordination of CCCM activities is maintained at the state level and within PoCs	6%	A
IOM	Shelter-NFI cluster partners receive quality cluster support and coordination which effectively responds to the needs of displaced populations	6%	A
IOM	Core Pipeline partners are supported with timely provision of Core Pipeline supplies for immediate emergency responses in South Sudan	10%	A
Medair	Vulnerable populations affected by acute onset emergencies have timely access to quality lifesaving NFI services	20%	A
SSHF	Support to NFI/shelter	9%	A
SSHF	Support to CCCM	3%	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of people provided with shelter and/or non-food items (NFI)	IOM / SSHF / Medair	31,350 / 42,000 / 24,000	101,849 / 56,000 / 33,854

Overall Situation
An estimated 1.7 million people were internally displaced, with the spike in sub-na­tional violence and floods triggering new displacements in 2020. More than 388,000 people were displaced to a new location in 2020, including new displacement and movement of existing displaced people to secondary areas of displace­ment. 21% of IDPs live in displacement sites and 79% with host communities.
[note] https://displacement.iom.int/reports/south-sudan-—-mobility-tracking-round-10-initial-findings?close=true

Partner Performance
During 2020, IOM continued to provide CCCM functions in Bentiu PoC, Malakal PoC and Naivasha (Wau) IDP site (see more on PoC transition to regular IDP camps under the risks and challenges section). Overall, 106,260 people in PoCs/camps were provided with functional coordination and management mechanisms, falling short of the 156,250 target. IOM reported that this was due to the decrease in the total population of IOM’s operating areas in the PoCs from the baseline period. As part of IOM’s frontline responses in hard-to-reach  areas, the CCCM mobile teams delivered critical site management support, including establishing coordination and service monitoring mechanisms. In Unity, mobile teams took part in two OCHA-led inter-agency missions to assess the flood situation and the response needed. A detailed scoping report and recommendations were shared with clusters following the missions for resource mobilisation. In total, 22 CCCM mobile assessments and responses were conducted, substantially exceeding the target of 7. All CCCM activities practised social distancing and followed hygiene protocols, with IOM also strengthening the capacity of frontline staff.

In hard-to-reach areas, IOM also provided 101,849 people with S-NFI assistance (substantially exceeding the target of 51,880) and provided 12,103 people with safe and dignified shelter solutions. Through rapid monitoring and PDM, IOM reported that based on the average of six PDM’s, 81% of respondents reported that S-NFI assistance was participatory, safe, and equally accessible. However, in Wau PoC, only 1090 people of the 4000 targeted were reached due to fewer IDPs registered than expected.

IOM’s management of the core pipeline in 2020 was a notable success despite multiple challenges, including the pandemic, which stretched the pipeline’s capacity to meet unprecedented needs. The response remained fast and effective, with 100% of approved partner requests for WASH and S/NFI Core Pipeline supplies processed within 72 hours and 94.6% of requested stock delivered to the response location within 15 days, exceeding the target of 85%. Moreover, IOM’s Core Pipeline annual partner satisfaction survey gathered feedback from 57 partners: a combined 93% of respondents were extremely satisfied or satisfied, and only 7% were neutral. This is an increase from an already impressive 90.4% in 2019.

Large scale outreach and education on HLP (housing, land, and property) matters has been significantly curtailed due to COVID-19 restrictions (indicator 2.6.1). However, IOM continued to reach rural and peri-urban communities with the provision of legal resources, education, and support. IOM importantly also continued to advance the passage of the draft National Land Policy, now also referenced in UNSCR 2567.

In 2020, Medair significantly exceeded the target for the number of people provided with NFI / Shelter support (33,854 against the target of 24,000). From the two PDMs conducted, 85% of people were using NFIs appropriately when the team went back to the community, while 84% of those surveyed reported that they were satisfied with the quality of the received S/NFI items. Medair received positive feedback, with many beneficiaries reporting that the assistance was timely, participatory, appropriate, and most saying their basic needs had been met.

Through an integrated sectoral approach and an ongoing effort to find more sustainable S/NFI solutions, the SSHF aimed to improve the living conditions of displaced families, IDP return­ees, spontaneous refugee returnees and host communities.

Gender and Social Inclusion
In 2020, Medair built strong community relations so that community leaders could help assess and verify the number of vulnerable households in each community. This was particularly important when flooding left many locations inaccessible. Before the distributions, Medair completed an effective analysis of the populations’ needs using the S/NFI Cluster’s analysis tools, involving communities in discussions to help determine the intervention to best suit the needs. Following the distribution, Medair teams completed exit interviews to remain accountable to the populations, to deal with any urgent issues whilst in the field, to identify any furthers gaps or needs, and for internal lessons learnt.

In Hai Masna, IOM CCCM facilitated a community-led leadership election process that resulted in the election of 56 new community leaders, with 46% of the elected leaders being women, which attests to the success of the work undertaken by IOM to promote the meaningful participation of women within governance structures. Women, girls, youth, and persons with disabilities are also prioritized in each S-NFI intervention.

Risks and Challenges
With the initiation of the UNMISS PoC de-designation and handover process, IOM CCCM teams in PoCs Bentiu and former Wau were engaged in the coordination of transition throughout 2020. This will also happen in Malakal at a future date, although local transition planning is already underway.  IOM has been proactive in engaging FCDO on transition issues, and FCDO visited Bentiu in December 2020 to observe the recent transition and its impact. FCDO shares the concerns of other actors regarding community engagement, sufficient notice, and the replacement of UNPOL with South Sudanese joint policing units. Community engagement appears to have been limited in the Bentiu case with the transition date arriving with limited notice.

Five of the six PoCs have now (as of date of this report) transitioned with the remaining one at Malakal perhaps posing the highest risk for residents security. Reduced funding for services in the former PoCs continues to be an issue with reduced food rations and difficulties in service provision such as fumigation.  Given the needs elsewhere some former IDP sites may fall victim to prioritisation in some cases, but the protection risk to inhabitants means that FCDO is continuing to prioritise activities there.  In addition, and on the back of briefings with IOM, FCDO was able to bolster the UNMISS mandate renewal with more robust language on community engagement and coordinated transition. The FCDO must continue to hold UNMISS and all members of the international community to account on commitments during the remaining PoC transition and fulfilment of the protection mandate.

Recommendations
FCDO, working closely with IOM and the humanitarian community, should identify opportunities to support advocacy on ensuring returns are voluntary, safe, and dignified. FCDO should work across the international community to ensure that existing guidelines are being correctly followed and risks relating to upcoming census and elections are managed. Any concerns should be raised at the highest levels to the Humanitarian Country Team, the UNHCR Country Representative, and the relevant Government of South Sudan ministries.

Pillar	Food Security and Livelihoods	Pillar Score	A
Risk:	Major	Impact weighting (%):	11%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

In 2020 11% of the HARISS impact weighting was attributed to the Food Security and Livelihoods (FSL) sector (excluding emergency food assistance). This was split between emergency livelihoods and resilience-building, delivered by five partners. FAO, ICRC and the SSHF delivered in the area of emergency livelihoods (distribution of seeds and tools, fishing kits, vaccination of cattle). GOAL delivered resilience building activities where a static presence and longer-term activities were possible, supporting communities to recover and increase their productive capacities, diversify their livelihoods and improve their resilience to shocks. IOM supported income generating activities for women and initiatives to support community resilience.

The tables below set out partner pillar scores and headline results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
GOAL	Beneficiary households' assets and livelihoods are strengthened and diversified	13%	A
GOAL	Skills and knowledge for resilience are improved	8%	A+
FAO	Emergency livelihood support provided to the most food insecure and vulnerable households	40%	A
FAO	Production and availability of livelihood inputs supported in Greater Upper Nile	6%	A
IOM	Strengthened community resilience through community-based climate change adaptation programming in flood affected areas	5%	A
IOM	Communities in Wau have strengthened resilience to shocks through community-driven infrastructure interventions and tailored skills and income-generating activities, with a focus on women	5%	A
IOM	Strengthened coordination of cash and market programming and advocacy through co-leadership and hosting CashCaP advisor of the Cash Working Group	4%	B
ICRC	To help people build resilience through the distributing of seeds and tools, fishing kits, livestock vaccinations and community development livelihoods projects	11%	A
SSHF	Support to food security and livelihoods	10%	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of vulnerable households (HH) supported with emergency livelihoods kits (seeds & tools, fishing kits)	FAO / ICRC	15,000 / 6,550	15,000 / 6,269
Number of vulnerable households supported to strengthen their resilience to shocks	GOAL / IMC	19,500 / 470	19,333 / 500
Number of livestock vaccinated and treated	FAO / ICRC	200,000 / N/A	224,033 / 34,500

Overall Situation
The counties of greatest food insecurity severity are found in locations where compounded shocks of violence, repeated flooding, the economic crisis and indirect effects of COVID-19 converge. These multiple shocks have severely impacted people’s livelihoods and access to food from markets, livestock and farming.
[note] 2021 Humanitarian Needs Overview https://reliefweb.int/sites/reliefweb.int/files/resources/south_sudan_2021_humanitarian_needs_overview.pdf

Partner Performance
FAO’s performance under this pillar has met expectations despite varying assessments from TPM monitoring. It will be important for FAO to continue working on timeliness of seed distributions, particularly for vegetable and crop kits, which were still raised as major issues requiring improvement.

In 2020, FAO undertook Rapid Response Missions (RRM) across counties in Jonglei, Unity and Upper Nile in areas affected by floods and conflict, reaching the milestone of 15,000 households, where they distributed ‘survival kits’ comprising seeds, tools and fishing kits. Following the COVID-19 outbreak, FAO prioritised a scale up to food security and livelihood needs in the Greater Upper Nile (GUN), revising the target for the main season response (MSR) from 10,000 to 50,000 households. The MSR target was exceeded with 59,821 households reached in 33 counties of GUN, providing seeds and tools for rain-fed staple crop production.

FAO’s Post-Distribution Monitoring (PDM) results show an improvement from last year in terms of mobilisation/information sharing as well as the timeliness of distributions. FAO report that by June they had received 93% of the total quantities of main season crop and vegetable seed procured for the main planting season, enabling delivery partners to complete distributions without delays. However, findings from TPMs carried out during the Dry Season Response (DSR) showed varying results. For instance, in Melut significant delays were identified in relation to the agricultural calendar and fishing season. PDM results also showed that while the target for quality was exceeded, there was a slight decline from last year. Some feedback from TPMs noted beneficiaries’ dissatisfaction with the germination of some seeds.

FCDO support covered two livestock vaccination and treatment campaigns in 2020 (one in the rainy season and dry season). In total, the target was exceeded with an additional 24,033 livestock vaccinated and treated. A nutrition education component was also introduced in 2020, however with the onset of the COVID-19 outbreak, FAO decided to scale down on capacity building activities and reduce the target by 50%.

In addition to its Emergency Livelihood Response programming, FAO also implemented cash for seed (CfS) modalities, which replaced seed fairs as part of its COVID-19 adaptation during the main season response in GUN. The target was fully achieved with activities completed in June and July 2020. TPMs in Melut and Renk verified that CfS distributions were in line with agreements, albeit with some delays due to the late arrival of financial service providers and poor road conditions. Key questions were raised around the timing of distribution and targeting, with reports of a large volume of complaints from the individuals who were not selected. A review of the selection and identification of beneficiaries is therefore recommended in those communities with high number of complaints.

Under its RECOVER programme, GOAL continued to build on its successes from 2019, with 3,300 households supported in staple crop farming, 7,600 in vegetable gardening, and 4,155 for fishing activities. Agricultural inputs were all distributed in Quarters 2 and 3; PDM conducted in Panyijiar in July for this activity showed that most farmers (87%) expressed being ‘very satisfied’ with the quality of seeds and tools distributed and 86% with the overall distribution process. Notably, 96% of respondents indicated that the tools received improved their farming.

GOAL also continued agricultural support through trainings and supervision. Accordingly, 19,333 individuals were trained within the year, achieving 108% against the target. Training included climate-sensitive agricultural practices, vegetable gardening, fishing processing techniques and vocational trainings for women and youth in income generating activities (IGA), and village savings and loan schemes (VSLAs). On the latter, 2949 women and youth received small business grants to invest in their own ventures, providing an alternative source of income, however most of the IGA did not perform very well because of the limited access to market due to COVID-19 and floods. The grant value to start an IGA was also exceedingly small and affected by exchange rate lost, which made it difficult for many beneficiaries to start a business, and for those who started, it was difficult to sustain it.

Through community-based climate change adaptation programming, IOM looked to strengthen community resilience. The repair of the existing dike in Bor was identified by the community as one of the top priorities to mitigate the impact of the floods and benefitted a total of 33,760 individuals in six villages. Due to extensive flooding in Bor, community mobilization activities were delayed until December, not meeting the target. IOM’s interventions to strengthen resilience to shocks through community-driven infrastructure interventions and tailored skills and income-generating activities, with a focus on women, all met or over-achieved targets.

Through Cash for Work, IOM also assisted 39,480 individuals in upgrading their shelters in Agyei Administrative Area and provided cash to 1,485 flood-affected vulnerable individuals in Bor, Jonglei. IOM’s cash-based responses are complementary to its co-leadership of the Cash Working Group and take place in locations assessed to have functioning markets and absorption capacity.

ICRC provided food supplies to farming households during the lean season, so that they would not have to consume seed meant for planting or barter farm implements for food. Some households were also provided with fishing kits. SSHF activities focused on improving food consumption, dietary diversity and coping strategies for vulnerable pop­ulations, enhancing emergency food production through complementary vegetable and crop seeds and fishing and livestock support.

Gender and Inclusion
FAO’s M&E assessments conducted in 2020 indicate that two-thirds of beneficiaries were women, girls, youth, and people with disabilities. FAO emergency livelihood kits are designed to be lightweight; distribution sites and times are to be appropriately planned by partners not too far from the homestead and during the day light for protection reasons.

RECOVER ensures that programme participants include IDPs, host communities and returnees during the distributions, and that both women and men were targeted. During the registration of cash transfer programme participants, new IDP arrivals and returnees were also considered. The selection of programme participants was planned in conjunction with the community to ensure the inclusion of vulnerable groups, such as female headed households and the disabled.

Risks and Challenges
GOAL’s RECOVER annual survey conducted in June 2020 shows significant improvements in household food consumption, a significant reduction in the number of households using emergency coping strategies compared with the previous year and evidence that the varied project interventions has diversified households’ income sources, with the increase linked to the sale of crops, vegetables and fish, and small businesses. However, there remain notable challenges associated with delivering resilience building programmes in such a dynamic and difficult context, ensuring that it delivers impact to communities without resorting to humanitarian style distributions. For example, the community continued to rely heavily on partner provided inputs in 2020. Despite the targeted support to traders to supply markets with essential commodities and tools, availability of fishing kits, farming tools and seeds remain modest. This affects the sustainability of the intervention.

Recommendations
FCDO should seek to look across its investments in HARISS and BRACE II with a view to determining the most efficient and effective models for strengthening resilience (in particular cash modalities) in South Sudan, identifying good practice from both FAO and GOAL.

Pillar	Protection and GBV	Pillar Score	A
Risk:	Major	Impact weighting (%):	10%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

In 2020 there were five main HARISS partners which contributed to this pillar: IMC, ICRC, HI, SSHF and IOM. Partner-supported activities included:
- GBV/protection prevention and response activities, including case management, psychosocial support, management of women and girls’ friendly spaces, and awareness raising.
- Visits to detainees and restoration of family links as well as training combatants on IHL.
- Integrated protection mobile responses (protection/GBV/child protection/mine action).

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
IMC	Safety of women and girls in the community enhanced through GBV risks mitigation activities including awareness sessions and capacity building for partners and community members.	14%	A
IMC	Appropriate GBV response activities, including sex and age-appropriate case management, referrals and WGFS activities is accessible for women and girls in Jonglei, Upper Nile, Western Bahr El Ghazal and Unity states.	23%	A
IMC	Women in Jonglei, Unity, Western Bahr El Ghazal and Upper Nile states engaged in feasible livelihood activities including Income Generating Activities (IGA)	11%	A
SSHF	Support to protection services	11%	A
ICRC	To help improve conditions for detainees	2%	A
ICRC	to help reconnect family members separated by armed conflict and other violence	2%	A
ICRC	To promote knowledge and respect for international humanitarian law (IHL) and international human rights law (IHRL)	2%	A
HI	Vulnerable individuals (with and without disabilities), families, groups and communities exposed to violence and adversity are empowered with positive coping and solidarity mechanisms	5%	A
HI	Improved quality of care, referral and coordination mechanisms in the MHPSS sector at local and national level	4%	A
HI	Increased capacity of humanitarian actors to mainstream disability within their strategic planning, operations and MEAL within their programme in South Sudan	6%	A
HI	Increased advocacy actions at national and state level on mainstreaming of disability sensitive measures in humanitarian action and in national legislation and policies	4%	A
IOM	Displaced populations in PoCs have access to targeted and appropriate MHPSS support	6%	A
IOM	Conflict-affected populations have access to targeted and appropriate MHPSS services, provided by psychosocial mobile teams and capacitated social worker trainees of the Ministry of Gender, Child and Social Welfare	4%	A+
IOM	Strengthened GBV case management and responses	4%	A
IOM	Strengthened coordination, integration, and harmonization of mental health and psychosocial support activities in South Sudan	3%	A
IOM	Strengthened centrality of protection – including disability inclusion, trafficking in persons, and prevention of sexual and gender-based violence – within all programming	5%	B

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Number of people trained on GBV prevention and response	IMC	1,179	1,028
Number of people reached with information on GBV, rights and services available	IMC / IOM	349,651 / N/A	337,087 / 3,792
Visits to detainees and training of military and police personnel on International Humanitarian Law	ICRC	N/A	65
Number of people reached with protection interventions	SSHF	42,000	70,000
Number of people (HARISS partner staff) benefitting from awareness sessions on disability	HI	350	475

Overall Situation
Protection issues are endemic across South Sudan and exacerbate the humanitarian crisis. Most violence resulted from conflict between community-based armed groups, mainly driven by competition of local resources, cycles of revenge, and sometimes fuelled by national elites. The severe violence exposes large sections of the population to a variety of protection risks on a daily basis and protection services are a key part of HARISS. Women, children and the disabled are particularly vulnerable to these risks. Levels of trauma and mental health needs are exceptionally high across the population due to the near constant experience of violence over the past 50 years.

In the past year armed conflict, sub-national organized violence, COVID-19 restrictions and flooding have exacerbated the already extreme levels of Gender-based violence (GBV). According to the 2021 Humanitarian Needs Overview, over 6,000 GBV incidents were recorded across the country between January and September 2020. Nearly all, or 97% of the reported GBV incident survivors, were female and a fifth of survivors were less than 18 years old. Intimate partners accounted for more than half of the alleged perpetrators. Displaced women and girls continue to bear the brunt of GBV, while basic GBV risk mitigation measures around sanitation facilities remain extremely rare outside large IDP camps.
[note] 2021 Humanitarian Needs Overview https://reliefweb.int/sites/reliefweb.int/files/resources/south_sudan_2021_humanitarian_needs_overview.pdf

Partner Performance
The majority of IMC’s programming is focused on the delivery of GBV prevention and response activities. Overall, IMC has performed well in 2020, meeting most of its targets.

To reduce suffering and provide support to vulnerable women and girls, IMC distributed 16,100 dignity kits. The content of the kits was informed by women and girls' feedback and included a range of sanitary and hygiene items. PDM showed that distributions were well organised, safe, and accessible, and generally the contents were appropriate and culturally acceptable. However, feedback suggested that the frequency of distribution and quantity should increase to target more women and girls of reproductive age. Some issues with quality were also captured through TPM: while recipients were satisfied with most of the items, there were some complaints regarding the poor quality of the torch and size of the slippers.

Other areas where IMC performed well in relation to GBV prevention activities included the training of community leaders and women’s committee members (694), NGO staff (334), and the number of women, men, boys and girls reached with information on GBV, rights and services available (337,087). Trainings included GBV concepts, referral pathway, how to conduct awareness raising and supporting women and girls. Sessions with NGOs and UN agencies also addressed case management, GBV National strategy and survivor-centred services provision to increase the effective and efficient collaboration among agencies and to ensure the provision of prompt support to beneficiaries including GBV survivors.

In addition, 22 safety audits were conducted across all project sites and were jointly participated with other partners including the protection cluster, NGOs, UN agencies, Ministry of Gender, Child and Social Welfare, and other local partners. The audit highlighted various issues of concern including around water selling by women and girls, gaps in CMR services, and issues related to hygiene and food security. Actions were subsequently agreed according to the different roles that partners had to play in mitigating those risks. It would be useful to keep sight of the progress of actions in the coming months.

On the response side, 1,392 GBV survivors received case management services from IMC through the women and girls’ friendly spaces. Physical assault has accounted for the majority of perpetrated cases, while psychological and emotional abuse accounted for the second highest number of GBV cases. In particular, IMC should be commended for its rape survivor response and Clinical Management of Rape (CMR) services which saw 75% of cases responded to for those that were able to report within the 72-hour window (noting this excludes the difficulties of other people in remote areas who were not able to report within 72 hours).

HI performed well in 2020, delivering most of its planned results throughout the year (albeit with some adjustments due to the impacts of COVID-19). This included reaching 3,967 people in Yei, Torit and Yambio with tailored Mental Health and Psychosocial Services (MHPSS) interventions and awareness raising activities to reduce stigma of mental health issues (27,975 people were reached, significantly exceeding the target of 16,930). On the latter, major topics covered during the sessions included COVID-19 risk communication, GBV, Disability Inclusion, and MHPSS. Feedback from callers during radio talk shows, which HI hosts to raise awareness of MHPSS to a wide audience, has remained largely positive with a call to HI to expand its activities to other areas within the state. An MHPSS hotline also launched in October 2020.

HI also delivers and strengthens coordination locally and nationally on MHPSS with humanitarian actors. In 2020, it trained 350 partner’s staff in MHPSS interventions and it organised 45 MHPSS coordination mechanism meetings in each field location and in Juba. A notable achievement is HI’s role in leading the development of the MHPSS referral pathway for Juba following repeated requests from partners and clusters.

Another significant component of HI’s programming has been the work to increase the capacity of humanitarian actors to mainstream disability within their programming in South Sudan. 475 HARISS partners staff were trained on disability and inclusion in humanitarian action, including sign-language training. In particular, HARISS partners UNICEF, IOM, WFP and IMC all benefited from both practical measures to mainstream as well as with enhanced disaggregated data collection.

IOM also provided MHPSS support to 10,222 people in PoCs and 11,442 people in host communities and hard-to-reach areas. Unaccompanied minors, GBV survivors, and individuals requiring general protection assistance received tailored social support, including referral to social, healthcare, and psychosocial services. To further strengthen GBV prevention and response, IOM partnered with a national NGO to improve survivors’ access to services. Through 2020, protection teams facilitated trainings of Protection from Sexual Exploitation and Abuse (PSEA), Protection and Disability inclusion to IOM units in Juba and in the field. Trainings on trafficking were significantly impacted by COVID-19 restrictions, both in terms of the rollout, as well as the number of participants being able to attend and will therefore take place in the first quarter of 2021.

All partners reported similar challenges and mitigation actions following the outbreak of COVID-19; all counselling activities and support group discussions were limited to no more than 10 participants and mass awareness campaigns were completed through megaphones by outreach workers going round the communities.

Gender and Inclusion
Women and girls are always at the forefront of designing and adjusting GBV interventions led by IMC. They are consulted about most programmatic decisions, such as choosing culturally appropriate and interesting activities in the Women and Girls Friendly Space (WGFS) targeted to different age groups, or in what type of business they want to run under the EEL Income Generating Activities (IGAs). Material assistance is also distributed on a needs-based basis instead of blanket coverage with standardized kits, and unaccompanied or separated girls, elderly women and persons with disabilities are all prioritized to receive the support. IMC has also cooperated with Welthungerhilfe (WHH) to ensure Persons with Special Needs, including pregnant and breast-feeding mothers and women with disabilities, are fast tracked during food distributions.

A Midline Evaluation Report was completed by Forcier on the HI project in June 2020 as part of ongoing monitoring and evaluation. Conclusions included that the recreational and peer support groups are confident of continuing meetings without HI involvement but skills development groups would need additional support. It was also found that while awareness levels on mental health and disability are broadly increasing, more sustained efforts are needed to contain stigma and religious actors need to be better integrated into project activities. Recommendations to improve sustainability include greater Mental Health and Psychological Support for skills development groups by helping members find markets for finished products, encouraging teachers and healthcare workers to continue spreading awareness in communities, and integrating religious actors by training them in the basics of counselling.

Risks and Challenges
GBV incidence in South Sudan is at an alarming level and societies seem to have accepted it as normal even when it affects the well-being of women and girls and particularly vulnerable groups, including persons living with disabilities. The situation is worsened by the increased tension among different factions of the conflict and other factors like flooding, and famine, which compound risks of violence rooted in discrimination against women and girls in the male dominant society. Survivors of rape are sometimes afraid to make reports because of the stigma associated with rape and the fear of victimization. Despite the ongoing efforts by partners to engage community members at all levels to address stigmas in these areas, TPM has consistently highlighted the challenges regarding the community buy-in needed to both prevent GBV and implement adequate responses. Other issues include limitations to making effective referrals to the legal sector due to financial barriers.

Recommendations
Substantial progress has been made in 2020 to strengthen inclusion across HARISS partners. For maximum impact and sustainability, HARISS partners should engage and empower Organisations of Persons with Disabilities to ensure they have the resources and skills to represent and advocate for their members with the wider humanitarian response.

Sub recommendation
IMC to continue to maintain quality of dignity kits

Pillar	MEAL	Pillar Score	A
Risk:	Moderate	Impact weighting (%):	1%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Under this pillar the Evidence and Learning Facility for South Sudan (ELFSS) provides Monitoring and Evaluation (M&E) services across the HARISS programme, conducting systematic visits to HARISS funded projects to verify the approach taken in terms of quality and results.
[note] All HARISS partners except the South Sudan Humanitarian Fund (SSHF) and the International Committee of the Red Cross (ICRC) are included in ELFSS TPMs

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
ELFSS	Third Party Monitoring	70	A
ELFSS	Key useful synthesis topics identified with stakeholders and synthesised field level report / findings generated	30	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Third party monitoring of HARISS partner programmes (cumulative)	ELFSS	200 Fact Sheets / 205 visits	202 Fact sheets / 205 visits
Number of Synthesis products	ELFSS	8	8

Overall Situation
In May 2020, the contract with IMC Worldwide and their downstream partner, Forcier Consulting, was extended for 12 months until the end of May 2021. Throughout 2020, the primary focus of ELFSS has been on Third Party Monitoring (TPM), as well as some synthesis of learning across from TPM visits. This is essential given the complexity of the HARISS programme as well as the volatile operating environment, which severely limits the FCDO’s ability to directly monitor programme implementation. TPM enables the FCDO to assess and manage risks across the portfolio, as well as identifying opportunities to improve delivery across HARISS partners.

Partner Performance
In 2020, ELFSS has either met or exceeded all its targets in relation to third party monitoring, despite the continuing impact of COVID-19 on programming and field monitoring visits.

To adapt to the restrictions imposed in the wake of COVID-19, ELFSS successfully designed and adopted a remote monitoring methodology for the TPM, with the first two monitoring missions carried out at the end of April to Rubkona and Bor South. Remote TPM follows a similar approach to conventional TPM visits but with two major differences: interviews are carried out by phone, and observations are made by local enumerators working under the supervision of the TPM team. Enumerators are drawn from an existing pool trained by the TPM team during the visits in 2017-2020 or by the wider Forcier South Sudan office to conduct quantitative household surveys. In-person visits resumed in October 2020 after the restrictions had been lifted and these were prioritised due to their robustness in comparison to the remote approach.

The number of completed TPM missions stands at 205 at the end of January 2021 (with 54 TPMs completed during the review period). Although the escalation of COVID-19 impacted fielding between February and April, the ELFSS team exceeded its targets between August and October to further catch up. The TPM visits were selected based on priorities relating to partner and geographic coverage, seasonality, sector, and FCDO requests. For instance, in 2020, FCDO requested that ELFSS monitor GBV activities and COVID-projects implemented under UNICEF and IOM in Wau. This resulted in the ELFSS researchers also presenting their findings to wider Embassy colleagues.  Results from these were used for assurance and reporting, as well as informing quarterly review meetings, particularly agenda items of risk management and any requirement to adjust/flex the approach.

By the end of January, 202 fact sheets were submitted, exceeding the milestone target of 200 (with 58 factsheets submitted during this period). Within this total, seven fact sheets related to BRACE II and no backlog was reported (previously there had been an issue with the number of TPMs fielded for which the associated fact sheet has yet to be produced). The core of the factsheets is verification of partner activities, but inquiries on outcomes were built into the analysis, when feasible, as well as consistently reflecting and reporting on the cross-cutting themes of gender and inclusion, accountability to affected populations, conflict sensitivity, and value for money.

In January 2019, it was agreed that ELFSS would document some of the learning from TPMs in focused synthesis studies. These studies allow for a more in-depth analysis of some of the key trends emerging across the HARISS portfolio, to better capture wider systematic observations, cross-cutting information, findings, and lessons. Following the second contract amendment and the successful submission of all the agreed Synthesis Studies, this work stream ended in May 2020. Nonetheless, it is important that FCDO continues to use the learning generated from the studies to ensure that this is applied to current programming, where feasible.
[note] Topics the Synthesis Studies covered: Revisiting Assumptions of multi-year funding, NNGOs: Obstacles and Impediments, Partnerships and contracts, FAO partner synthesis, Measuring VfM, WFP partner synthesis, Needs Assessments and Beneficiary Targeting

Gender and Inclusion
ELFSS researchers have a good understanding of local dynamics and power within communities, with TPMs regularly assessing progress against issues of gender and social inclusion, whether these are explicit programme objectives or cross-cutting themes.

Risks and Challenges
Following visits, ELFSS debriefs both the FCDO and implementing and downstream partners, to maximise information sharing and allow for nuanced discussions regarding findings (including analysis of local conflict trends and risks), timely actioning of urgent findings, and reflections on priorities. However, there is a risk of a gap in terms of a feedback loop and accountability mechanisms. Whilst ELFSS shares findings and recommendations (which are almost always accepted), there is no way of seeing whether they have been implemented or changes taken place. A future approach could look at options or platforms for feedback that includes the involvement of FCDO and the MEL partner. FCDO should also look to bridge a current gap in how TPM can integrate conflict analysis into data collection and feedback loops to inform programming.

This map shows the geographic spread of ELFSS TPMs until the end of January 2021

Recommendations
- As the contract finished in May 2021, ELFSS and FCDO should undertake an exercise to ensure key lessons are captured from the ELFSS contract, drawing on the synthesis studies and the issues that are consistently captured in the TPMs. In particular, future design should consider a feedback loop mechanism and continued M&E of community perception of humanitarian programming and emphasis of conflict sensitivity risk analysis, including regular conflict trend analysis to inform planning and risk mitigations. FCDO should draw on conflict advisers to support this process and ensure conflict sensitivity analysis and mitigations meet FCDO standards.
- FCDO to revisit its internal monitoring processes now that field visits are more feasible than last year and prioritise partners / projects given the current gap in Third Party Monitoring services.

Pillar	Enabling Environment	Pillar Score	A
Risk:	Moderate	Impact weighting (%):	14%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	Y

Under this pillar HARISS has supported the Logistics Cluster (LC), United Nations Humanitarian Air Service (UNHAS) and enabled the provision of specialist technical advice to key organisations (Standby Partnerships). Also included are the efforts by HARISS partners to strengthen monitoring and community engagement. Activities included:
- Providing logistical support to all humanitarian partners through the cluster system and safe air travel services for the humanitarian community.
- Addressing key gaps in technical expertise within coordination and common service functions.
- Community engagement and monitoring by selected HARISS partners.

The tables below set out partner pillar scores and headline partner results, which have fed into the overall pillar scoring.

Partner	Output Description	Pillar Impact Weight (%)	Output Performance
IOM	Frontline responses in Kodok reinforced through establishment of a Humanitarian Hub in order to strengthen access populations in need in hard-to-reach areas/deep field locations	3%	B
IOM	Humanitarian and development responses are better targeted based on updated needs, intentions and mobility trends of displaced persons	5%	A
FAO	Evidence-based humanitarian response coordination, planning and monitoring	4%	A
FAO	Natural Resource Management and Climate Change Adaptive Agricultural Practices Improved	4%	A
GOAL	RECOVER management is adaptive and informed by community’s voices and feedbacks, and MEAL	2%	A
UNHAS	Efficient provision of common logistics services, including cargo transport, common storage capacity and coordination and information sharing	12%	A
UNHAS	UNHAS services provided to its users as planned, including passenger services, light cargo transportation and emergency relocations/evacuations	12%	A
Standby partners	Support to surge and thematic humanitarian coordination and leadership capacity	4%	A
SSHF	Education / Logistics / Common Services	5%	A
WFP Roads	Trunk Road Improvement and maintenance	38%	A
REACH	Accountability to Affected Populations	1%	A
REACH	Expansion of Population Movement Contextualisation and Exploration of Climatic Driven Movement	1%	B
REACH	Expansion of the Shocks Monitoring Index to Include Climatic Driven Shocks	2%	B
REACH	Integrated Needs Tracking System	3%	A
REACH	Coping Strategies Research - expansion of previous activity (improved Food Security Monitoring Systems)	1%	B
REAH	Nutrition Monitoring and Capacity Support	1%	A
REACH	Needs Analysis Working Group Engagement - Emergency Sectors	1%	A

Headline results	Partner	FCDO Funded Milestone	FCDO Funded Results Achieved
Percentage of priority locations served	WFP UNHAS	50	57
Tonnage of light cargo transported monthly	WFP UNHAS	100	96
Number of passengers transported per month	WFP UNHAS	6,500	3,543
Number of agencies and organisations using humanitarian air services	WFP UNHAS	290	308
Proportion of beneficiaries who know where to complain/provide feedback	GOAL	90%	97.8%
Number of kilometres of critical road sections/choke points rehabilitated	WFP	1,253.9 km	632.3km
Amount of $ in savings to shift from air drop to road transport	WFP	N/A	$18,373,330
Number of quarterly AAP factsheets published	REACH	2	2
Field missions to close the feedback-loop with communities from whom previous qualitative data collection was carried out	REACH	1	2

Overall Situation
Heavy rains, poor road conditions, active armed conflict, restrictions of movements, attacks against humanitarians and assets, and bureaucratic impediments have rendered humanitarian activities severely restricted, or in some cases impossible. Activities that contribute to an enabling environment that optimises operational response and access is therefore essential.

Partner Performance
The majority of funding under this pillar supports the crucial work of WFP. The Logistics Cluster (LC) and UNHAS facilitate the delivery of humanitarian assistance to vulnerable populations in South Sudan by augmenting the logistical capacities of the humanitarian community through the provision of common services (transport and warehousing), logistics information management, coordination, and passenger and light cargo transport. UNHAS also provides medical evacuations and security relocations for the humanitarian community in South Sudan.

Despite multiple challenges faced in 2020, the LC exceeded planned targets and facilitated the transportation of a total of 7465 metric tonnes (MT) of life-saving supplies to 166 locations across South Sudan (15% above initial target). UNHAS supported humanitarian workers with a dedicated Caravan for the COVID-19 response, playing a critical role in providing logistical air support at zero cost to humanitarian partners and South Sudan government through the Ministry of Health. On average each month, UNHAS transported 3,543 passengers. This was lower in comparison to the same period in the previous year, where the average was 6,500 passengers per month. COVID-19 restrictions have significantly decreased the overall UNHAS passengers performance in 2020.

The implementation of road rehabilitation and spot repair projects is essential for WFP and other humanitarian aid providers. The road repairs and subsequent road maintenance activities are expected to significantly reduce the transportation costs, decrease time for delivery of aid and commercial goods and increase farmers and other community members’ access to agricultural inputs, markets and social
Infrastructure.

The main objective of WFP’s chokepoint repairs and maintenance activity is to ensure that critical supply routes remain open for transport of food assistance items during the rainy season. The interventions funded under the two FCDO grants were aimed at ensuring serviceability of key supply routes across the country in the year 2020. The rehabilitation of choke points along the Yirol – Rumbek, Torit-Kapoeta, Maban-Jamam-Palouch road, Kapoeta-Nadapal road, Wunrok-Abyei road and Mvollo-Rumbek road enabled WFP to use these key supply routes throughout the 2020 rainy season. Results of the 2020 interventions show that WFP contracted commercial trucks have been able to deliver food commodities via the routes despite the heavy rains. In addition, the works executed on Bor-Mabior-Ayod road, Bentiu-Leer-Adhok road and Abyiemnohm-Mayom road allowed WFP to use these supply routes longer into the rain season. Being located predominantly in flood plains, these supply routes become inaccessible with first rains that usually occurs in April-May every other year. With the 2020 FCDO supported intervention, the routes remained open until early August 2020 before the flooding made it impossible to continue with the rehabilitation works thus making the roads impassable.

Throughout 2020, REACH has been successful in using products and activities to influence the response, including but not limited to the use of COVID-19 adapted programming to influence which counties should receive priority COVID-19 prevention response, significant advocacy for the inclusion of AAP as a priority in the HNO and HRP, and leveraging REACH’s role in the Needs Analysis Working Group (NAWG) to advocate for sufficient response scale up in high priority counties like Pibor.

The further refining of the Integrated Needs Tracking Systems (INT) and Shocks Monitoring Index (SMI) have allowed for regular monitoring of the relative risk of increasing needs across FSL, WASH, Health, Nutrition and Protection. REACH has particularly contributed to Food Security and Livelihoods as well as Nutrition through significant involvement in the IPC analysis, including sitting on the IPC Technical Working Group and having analysts within the county and state level analysis. As a result of the emergence of COVID-19 and a corresponding shift in priorities, several activities were either adapted or delayed, meaning some results will not be achieved until 2021. For instance, integration of the Population Movement Baseline (PMB) database with the Shocks Monitoring Index and Coping Strategies Research.

FCDO’s support to Standby Partnerships increased in 2020 to provide specialist support to UN agencies during humanitarian emergencies. For relatively small costs, this is an effective mechanism for targeted support within the wider humanitarian system. FCDO supported a number of positions, including WASH (UNICEF) and protection/GBV coordination (UNHCR), as well positions to support the COVID-19 response, including state level public health coordination (WHO) and information management (OCHA). FCDO has also supported an HSOT COVID-19 preparedness advisor within the British Embassy, who has provided technical inputs into the national preparedness and response strategy.

Gender and Inclusion
In all activities, REACH aims for a representative understanding of the needs of men, women and youth as well as persons with disabilities, where feasible. As part of this, REACH collects gender disaggregated data through the AoK and during assessments as far as is possible given the limitations of the methodology being used, including in relation to critical protection issues such as safety and security, child protection, sexual and gender-based violence. Within several of REACH’s products, data collected will be disaggregated by women/men/girls/boys to enable a better understanding of the difference in humanitarian needs for these groups in the response.

Risks and Challenges
The sheer breadth and depth of needs in South Sudan requires a strong evidence base that can be used to prioritize locations requiring emergency response. The triggers and mechanisms used for prioritization are not well defined or agreed between various response actors. The data can also be highly sensitive and some processes, particularly the IPC, can become highly political. The IPC in 2020 failed to reach a consensus between various actors and the Government, which resulted in multiple “final” versions being circulated and delays in releasing and importantly, operationalising the data.

Recommendation
- The Logistics Cluster should continue to work with partners to improve prepositioning of stocks during the dry season and to further capitalise on efforts to use cheaper road and river transport, reducing the reliance on air freight.
- The UK should develop a strategic approach to the Standby partnership mechanism, working with UN partners to identify and address capability gaps crucial to response delivery

## D: VALUE FOR MONEY
[note] The new FCDO Annual Review template (April 2021) does not include a standalone VfM section, rather VfM is to be assessed against each output. However, given the vast number of outputs in this review, this was not possible

Assess VfM compared to the proposition in the Business Case, based on the past year
The original HARISS business case identified South Sudan as one of the most fragile, logistically complex high risk operating environments in the world, which also makes it one of the most expensive to deliver humanitarian assistance. In 2020, this remained the case as sub-national and intercommunal violence continued to deteriorate, compounding humanitarian needs. A key element of HARISS’ approach to value for money, namely the shift from immediate needs to building resilience to shocks, has therefore been extremely limited.
[note] The original Business Case identified the main cost drivers as the cost of supplies/inputs, transportation, bureaucratic impediments, exchange rate volatility, security and staffing which converge to make operating costs for humanitarian agencies and the delivery of programmes extremely high

The impact of the COVID-19 pandemic has been significant, as demonstrated throughout this review. Mitigation measures in South Sudan have put pressure on markets and the movement of goods, leading to high commodity prices and the unavailability of essential supplies. For instance, in 2020, the cost of a standard food basket increased by 42%. In response, partners have adjusted activities, which has undoubtedly had implications for the overall VfM of the programme.

The worsening economic crisis has involved major exchange rate volatility and divergence between the “official” rate and the black market rate. By November the South Sudanese Pound (SSP) reached a record low in value against the US dollar. This was a key challenge for several partners, creating both fiduciary risks and VfM concerns, particularly for those involved with cash transfers. If partners were unable to negotiate a better exchange rate for cash transfer payments, then the real value of the cash transfer to the household was affected. Other issues reported include the higher cost of some supplies and the availability of casual labour. To address this, some partners have negotiated a better exchange rate with financial services providers, but this has not been universally taken forward.
[note] The black market rate is the one that governs everyday transactions for South Sudanese citizens and is the value used to set prices of commodities. Implementing partners being required to use the official rate when exchanging dollars would have far less purchasing power than the value of the black market rate

Meanwhile, the impact of the pandemic on the UK economy also resulted in the FCDO carrying out a review of the ODA budget in the summer of 2020, which led some HARISS partners to make in-year savings to programmes. This was on top of an already uncertain financial operating environment, which has seen the budget reduce compared to previous years. A key assumption of the original Business Case was the provision of multi-year funding which would allow partners to plan expenditure in line with better VfM practice. However, the current approach of annual budget allocations means that partners are often absorbing large disbursements within a limited timeframe which can only reduce purchasing power and limit their ability to plan effectively and realise efficiencies.

All partners report regularly on VfM in their programmes and most partners have developed VfM matrices which are used to identify and drive VfM across the HARISS programme. Despite these challenges noted above, there has still been good evidence across the portfolio of partners achieving VfM.

VfM measure	Approaches adopted
Economy	The continued shift in emergency food distribution from expensive airdrops to delivery by road and river (WFP). An average of $1500/MT is saved. / Increased accessing of Logs Cluster resources and UNHAS flights by agencies to keep transportation costs low, where possible (ICRC, Medair). / Pre-positioning of supplies due to seasonal access issues caused by flooding (WFP, IOM, UNICEF nutrition, FAO). WFP prepositioned 58 percent of total food commodities, slightly less than in 2019, prior to the initial COVID-19 travel restrictions and the rainy season in the early months of 2020. / Some agencies have carried out competitive tenders in local and regional markets and entered into longer-term agreements, to reduce procurement costs.
Efficiency	Efforts to recruit and train national staff based on a rigorous results-based framework. This decreases reliance on international staff, response time and utilises fewer resources to reach outputs. / Increased use of solar power to save fuel consumption costs in generators (IMC) / Vaccinating small ruminants continued to be the most cost-efficient livestock livelihood saving intervention compared to other interventions, such as livestock treatment (FAO, ICRC)
Effectiveness	Integrated programmes offer the potential to significantly improve the achievement of outcomes. E.g. linkages between SAM and MAM programming alongside health strengthen the effectiveness of efforts to treat malnutrition (UNICEF), multi-sectoral ERT responses (Medair) / Through WFP’s SCOPE CODA system, frontline workers can record information; track the nutrition and health status, of a young child or a pregnant woman; identify when someone has recovered; and indicate whether the treatment has been successful. / Training provided to beneficiaries who have adopted new practices and behaviours as a result (GOAL) / Inclusive discussions with the inter-cluster cluster coordination group (ICCG), drawing from existing data sources such as the IPC and intersectoral severity of needs, to ensure that funds are allocated to the most vulnerable people. The SSHF allocation process ensures that all allocations and determination of priority locations is based on needs and needs alone.
Equity	HI’s knowledge of inclusive programming has benefitted HARISS partners working to improve standards and compliance. VfM is improved through shared learning between HARISS partners and tailored technical support with developed Action Plans. / Gender and inclusion are reported during ELFSS TPM. More broadly, through the learning and recommendations generated, this informs programme quality and key lesson learning.

Ongoing VfM of the programme
The challenges in 2020 highlight the importance of VfM, particularly in the context of reduced budgets and increasing humanitarian needs. The 2019 Annual Review recommended that the FCDO, working with HARISS partners, should review VfM tools (in particular VfM matrices) to enable VfM reporting to focus more on effectiveness and equity as well as economy and efficiency. This followed the ELFSS Synthesis review of how VfM was approached across HARISS partners. Due to resourcing gaps, this work has not progressed as anticipated. This work should therefore be reprioritised in 2021.

Recommendation
- FCDO to consider the impact of budget cuts on programming, including VfM. To strengthen analysis, FCDO, working with HARISS partners, should review VfM tools (in particular VfM matrices) to enable better reporting on effectiveness and equity.
- Exchange rate volatility has always been identified as one of the key risks which should be monitored and addressed across the HARISS programme. The FCDO should work with partners to advocate for a more coordinated approach through the Cash Working Group.

E: RISK
Overall risk rating: Major

Top Risks
The programme faces a multitude of serious risks rooted in the innate challenges of delivering humanitarian aid in a highly insecure context vulnerable to numerous shocks. Some of the particular risks the programme encountered in 2020 were:

- The continued deterioration in the context and increasing humanitarian needs meaning the UK and partners are unable to respond at the scale required, resulting in increased mortality across the country
- The impact of COVID-19 on partners ability to operate and on the capacity of FCDO staff to monitor programmes directly
- Insecurity leading partners either being at harm or having to suspend activities and therefore not reaching beneficiaries

Overview of risk management
Risk is managed through an overall programme risk matrix which articulates HARISS programme risk appetite, including the appetite for different risk categories. This is updated on a quarterly basis, using information from partners' quarterly reports, risk matrices, delivery chain risk mapping and meetings. Risk is discussed regularly at team meetings, particularly in respect to changes in context. Any major increase in risk is identified, discussed with the relevant partner(s) and escalated to the Head of Office and HQ if needed. For instance, in 2020 the widening of the gap between official and market rates posed a significant fiduciary risk and VfM concern, particularly for those partners implementing cash transfer programmes. As a result, the FCDO undertook a stocktake across the HARISS programme to inform our understanding and to determine what mitigation actions were required (see more in the value for money section above).

As referred to above, all HARISS partners are required to update their risk matrices on a quarterly basis and submit them with the narrative reports. These outline top delivery chain risks, mitigation measures and risk owners. They are analysed and discussed during partner meetings. These are then reported to the Quarterly Programme Board and incorporated into office-wide risk assessments, allowing the office to track trends and share best practice.

As with all programming, COVID-19 represented a major challenge to programme delivery as staff drawdowns, international travel restrictions and domestic lockdowns hampered programme delivery and monitoring capacity. In some cases, programming had to be paused or delayed but on the whole partners adapted to maintain delivery and adapt to operating within a COVID-19 context. Restrictions on movements outside of Juba heavily reduced UK staff ability to directly monitor programmes in 2020. However, the TPM contract continued to function and provide effective oversight of the programme that is used to engage with partners on programme delivery, quality, and assurance.

The looting of humanitarian assets continues to be an issue in South Sudan; this is the most common incident reported by HARISS partners. This is often linked to inter-communal violence and presents a risk to pre-positioned supplies in particular. Partners continue to put in place reasonable and context-appropriate mitigation measures such as guarding commodities, transporting commodities in convoys, and tracking commodity movements. In addition, humanitarian actors coordinate with UNMISS to prevent or mitigate this, and there is a sliding scale of responses up to and including the suspension of operations, and then a series of conditions to be met before resumption, including accountability, return of goods/compensation where feasible, and assurances for the future. More broadly the UK’s approach to access and protection emphasises the obligation of the government to provide a conducive environment, including the protection of assets, and our diplomatic efforts continue to push this at national and state level.

The operating environment also presents high safeguarding risks due to imbalances of power and high levels of poverty, amongst others, which have been exacerbated by the COVID-19 outbreak. Partners have reported that they regularly update risk assessments, provide training to staff, and review their referral pathways. Nonetheless only a handful of cases have been reported to FCDO despite efforts to combat the stigma of reporting cases and accessing services. A key finding across these cases has been the importance of ensuring that investigation procedures are survivor centred. FCDO will challenge partners on this, as well as other areas, when a refresh of Due Diligence Assessments is conducted in 2021.

In an already extremely difficult access context, the growing issue of interference and violence towards aid agencies has presented significant risk in 2020. The reasons for this are complex but are exacerbated in the dire economic situation in South Sudan and the lack of employment opportunities outside of the aid sector.

Renk
A notable example in Renk in late 2019 resulted in the HCT (with UK support) agreeing to suspend operations in the face of significant interference from local groups labelling themselves as ‘youth’. The UK coordinated closely with affected implementing partners (particularly Medair) and across the humanitarian system to ensure a coordinated response grounded in humanitarian principles to avoid setting a dangerous precedent across operations in South Sudan. This has been followed up with an agreed donor principles paper on how to respond to future incidents. Unfortunately, numerous incidents have incurred since and responding to increased insecurity in the operating environment will be a key priority for the UK and the humanitarian community in South Sudan.

Recommendations
- HARISS continues to operate at a major risk level with regular escalation of risks that challenge agreed tolerance levels
- The UK continues to coordinate with donors and the wider humanitarian community to collectively respond to issues that affect programme delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and FCDO, notably on commercial, and financial issues
This Annual Review was led by the HARISS Senior Programme Manager, in collaboration with Humanitarian Advisers, Programme Managers and Programme Officers within the Humanitarian and Livelihoods Team. Cross-cutting advisers from the British Embassy Juba also input to the process. Due to the complexity of HARISS as a programme, the standard FCDO annual review process has been adapted to reflect its portfolio nature. The performance of each HARISS partner was scored individually against their log frame and technically reviewed by FCDO advisers. These scores were then grouped by sector and aggregated into pillars (as per section C).

Throughout the year, FCDO receives quarterly reports from partners, including narrative reports, financial reports, VfM matrices, log frames and delivery chain risk maps, to ensure that the programme is on track to deliver as expected. Any issues are then followed up during quarterly partner meetings. In 2020, reports have been submitted on time and have been of a good quality. The FCDO also uses findings and recommendations generated from TPM as an extra layer of assurance. Given the COVID-19 restrictions, the FCDO only undertook field trips at the start of 2020 to Malakal, Yambio, Yei and Wau.

Financial performance
HARISS was originally designed as a five-year, £443m programme. In 2018, the value of the programme was increased by £122m and then again in 2019 by a further £122m. In February 2021, a third cost extension of £100m was approved, taking the overall programme value to £787m.

The chart above depicts the FCDO’s internal financial management performance, in particular the performance of forecasting across 2019 and 2020. It compares the actual spend in a quarter to the forecast entered at the beginning of the quarter. For the most part spend is higher and this reflects the routine budget uplifts that HARISS has received, either from the Crisis Reserve or divisional underspends. The starkest example is Q1 of 2020 (Jan-Mar) where expenditure increased by £18m. The other key highlight is the lower than anticipated expenditure in the period July to September 2020 and this represents the savings that were required as part of the COVID-19 re-prioritisation work.

The FCDO has continued to improve its approach to financial management, streamlining processes and improving the quality of data recorded. It is these improvements that allow the programme to scale up, as it did in January to March 2020, while retaining control of the expenditure and providing the necessary assurance that all FCDO financial management rules have been followed. There was also greater scrutiny of partner financial reports and statements, with good processes initiated to receive and comment on partner financial reports.

The impact of COVID-19 was challenging for partners and meant that spending to planned budgets was unlikely. As a result, there were a number of budget realignments to maximise deliverables in a period of uncertainty. IMC, REACH and HI communicated these issues in advance, meaning that adjustments could be made accordingly and the FCDO could accurately monitor spend. Medair and GOAL performed well overall, providing clear explanations for any variance and the quality of FAO’s financial reporting improved. One payment to IOM had to be delayed due to a high underspend in Q2, however the full year target was met by the end of 2020. There was continued difficulty with UNICEF’s financial reporting, both in format and accuracy but also issues with understanding and communication of variances. Engagement increased throughout 2020 and this will continue to be closely monitored in 2021. Some multilateral partners (WFP, ICRC) are often bound by central agreements which support limited financial reporting at post.

Annual audited accounts (or copies of accounts) for 2020 have been received for all HARISS partners and in all cases were certified to be true, fair, and unqualified by independent auditors.

Asset monitoring and control
All NGO partners maintain asset registers and have policies in place for asset management. For UN organisations (including SSHF, as funds are channelled through UNDP) and ICRC, assets are managed in accordance with UN/ICRC policies and procedures. Due to COVID-19, the FCDO has been unable to undertake periodic spot-checks, though assets have continued to be reported on by partners.
[note] This arrangement changed at the end of 2019 as OCHA took over Managing Agent responsibilities from the UNDP Multi-Partner Trust Fund
[note] The looting of humanitarian supplies, including FCDO assets, is a significant risk for the FCDO. See more on mitigation measures under the risk section

Delivery against the planned timeframe
COVID-19 has presented many challenges throughout 2020, which has led partners to adapt programming accordingly. As such many timeframes for delivery have changed. The majority of partners communicated issues in advance, which mitigated the impact of this as much as possible. Where there have been concerns about the timely delivery or broader performance of HARISS-funded projects, FCDO has taken a responsible approach to seeking solutions and engaging with partners.