 Annual Review Template

Title: Global Environment Facility (GEF) Seventh Replenishment
Programme Value £ (full life): £250m		Review date: 12 July 2021
Programme Code: / 300057	AMP start date: July 2018	AMP end date: June 2022

Summary of Programme Performance
Year	2019	2020	2021
Overall Output Score	A	A	A
Risk Rating	Minor	Minor	minor

DevTracker Link to Business Case:	37917779
DevTracker Link to results framework:	52177823

A. SUMMARY AND OVERVIEW

Description of programme

The Global Environment Facility (GEF) was set up in 1991 to provide funding to developing countries to address global environmental challenges, including climate change, biodiversity loss, land degradation, marine degradation, and chemicals pollution.  The GEF provides funding in support of five major international environmental conventions, which are the Convention on Biological Diversity, United Nations Framework Convention on Climate Change, Stockholm Convention on Persistent Organic Pollutants, UN Convention to Combat Desertification, and Minamata Convention on Mercury.  The work the UK funds and catalyses through GEF underpins the UK position in the international climate, biodiversity and other environmental negotiations and agreements.  GEF funding also supports UK Government priorities including the illegal wildlife trade and marine protection and contributes to the achievement of the Sustainable Development Goals (SDGs).

Since its inception in 1991, the GEF has supported management of more than 3,860 protected areas covering 960 million hectares (an area larger than Brazil), 1,035 climate change mitigation projects contributing to over 9.4 billion tonnes of greenhouse gas emission reductions, sustainable management of 61 of the world’s major river basins and provided $230m to the Global Wildlife Programme to tackle the illegal wildlife trade. Key results in this funding period to date include that the GEF7 target of a co-financing ratio of seven dollars mobilised for every “GEF dollar” spent has been surpassed with eight dollars raised for every dollar provided by the UK and other donors, as of June 2021 raising over $22bn of expected co-finance. This funding in turn will support the creation and improved management of more than 101.4m hectares of protected areas; and mitigate 1406.2m metric tons of CO2e tonnes of greenhouse gases (GHGs); and an estimated 164.4 million (m) people (79.8m women) will benefit from these investments.

The GEF provides grants and other support to developing countries for projects and programmes to address global environmental problems.  The GEF works with developing countries, and a set of 18 accredited agencies (including multilateral development banks (MDBs), UN agencies and environmental NGOs), to develop and implement projects and programmes. The GEF is governed by a balanced board (GEF Council) of developed and developing country representatives; its work is co-ordinated by a Secretariat and the World Bank is Trustee.  The UK has its own constituency seat on the board, represented by FCDO.  The projects and programmes funded by the GEF are developed in accordance with a set of Programming and Policy Directions set at the start of each four-year replenishment period.

Summary supporting narrative for the overall score in this review

This annual review takes place in the context of, and takes account of, the second year of the covid-19 pandemic.  GEF continues to respond well to the crisis, quickly moving from its developed short-term response to medium and long-term steps to respond to the pandemic.  GEF has also adopted new ways of working to keep international business going with the GEF Council meetings and the next replenishment being held virtually.

This Annual Review assesses the third year of programming under the 7th replenishment of GEF.  The programme is performing well according to the programming and policy directions set at the start of the current replenishment.  Through the approval of a work-programme at the June 2021-Council meetings, the three-quarters-way point of the 4-year replenishment period, 81% of overall resource programming under GEF-7 has now been approved.  The funds programmed, as captured under output 1 below, are delivering the expected results anticipated at this stage of the replenishment cycle, and against some indicators already exceeding the expected results for the entire replenishment period.

Twenty percent of the total UK pledged contribution is conditional on achievement of agreed targets for performance against agreed policy reforms.  The GEF has made good progress in these policy areas which include improved resource allocation; optimising the use of GEF resources in different countries; results reporting; private sector engagement; increased operational efficiency and transparency; improved management of data and information; and gender equality and women’s empowerment.  As a result of achieving these targets the GEF received the full amount committed by the UK for this year.

Overall output score and description

Overall output score is A with the following individual output scores:

Output 1 - Global environmental benefits to be delivered through approved GEF7 projects and programmes:  A.

Output 2 - GEF7 policy recommendations delivered successfully: A.

Major lessons and recommendations for the year ahead

- GEF has adapted well to the current covid-19 pandemic, both by ensuring programming policies enable projects to move forward and using virtual engagement for governance and engagement with stakeholders.
- The Pandemic will also shape the next replenishment of the GEF – GEF8 – in terms of the types of activities and programmes supported to enable a global green recovery.
- Two sets of events will shape the year ahead: The Conference of Parties (COPs) of a number of conventions for which GEF is the financing mechanism, and; the negotiations leading up to the next replenishment of GEF (GEF8).
- With respect to the COPs, the climate (COP26), and biodiversity (COP15) are particularly significant, where agreements could shape the financing for climate and biodiversity for years to come, with GEF being a key actor. As such it will be important to ensure future GEF work responds appropriately to the outcome of those meetings.
- With the negotiations for the next replenishment of GEF already started, the coming and final year of GEF7 will be forward looking. The measurement and achievement of results under GEF7 will determine the targets and measurement of results under GEF8. The evaluation by GEF’s Independent Evaluation Office (IEO) of GEF7 will be pivotal in determining priorities and policies under GEF8 and should provide a key source of evidence for future engagement by the UK with GEF.
- The hard-won progress under GEF7 on the private sector, with the approval in the last year of the private sector engagement strategy, will need to be built on under GEF8 to continue the forward momentum.

 B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Summary of the theory of change
The theory of change is built around the contribution the GEF makes in supporting sustainable development and reducing the detrimental impact of climate change and environmental degradation on the poor because poorer people and poorer countries are especially vulnerable to environmental degradation because they rely most heavily on natural resources but have the lowest capacity to influence political processes and decision making at all levels.  In summary, the assumptions made in the business case and theory of change are that an adequately resourced GEF, which is managed effectively, through delivery of high impact projects will deliver sustained global environmental benefits.  Given the poorest people and the poorest countries in the world are the most reliant on the environment for their incomes and livelihoods, delivering these global environmental benefits contributes to delivering the Sustainable Development Goals, particularly those related to the environment: SDG13 (climate action) SDG14 (life below water), SDG15 (life on land). GEF’s role in this context is to provide the leadership in demonstrating the practical actions to tackle environmental degradation.

No major changes have been made to the GEF’s theory of change in the past year.  However, like all programmes, GEF has been affected by covid-19.  The UK continues to keep a close eye on this.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

GEF7 programming remains highly relevant to addressing the overall impact for the programme: The reduction or reversal of trends in environmental degradation at a global scale. However, GEF resourcing itself only provides a small contribution to the overall financing in the hundreds of billions of dollars required to have a major impact on the tide of global environmental degradation. The challenge remains huge, and any progress made is fragile, and potentially undone by events such as the covid-19 pandemic. The GEF does however play an important catalytic role and through the integrated Impact Programmes, is delivering a more transformative shift by addressing the systems underlying biodiversity loss and climate change.

GEF responded quickly to the covid-19 pandemic: A Response Task Force met throughout 2020 to assess the pandemic and implications for environmental programming; In November 2020 it published a policy paper identifying future risks linked to emerging infectious diseases and outlining possible investments that could mitigate them; GEF has prioritised projects that help countries respond to urgent environmental needs, and those that enable countries to plan a green, blue, clean, and resilient recovery from the pandemic; and have amended programming policies to enable projects to move forward where there is pandemic-related disruptions.

While the covid-19 pandemic continues to require new business practices and adapt to more virtual interactions, the GEF partnership has mostly found ways to get back to business and continue the implementation of existing projects and engage with the proper stakeholders and country agencies to submit pipeline of projects. GEF internal practices in project review now include a covid-19 screen that assesses the risks and opportunities associated with each project being submitted for consideration by the GEF. Efforts have been made to both alleviate the negative impacts in local communities and contribute to post pandemic recovery efforts.

There has been a major progress on GEF’s engagement with the private sector, with the approval of the Private Sector Strategy (further detail at Output 2). The private sector is an important element of the GEF7 replenishment, and key to delivering transformative change. GEF stakeholders have worked together with the GEF Secretariat to deliver a private sector strategy that now has the support from all sides of the GEF partnership.

Progress towards impact is measured through the GEF’s Independent Evaluation Office’s Overall Performance Studies (OPSs). OPSs are comprehensive evaluations that assess the performance, institutional effectiveness, and impact of GEF. The Overall Performance Study for GEF7 (OPS7) is in the process of being completed, drawing on the evidence from 34 completed evaluations, or evaluations in the process of being completed. The UK welcomes the focus of OPS7 on assessing GEF’s progress towards greater integration, innovation, scaling up, and achieving impacts with greater efficiency.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The GEF remains critical in providing the finance to achieving the sustainable development goals, particularly those related to climate and environment. Alongside the trade in wildlife, and markets that sell it, the emergence of coronaviruses can be linked to habitat destruction and human encroachment into wildlife habitats. This arises from agricultural expansion or other development purposes which bring people and their livestock into closer proximity to wildlife, creating opportunities for the emergence of novel infections in human populations.  Transformative GEF programming promotes food security through sustainable agriculture, combats illegal wildlife trade, reduces poverty, and tackles environmental degradation.  All are critical in reducing the risk of future pandemics but also addressing drivers and pressures on the environment that may occur as a result of the economic impact of covid-19.  The above points towards the importance of continuing to support the GEF in promoting transformational change

C. DETAILED OUTPUT SCORING

Output Title	Global environmental benefits to be delivered through approved GEF7 projects and programmes
Output number per LF		1	Output Score	A
Impact weighting (%):		70	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / to June 2021	Expected results of projects and programmes approved at June 2020	Expected results of projects and programmes approved at June 2021
1.1 Terrestrial protected areas created or under improved management for conservation and sustainable use (million hectares)	150	88.2	101.4
1.2 Marine protected areas created or under improved management for conservation and sustainable use (mha)	6	1,276.3	1,369.9
1.3 Area of landscapes restored (mha)	4,5	6.6	7.9
1.4 Area of landscapes under improved practices (mha; excl. protected areas)	240	107.4	163.3
1.5 Area of marine habitat under improved practices (mha; excl. protected areas)	21	6.6	93.5
1.6 Greenhouse gas emissions mitigated (million metric tons of CO2e)	1100	1,157.9	1,406.2
1.7 Number of shared water ecosystems (fresh or marine) under new or improved cooperative management	24	31	49
1.8 Globally over-exploited marine fisheries moved to more sustainable levels (thousand metric tons) (Percent of fisheries, by volume)	2,625	1,657	2,316.8
1.9 Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (thousand metric tons of toxic chemicals reduced)	75	34.9	38
1.10 Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent [gTEQ])	975	1,479.6	2,846
1.11 Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment	New indicator	15.2 million / (50% women)	164.4 / (49% women)
[note] The UK’s logframe includes milestones for each of the 4 years of GEF 7, which have been calculated upon an assumption that there is a linear increase in results to the 4-year GEF target. Given the time to develop concepts over the replenishment period in some focal areas in particular the approval of projects and their expected results does not always follow such a linear path.
[note] The results for GEF7 are expected results from the sum of projects approved for funding from financing secured under the GEF7 replenishment. Actual achieved results following implementation may differ.
[note] gef-7-corporate-scorecard-june-2021

Briefly describe the output’s activities and provide supporting narrative for the score.

The GEF7 results framework is linked to the GEF7 programming strategy through 11 agreed core indicators. Output 1 of the UK’s logframe for GEF7 is taken from these agreed indicators and targets. The framework allows for the comprehensive monitoring of the results expected by GEF projects and programmes, including multiple benefits across focal areas as well as tracking data on beneficiaries disaggregated by gender.

By June 2021, overall GEF7 programming has allocated 81% at the 75% timeline mark in GEF-7 of the overall GEF7 resource allocation of $3,895m. Allocation of resources across focal areas is relatively even, with programming to date varying from International Waters at 79.8% of allocated resources to Land Degradation and Biodiversity at 88.1% and 81.5% respectively.  Chemicals and Waste and Climate Change fall within these levels of programming at 76.3% and 74.1% respectively.

The above programme of GEF7 finance is translating into increases across GEF core indicators, and in some cases (1.2, 1.3, 1.5, 1.7, 1.10) already exceeding the final targets for GEF7.  However, 1.2 is a significant outlier due to one project endorsed under GEF7 aiming to conserve a significant area (3.5%) of the Ocean.

Indicators 1.1, 1.4, 1.9 have not met the UK’s annual milestones based on expected results presented at concept note approval. However, as projects and their results are refined for final endorsement previous evidence suggests that the results will be closer to the expected targets for the whole of the GEF7 period. At this third year of the replenishment there remains significant and relatively even programming of resources across the focal areas. This has translated into good progress against the 11 core indicators. As such this output 1 has been given an aggregate score of A within this annual review.

VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The business case highlights the importance of effectiveness (spending wisely) i.e., ensuring the chosen outputs of an intervention are those most likely to result in the desired outcomes. The new GEF results framework of eleven core indicators, covering the five focal areas for GEF, provides an ability for GEF to capture, monitor, aggregate and report on results across the different types of intervention financed by GEF. This is most relevant to Impact Programmes, which seek to provide multiple benefits across different focal areas. As noted above, the GEF7 allocation for impact programmes has now been almost fully programmed. With the high percentage of core indicator results delivered through such programmes, and with the performance against these indicators broadly on track, GEF can be seen to be delivering value-for-money against the results for this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The 2020 Annual Review recommended monitoring the impact that covid-19 may have in meeting the final GEF7 targets and therefore continuing to track performance against results targets for all core indicators, and resource allocations that have been agreed across the GEF7 portfolio. As demonstrated above the GEF expected results have not suffered during the last year.

Over the coming year, the last year of programming under GEF7, the UK will need to assess progress against the agreed core indicator targets for the whole of the GEF7 period and ensure GEF provides clear reasons behind variations from the targets. Where appropriate it will be important to update indicators, and methodologies in advance of setting targets under the subsequent replenishment, GEF8 (2022-26).

C. DETAILED OUTPUT SCORING

Output Title	GEF7 policy recommendations delivered successfully
Output number:		2	Output Score:	A
Impact weighting (%:		30	Weighting revised since last AR?	N

Indicator(s)	Milestones to June 2021	Progress at June 2020	Progress at June 2021
2.1 Resource allocation (System for Transparent Allocation of Resources)	Council agreed updated STAR being implemented. / Secretariat reporting to Council on the programming of funds and expected global environmental benefits across core indicators	Achieved. The latest corporate scorecard from June 2020 provides the GEF-7 utilisation rates against STAR, of funds per focal area, by region, for the group of countries categorised as LDCs, and for the group of countries categorised as Small Island Developing States (SIDS)	Achieved / The latest scorecard provides the GEF-7 utilisation rates of funds per focal area, by region, for the group of countries categorised as LDCs, and for the group of countries categorised as SIDS. / The Least Developed Countries and Small Islands / Developing States have respectively reached 92% and 77% of / their respective STAR allocation in GEF-7. Nearly three quarters / of countries made use of the flexibility provided in the use of / resources.
2.2 Optimising the use of GEF resources in different countries	Overall GEF portfolio to reach at least 7:1 Co-Financing ratio to GEF Project Financing. / For the portfolio of projects and programmes approved in Upper-Middle Income Countries and High-Income Countries that are not SIDS or LDCs to reach a ratio of Investment Mobilised to GEF financing of at least 5:1	Achieved. 8.3:1 Co-financing. / Investment Mobilised 6.0:1	Achieved. Co-financing 8.2:1. / Investment Mobilised in Upper-middle- and High-income countries 5.8:1.
2.3 Results	Council agreed measures on results and sustainability being implemented. / Concrete measures undertaken in the design, monitoring and evaluation of projects and programmes that would allow for increased sustainability, including financial sustainability	Achieved. In the last year, the Secretariat has engaged in significant consultations on sustainability (or “durability” GEF/C.57/08) across the GEF partnership. These engagements have included discussions with Agencies, with countries, with the Scientific and Technical Panel (STAP), and with the GEF Council itself through two Council papers.	Achieved Following last year’s significant consultations on sustainability/durability across the GEF partnership outlining a series of actionable design and implementation elements on durability, this year GEF is reporting for the first time on results at the sub-indicator level. It also reveals that five of the core indicator targets set for GEF-7 have already / been met and shows good progress in support of marine biodiversity and fisheries.
2.4 Private sector engagement	Council agreed strategy on private sector engagement being implemented. / Reporting on private sector co-financing / Percentage of GEF funding through NGIs	Partially Achieved At the 58th Council Meeting June 2020, The Council requested the GEF Secretariat to prepare an Implementation Plan to be presented at the 59th Council Meeting alongside a revised Private Sector Engagement Strategy. To support this work, a Working Group of interested Council Members and the GEF Secretariat has been created.	Achieved There has been significant progress since last year’s annual review. The Private Sector Engagement Strategy (GEF/C.59/07/Rev.01) was approved at the 59th Council Meeting in December 2020. Council Members also noted the accompanying Implementation Plan (GEF/C.59/Inf.18) which was submitted as an information document. / As part of the actions documented in the Implementation Plan, the GEF Agency Private Sector Working Group agreed a plan to develop private sector knowledge resources and management tools. / As of December 2020, the share of private sector of the total indicative co-financing mobilised in GEF-7 is 18%. / As of December 2020, US$ 109.5 million (80%) of the US$ 136 million non-grant instrument (NGI) Programme was programmed, with the remaining resources approved at the June 2021 Council.
2.5 Operational efficiency and transparency	Council agreed measures to enhance operational efficiency and transparency being implemented.	Achieved. The new set of policy measures came into effect in March 2019.	Achieved the GEF Monitoring Report 2020 provided progress data on efficiency metrics, highlighting the percentage of projects reaching endorsement in FY20 within 8 months of Council approval of the Project Identification Form (PIF) and progress in financial closure of projects that have already reached their Terminal Evaluation. / Due to covid-19, the Secretariat invoked provisions in the GEF Cancellation Policy that allow for a cancellation deadline extension, extending deadlines for a total of six months. This provided Agencies and recipient countries with the extra time needed to prepare quality projects.
2.6 Improved management of data and information	Continued implementation of the improved information management system. / Regular reporting to IATI (International Transparency Initiative) registry	Achieved. The GEF became an IATI publisher in June 2019 with its first submission of project level data to the IATI registry	Achieved. While the GEF’s new information management system – GEF portal – continues to go through improvements and data transfer, the Secretariat is working to implement systemised reporting to IATI registry on a regular basis
2.7 Gender equality and women’s empowerment	Council agreed measures in GEF7 gender strategy being implemented according to agreed timetable. Annual updates by the Secretariat on the progress on activities outlined in the Strategy, as well as on the results framework. / Percentage of projects that have conducted a gender analysis, plan to carry out gender-responsive activities / Percentage of projects that include sex-disaggregated and gender-sensitive indicators / Percentage of female beneficiaries--	Achieved. The GEF-7 corporate scorecard from June 2020, provides information on quality at entry of GEF-7 approved projects and covers the indicators outlined in the GEF-7 Results Framework on Gender Equality and Women’s Empowerment: / 99% of projects that considered gender issues at the initial project design. / 87% of projects expecting to develop gender sensitive indicators / 93% of projects tagged to close gender gaps. 50.4% of the expected beneficiaries in these projects are women.	Achieved: The GEF-7 corporate scorecard from June 2021 provides information on quality at entry of GEF-7 approved projects and covers the indicators outlined in the GEF-7 Results Framework on Gender Equality and Women’s Empowerment: / 100% of projects that considered gender issues at the initial project design. / 91% of projects expecting to develop gender sensitive indicators. / 95% of projects tagged to close gender gaps. In addition, 49% of the expected beneficiaries in these projects are women.
[note] gef-7-corporate-scorecard-june-2021
[note] https://www.iatiregistry.org/dataset/gef-activities

At the Seventh Replenishment of the GEF, Trust Fund participants agreed a set of Policy Recommendations, in line with UK priorities, these form the basis for the indicators of this output and included:
System for Transparent Allocation of Resources (STAR) methodology updated. At the start of the GEF7 replenishment the GEF Secretariat presented a new Policy for the STAR, which introduces new focal area floor allocations, increases the weight of the GDP index, and increases flexibility.

Optimising the use of GEF resources in different countries with a view to mobilising greater investments in measures to achieve global environmental benefits. This included: updating the co-financing policy; introducing the concept of “investment mobilised”; raising the level of ambition for the overall GEF portfolio to reach a co-financing ratio of 7:1; and setting out clearer requirements for Agencies and the Secretariat to document, monitor and report on co-financing and investment mobilised at the project, programme, and portfolio levels. Despite being a year when co-financing could have declined due to the covid-19 pandemic, co-financing has surpassed the replenishment level ambition of 7:1. In addition the Investment mobilised in Upper Middle Income and High-Income countries surpassed the target of 5:1.

Results. Updated Results Architecture for GEF7 includes: a simplified results framework of eleven core indicators and associated sub-indicators; agreed GEF7 targets across the core indicators; streamlined monitoring and reporting requirements; measures to enhance the availability, accessibility, quality and timeliness of data and information on results; and the capture of data on beneficiaries. Milestones under this indicator also include measures to increase the sustainability of GEF projects, including their financial sustainability. GEF Secretariat this year is reporting for the first time on results at the sub-indicator level. It also reveals that five of the core indicator targets set for GEF-7 have already been met and shows good progress in support of marine biodiversity and fisheries.

Enhanced engagement with the private sector The GEF7 replenishment agreed two pillars for implementation on the private sector: expanded use of blended (non-grant) finance instruments; and mobilising the private sector as an agent of market transformation, through the development of a private sector engagement strategy. Following discussion at the 57th and 58th Council meetings with recommendations for improvement, and the formation of a Working Group of interested Council Members (including the UK), the Private Sector Engagement Strategy and associated Implementation Plan, were approved at the 59th Council meeting in December 2020. In the first two quarters of 2021, the Secretariat has successfully engaged a broad range of private sector actors as part of technical discussions ahead of the GEF Replenishment in the Independent Evaluation Office (IEO) assessment of private sector engagement, notably with MSMEs, and in the STAP workplan to understand biodiversity mainstreaming with the private sector.

Operational efficiency and transparency. In March 2019, Policy Measures to Enhance Operational Efficiency, Accountability and Transparency came into effect. These included: a new provision to address timely project preparation; the speed of implementation and Agencies’ compliance with key reporting requirements; and the timing of financial closure (FC) of projects, to require closure within 12 months of submission of a Terminal Evaluation (TE). The GEF Monitoring Report 2020 provided progress data on efficiency metrics, highlighting the percentage of projects reaching endorsement in FY20 within 8 months of Council approval of the PIF and progress in financial closure of projects that have already reached their Terminal Evaluation. Due to covid-19, the Secretariat invoked provisions in the GEF Cancellation Policy that allow for a cancellation deadline extension, extending deadlines for a total of six months. This provided Agencies and recipient countries with the extra time needed to prepare quality projects.

Improved management of data and information. GEF became an IATI publisher in June 2019 with its first submission of project level data to the IATI registry. While the GEF’s new information management system – GEF portal – continues to go through improvements and data transfer, the Secretariat is working to implement systemised reporting to IATI registry on a regular basis.
[note] https://www.iatiregistry.org/dataset/gef-activities

Practical approaches to gender mainstreaming and capacity development. The third report on the GEF Gender Implementation Strategy was brought to the June 2021 Council meeting. Since the Policy became effective in July 2018, the GEF’s improved standards and increased ambition on gender equality has been translated into practice across GEF-7 portfolio. Projects are now better designed with gender sensitive stakeholder consultations and informed by gender analyses. Most projects incorporate gender-responsive measures to address critical gender gaps and include gender sensitive indicators to monitor progress and results over time. The Secretariat has already translated some early lessons learned in the draft GEF 8 Programming Directions with specific provisions already suggested to be incorporated, including:
- Supporting women’s improved access, use, and control of resources, including land, water, forest, and fisheries.
- Enhancing women’s meaningful participation and role in natural resources governance and decision-making processes at all levels (i.e., promoting women’s equal voice and leadership in community, rural and urban planning processes and supporting women as innovators and agents of change).
- Targeting women as specific beneficiaries by supporting activities that support women’s sustainable livelihoods, income-generation, entrepreneurial opportunities in the blue and green recovery and access to finance.
- Investing in women’s skills and capacity by supporting capacity development of different groups, including women’s organisations, and government officials at the national and subnational levels.

Across the 7 areas of policy there has been consistently good progress. In light of this, this output is scored as an A.

VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The business case included consideration of ‘equity’ or how benefits are distributed amongst the population and emphasised that equity was particularly important in delivering FCDO’s commitment to ‘leave no one behind’. GEF’s new “Policy on Gender Equality” (with recent update) which requires gender analysis as part of project design, and improvements on monitoring and reporting in GEF financed projects, is an important commitment by GEF to leave no one behind. Indicator 2.7 of this output (articulated above) directly relates to that policy and demonstrates GEF’s continuing commitment to monitor and deliver against this aspect of equity.
[note] GEF Gender Equality Policy - 2017
[note] GEF_Gender_Implementation_Strategy_1.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Due to covid-19 we discussed in the 2019/20 annual review continuing to track performance against results targets for all core indicators, and resource allocations that have been agreed across the GEF7 portfolio. This was done systematically throughout the year. The current edition of the Scorecard innovates by reporting for the first time on results at the sub-indicator level. It also reveals that five of the core indicator targets set for GEF-7 have already been met and shows good progress in support of marine biodiversity and fisheries.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from last year highlighted the importance of the private sector and engaging in the working group on the Private Sector Engagement Strategy. The UK was an active member of the working group. The culmination of the working group’s efforts saw the approval of the Strategy at the December 2020 Council meeting.

For the year ahead, the final year of the GEF7 period, the UK will continue to encourage consideration of greater upstream engagement in programme design, for example more proactive engagement with women’s rights organisations to help support GEF7 gender ambitions, with attention being paid to opportunities with the Impact Programmes.

D: RISK

Overview of risk management

The overall risk category of ‘minor’ has been maintained in the last year, considering the due diligence and the new Enhanced Due Diligence on Safeguarding, both completed in January 2020. These indicated that the controls in effect were sufficient to monitor and respond to GEF risks as needed. These controls apply to all GEF’s implementing agencies, including: Minimum Fiduciary Standards for GEF Implementing and Executing Agencies and Minimum Fiduciary Standards on Issues Related to Anti-Money Laundering and Combating the Financing of Terrorism, and an updated Policy on Environmental and Social Safeguards.

A risk register for GEF has been maintained since the Business Case risk assessment and aligned with the new FCDO risk management framework. Two of the components assessed over the year, which we have actively engaged with the GEF Secretariat and at Council meetings include:

- Ensuring a robust response to the Independent Audit UNDP undertook on its GEF portfolio published audit in Nov 2020. Follow-up action and reporting to the Council is ongoing. The Secretariat is providing monthly updates on matters relating to this process to the GEF Council.
- Engaging the GEF Secretariat directly and raising in GEF Council meetings to ensure a portfolio wide approach to risk and risk appetite is considered in GEF 8.

Covid-19 and Risk Management
The GEF has provided uninterrupted support to developing countries throughout the covid-19 pandemic to keep urgent environmental priorities on track even under crisis. Recognising
the adversity and budgetary strains the covid-19 pandemic has caused in many developing countries, the GEF is applying a green covid-19 response lens to all its programming.

At the end of the third year of GEF-7 implementation, programming accounts for 81 percent of the seventh replenishment resources, up from 73 percent in the previous GEF work programme. It included new financing through the Africa mini-grids programme and two programmes supporting chemicals and waste sustainable management. The June 2021 work programme also included 36 projects, with many of them targeting Small Island Developing States and Least Developed Countries.

As highlighted in last year’s review, the GEF Secretariat developed a short, medium, and long-term response to the risk posed to the GEF portfolio from covid-19. While the covid-19 pandemic continues to require new business practices and adapt to more virtual interactions, the GEF partnership has mostly found ways to get back to business and continue the implementation of existing projects, design projects for endorsement, and engage with the proper stakeholders and country agencies to submit a strong pipeline of projects. Internal practices in project review now include a covid-19 screen that assesses the risks and opportunities associated with each project being submitted for consideration by the GEF.

- Many projects now consider some form of virtual engagement for the stakeholder engagement processes and other critical meetings needed for the design and preparation of projects for CEO endorsement
- The use of local technical expertise has become more prevalent due to the difficulty of travel of consultants.
- Project execution has been reliant on local government entities in some cases that are closer to the project areas. On a more strategic level, agencies are also aligning project objectives to play a central role in the mitigation of the impacts of the pandemic or contributing to the prevention of future pandemics. Examples include:
- Projects are proposing strategies to ensure that GEF investments can contribute to a green and blue recovery.
- The promotion of nature-based solutions as a measure to mitigate future pandemics.

Safeguarding: As per the December 2109 GEF Policy on Environmental and Social safeguards, the GEF continues to rely on its Agencies Environmental and Social Safeguards policies and procedures to supervise, monitor and report the implementation of Environmental and Social Safeguards management plans or equivalents. GEF Secretariat is in close communication with its Agencies regarding updates on GEF projects under implementation and continue adherence to GEF environmental and social safeguards.
[note] Assessment Agencies Compliance

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

The UK has been a member and major contributor to GEF since its inception in 1991. The UK is a permanent member of the GEF Council, which functions as an independent board of directors, with primary responsibility for commissioning, approving, and evaluating GEF programmes. The UK has influence over policy priorities and level of ambition, through the replenishment process, and in driving monitoring of operational effectiveness and efficiency through the Council. The experience of the UK team has enabled effective development and promotion of innovation and improvements in implementation, as indicated by the proportion of UK policy proposals adopted and the increases in resource allocation to UK priorities (e.g., Illegal Wildlife Trade – (IWT) and nature-based solutions to climate change) to GEF7.

The UK and the GEF Secretariat continue to have a productive working relationship.

VfM performance compared to the original VfM proposition in the business case

Since inception to March 31, 2021 funding approvals made by the Council and CEO total USD 21,683 million, of which 89% was approved for Projects and Project Preparation activities, 7% for Agency Fees and 4% for Administrative budgets. From the inception of UK support for the GEF, there have been continual efforts by the UK to ensure that there is scrutiny and downward pressure on the fees charged by the implementing agencies. In 2012 the GEF Council approved a new fee policy for GEF agencies, which established a reduced fee for all agencies of 9.5% for project grants up to $10 million, and 9% for project grants above $10 million.
[note] Trustee report Mar 2021

The Secretariat’s budget for FY21 expenses is projected at $24.708m a 5.2% increase compared to the FY21 budget. This follows a decrease of 0.3% in the Secretariat budget for FY21 compared to FY20, and reflects the work demands and needs for FY22. The reduced costs in the current fiscal year due to the continuation of covid-19 has generated underruns and additional savings for the Trust Fund vis-à-vis original GEF-7 overall projections. At this stage it is anticipated that the GEF-7 administrative costs will be well within the budget envelope negotiated as part of the GEF-7 replenishment.
[note] Business Plan and Corporate Budget for FY22

GEF’s Independent Evaluation Office will produce a detailed assessment of GEF’s performance, which will provide detailed assessments of projects funded through the GEF as part of the Overall Performance Study for GEF7 (OPS7). This will be available at the 2nd meeting for the eighth replenishment (GEF8) in September 2021.

On current evidence provided above, the programme continues to represent value for money.

Quality of financial management
The World Bank as Trustee reports on GEF expenditure and resource availability at the biannual GEF Council meetings. The most recent Financial Report was presented to the GEF Council in June 2020, and highlighted the shortfall being faced by the GEF’s seventh replenishment due to unexpected exchange rate fluctuations. The GEF most recently filed an Independent Auditors’ Report and Statement of Receipts, Disbursements and Fund Balance in October 2020 in which the auditors did not provide any qualifications to their opinion. The independent audit of the GEF Trust Fund by the World Bank’s external auditors has been concluded for the period ended June 30, 2020 and is to be issued in October/November 2021.

Date of last narrative financial report	June 2021	Date of last audited annual statement	October 2020