Amendment Letter No. 4-2021
Provision of Humanitarian Air Services in Nigeria FCDO Project No. 300432-104
1. I refer to the Multi-year Memorandum of Understanding between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) formerly known as the Department for International Development ("DFID") and Word Food Programme (WFP) signed on 28 June 2019 and subsequently amended through Amendment No 1/2019 signed on 4 December 2019, Amendment No 2/2020 signed on 21 October 2020 and Amendment No 3/2020 signed on 8 December 2020.
2. In completing the payments agreed and following delays in meeting the previously agreed schedule for the 2021 payment and as support to mitigate possible pipeline breaks, FCDO proposes to amend the disbursement schedule in Paragraph 2 of Amendment No 3/2020 with the following text in order to support the continued delivery of UNHAS's essential humanitarian air services to FCDO's programmes in northeast Nigeria in the year 2021.

	MoU Payment due date	UK£/Amount	Proposed Amended due date	UK£/Amount
1.	1 June 2019	£2,000,000	1 June 2019	£2,000,000
2.	1 June 2020	£4,000,000	15 December 2019	£2,000,000
3.	1 June 2021	£4,000,000	31 October 2020	£2,000,000
4.			07 December 2020	£2,500,000
5.			1 September 2021	£1,500,000
	Total	£10,000,000	Total	£10,000,000

All other terms of the Memorandum of Understanding, including the previous amendments, still apply.

1. This letter of amendment will place on record our common understanding of the above change and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 4-2021.
2. Please sign this copy of this letter; return a signed copy to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact details
Date:

Signed on behalf of the partner: ,
Name:
Position:
Address/Contact details
Date: