Amendment Letter No. 9-2021
Contribution to 2019 Humanitarian Operations in North East Nigeria under WFP Country Strategic Plan (SO1)
FCDO Project No. 300432-109

I refer to the Memorandum of Understanding between the Government of the UnitedKingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) formerly known as Department for International Development (“DFID”) and World Food Programme (‘WFP’) signed on 17 October 2018, Amendment No 1-2019 signed on 10 May 2019, Amendment No 2-2019 signedon 11 September 2019, Amendment No 3-2019 signed on 11 December 2019,Amendment No 4-2020 signed on 31 March 2020, Amendment No 5-2020 signed on28 August 2020, Amendment No 6-2020 signed on 22 October 2020, Amendment No 7-2020 signed on 3 December 2020 and Amendment No 8-2021 signed on 30 March 2021.

Following dialogue with WFP on increased resource requirements to address the current humanitarian crisis in North East Nigeria, exacerbated by the lingering impact of the COVID-19 pandemic, restricted market access due to insecurity and inflationary pressures, in meeting the food needs of a targeted 1.7million people, FCDO proposes to contribute an additional £14,000,000.00 (Fourteen Million Great Britain Pounds Only) to the implementation of WFP’s Strategic Outcome 1 (One) under its Nigeria Country Strategic Plan (2019-2022).

FCDO further proposes that the figures and words £88,077,832 (Eighty-Eight Million, Seventy-Seven Thousand, Eighty Hundred and Thirty-Two Pounds only) in paragraph 3 of the Amendment Letter 7, which was left unchanged in the terms of Amendment Letter 8’s time extension be replaced with the figures and words £102,077,832 (One Hundred and Two Million, Seventy-Seven Thousand, Eighty Hundred and Thirty-Two Pounds only).

FCDO also proposes that the end date of the project for SO1 in paragraph 2 of Amendment letter 8 be replaced with 31 March 2022.

Following from this, FCDO proposes the schedule of contribution in Paragraph 4 of Amendment 7 is amended as follows:

Strategic Outcome	Payment Due Date	UK£/Amount
SO1	17 October 2018	£15,000,000
SO1	15 May 2019	£15,000,000

SO1	15 September 2019	£10,000,000
SO1	15 December 2019	£10,000,000
SO1	31 August 2020	£13,000,000
SO1	31 October 2020	£14,000,000
SO1	4 December 2020	£7,000,000
SO1	1 September 2021	£14,000,000
SO3	15 May 2019	£1,500,000
SO3	5 August 2019	£1,500,000
SO3	25 March 2020	£1,077,832

In accordance with Paragraph 11 of the Framework Agreement, WFP Nigeria shall provide FCDO with the following reports

  1. 1 (One) Progress Report every six (6) months, updating FCDO on the status of the SO1 project together with latest available approved budget within six (6) weeks after the end of the relevant period.

  1. WFP Annual Country Report – which WFP will submit, not later than 31 March of each year; an annual financial report in WFP’s Annual Country Report (ACR) format or, where relevant, standard trust fund reports, as of 31 December every year, certified in accordance with the WFP’s standard procedures for certification.

  1. Provisional Reports – within three (1) months following the date of completion or termination of the respective Contribution Agreement, the relevant WFP country office (or regional or Headquarters unit in the case of, respectively, regional and global projects) will submit a provisional narrative report summarising the project performance and results as well as provisional financial data in WFP’s ACR or trust fund report format, as the case may require.

  1. Final Reports: Upon completion of the WFP programme/project, WFP shall submit, no later than 30 June of the year following its financial closure, a final financial statement in WFP’s ACR format certified in accordance with WFP’s standard procedures for certification.

All other terms of the Framework Arrangement and Memorandum of Understanding will apply.
This letter of amendment will place on record our common understanding of the above changes and will come into operation on the date you sign the confirmation below. This note will be known as Amendment No. 9-2021.

Please sign this electronic letter and retain a digital copy for your own records.

Signed on Behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on Behalf of WFP:
Name:
Position:
Address/Contact Details:
Date: