ADDENDUM TO BUSINESS CASE

SUMMARY INFORMATION
Project Name	North East Nigeria Transition to Development (NENTAD)
Country or region targeted	Nigeria
Type of cost extension (if applicable)	Cost Extension
Original project budget	£400m
Original project start and end dates	April 2017 – March 2022
Cost extension value (if applicable)	£25 million
New project end date (if applicable)	n/a
Business Case Quest Document No.	16115362
Business Case Addendum Document No.	34586520

INFORMATION
What is the project’s purpose?
The North East Nigeria Transition to Development Programme (NENTAD) is designed to deliver life-saving humanitarian assistance while supporting the transition from humanitarian response to development programming in North East (NE) Nigeria. The programme aims to save lives, alleviate suffering, and strengthen household and community level resilience whilst supporting Government capacity to respond and reduce the number of people needing humanitarian assistance and enabling a transition to longer term, development interventions that start to address the root causes of the conflict. During its first three years, NENTAD reached over 1.5 million people with food assistance, 510,000 children under five and nearly 160,000 pregnant and lactating women with nutrition interventions, over 500,000 people with basic health care along and supported safe humanitarian access to communities in need, strengthened humanitarian coordination, and provision of protection services for the most vulnerable internally displaced persons (IDPs). / While the trajectory in 2017 was positive, major risks have materialised since 2018 in terms of a deteriorating security environment, constraints on humanitarian access, and increased humanitarian needs compounded by the direct and indirect impacts of Covid-19. NENTAD’s key purpose of providing humanitarian assistance to people in need remains a critical priority. A cost extension of £100m was approved in 2018 in recognition and response to the sustained scale of severe humanitarian need.
What is the objective of the cost extension or other changes?
The objective of this cost extension is to continue providing life-saving and life-sustaining humanitarian assistance to address urgent humanitarian needs, including increasing levels of crisis and emergency levels of food insecurity, with a risk of pockets of famine in some areas. The cost extension will enable the UK to deliver humanitarian assistance during the final year of the NENTAD programme, addressing critical food, nutrition and protection needs and supporting a safe, coordinated and Covid-19 sensitive operating environment for the humanitarian community. Specific objectives are to: / Reduce morbidity and mortality, especially for vulnerable children and women, by supporting basic needs assistance that combat the drivers and consequences of food insecurity and malnutrition / Enhance the protection of civilians – men, women, boys and girls – through integrated cross-sectoral protection interventions and monitoring. / Strengthen humanitarian access by supporting safety and security of humanitarian workers and enabling their access to deep field locations.
What is the additional and total support the UK will provide?
The existing NENTAD budget ceiling of £400m was 98% exhausted by the end of FY20/21, with £9m headroom remaining. This cost extension will add £25m to the NENTAD programme, increasing the total budget ceiling to £425m. The cost extension will enable FCDO Nigeria to deliver humanitarian assistance in line with FY21/22 final budget allocation and approved business plan and UK commitments to the G7 Compact on Famine Prevention.
What are the expected results?
This cost extension will enable delivery of HMG’s strategy in the Lake Chad Basin by maintaining humanitarian assistance to the extent possible within the final FY21/22 budget allocation and approved business plan. The overall expected results of this cost extension are reduced humanitarian suffering amongst conflict affected populations due to their basic needs being met and a reduction in morbidity and mortality. / Key indicative results for the budget proposed in the FCDO business plan are below. These indicative results and allocations will be reviewed with individual partners prior to signing of individual agreements. Allocations below include components of existing multi-year agreements, which have been revised to fit within final approved FY21/22 budget allocation. This cost extension will enable continued delivery of services. / Partner Sector FY 2021/22 / Indicative allocations Indicative results / WFP Food security £14m 400,000 people supported with food assistance (cash/in-kind). / Action Against Hunger Nutrition, WASH £2.5m Treatment for 3,200 severely malnourished children. / Clean water provision for 2,900 people. / Nutrition-sensitive livelihood support for 1,460 families. / UNICEF Multi-sectoral nutrition, WASH £8m 13,600 children aged under 5 treated for Severe Acute malnutrition. / 90,000 people with improved access to sanitation infrastructure and access to safe drinking water / 147,500 children 6-59 months receive treatment against acute watery diarrhoea and pneumonia / Procure treatments for 30,000 severely malnourished children (Ready-to-Use Therapeutic Foods) / ICRC Multi-sectoral £3m Approx. 25,000 persons assisted with food consumption or production. / 5,200 assisted with living conditions. / Income support to 9,600 people. / Support to one health facility. / 42,000 people assisted supported with water and shelter / 450 detainees supported with food and 260 supported with living conditions. / IRC Protection £3m Case management for 1,500 unaccompanied children and children formally associated with armed groups. / Over 100,000 people receive explosive ordinance risk education risk across communities in 20 LGAs of BAY states. / Approx. 80,000 people receive civil documentation. / Seven women’s/community protection groups formalised to advance localisation and reach up to 70,000 vulnerable individuals and refer to specialise services. / Security, logistics, monitoring and evaluation and technical support Logistics £2.85m Essential transport for 3,200 passengers, and over 7 tonnes of humanitarian cargo; security support for at least 63 NGOs, technical and monitoring oversight of the response. Third party monitoring and technical assistance / TOTAL £33.35m / Indicative results are calculated for the expected FY21/22 country plan allocation of £33.35. The cost extension sought is for £25m as there is approx. £9m available within the existing business case threshold of £400m.
What is the approach to implementation?
The cost extension will be implemented in line with the HMG strategy for the Lake Chad Basin, which aims to keep humanitarian aid at or as near to current levels to meet needs and advance FCDO key policy objectives including prevention of famine, treating acute malnutrition, and tackling violence against women and girls. The humanitarian response is closely coordinated with a regional approach to stabilisation, peacebuilding, and cooperation mechanisms. In NE Nigeria, the NENTAD programme is closely coordinated with development programmes to ensure that opportunities to transition vulnerable people to recovery and development in more stable areas are identified and acted upon. Moreover, the NENTAD programme will work closely with the UK Famine Prevention Initiative. / The additional funding will be managed by revising current arrangements through existing partners as detailed above, including through time and cost extensions to existing Memoranda of Understanding and Accountable Grant Agreements. These are the standard method of providing funding to partners, using templates already agreed centrally by each agency that outline reporting, financial management, and other relevant requirements. Each partner has a strong track record of delivering results for vulnerable populations through effective use of FCDO funding in complex, insecure and volatile environments, including in NE Nigeria. The partners cited above have demonstrated capacity to deliver results required for this cost extension; we will continue to monitor their performance closely. NENTAD has scored A in all three annual reviews since the programme began and has exceeded most of the headline results set out in the business case, highlighting the high and consistent performance of existing partners. Final allocations will be signed off by the Development Director. / For multilateral agencies, disbursed funds are subject to the internal and external auditing procedures laid down in the agencies’ financial rules and regulations. Funds disbursed to INGO partners are subject to an FCDO commissioned audit in line with Smart Rule. All partners have been subject to Due Diligence Assessments including an Enhanced DDA which assessed their Safeguarding policies and procedures. We have reviewed and are satisfied with partner approaches to safeguards including preventing sexual exploitation and abuse, and their fraud reporting and management. Risk management is a regular focus for partner engagement to ensure programme delivery remains within the agreed FCDO risk threshold. Programme log frames and risk matrices are reviewed regularly Following a disability audit of the humanitarian portfolio in 2018, all programmes are working to integrate disability, and the voices of persons with disability, proactively into the programme cycle. Partners are ensuring that the most vulnerable, often women and girls, are prioritised and reached with appropriate humanitarian response, ensuring compliance with the Gender Equality Act. / No funds will be provided directly to the Government of Nigeria, nor implemented by government agencies. However, all partners will work in accordance with Nigerian legislation and registration requirements. / The NENTAD programme risk is severe as a result of the deteriorating security situation. After Covid-19 related risks were mitigated through adaptation of programmes and operations, deteriorating security and increasing threats to humanitarian workers are likely to result in sustained drawdown of partner operational staff with potentially elevated risk of aid diversion. Our delivery partners are experienced operators in this complex environment and have adapted programmes to mitigate Covid-19 related risks. We will continue to monitor the context closely to ensure operational risks are assessed and addressed appropriately. FCDO’s third-party monitor provides independent monitoring of UK assistance. We will continue to work with partners to ensure remote fraud and whistle-blowing options are updated. Our support to an NGO security organisation enables real-time tracking security threats for NGO partners. UN agencies use GPS trackers on vehicles to monitor delivery of key supplies. Regular partner meetings are conducted remotely to monitor progress. / This cost extension will support key propositions for Value for Money (VfM), through providing predictable funding allowing partners to plan better including sequencing funds from other donors and enabling leveraging of additional resources. Partners have also signed up to additional VfM, including, for example, in 2019, WFP distribution of food procured locally increasing by 12 percent in metric tonnage and six percent in value while in 2020 a further 7 percent increase in metric tonnage and 13 percent in value was reported resulting in local market promotion and ensuring that local commodity prices did not exceed import parity;. Similarly, ICRC’s partnership with the Nigerian Red Cross offers a cost-effective approach to delivery, builds the capacity of local volunteers, rather than establishing its own platform and bringing in international staff. Annual reviews have consistently assessed NENTAD as delivering good VfM through the provision of life-saving and essential services, including food and nutrition, WASH, protection, formal and non-formal education and facilitating response-wide services such as safe air transportation services. VfM is further assessed on a quarterly basis with partners. / Not granting a cost extension would significantly reduce the VfM of investments already made through NENTAD in meeting the humanitarian needs of conflict affected populations. For example, close-out of the IRC-led protection consortium, who have developed a network of community volunteers and semi-formal structures, would result in loss of experienced staff/volunteers and dissipation of networks. Continued funding to this will increase economy and effectiveness as these community networks are formalised into a local NGO model, delivering at lower cost than INGOs and progressing the localisation agenda, a key Grand bargain commitment.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The UK, as P3 lead and UN Security Council penholder, has long played a leading role in responding to instability in the Lake Chad Basin. Following the 2014 kidnap of schoolgirls from Chibok, the UK has stepped up counter-terrorism, military, diplomatic, humanitarian and stabilisation activity in the NE. Since 2015, the crisis has become increasingly regional in nature. In response, the cross-HMG Lake Chad Basin strategy is making a regional pivot characterised by a more coherent and integrated offer across all UK interventions to achieve overall objectives to contain the threat of non-state armed groups and support a transition to peace and development. Humanitarian response is a critical component of this, notwithstanding the need for a political settlement is needed to achieve sustained resolution of the crisis. / The NENTAD programme targets assistance to NE Nigeria, the epicentre of the crisis and humanitarian need. The programme was initially designed in 2016-17 to transition away from acute humanitarian response towards recovery and development, with the balance of expenditure reflecting this. The Theory of Change recognised the high-risk environment and acknowledged the underlying assumption that the environment needed to be conducive for this transition to take place, most notably a reduction in violence and for Nigerian security forces to be able to increasingly establish control and stabilise areas of the BAY states. Despite a promising trajectory of reducing needs in 2017-18, this assumption has not held, and major risks to the Theory of Change beyond the control of the programme have been realised. This is particularly the case in terms of a deteriorating security environment, challenges in humanitarian access, and increased humanitarian needs. As a result of deteriorating security, compounded by the impacts of Covid-19, the number of people in need of humanitarian assistance in NE Nigeria has increased from 7m people in 2016 up to 8.7m in 2021. The NENTAD programme’s work to support shock responsive social protection reflects an acknowledgement that a large proportion of the poor and vulnerable humanitarian caseload will require ongoing access to social assistance, and efforts to support the expansion of the government’s social protection system across the BAY states are crucial. / In August 2019, the Nigerian military changed their strategy to protect personnel and assets following casualties of roughly 2,000 soldiers in the first eight months of 2019. The ensuing tactical withdrawal of troops from the front line to 21 ‘super camps’ resulted in the ceding of previous territorial gains, reduced security along main supply routes, and a removal of protection by presence in deep field locations. JAS and the Islamic State West Africa have retaken large areas of territory causing hundreds of thousands of people to be displaced to IDP camps in Government controlled areas or other habitable host communities translating into a surge in humanitarian need. The estimated number of people in areas inaccessible to humanitarian assistance has increased to 1.24m in 2020. / Threats to humanitarian operations are serious and growing, with non-state armed groups frequently attacking communities, abducting and killing civilians, and now targeting aid workers as an explicitly and demonstrable policy: 27 aid workers have been killed over the past two years. Road transport is now largely restricted to humanitarian and commercial cargo, attacks on humanitarian hubs demonstrate the further need for strengthened security, and helicopter transport has been restricted as a result of security concerns. / The direct and indirect impacts of Covid-19 on already fragile systems in the NE have been severe with lockdowns disrupting markets, livelihoods and service provision, including the closure of schools and refocusing of health services to Covid-19. Covid-19 has further impacted the overall socio-economic position in NE Nigeria. Falling oil prices have reduced the central Nigerian Federation Account Allocation which in turn has impacted State budgets and reduced the capacity of State governments in the NE to provide basic services to conflict affected populations, further disrupting plans to transition from humanitarian support to integrated service provision and long-term development. / Cadre Harmonisé data now projects that 4.36 million people in the NE will face acute food insecurity (IPC 3 and 4) during the June-August 2021 lean season, a return to levels last seen when the famine alert was raised for the 2017 lean season. In September 2020, OCHA briefed the UN Security Council on concerns regarding alarming levels of conflict-related food insecurity and hunger in NE Nigeria under UN Security Resolution 2417. Covid-19 lockdowns have negatively impacted food production, access to food and increased the prices of basic food items. The primary obstacles to an adequate provision of humanitarian assistance, however, are humanitarian access and funding constraints. Access is constrained by both the Nigerian authorities and non-state armed groups and humanitarian operations are restricted to areas controlled by the Nigerian security forces, compromising the neutrality and impartiality of the humanitarian operation. The estimated 1 million people currently inaccessible to the humanitarian community are likely amongst those with the most severe needs and most at risk. / Deteriorating food insecurity is accompanied by alarming trends in malnutrition.1.5 million people are in need of nutrition assistance in 2021, up from 1 million in 2020. This includes nearly 300,000 children under 5 projected to face Severe Acute Malnutrition in 2021. The ability of Nigerian authorities to support conflict-affected households remains insufficient, poorly coordinated and sporadic. Continued international assistance is required but it is highly unlikely that food and nutrition shortfalls will be fully met by donors. The World Food Programme has increased their caseload to 1.5 million in 2021, up 0.6 million in 2020, while facing a funding shortfall of $147m.
[note] UNOCHA, January 2021 Global Humanitarian Response plan
[note] UNOCHA, March 2020. Nigeria Humanitarian Response Plan