## SDF Annual Review – Post April 2019

Title: Special Development Fund 9th Replenishment
Programme Value £ (full life): £18,000,000		Review date: 27/11/2020
Programme Code: 204675	AMP start date: 29/11/2017	AMP end date: 01/07/2022

Summary of Programme Performance
Year	2017	2018	2019
Overall Output Score	A	A	A
Risk Rating	Minor	Minor	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204675
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-1-204675

A. SUMMARY AND OVERVIEW

Description of programme

The IFIs, comprising the International Monetary Fund (IMF) and Multilateral Development Banks (MDBs), are at the heart of the global development system. They provide expertise and financing to governments and businesses to achieve development objectives agreed with partner countries. They also play a critical role providing sound macro-economic policy advice to promote good governance, trade and open markets. The Special Development Fund (SDF) is the Caribbean Development Bank’s (CDB) concessional arm, which provides grants, low-interest loans and technical assistance to the most vulnerable and poorest countries in the Caribbean region.
[note] Beyond the SDF, the UK has several other important ties to the CDB. The UK’s shareholding in the Bank is 9.31%, making the UK the joint largest non-regional shareholder with Canada. CDB is also the implementing partner for the £330m UK Caribbean Infrastructure Partnership Fund (UKCIF), a fund established in 2016 to build economic infrastructure in the Caribbean.

The 9th replenishment of the Special Development Fund (SDF 9) is supporting economic and social development through investments in sectors that contribute to the achievement of the Sustainable Development Goals (SDGs): transport, education, water and sanitation, agriculture, and climate change/environment. It also has a specific focus on inclusiveness (leave no one behind, jobs and prosperity) and broader poverty reduction through the Basic Needs Trust Fund (BNTF), which focuses on local vulnerable communities and pockets of disadvantage. SDF has grant funding “set asides” for Haiti ($45 m), the Basic Needs Trust Fund (BNTF $45 m), disaster responses ($3 m) and regional collaboration ($4 m).

FCDO has contributed £18 million to the replenishment of SDF9 (running from 2017 – 2020). This included a final performance-based tranche of £4.5mn which was made in the August 2020.
[note] This includes funding from the Department for International Development (DfID) prior to merger with the UK Foreign and Commonwealth and Office (FCO) in September 2020 - becoming the Foreign, Commonwealth and Development Office (FCDO). This annual review covers a period in which the project was managed by both DFID and FCDO. FCDO is used to refer to the department throughout.

Summary supporting narrative for the overall score in this review
2019 saw the CDB deliver strong results against our targets across output one (CDB's contribution to country and regional outcomes) and output four (Organisational effectiveness of CDB) where it has scored an A+ for both. The Bank is also making progress towards its targets for regional outcomes, exceeding expectations across targets for both ‘education and training’ (output 1.2) and environmental programmes (output 1.3). The Bank has continued its downward trend on administrative expenses (output 4.1) in line with that envisaged in the 2015 – 2019 Strategic Plan. It is also good to see the Bank has continued to maintain a high allocation of financing for less developed Borrowing Member Countries (BMCs) (output 2.5) – vital to ensuring alignment with UK priorities.

There remains scope for improvement. This is particularly true of the Bank’s operations and speed of delivery (output 3 - Operational quality, effective portfolio performance and resource allocations) where the Bank continues to face challenges. The Bank scored a B against this output, meeting one sole indicator (it managed to consolidate 2018’s success on indicator 3.2 for PCR completion). Low rates of commitment were flagged in last year’s annual review as a concern at the mid-point of SDF9. In 2019, overall commitments were less than in previous years across both loans and grants. At the end of 2019, the Bank had approved 43% of the replenishment resources compared with 69.8% for the comparable period of the SDF Eighth Cycle (SDF 8). However, the use of SDF funds in 2020 to meet the unprecedented needs created by the COVID-19 pandemic mean that the previously substantial risk of the Bank not making full use of resources available during the SDF9 cycle is now low (although the objectives of the programme now flex in response e.g. some resource now providing debt relief so creating fiscal room to respond to the pandemic). These issues will be ones we continue to monitor in the final year of the programme. We continue to feed in early findings to ensure we focus on resource levels and commitment authority as part of SDF10 negotiations.

Overall, the Bank has scored A+ across two outputs and B across two outputs, warranting an A overall.
Major lessons and recommendations for the year ahead
Recommendation 1 – Promote better disbursements, approvals, and more diversity. Given some of the implementation challenges the Bank continues to face, we identify the need to maintain a focus on the ‘Transformation Programme’ intended to strengthen organisational performance. We have secured agreement for management to provide regular Board of Directors’ updates and ensured that audits of internal process identify good lessons for improvement. As part of the Transformation Programme we shall focus on representation of women in senior management positions too. Further to this, the newly established Resident Implementation Officers in countries with low disbursements will be important to tackle blockages and identify lessons which we will look to the Bank to mainstream across its wider portfolio. There is also scope to ‘deep dive’ into the project approval process, where the Bank should speed up its process, whilst ensuring that implementation issues are identified at design stage. We will ask for such work next year.

Recommendation 2 – Build stretch into future targets. In conducting the SDF10 negotiations, a key lesson form this Annual Review (AR) has been to ensure that future SDF targets and objectives achieve an optimal balance between process-type output targets (e.g. the review of country regulatory frameworks and policies for the energy sector) and stretching outcome focused results (e.g. increasing the share of renewables to transform the energy matrix). We will seek to deliver these objectives through the replenishment negotiations for the next SDF cycle, with a focus on key sectors, and at the same time ask the Bank to prioritise strategies and country plans that identify national targets that consolidate at overall fund level.

Recommendation 3 – Stronger results reporting. We are moving into the final year of the SDF9 cycle and next year’s AR will be the Project Completion Report (PCR). We will therefore be looking to use the year ahead to consolidate the results the Bank has achieved under the SDF9 cycle and build on these going into SDF10 (and inform any final calibration during year one of the new programme cycle). A significant lesson has been on the need to disaggregate better SDF specific impacts. These can then confirm we are achieving broad equity through SDF disbursements (as we have confirmed through CDB’s recent improvements on mainstreaming gender considerations into its programming, for example) and assess and improve value for money. Through our SDF10 negotiations we will seek Bank agreement to remedy this, build in more focus on the most vulnerable borrowers and seek greater disaggregation for both gender and climate change progress indicators.

Recommendation 4 – Develop flexible monitoring strategies. Our ability to undertake our own monitoring for the SDF9 cycle has been impaired this year by COVID-19, which has prevented travel to the region to meet with Bank staff or beneficiaries. With the PCR coming up next year, we will be assessing our approach to monitoring and evaluation (M&E) and identify how we can build a better sense of Bank operations in country. Virtual ‘visits’ and increased collaboration with Resident British Commissioners (RBCs) or British High Commissions in country will strengthen the approach along with other options we will identify through the Better Delivery network.

Recommendation 5 - Account for COVID-19 support. Given the extraordinary circumstances this year and the need to respond to the global pandemic, the UK and other Bank members have agreed for the Bank to prioritise its final year support towards managing regional impacts. The Bank has re-programmed approximately $300m in 2020, of which about 50% is from the SDF. We will need to factor this into next year’s PCR when accounting for final year results. In anticipation, we will adjust the log frame so to assess the impacts of this support.

Recommendation 6 – Improve engagement between HMG posts in region and the Bank – The formation of FCDO provides new opportunities to strengthen the relationship with the Bank and increase our understanding about the impact of the CDB’s work across the region. We will seek advice from both posts and the Bank on how best to achieve this and act on findings.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change (ToC) for SDF 9 combines both the resources provided for the SDF 9 replenishment and the ongoing engagement with the CDB, through the Board and other channels. It has not changed over the last year and is set out below:

Impact
Outcome
Input
Outputs
Key Assumptions
- Financial contribution
- Policy engagement during negotiations and delivery
- Other development partners provide resources
- Clients continue to engage positively with SDF projects and demand remains high
- Reform led from HQ in Barbados has an impact on ways of working in-country and at HQ
- Reforms are relevant, and do improve the Bank’s ability to deliver results through speedier and more effective project processes
- Projects are resilient to risks arising in country
CDB organisational and operational outputs e.g.
Around $350 m of concessional funding to SDF countries including $45m to Haiti
CDB joins International Aid Transparency Initiative (IATI)

Eradicate poverty and achieve the Caribbean Sustainable Development Goals
- The Bank is capable of having a sustained impact on the sectors and policy areas it programmes in
- There is the political will and capacity in partner countries to ensure bank projects have a sustained impact
- The UK is successful in influencing the shape of SDF 9
- The Bank implements and monitors the agreed organisational and operational changes
SDF resources delivering material impact in partner countries as outlined in the results framework: e.g.
- 120,000 beneficiaries from road projects,
- 198,000 students benefiting from improved facilities,
- 950 km of water supply lines built

The CDB is expected to deliver both direct development results through the SDF 9 and internal reforms agreed as part of the SDF replenishment negotiations. These reforms, if implemented as planned, should strengthen its efficiency and effectiveness leading to improved performance during the SDF 9 period and beyond.

The 2019 SDF 9 Annual Review found that the log frame required some minor adjustments to ensure that it remained a fair and challenging measure of CDB’s performance. Based on this assessment, in February 2020 it was identified that updates should be made to the ‘Output One’ indicators in the SDF9 log frame. This output originally had four sub-indicators which measured CDB performance against some of the FCDO’s priorities. However, CDB reports on 32 different deliverables and thus choosing any four risks presenting an unbalanced picture of overall performance. As such it was suggested that FCDO consider how to reflect the CDB’s performance across the wide range of deliverables on which it reports. It was decided the ‘Output One’ indicators would be replaced by four indicators covering overarching UK priority themes, and a composite indicator for the remaining themes. This would allow additional weighting for UK priority themes whilst not neglecting other areas.

In the year under review, and in keeping with the statement on outcomes in the ToC, SDF 9 has made commitments across several sectors which promote economic development and resilience in eligible countries, including environmental sustainability, climate change and sustainable energy, regional cooperation and private sector enabling environment. The themes of SDF 9 loans can be seen below.

At an outcome level, SDF work in 2019 included delivery of results in some of the Bank’s poorest members. For example, the Bank’s programme in Haiti supported the transformation of schools in four rural locations with the creation of 32 new classrooms with a capacity for 1,280 students. The Bank also continued to provide a source of regional support to members for emergency response. In 2019, the Region was impacted not only by hurricanes, resulting in loss of lives and livelihoods in The Bahamas, but also by prolonged drought, which led Belize to declare a state of emergency in some affected districts. In both cases, the Bank intervened with its emergency response grants to aid the immediate recovery effort.

As set out in Section A, ongoing issues around implementation and delivery remain. However, the Bank continues to offer value for money (VfM) as per the Business Case statement. The progress to date across projects demonstrated under our ‘Output One’ indicators show that through the SDF the Bank is promoting economic development and resilience in a region where the FCDO has a limited development expertise footprint. A significant assumption under our ToC was that the Bank would continue to make improvements in operational effectiveness at HQ and translate this into delivery improvements. Whilst the Bank faces ongoing issues around speed of delivery, we continue to see it making efforts to improve on this. In this annual review period, we have seen the Bank meet outputs specifically identified in our ToC on Bank effectiveness – which were used as indicators for the FCDO SDF9 performance-based payment tranche. These related to speed of delivery and joining IATI and were assessed on progress made up to December 2019. In August 2020 the final payment was made to the Bank following confirmation these indicators had been met.
[note] The overall VfM statement in the SDF 9 Business Case was “The limited analysis possible suggests that the SDF represents VfM in addressing the development needs of the region, particularly in promoting economic development and resilience in the smaller and poorer members where other MDBs do not operate and given the limited capacity of DFID to manage projects directly.”
[note] After consultations and discussions with CDB in October 2016, Ministers decided in November 2016 to link part of the UK’s payment to the SDF 9 (£4.5 m out of a total of £18 m) to overall progress regarding speed of delivery and CDB joining IATI
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
At a broader impact level, the Bank has consistently struggled to produce level one data within its results monitoring framework. This has been due to issues around data collection, particularly in the Banks poorest members, where there is a lack of governmental capacity to access reliable poverty data at national and regional levels. It is therefore not possible to review “regional progress towards selected Caribbean-specific MDG targets and development outcomes”.

There is evidence of positive results at the outcome level - net enrolment in primary education remained on track in 2019 to increase on baseline figures. However, progress has slipped on indicators tracking female enrolment in secondary education. The Bank was also not able to report data across two of the outcome indicators within our log frame - urban access to improved water sources and proportion of population with access to improved sanitation.

Issues with collecting data at impact level, and with illustrating the results that the Banks outputs are achieving in terms of poverty reduction, is something the UK is placing pressure on the Bank to address during SDF10 replenishment negotiations. The Bank has identified its Enhanced Country Poverty Assessment Programme as having the potential to provide timely and reliable country poverty data and FCDO continues to engage on this through Board and SDF10 replenishment meetings.

As part of this year’s annual review, we engaged with FCDO posts within the Caribbean to ask whether they were able to provide views on the effectiveness and impact of CDB programmes. Responses indicated a lack of engagement between FCDO posts and the CDB, and a heavy reliance on the Barbados office (where the CDB is headquartered) to engage with the Bank on their behalf. Moving forwards, the FCDO will explore how we can strengthen engagement between posts and the Bank and gather more evidence beyond that provided by the Bank to support the annual review process, particularly as we enter the final year of the SDF9 cycle and into SDF10.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Overall, the programme has done well this year and broadly met FCDO objectives - scoring particularly well against contribution to country and regional outcomes. Whilst some challenges with implementation and delivery remain, we can continue to see the Bank offering VfM as per the Business Case statement and the programme has therefore scored an ‘A’ overall. FCDO has limited bilateral development presence in many of the countries covered by the SDF and this makes the CDB invaluable in allowing the UK to address development needs in countries we otherwise might not reach. The CDB continues to be a well-regarded player, with a high number of staff from within the region and the ability to inform policy through a sense of regional ownership. The Bank is continuing to work to make improvements on its effectiveness in line with FCDO priorities. This can be seen particularly in 2019 with the Bank having met targets under indicators set as part of the FCDO SDF9 performance-based payment tranche.
[note] Receiving Blend of SDF and OCR: Belize, Dominica, Grenada, Guyana, Jamaica, St Lucia, St Vincent and the Grenadines, Suriname. Receiving mainly SDF: Haiti.

## C. DETAILED OUTPUT SCORING

Output Title	CDB's contribution to country and regional outcomes
Output number:		1	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Project outputs in Economic and Social Infrastructure Theme (average progress to date across projects on meeting targets for 2014 - 2019)	Target: 90 – 100% / Achieved: 82%	Target Moderately not met expectation
1.2 Project outputs in Education and Training Theme (average progress to date across projects on meeting targets for 2014 - 2019)	Target: 90 – 100% / Achieved: 109%	Target Moderately exceeded expectation
1.3 Project outputs in Environmental Sustainability Theme (average progress to date across projects on meeting targets for 2014 – 2019)	Target: 90 – 100% / Achieved: 184%	Target substantially exceeded expectation
1.4 Project outputs in all remaining themes (average progress to date across projects on meeting targets for 2014 - 2019)	Target: 90 – 100% / Achieved: 146%	Target substantially exceeded expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Output one examines CDB’s contribution to country and regional outcomes, assessing across a range of UK priority themes (economic progress, education and environment) and a composite of progress under the rest of the themes measured. CDB have performed well, warranting an ‘A+’ in meeting or exceeding expectations on expected progress across most of the indicators. The Bank performed particularly well in progress against targets for projects under the Environmental Sustainability theme (1.3), where CDB supported several initiatives focusing on developing sector policies and designing and implementing customised tools for multi-hazard risk assessment and climate resilience. It is noted that some of the ‘softer targets’ such as the review of country frameworks and policies for the energy sector are easier to achieve, while others such as transforming the energy matrix to increase the share of renewables are behind target outcomes.

The Bank did not meet expected progress on indicator 1.1, due to significant underperformance across two of the indicators under this theme, ‘installed water capacity’, where progress against targets for 2014-19 was only 25%; and ‘Beneficiaries of community infrastructure construction and enhancement projects’ which was at 50% of expected progress during 2014-19.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Under output 1, we can see the CDB producing development results across a region where the FCDO has limited bilateral development presence in country. For example, part of the SDF is a specific set aside for Haiti where we have no office in country. Our indicators represent a range of UK priority themes and the Bank can therefore be seen to be providing an efficient way for the FCDO to meet our strategic priorities and an effective way to deliver UK aid. Two of the output indicators have been substantially exceeded, and only one indicator was moderately not met. This indicates strong VfM in terms of efficiency and economy, the CDB achieving significant gains for the amount being spend and the FCDO therefore achieving high development output in the region. We should continue to monitor closely indicator 1.1. where progress has been less strong. Due to the way in which indicators in output 1 have been developed, it is more difficult to establish an assessment of equity. This will instead be explored under the other outputs.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

As described in the ToC section, in February 2020 it was identified that updates should be made to the ‘Output 1’ indicators in the SDF9 log frame. Indicators now reflect project outputs across three FCDO priority themes and the final indicator presents an average across all remaining themes. Outputs 1.1-1.3 are scored based on the balance of projects where progress was “on track”, “behind” or “ahead” of expected results for 2014-2019, and output 1.4 is scored based on a summation of the balance of projects where progress was “on track”, “behind” or “ahead” of expected results for 2014-19 across the remaining five themes.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The previous annual review recommended updating the log frame indicators for output one and this has been completed. FCDO are currently engaging with the CDB on the next replenishment of the SDF. The focus in the year ahead should therefore be:
1. Ensuring the Bank is consolidating and recording progress made in country and regional outcomes under SDF9, through ongoing engagement with HQ staff during board meetings.
2. Building on the progress towards targets under plans for SDF10 through engagement with the Bank on results monitoring and target setting as part of the SDF10 negotiation cycle.
3. Ensuring the Bank is able to record and address relevant lessons from indicators that have seen limited progress under the SDF9 cycle, particularly those under the economic and social infrastructure theme.

Output Title	Strategic Focus
Output number:		2	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Approved projects with a gender-specific or gender mainstreamed rating (as a % of total projects)	Target: 80% / Achieved: 73%	Target met
2.2 Approvals supporting environment, renewable energy/energy efficiency and climate change (as a % of total financing)	Target: 16 – 24% / Achieved: 22%	Target met
2.3 Technical Assistance (TA) approvals supporting private sector development and PPPs (as a % of total TA financing)	Target: 8-12% / Achieved: 5.6%	Target substantially not met expectation
2.4 TA approvals supporting regional cooperation and integration (as a % of total TA financing)	Target: 40-50% / Achieved: 28%	Target substantially not met expectation
2.5 Financing directed to less developed BMCs (% 3-year average)	Target: >51% / Achieved: 63%	Target moderately exceeded expectation
[note] Whether a target has been met under Output 2 is calculated based on the Bank achieving between 90% - 100% of progress towards the target. This is done to allow for the ranges across several the indicators and for an assessment of how close the Bank comes to meeting targets (or exceeding them). For those indicators with a range, the higher end of the range is taken to be ‘100%’. For Indicator 2.1, the Bank achieved progress of 91% (with 80% equating to 100% progress achieved). We have therefore recorded this indicator as having been met.
[note] The CDB defines its less developed BMCs in line with CARICOM’s Revised Treaty. These countries are Belize, Dominica, Grenada, Guyana, Haiti, Montserrat, St. Kitts and Nevis, Saint Lucia, and St. Vincent and the Grenadines.  Of these Haiti is by far the largest recipient due to the set aside within the SDF for Haiti specific grants as the regions only low-income country

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicators under output 2 reflect the strategic focus of the Bank’s programme work and its alignment with UK priorities. The range within indicators is intended to represent a reasonable lower band. Exceeding the upper band of the range is therefore looked upon favourably. The Bank has performed relatively well across this indicator but substantially missed two of the targets, warranting a B overall.

It is worth noting that under all the indicators that the CDB met or exceeded, percentages dropped compared to those reported last year. Under output 2.1, in 2018 approved projects under this indicator were at 74% and the same is true of output 2.2 where there was a substantial drop off from approvals in 2018 and 2017, which were at 55% and 71% respectively. Our approach will be to focus in on priority approvals (i.e. for responding to climate change) and ensure a disaggregated target and to lobby to the Bank to set this at a higher level.

The progress made against output 2.4 in 2019 is particularly disappointing. The Bank substantially missed this indicator, achieving only 28% TA approvals supporting regional cooperation and integration compared to the minimum target of 40%. This has also decreased from 47% in 2017 and 36% in 2018.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Whilst not meeting a number of targets under strategic focus this year, the Bank has continued to maintain a high allocation of financing for less developed BMCs, a key indicator of equity in having the benefits of the SDF be prioritised for the groups that need it most. The Bank has also met our targets under indicator 2.1 on the percentage of approved projects with a gender-specific or gender mainstreamed rating. This has meant the Bank is continuing to maintain a high proportion of projects reaching a marginalised group, again a good sign of equity. The Bank has substantially failed to meet spending targets across two of the indicators under output 2, and we should therefore monitor indicators 2.3 and 2.4 closely going into the PCR as this could indicate issues around VfM for the SDF, with the Bank failing to achieve its desired development results across both the private sector and regional cooperation technical assistance.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Targets are intended to reflect year on year improvements in the CDB’s work and have therefore been increased for two of the indicators since the last annual review (indicator 2.1 increasing from 76% to 80% and indicator 2.3 increasing from 6-10% to 8-12%). Results have fallen compared to the previous annual review even where indicators were met. These indicators therefore remain stretching for the Bank and we do not anticipate making any changes as the result of this review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In the previous year’s annual review, it was recommended that FCDO explore whether indicator 2.2 was stretching enough for the Bank’s work given the Bank has consistently been meeting this target. Rather than update for this cycle, as the indictor was not substantially exceeded in 2019, the decision was taken to instead develop a more granular set of indicators around climate spending for the next cycle of the SDF.

Output Title	Operational quality, effective portfolio performance and resource allocations
Output number:		3	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Portfolio performance rating for implementation (% rated excellent to satisfactory)	Target: 90% / Achieved: 79%	Target moderately not met
3.2 PCRs prepared/completed within two years of project completion (%)	Target: 80% / Achieved: 97%	Target moderately exceeded
3.3 Average time taken from appraisal mission to approval (months)	Target: 3 months / Achieved: 4 months	Target moderately not met
3.4 Average time taken from approval to first disbursement (months)	Target: 7 months / Achieved: 11.5 months	Target substantially not met
3.5 Average length of project extension (months)	Target: 22 months / Achieved: 36 months	Target substantially not met

Briefly describe the output’s activities, and provide supporting narrative for the score.

Indicators under output 3 measure how well the Bank is managing its operations, looking at how effective the management of the portfolio has been over the last year. The Bank has seen a significant reduction in achievement under output 3 compared to 2018 where the Bank only failed to meet one indicator. Overall, this output therefore warrants a B.

Of the unmet targets, there has been a significant drop from previous years across several. The fall under output 3.1 is particularly disappointing. The Bank substantially failed to meet its target of 90% portfolio performance for implementation rated excellent to satisfactory and also saw a significant drop off from the previous year where it achieved 98%. In the development effectiveness review the Bank cited overall issues with portfolio performance continuing to be impacted by lengthy start-up and implementation periods of projects linked to institutional weaknesses in country and inefficient business processes within CDB.

The issues seen across outputs 3.3 – 5 reflect the ongoing struggle the Bank has faced around delivery, reflected in Section A. Given current performance, the Bank is at risk of not meeting its 5-year status across level 3 portfolio performance targets – several of which have significant further stretch in the targets for the final year.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Concerns around operational performance, tracked by indicators under output 3, were raised as a specific concern in terms of VfM in the SDF9 Business Case. Operational delivery continues to be an issue for the Bank, partly the result of weak capacity in the region, where national governments, civil society and the private sector have financial and human resource constraints. These indicate potential issues around efficiency and effectiveness, with the Bank failing to meet the targets it has set on internal improvement despite investment. The Bank has ongoing programmes in place to improve operational efficiency, including the ongoing Transformation Programme. As well as a restructuring of the organisation, maximisation of existing capabilities will be key to this. In terms of progress, CDB has reviewed most of its business processes, both in the operational and corporate services areas, with a view to rationalise workflow. It is reporting on the progress of the transformation programme at quarterly board meetings. Ensuring that this work is consolidated will be key to ensuring VfM for SDF10. FCDO will be working closely with the Bank during negotiations to ensure that this is reflected in the Banks planning.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no major changes to the log frame for this indicator in the last year and given the continued stretch that this indicator is providing for the CDB we should continue to monitor progress closely.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s annual review recommended that if continued strong performance of the Bank was seen under this output, we might wish to increase the stretch in the targets or update them to ensure that as much information as possible on performance is being extracted from the Bank. As there has been a significant fall in performance this year, the indicators can be seen to still provide enough stretch and should not be updated to ensure that they can be monitored moving into the final year of the SDF cycle. We should push the Bank to focus on a number of recommendations under Output 3 given their weak performance particularly on timing. FCDO should:
Maintain a focus on the ‘Transformation Programme’ and its role in strengthening organisational performance. This includes ensuring the Bank continue their work on strengthening BMC capacity, where low levels of staff and in country expertise have been identified by the Bank as creating significant delays on disbursement.

Output Title	Organisational effectiveness of CDB (administration and human resources)
Output number:		4	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Administrative expenses per million US$ of project disbursements (3-year average) $000s	Target: Below 167 / Achieved: 120	Target substantially exceeded
4.2 Ratio of professional staff to support/administrative staff	Target: 1.72:1 / Achieved: 1.98:1	Target moderately exceeded
4.3 Vacancy rate at management and professional levels (%)	Target: ≤6% / Achieved: 5	Target moderately exceeded
4.4 Staff in management positions who are women (%)	Target: 44-54% / Achieved: 36%	Target moderately not met

Briefly describe the output’s activities and provide supporting narrative for the score.
Indicators under output 4 measure the Bank’s organisational effectiveness. The CDB has performed well against this output in 2019, warranting an A+ overall.

It is good to see under output 4.1 that administrative expenses per million US$ of project disbursements were comfortably below the target with a further drop from 2018 when they were $140,000. The Bank has also further improved on the ratio of professional staff to support/admin staff since 2018 (output 4.2), increasing from 1.91 to 1.98. This exceeds the target for 2019 considerably and consolidates progress in this area. Given that in 2018 this ratio was sitting at 1.78 it is good to see the Bank making significant strides in this area, which is an indication of efficiency in the way the Bank is spending administrative budget.

Whilst these indicators show the Bank to have performed well on its internal operations over the last year, it has substantially not met one of the targets (4.4) with the percentage of women in management positions significantly below the target figure. It is also a reduction in the percentage compared to 2018 figures where it was 40%. FCDO should push the Bank on this and reinforce our views on the importance of ensuring senior representation of women at the Bank.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
As set out in the Business Case, FCDO used the SDF 9 negotiations (February – October 2016) to push for improvements on reporting on value for money in the results framework, and to ensure that the Bank’s administrative budget remained at an agreed range. Indicators under output 4 therefore provide a good overview of the Banks economy and efficiency and as can be seen, the Bank has been performing strongly in this area. Monitoring progress on administrative expenses is a key aspect of the Banks VfM monitoring, and the downward trend seen is in keeping with that envisaged in the 2015 – 2019 Strategic Plan. The one indicator where further significant progress should be pushed for is staff in management positions who are women where the Bank is continuing to struggle. This is an indication of issues on equity, the Bank struggling to achieve targets on staffing figures for marginalised groups. FCDO should continue to reinforce our views on this to the Bank and encourage improvement as part of the SDF10 cycle.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no major changes to the log frame for this indicator in the last year. The Bank continues to perform well against the indicators under this output year to year. It will be important to consolidate these results going into SDF10 and FCDO should explore how we can add additional stretch to the targets on administrative expenses which have been substantially exceeded this year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The progress under output 4 is very welcome and the focus should be on consolidation and ensuring stretching indicators are utilised for the next cycle of the SDF, currently under negotiation. In terms of recommendations for the year ahead:
1. FCDO should engage with the Bank on ensuring that stretching indicators are included on operational effectiveness for the next cycle of the SDF - SDF10.
2. FCDO should strengthen our push for representation of women in the Bank in line with the poor performance seen under output 4.4.

D: RISK

Overview of risk management

In 2019 the risk associated with this investment is considered to be moderate
Category	Risk and risk appetite	2019 Assessment
External Context	Debt crisis develops in the Caribbean due to high levels of indebtedness leading to arrears and negative impact on the CDB credit rating and ability to lend – high risk appetite as MDBs are intended to lend in such challenging circumstances and sustainably.	This risk is assessed as moderate as while the Bank’s risk modelling shows it to be well insulated against borrower downgrades due to its strong capital position and the use of the SDF to provide debt relief during 2020, debt levels are high within the region. Mitigation is to continue to push the Bank to reduce portfolio concentration with key borrowers, identify options for further risk exposure swaps, and ensure the sustainability of lending.
Delivery	SDF allocations are not fully utilised resulting in lower development outcomes and a weaker case for the future replenishment – moderate risk appetite as financing is demand driven and borrowers have other options (WBG, IADB etc), but it would impact on VfM and opportunity cost for ODA.	This risk is assessed as low as the end position for the SDF 9 cycle shows near full utilisation. The unique need for COVID-19 support in 2020 means that the Bank have diverted project funding for exceptionally agreed objectives.
Safeguards	Safeguards are breached on specific projects or are associated with safeguarding issues – low risk appetite due to avoiding harm to local communities.	This risk is assessed as moderate. The most recent Central Assurance Assessment found that the CDB has developed a strong overall framework for preventing, identifying and mitigating safeguarding risks. With the appointment of a new VP for Operations, we will have an opportunity to ensure that strong senior leadership continues and ensure that the Board of Directors undertakes a review of the framework in 2021.
Operational	Operational risks linked to slower delivery of outputs due to limited capacity amongst borrowers and/or slow implementation of internal reforms reduce to development impact of the Bank’s activity – moderate high appetite given the time required to develop absorptive capacity in borrowers.	This risk is assessed as moderate. The Board of Directors is focussed on this risk and regular reports on the Transformation Programme highlight the Bank’s progress in this area. Newly appointed Resident Implementation Officers should help unlock borrower capacity issues. We continue to monitor key vacancies across the Bank and will push for action should these persist.
Fiduciary	Funds are diverted for non-development purposes through fraud due to the complex nature of CDB projects and delivery resulting in foregone development impact and reputational injury – low risk appetite in order to protect the taxpayer pound and penny.	This risk is assessed as low. The CDB has established and is expanding its Office for Integrity, Compliance and Accountability which seeks to strengthen the Bank’s processes and procedures to tackle fraud. 2019 saw ICA expand in terms of training, conducting six mandatory training and awareness for all staff in 2019. / The CDB is smaller than the other MDBs and risk is therefore particularly high for its decentralised programmes where the Bank has limited capacity for oversight. The Bank’s Basic Needs Trust Fund (BNTF) is an example of this, where programmes occur at a sub-national level and often through multiple different projects. This remains a significant focus for the UK and we welcome the improved project monitoring and ‘live’ systems that are being established by the Transformation Programme.
Reputational	Reputational risks impact on the Bank, borrowers, or donors – moderate risk appetite as risk may derive from factors outside our control and visibility.	This risk is assessed as low. Through the Board we are able to identify potentially contentious projects at an early stage. Our strong relationships including through our Director at Bank HQ enable us to anticipate and address potential issues.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

The Board of Directors at the Bank (on which the UK sits) regularly review Bank financials and offer scrutiny during quarterly Board meetings. These documents are well written and accurate, and the UK and other Board members have the opportunity to review and comment in advance of the meetings. The Bank financial statements are audited by Ernst and Young and published as part of the Banks Annual Review (link to last audited statement below).

Is the SDF operating economically?
In 2019, SDF administrative expenses fell by $0.9m to $15.4m, approximately a 5% fall from 2018. Output target 4.2, which measures the ratio of professional to administrative staff, was substantially exceeded and the CDB also met output target 4.4 by holding the management level vacancy rate below 6%. These results demonstrate that the SDF is being administered increasingly economically.

Evidence suggests that the SDF also has appropriate policies in place to ensure economical procurement in-country. The FCDO’s 2018 Central Assurance Assessment found that the CDB’s procurement policies and procedures are good.

The SDF business case acknowledged that the CDB lags behind some larger institutions (e.g. the WB and IDB) on the flexibility and efficiency of its administration; for example, the CDB’s small size means that it lacks staff capacity to engage on every project. Improving the resource management skills of CDB staff and BMC officials is something the FCDO should consider monitoring under the SDF10 cycle through indicators on technical assistance spend.

Is the SDF operating efficiently?
Efficiency measures how well the SDF converted inputs (funding and expertise) into outputs (loans, grants, and development programmes). In 2019, the SDF demonstrated relatively poor efficiency.

The time taken to appraise and approve investments at the CDB increased from 3 to 4 months in 2019. Similarly, the CDB missed targets on the time from approval to first disbursement and on the average length of project extensions; the average project is currently extended by 36 months. Loan approvals fell substantially from $26.7m in 2018 to $10.5m in 2019, with just two SDF loan approvals completed in 2019. The long delays and fall in approvals reduce the value for money of the UK’s SDF contribution. As discussed in section A, we anticipate that due to the use of SDF9 financing for COVID-19 support there is a low risk of undisbursed SDF funding at the end of this cycle; however, continuing to work closely with the Bank on operational efficiency is a key priority for the UK’s SDF10 negotiations.

Is the SDF operating effectively?
The business case for the UK’s contribution to SDF 9 explained how the UK’s contribution would contribute to meeting the Caribbean Sustainable Development Goals and allow the UK to support the region’s smaller, poorer countries which have limited access to other MDBs. In 2019, the effectiveness of the SDF in achieving these outcomes has been mixed.

The limited data available suggests that economic growth was largely flat across the Caribbean region in 2019. A number of challenges persist; unemployment in the region rose to 13.8% and gender inequality in the labour market worsened. In education (education projects make up 32% of the SDF portfolio), enrolment in secondary education fell slightly from 81.4% to 80.8% for girls and 77.9% to 77.1% for boys. However, the region did see an improvement in basic education enrolment, and significant disbursements in Guyana, Saint Vincent and the Grenadines, and Saint Lucia, and Haiti, four countries prioritised by the FCDO for support.

Is the SDF operating equitably?
In 2019, the CDB met a key FCDO target for improving its gender mainstreaming in its programming (Output 2.1) but missed the 44%-54% target for female representation amongst its own management staff. SDF disbursements in 2019 continued to reach the poorest countries in the Caribbean region, including a $3m grant commitment to Haiti; however, overall, the CDB still lacks a strong evidence demonstrating that it is committed to spending fairly across the region. Currently (as discussed in our recommendations section) the Bank produces only limited reporting data on the impact of its programmes and improvement on this is key to ensure that spending is equitable. FCDO is pushing the Bank to produce more granular data on the success rate of programmes that focus on marginalised groups and the impact of the SDF as part of our SDF10 negotiations.

Overall cost effectiveness of the UK’s SDF contribution
Overall, there remain strong value for money arguments for supporting the SDF. The SDF has already disbursed $162.8m (£120m) in grants and loans under SDF 9, generating a development impact it would have been hard to match by spending the UK’s £18m contribution bilaterally. The programme’s A+ score on Output 1 demonstrates that the SDF remains well aligned with UK interests and can produce strong development results.

In 2019, however, the SDF has performed relatively poorly on key efficiency and effectiveness criteria. For example, the CDB has failed to meet the FCDO’s target for expediting disbursements. To ensure value for money from the UK’s contribution to SDF 10 it is important that the FCDO works with the CDB to:
- ensure that key efficiency indicators are prioritised in 2020;
- provide more detailed data on SDF efficiency and effectiveness, which can be used to assess and improve value for money; and
- provide evidence of a more nuanced approach to achieving equity through SDF disbursements, which complements the CDB’s recent improvements on mainstreaming gender considerations into its programming.

DFID has deposited all four Promissory Notes of £4,500,000 each as per the agreed schedule, including a final performance-based payment in July 2020.

Date of last narrative financial report	31/12/2019	Date of last audited annual statement	21/07/2020